## Slide 1
Annex: Summary of the route to financial balance and sustainable value 2026/27–2029/30
Health Board Meeting
24th September

## Slide 2
Executive Summary
A clear route to balance is identified; the priority is now delivery certainty and organisational alignment.
£76.6m
2026/27 planned deficit
£24.9m
remaining current-year savings gap @ Mth 4
£66m–£68m
likely annual requirement in each of the next two years
1 April 2027
next-year plans ready to deliver
Immediate priority
Deliver the 2026/27 savings plan, maintain grip on operational expenditure and embed recurrent benefits in budgets.
Medium-term focus
Concentrate leadership and Delivery Unit capacity on workforce productivity & efficiency, LTA rebase, medicines, CHC, procurement and productivity.
Sustainable response
Align financial recovery with quality, workforce productivity & efficiency , service redesign, digital, estates, prevention and system partnerships.
Overall assessment: the strategic route is clear, but identified opportunities must become owned, quality-assured, recurrent and visible in the ledger.
SBUHB Finance
Executive Summary
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 4–10, 17–18, 22, 26–28, 37, 40, 43–45. [/Sources]

## Slide 3
The purpose: protect services while restoring sustainability
The financial plan supports a wider ambition for high-quality, effective and sustainable care.
Why action is needed
The Health Board has a significant planned deficit and must meet its statutory responsibilities while continuing to deliver safe services for the population of Swansea Bay.
What the plan does
It links immediate financial control with recurrent savings, service transformation and better use of workforce, medicines, commissioned care, procurement, digital and estates.
If focuses on sustainable value by reducing low-value activities, optimising enabling costs and prioritising high-value patient care.
How success will be judged
Execution certainty will be achieved through a focus on collaboration and culture supported by Transforming Our Future and cultural change programmes, including staff engagement, behaviours and mindset and leadership supported by the Delivery Unit.
Success means improved care and value, an affordable recurrent cost base, transparent delivery and benefits that are visible in budgets and the financial ledger.
Finance is one part of the response: quality, workforce productivity & efficiency , clinical services, productivity and partnerships must move together.
SBUHB Finance
Purpose
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 8, 15, 40, 43, 63–64. [/Sources]

## Slide 4
The immediate financial challenge @ Month 4
The 2026/27 position requires faster savings delivery and continued control of operational expenditure.
£76.6m
2026/27 planned deficit
£65.0m
2026/27 savings target
£40.1m
Green and Amber at Month 4
£24.9m
remaining savings gap
What must happen now at pace
Convert identified opportunities into deliverable schemes.
Enhance cross-cutting themes through the Delivery Unit.
Progress Service Group and FBP opportunities from Financial Performance Reviews.
Convert schemes rapidly into Green and Amber with clear values and profiles.
Maintain weekly oversight of savings and the actual expenditure run rate.
Use proportionate pay and non-pay controls if delivery weakens.
What must be protected
• Patient safety and service quality.
• Clear operational ownership and accountability.
• The recurrent value of savings, not only the in-year position.
The current-year task is urgent: close the gap while avoiding measures that create larger pressures in future years.
SBUHB Finance
Current position
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 17–18, 22–23. [/Sources]

## Slide 5
A three-stage route to balance
Immediate control, medium-term recurrent recovery and long-term transformation are connected.
1
DELIVER 2026/27
0–6 months
Close the current savings gap, keep expenditure within plan and embed recurrent benefits in budgets.
Maintain clear ownership, milestones and monthly escalation of under-delivery.
2
TACKLE THE DEFICIT
1–3 years
Build executable plans around workforce productivity & efficiency, medicines, CHC, procurement, productivity and commissioning.
Secure decisions early enough to achieve full-year benefits from 1 April 2027 and 1 April 2028.
3
CREATE SUSTAINABLE VALUE
3–5 years
Redesign services using digital, prevention, estates and partnership working to sustain an affordable model.
Balance depends on converting known opportunities into credible recurrent plans and accountable ownership, not relying on short-term controls alone.
SBUHB Finance
Route to balance
Plan to Balance 2026/27–2029/30
Outcome: 2026/27 savings delivered with a credible recurrent exit position.
Outcome: an executable 2027/28 savings portfolio with reduced delivery risk.
Outcome: the operating model and transformation programme embedded and delivering.
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 6, 9, 15, 40. [/Sources]

## Slide 6
The medium-term requirement remains substantial
Planning scenarios indicate a similar level of savings will be needed in each of the next two years.
£66m–£68m
likely annual requirement in 2027/28
£66m–£68m
likely annual requirement in 2028/29
1 April 2027
plans must be ready to deliver
What affects the requirement
Welsh Government funding, pay-award funding, inflation, service growth, commissioning assumptions and current-year recurrent savings delivery.
What the portfolio shows
There is sufficient potential opportunity in aggregate, but portfolio value is not directly equivalent to assured or cash-releasing savings.
The planning priority
Complete validation, profiling, quality assessment and ownership early enough to secure full-year benefits from 1 April 2027.
The key risk is not a shortage of ideas; it is the pace and certainty with which opportunities become executable plans.
SBUHB Finance
Medium-term outlook
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 26–28, 37, 44. [/Sources]

## Slide 7
Focus delivery on the key value savings opportunities
Leadership and delivery capacity should concentrate on the opportunities capable of addressing the deficit at scale.
WORKFORCE PRODUCTIVITY & EFFICIENCY
Service redesign, staffing trajectories, productivity, vacancy and variable-pay controls.
Primary recurrent lever
COMMISSIONING / LTA
Validate and negotiate the high-level £17.6m commissioning gap.
Partner dependent
MEDICINES
Biosimilars, patent expiry, deprescribing, homecare and prescribing improvement.
Material clinical programme
CHC
Eligibility, reviews, joint funding, market management and operating-model change.
Transformation required
PROCUREMENT & NON-PAY
Standardisation, contracts, clinical consumables, inventory and demand control.
Near and medium term
Digital, estates, prevention and productivity are essential enablers that broaden and sustain the opportunity over time.
SBUHB Finance
Priority value engines
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 28, 30–36, 37, 40, 67. [/Sources]

## Slide 8
Financial Strategy sits within a wider organisational transformation
A lower cost base must be achieved through better service design and value, not finance action in isolation.
QUALITY & OUTCOMES
Protect safety and direct resources to interventions that improve outcomes.
CLINICAL SERVICES
Redesign pathways, flow and models of care with clinical ownership.
WORKFORCE PRODUCTIVITY & EFFICIENCY
Align staffing, skills and productivity with the future service model.
DIGITAL & DATA
Automate, support decisions and link cost, activity and outcomes.
ESTATES & ASSETS
Improve utilisation and align sites and capital with the clinical strategy.
SYSTEM PARTNERS
Work regionally and nationally to standardise, share capacity and manage risk.
The financial strategy provides discipline and affordability; organisational change creates the sustainable solution.
SBUHB Finance
Wider organisational picture
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 8, 40, 43, 63–65. [/Sources]

## Slide 9
Identified opportunity must become assured delivery
Every material scheme should pass a common test before it is treated as a saving.
1
NAMED OWNER
An accountable executive and operational lead.
2
QUALITY ASSURED
Clear impact on safety, outcomes, equality and performance.
3
RECURRENT
A sustainable reduction in the underlying cost base or avoided growth.
4
PROFILED
Milestones, monthly values, dependencies and implementation dates.
5
VISIBLE IN THE LEDGER
A defined budget line and evidence that the benefit has been realised.
Critical distinction
Productivity creates a cash saving only when capacity is removed, redeployed or used to avoid planned growth.
SBUHB Finance
Delivery assurance
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 28, 37, 43, 63, 68. [/Sources]

## Slide 10
Immediate roadmap and critical decisions
Action during autumn and winter determines whether full-year benefits can begin on 1 April 2027.
NOW
Deliver 2026/27
Close the remaining gap, embed recurrent savings and maintain weekly oversight.
AUTUMN / WINTER
Make Year 2 executable
Move priority opportunities to Green or robust Amber with owners, profiles and quality assurance.
BY 1 APRIL 2027
Embed strategic change
Finalise Organising for Success and Transforming Our Future in structures, budgets, workforce plans and benefits.
Critical dependency: decisions and ownership must be in place early enough to protect full-year delivery.
SBUHB Finance
Roadmap
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 7, 10, 37, 43–44. [/Sources]

## Slide 11
What success looks like and the assurance required
The route is clear, but credibility depends on evidence of delivery and transparent management of risk.
A lower 2026/27 deficit
Savings and operational control reduce the forecast while protecting safe care.
A credible recurrent exit position
Benefits are built into budgets and do not depend on one-off action.
Executable plans for 2027/28
Priority schemes are owned, quality-assured and ready from 1 April.
A sustainable operating model
Transformation, workforce productivity & efficiency, digital, estates and partnerships reduce the underlying cost base.
Assurance expected
Monthly reporting should show delivery against plan, recurrent and non-recurrent benefits, quality and workforce impacts, movement of schemes to Green, risks and dependencies, and cash release reaching the ledger.
Overall conclusion: there is a clear route to balance, but delivery certainty must now be demonstrated through pace, ownership and recurrent results.
SBUHB Finance
Conclusion
Plan to Balance 2026/27–2029/30
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 45, 66, 68–69. [/Sources]

## Slide 12
Recommendations
The Board is asked to confirm the recovery direction, delivery priorities and assurance expectations
The Board endorses the direction of travel and requires monthly assurance on delivery, quality, risk and cash release.
SBUHB Finance
Conclusion
Plan to Balance 2026/27–2029/30
1
ENDORSE
The route to financial balance by 2028/29 and the requirement for sustained recurrent savings.
2
SUPPORT
Accelerated organisational and consequential workforce transformation, with service-level delivery milestones and quality safeguards.
3
PRIORITISE
CHC, Workforce, medicines, commercial strategies and LTA rebase as the core medium-term value instruments for delivery.
4
REQUIRE
All 2027/28 opportunities to become delivery plans, owned, quantified, risk-adjusted and quality-assured 0reen/Amber plans before 1 April 2027.
PROPOSED RESOLUTION
Notes: [Sources] User-provided presentation “Slides Master Pack Board Sept v10.pptx”, slides 45, 66, 68–69. [/Sources]