| Perinatal Improvement Programme Scorecard |  | July 2026 data / September 2026 Board Meeting |
| --- | --- | --- |
| The Perinatal Improvement Programme Scorecard provides up to three metrics that map progress against the ten thematic recommendations of the Independent Review into Maternity and Neonatal Services in Swansea Bay. Note: Metrics marked as TBC or N/A are included for transparency and to show the intended scorecard scope, but they are not yet available for performance interpretation in this reporting cycle. These fields should be updated as source data, baseline definitions or reporting mechanisms are confirmed. |  |

| 1. Single Point of Access for Maternity Triage 76.6% ████████░░ Amber | 2. Consistent Senior Clinical Oversight 100% ██████████ Green | 3. Maternity Early Warning Score Implementation 96.2% ██████████ Green | 4. Quality of Investigations Mixed Partially met Amber – 1 met, 1 requires mitigation, 1 not yet available | 5. Compassionate & Trauma-Informed Care N/A ░░░░░░░░░░ Not started |
| --- | --- | --- | --- | --- |
| 6. Governance & Oversight 100% ██████████ Green | 7. Fetal Monitoring Training 97% ██████████ Green | 8. Induction of Labour Prioritisation Mixed Partially available Amber – 1 met, 2 not yet available | 9. Policies & Guidelines 81.3% ████████░░ Amber | 10. Engagement with Women & Families 86.3% █████████░ Green |

Detailed metric view

| Recommendation / Theme | Metric number | Metric description metric | % | Visual bar | Status |
| --- | --- | --- | --- | --- | --- |
| 1. Single Point of Access for Maternity Triage | 1.1 | Women seen within the primary target of 15 minutes | 76.6% | ████████░░ | In progress - mitigation in place while full solution is delivered |
|  | 1.2 | Secondary target of 30 minutes achieved | 75% | ████████░░ | In progress - mitigation in place while full solution is delivered |
|  | 1.3 | Dropped calls | 10% | ████░░░░░░lower is better | In progress - mitigation in place while full solution is delivered |
| 2. Consistent Senior Clinical Oversight | 2.1 | Neonatal senior clinician presence in complicated deliveries, including deliveries <28 weeks | 100% | ██████████ | Target met |
|  | 2.2 | Senior obstetric presence at complicated Caesarean section or rotational forceps deliveries | TBC | ░░░░░░░░░░ | Not available - Badgernet reporting in development ; Nov 2026 |
|  | 2.3 | Compliance with All Wales Midwifery Care Guidelines in midwifery-led birth settings | 100% | ██████████ | Target met |
| 3. Maternity Early Warning Score Implementation | 3.1 | Maternity Early Warning Score audit compliance for key assurance indicators | 96.2% | ██████████ | Target met |
|  | 3.2 | NEWTT2 audit compliance for key assurance indicators | 95.7% | ██████████ | Target met |
|  | 3.3 | Practical Obstetric Multiprofessional Training compliance | 92.8% | █████████░ | Target met |
| 4. Quality of Investigations | 4.1 | Investigations/reviews completed by Multidisciplinary Team (last 12 months) | 100% | ██████████ | Target met |
|  | 4.2 | Number of investigations that exceeded agreed timescale for completion (30, 60, 120 days) | 41% | ░░░░░░░░░░low is better | In progress – mitigation in development |
|  | 4.3 | Satisfaction rate with the way the investigation has been handled | N/A | ░░░░░░░░░░ | Not started |
| 5. Compassionate & Trauma-Informed Care | 5.1 | Metrics paused pending agreement of next steps for this recommendation | N/A | ░░░░░░░░░░ | Not started |
| 6. Governance & Oversight | 6.1 | Perinatal reports submitted in accordance with the agreed governance timetable | 100% | ██████████ | Target met |
|  | 6.2 | Reporting framework for maternal and neonatal outcomes, performance indicators and workforce KPIs | 100% | ██████████ | Target met |
|  | 6.3 | Governance awareness / training metric to be reconsidered as a medium-term development | TBC | ░░░░░░░░░░ | Not started |
| 7. Fetal Monitoring Training | 7.1 | Obstetric and midwifery workforce undertake fetal monitoring training in line with the All-Wales package | 97% | ██████████ | Target met |
| 8. Induction of Labour Prioritisation | 8.1 | Proportion of inductions of labour undertaken as per risk assessment timeframe | TBC | ░░░░░░░░░░ | Not available currently - Badgernet reporting in development ; Nov 2026 |
|  | 8.2 | Evidence of dynamic MDT risk assessment of induction of labour delays | TBC | ░░░░░░░░░░ | Not available currently - Badgernet reporting in development ; Nov 2026 |
|  | 8.3 | Adverse outcomes where induction of labour was out of sync with risk assessment or delayed | 0 | ██████████ low is better | Target met |
| 9. Policies & Guidelines | 9.1 | Locally owned maternity guidelines in date | 81.3% | ████████░░ | In progress - mitigation in place while full solution is delivered |
|  | 9.2 | Locally owned neonatal guidelines in date | 84 | ████████░░ | In progress - mitigation in place while full solution is delivered |
|  | 9.3 | National guidelines adopted and embedded into local service | TBC | ░░░░░░░░░░ | Not started |
| 10. Engagement with Women & Families | 10.1 | Rate My Shift engagement score trial | TBC | ░░░░░░░░░░ | Not started – will report from Nov 2026 |
|  | 10.2 | Friends and Family Test score from maternity and neonatal staff | 86.3% | █████████░ | Target met |
|  | 10.3 | Formal concerns and complaints raised through the Listening to People process | N/A | ░░░░░░░░░░ | Not available |