## Slide 1
Perinatal Improvement Plan: Board summary
PURPOSE OF THIS PACK
A concise update on progress, impact and assurance across four workstreams
This document gives the Board a consistent, workstream-by-workstream view of delivery against the Perinatal Improvement Plan. Each page brings together progress since the last report, associated outcome measures and trends, the difference being delivered, and the next steps, risks and opportunities requiring oversight.
Track delivery and emerging impact across the improvement plan
Seek assurance on key risks, mitigations and governance
Test whether actions are translating into safer, more consistent and more person-centred care
Identify decisions, support or escalation required
Four workstreams
1
Clinical Critical Safety Actions
2
Family Engagement
3
Workforce, Leadership, Education and Training
4
Governance
Perinatal Improvement Plan | Board summary

## Slide 2
Workstream 1: Clinical Critical Safety Actions
*Data for July 2026
What this workstream encompasses
Immediate and critical clinical safety improvements, including triage, escalation, multidisciplinary training, investigations, learning and oversight, and postnatal care.
Progress actions since last report
1
Maternity triage
Review of maternity triage service arrangements including single point of access contact number completed, including clinical staff and patient feedback
2
Two-site working
Case for Case for reconfiguration of Perinatal Services developed collaboratively.
3
Awareness campaign of the Improvement Plan with Morriston staff
Development of materials for awareness campaign with staff on non-maternity sites
Associated outcome measures*
76.6% of women seen within BSOTS primary target of 15 mins
75% of women seen within BSOTS secondary target of 30 mins
Dropped calls account for 10% of total calls received to single point of access line
Comprehensive case for change for presentation to Board that articulates current risks and long-term plan for resolution in line with our strategic clinical services plan.
Briefing pack
Posters
Cascade plan
Difference for women, babies and families and/or staff
1
Improved access to timely advice
Women and their families can access timely advice about any concerns, and be referred and signposted appropriately, improving patient safety and patient experiences and improves quality and outcomes
2
Sustainable, safe, quality services for future populations
3
Better informed staff; consistent care for women
Staff on non-maternity sites better informed and understand escalation routes when a pregnant woman reports to their service. Women receive consistent care wherever they attend our services.
Next steps for Workstream
• Case for change for reconfiguration of Perinatal Services to be presented to Board in September 2026. • Establishment of Task and Finish Group for maternity triage to review call volumes, triage breaches, single point of access utilisation, telephone system issues and required mitigations.
Risks
• Delay to implementation of Obstetrics and Gynaecology rota as vacancies not filled in new structure – delayed from September 2026 to January 2027.
• Cannot address long-term demand for maternity single point of access number without dedicated telephone midwife. Recruitment process of dedicated telephone midwife commenced, likely to be completed March 2027.
• Reconfiguration of Perinatal Services is a long-term action and will require ongoing mitigation in the interim period.
Opportunities
• Improve experience and efficiency for women accessing maternity triage services. • Implementation of Obstetrics and Gynaecology rota improve support for two-site working as a dedicated resource for emergency gynaecology issues outside of maternity-settings and enhance medical offer in maternity triage.
Perinatal Improvement Plan | Workstream update
Perinatal Services are co-located alongside critical and emergency care departments, women receive safe and timely care for multidisciplinary teams
OVERALL STATUS
AMBER — key safety improvements are operating, but performance gaps, delayed workforce changes and unresolved two-site risks require continued mitigation
Notes: Template guidance: Replace bracketed placeholders with current reporting period content. This version keeps outcomes and differences as separate boxes, with arrows showing the flow from actions to outcomes to difference for women, babies and families. The difference column is formatted like the first two columns with individual numbered rows, no row titles and no enclosing background box. Section heading boxes use 10pt font. [Sources] M365 search result turn1search21: Perinatal Improvement Plan content describing four workstreams, action leads, timescales and performance metrics. Workstream: Workstream 1: Clinical Critical Safety Actions.

## Slide 3
Workstream 2: Family Engagement
What this workstream encompasses
Listening and acting to ensure mothers and families at the heart of our decision making and service delivery, with a focus including: Response to harm; Decision making and consent; Investigations and learning; Birth trauma; Culture/behaviours, cultural awareness and diversity; Continuous improvement.
Progress actions since last report
1
Revised Family Engagement, Insight and Coproduction Strategy
Clearer priorities, metrics and delivery plan with allocated resources, including a section covering investigations, reviews and complaints.
2
Learning Group and Strategy
Scoping work for establishment of organisation-wide Learning Group completed
3
Maternal Weight Management Group using principles of Engagement strategy to address maternal weight management
Associated outcome measures*
% of planned engagement activities delivered in line with the agreed Engagement Plan;
% or number and diversity of women, families, staff and community representatives participating in engagement activity;
% of engagement activity with documented output, theme, action or decision reported through agreed governance routes
Themed learning summaries.
Quarterly triangulated learning reports.
Recommendations for policy, training, pathway or system changes
Use of engagement insight, lived experience and population health intelligence to develop new offer using grant funding.
Views of women sought
Difference for women, babies and families and/or staff
1
Women and families are listened to, and action taken to demonstrate that lived experience shapes and leads to change in the services we provide.
2
System-wide learning
Learning can be shared and embedded across the organisation; improving patients’ experiences wherever they access our services.
3
Women’s voices shape our service
Women have told and shown us what services help them feel supported in managing their weight during pregnancy which means we can develop an offer that meets their needs and reaches those that most need it.
Next steps for Workstream
• Patient “sounding board” on maternity triage to be held October 2026. • Inaugural meeting of the Learning Group 22 September 2026.
Risks
• Strategy actions will be delivered over the long-term due to resourcing constraints which could lead to a delay in hearing from patients, particularly those that experience barriers to accessing health care. • Limited funding for weight management service offer on a one-year basis
Opportunities
• Opportunity to work with third-sector partners to enhance our offer and draw in local expertise to ensure our population is heard. • System-wide learning beyond Perinatal Services.
Women and families are heard
Addressing health inequalities
*Data for July 2026
Perinatal Improvement Plan | Workstream update
OVERALL STATUS
AMBER — engagement structures and activity are established, but outcome measures, representative reach and systematic learning are not yet fully embedded.
Notes: Template guidance: Replace bracketed placeholders with current reporting period content. This version keeps outcomes and differences as separate boxes, with arrows showing the flow from actions to outcomes to difference for women, babies and families. The difference column is formatted like the first two columns with individual numbered rows, no row titles and no enclosing background box. Section heading boxes use 10pt font. [Sources] M365 search result turn1search21: Perinatal Improvement Plan content describing four workstreams, action leads, timescales and performance metrics. Workstream: Workstream 2: Family Engagement.

## Slide 4
Workstream 3: Workforce, Leadership, Education and Training
What this workstream encompasses
Leadership & Culture - Compassionate leadership/culture / behaviours; Cultural awareness for minority groups; Trauma informed care; Staff Retention, Wellbeing; Education and Training; Staff survey 2025 key themes; Perinatal Assessment key themes
Progress actions since last report
1
Trauma-informed perinatal care
Updated business case on development of embedded Maternity and Neonatal Psychology Led Therapeutic Service progressing through Service Group governance.
2
Education and Training Plan for Perinatal Services
Includes 4 pillars of Mandatory & Statutory Training; Essential to Role; Continuing Professional Development; Personal Development Offer. For all staff groups of Perinatal Services.
3
Rate my Shift pilot
Final specifics including training, coaching and comms for staff agreed for rollout in October.
Associated outcome measures*
% of women reporting that they felt listened to and involved in decisions about their care, or describing care as compassionate, respectful and personalised.
% reduction in concerns and complaints relating to communication, compassion and involvement in care.
Improved staff perceptions of compassionate leadership and psychological safety.
Monthly Workforce Key Performance Indicators (KPI) Monitoring eg turnover; absence
Qualitative Feedback through Staff Survey, Guardian Service. Reporting via Health Education and Improvement Wales / Health Inspectorate Wales Audits and Trade Union colleagues.
Real-time data on staff sentiment on shift.
Thematics on what made shift good and what impacted on a bad shift
How responsive we were to staff concerns.
Difference for women, babies and families and/or staff
1
Women and staff feel emotionally safe in Perinatal Services
Through a culture of openness, transparency and continuous learning, our staff will provide care that women and families feel is increasingly compassionate, personalised and responsive to their needs.
2
A resilient, highly-skilled workforce delivering consistent care
Women, babies and their families will benefit from more consistent standards of care, improved clinical decision-making, and greater assurance that staff are competent in the safety-critical aspects of their role.
3
Real-time feedback, building our intelligence of workforce challenges
Our staff feel safe to speak up, allowing us to map feedback against data, such as ward acuity, absence, peak demand. We will be able to build an informed picture of challenges and respond and support our teams.
Next steps for Workstream
• Pending Service Group Governance, business case for therapeutic led service will progress. • Conclusion of in-depth evaluation of of Multidisciplinary Team Development Programme delivered in Q1. • Test initial Training Plan and review in line with feedback and service demands – Q3 2026/27
Risks
• Ensuring a balance between release of key staff for training while maintaining appropriate coverage in the service, particularly in times of high demand (known as high acuity) • Potential lack of specialist skills and resource to deliver full breadth of to provide Psychology Led Therapeutic Service.
Opportunities
• Listening to women and their families going beyond on an inclusive provision, but one that is actively anti-discrimination.
• Become an employer of choice for Perinatal Services in Wales
Perinatal Improvement Plan | Workstream update
*Data for July 2026
OVERALL STATUS
AMBER - core plans and pilots are established, but implementation, evaluation and evidence of impact remain outstanding
Notes: Template guidance: Replace bracketed placeholders with current reporting period content. This version keeps outcomes and differences as separate boxes, with arrows showing the flow from actions to outcomes to difference for women, babies and families. The difference column is formatted like the first two columns with individual numbered rows, no row titles and no enclosing background box. Section heading boxes use 10pt font. [Sources] M365 search result turn1search21: Perinatal Improvement Plan content describing four workstreams, action leads, timescales and performance metrics. Workstream: Workstream 3: Workforce, Leadership, Education and Training.

## Slide 5
Workstream 4: Governance
What this workstream encompasses
Board reporting, governance routes, risk management, complaints, incidents, claims, clinical guidelines, assurance and external reporting.
Progress actions since last report
1
Quality of investigations
Development of additional opportunities for families to share their experience of how we have handled their concerns.
2
Guidelines tracker
Resolution confirmed for outstanding architecture issues
3
Trigger process for independent reviews into investigations and concerns
Mapping document setting out triggers and associated process developed.
Associated outcome measures*
100% Investigations/reviews completed by Multidisciplinary Team (last 12 months)
41% of investigations that exceeded agreed timescale for completion (30, 60, 120 days) Team (last 12 months)
81.3% of locally owned maternity guidelines in date.
84% of locally owned neonatal guidelines in date.
% of national guidelines adopted and embedded – will be included in the digital solution.
Number of open investigations
Number of open external reviews
Number of PMRT reviews outstanding
Reviews completed within timescale
Overdue reviews
Difference for women, babies and families and/or staff
1
A system where women and their families can be heard, have answers and understand about what happened during their care
Families will be more involved in learning and improvement, concerns will be identified and addressed. Thematic learning and lived experience will inform the way we work.
2
Best practice in line with national standards
Women and their families with confidence that our service is working consistently in line with best practice and national standards. Staff are provided with consistent, up-to-date guidance on working practices.
3
Clarity and a strengthened process
Staff understand and know how and when to refer and escalate concerns and incidents; women and families concerns are listened to, escalate and promptly resolved.
Next steps for Workstream
• Formal reviews of governance arrangements for the Perinatal Improvement Plan in October 2026 • Alignment of Perinatal reporting, including metrics and outcomes measures and removal of duplication between reporting formats to be tested Q3 2026/27 • Trial of collection of satisfaction with the way investigations were handled for stillbirths and unexpected neonatal deaths from September 2026.
Risks
• Availability of specialist independent experts to support investigations – scoping meetings with additional providers to discuss capacity to support •Parity of offer on governance training and awareness of Floor-to-Board arrangements across staff groups; to be strengthened with Workstream 3 via Training and Education Plan but in next financial year.
Opportunities
• Families will be more involved in learning and improvement • Concerns will be identified and addressed more quickly • High-quality care informed by evidence, learning and lived experience
*Data for July 2026
Perinatal Improvement Plan | Workstream update
OVERALL STATUS
AMBER — governance and reporting systems are established, but investigation timeliness, guideline compliance and full embedding remain outstanding.
Notes: Template guidance: Replace bracketed placeholders with current reporting period content. This version keeps outcomes and differences as separate boxes, with arrows showing the flow from actions to outcomes to difference for women, babies and families. The difference column is formatted like the first two columns with individual numbered rows, no row titles and no enclosing background box. Section heading boxes use 10pt font. [Sources] M365 search result turn1search21: Perinatal Improvement Plan content describing four workstreams, action leads, timescales and performance metrics. Workstream: Workstream 4: Governance.