CORPORATE RISK REGISTER

April 2026

CORPORATE RISK REGISTER – HEATMAP OF RISKS

| Impact/Consequences | 5 |  |  | 113: Sustainability of Digital Services Decreased from 20 | 60: Cyber Security 66: Access to Cancer Services – SACT 107: EPRR and Recovery 110: Access to Cancer Care 114: MHLD Staffing New 115: MHLD Estate New 116: Maternity Services Site New 117: Access to Timely UEC New | 92: Finance: Forecast Deficit |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 |  |  | 52: Impact Assessment Requirements 53: Compliance with Welsh Language Standards Decreased from 15 93: Finance: Reduced capital funds 94: CAMHS failure to meet required standards of performance De-escalated 100: Partnerships & Collaboration 109: Access to Planned Care 112: Research Development & Innovation De-escalated | 03: Recruitment of Consultant Medical and Dental Staff 36: Paper Record Storage 85: Non-Compliance with ALN Act Decreased from 20 105: Increased Cost of replacement Pathology System LIMS 108: WCCIS/Connecting care 111: Listening to People | 04: Healthcare Acquired Infection 64: H&S Infrastructure 80: Transfer of Clinically Optimised Patients 89: Healthcare Nursing Staff Levels (HMP) 90: Subject Access Requests 96: Failure to Develop an Approvable IMTP 104: Clinical Coding Completeness 106: Emissions Reduction |
|  | 3 |  |  |  |  |  |
|  | 2 |  |  |  |  |  |
|  | 1 |  |  |  |  |  |
| C X L |  | 1 | 2 | 3 | 4 | 5 |
|  |  | Likelihood |  |  |  |  |

Corporate Risk Register Dashboard

| Strategic Objective | Risk Ref | Description of risk identified (Concise Extract) | Date Opened | Inherent Score | Current Score | Trend | Last Reviewed | Director Lead | Scrutiny Committee |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 - People of Swansea Bay live healthier, fairer and more prosperous lives | 52 (1763) | Statutory Compliance: Engagement & Impact Assessment The Health Board does not have sufficient skills & resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. | Apr 2019 | 16 | 12 |  | Apr 2026 | Director of Insight Communication & Engagement | Performance & Finance Committee |
| 1 - People of Swansea Bay live healthier, fairer and more prosperous lives | 100 (TBC) | A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners at the Public Services Board (PSB) and/or Regional Partnerships Board (RPB), there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. | May 2024 | 12 | 12 |  | Apr 2026 | Executive Director of Planning, Partnerships & Performance | Population Health Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 4 (739) | Healthcare Acquired Infection Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve national infection reduction goals. | Apr 2019 | 20 | 20 |  | Apr 2026 | Executive Medical Director | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 94 (3516) | CAMHS failure to meet required standards of performance De-escalated The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. | Oct 2023 | 20 | 12 | - | Apr 2026 | Chief Operating Officer | Performance & Finance Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 80 (1832) | Transfer of Clinically Optimised Patients Risk that we fail to significantly reduce the number of Clinically Optimised Patients in hospital beds. A deficit in the availability of appropriate community / domiciliary care results in unacceptable delays in discharging patients from acute hospital beds. As a result, patients can decompensate and never gain the independence that could have been available from an early discharge. The use of surge capacity across the Health Board to support UEC flow is directly impacted by the clinically optimised patient group remaining in acute beds for prolonged periods of time waiting for interventions or care in the community. Lack of access to same day domiciliary care/emergency placements in the community hinders ability to avoid admission and associated harms. | May 2021 | 20 | 20 |  | Apr 2026 | Chief Operating Officer | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 66 (1834) | Access to Cancer Services (SACT) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. | Nov 2019 | 25 | 20 |  | Apr 2026 | Executive Medical Director | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 109 | Access to Planned Care If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to meet the non-urgent physical and mental health needs of adults and children, there is a risk that we will be unable to improve access to timely, safe, effective, and person-centred planned care, resulting in a potential for patient harm, increases in length of stay, placement of patients in unsuitable places, and a negative impact on patient & staff experience | Mar 2026 | 16 | 12 |  | Apr 2026 | Chief Operating Officer | Performance & Finance Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 110 | Access to Cancer Care If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to provide timely diagnosis and treatment of adults and children, there is a risk that we will be unable to improve provision of safe, effective, and person-centred cancer care, resulting in a potential for patient harm, poor outcomes, and a negative impact on patient & staff experience. This will impact not only on SBU patients but those of partner organisations depending on this health board as a regional centre for cancer care. | Mar 2026 | 25 | 20 |  | Apr 2026 | Chief Operating Officer | Performance & Finance Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 111 | Listening to People If we do not listen to and act upon the issues raised by people there is a risk that matters of concern to them will continue unaddressed, resulting in dissatisfaction, the potential for poor outcomes, greater regulatory intervention and loss of public trust and confidence. | Mar 2026 | 20 | 16 |  | Apr 2026 | Executive Director of Nursing & Patient Experience | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 112 | Research, Development & Innovation De-escalated If we do not identify and capitalise upon opportunities to engage in research and development, there is a risk that we will not continue to deliver high quality care and potential opportunities to work more effectively, more efficiently and/or to generate income, may be missed, resulting in reduced options to address other strategic objectives, and the reduced attractiveness of the organisation for the recruitment and retention of staff. | Mar 2026 | 16 | 12 | - | Apr 2026 | Executive Medical Director | Digital, Data, Research & Innovation Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 114 | Mental Health & Learning Disabilities Staffing NEW If workforce shortages and fragility persist across Mental Health and Learning Disabilities services (vacancies, sickness, turnover, reliance on temporary staff and insufficient skill mix), then services will be unable to deliver safe staffing and consistent therapeutic input across community, crisis and inpatient pathways. This may lead to avoidable harm (including self-harm/suicide risk), increased restrictive practice, delayed access and extended length of stay, deteriorating staff wellbeing and retention, failure to meet national quality expectations and performance standards, and increased regulatory, financial and reputational impact. | Apr 2026 | 25 | 20 | - | Apr 2026 | Chief Operating Officer | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 115 | Mental Health & Learning Disabilities Estate NEW If the condition, configuration and security of the mental health inpatient, crisis and community estate (including ligature risks, blind spots, backlog maintenance, ageing infrastructure, water/heating/ventilation vulnerabilities and inadequate seclusion and Section 136 facilities) cannot be stabilised and improved at pace, then the Health Board may be unable to provide safe, therapeutic and dignified care. This may result in serious harm or death (including self-harm/suicide risk), increased violence/aggression and restrictive practice, service disruption or temporary closure/decant due to infrastructure failure, failure to meet statutory health & safety requirements, national standards and HIW expectations, and significant regulatory, financial and reputational impact. | Apr 2026 | 25 | 20 | - | Apr 2026 | Director of Finance | Performance & Finance Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 116 | Maternity Services Site NEW There is a risk that women and birthing people requiring emergency obstetric intervention and/or escalation to intensive care will experience delay, clinical deterioration or poorer outcomes because obstetric services are not co-located on the same site as ITU facilities (the only perinatal service without co-located ITU in the UK), emergency services and acute specialties at Morriston Hospital. This may affect the timeliness of access to critical care, multidisciplinary decision-making, transfer arrangements and the organisation’s ability to provide care in line with best practice expectations for critically ill women in childbirth. [See main register entry for further consequences] | Apr 2026 | 25 | 20 | - | Apr 2026 | Executive Director of Nursing & Patient Experience | Quality & Safety Committee |
| 2 - Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | 117 | Access to timely Urgent & Emergency Care NEW [Detailed description and risk entry are in development with Chief Operating Officer’s team.] | Apr 2026 | 25 | 20 | - | - | Chief Operating Officer | Performance & Finance Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legal and regulatory compliance. | Sep 2019 | 20 | 20 |  | Apr 2026 | Executive Director of Finance | Quality & Safety Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 36 (1043) | Storage of Paper Records Failure to provide adequate storage facilities for paper records then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. | Apr 2019 | 20 | 16 |  | Apr 2026 | Director of Digital | Digital, Data Research & Innovation Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 60 (2003) | Cyber Security (In Committee Risk) If the Health Board suffers a cyber-attack, then there is a risk of significant and prolonged operation impact, personal data loss, and fines up to £17 million from non-compliance with the Network and Information Systems (NIS) Regulations. | Jul 2019 | 20 | 20 |  | Apr 2026 | Director of Digital | Digital, Data Research & Innovation Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 104 (443) | Failure to meet Tier 1 targets in Clinical Coding Completeness There is a risk that clinical notes for inpatient episodes will not be coded in a timely way. | May 2025 | 20 | 20 |  | Apr 2026 | Director of Digital | Digital Data & Innovation Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 105 (3114) | Significant increased cost for the replacement Pathology System LIMS If the national Laboratory Information Management (LIMS) 2.0 programme is unable to secure funds from Welsh Government for the overrun into Q1 and Q2 FY 2026/27, then there will be significant additional cost across NHS Wales which could impact the Health Board’s financial plans in 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. There is also an emerging financial risk associated with access to legacy data (see Gaps in Assurance). | May 2025 | 25 | 16 |  | Apr 2026 | Director of Digital | Digital Data & Innovation Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 108 (4334) | WCCIS/Connecting care - Provision of an Integrated Health Record for MH&LD and PCT If the Connecting Care programme fails to deliver a digital solution that meets the operational, clinical, and reporting needs of Mental Health & Learning Disabilities (MH&LD) and Community & Therapies services, then wider MH&LD, Community and Therapies teams will lack access to timely, accurate, and shared information across care settings, resulting in fragmented service delivery, limited availability of high-quality data for performance monitoring and informed decision making, increased duplication of effort, and elevated clinical and governance risks. | Dec 2025 | 20 | 16 |  | Apr 2026 | Director of Digital | Digital Data & Innovation Committee |
| 3 - Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | 113 | Sustainability of Digital Services Decreased from 20 If the organisation is unable to maintain & replace existing digital systems & infrastructure in a timely manner, there is a risk that this could lead to system failures and cybersecurity vulnerabilities, resulting in disruptions in clinical service delivery. This risk encompasses the need for ongoing investment in digital assets to ensure they remain functional & secure. Factors contributing to this risk include financial constraints, aging infrastructure, & the need for continuous updates & support to meet evolving service requirements. | Mar 2026 | 25 | 15 |  | Apr 2026 | Director of Digital | Digital Data & Innovation Committee |
| 4 - The health board is a great place to work where all staff feel valued and work together towards a common goal | 3 (843) | Recruitment of Consultant Medical and Dental Staff Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard to fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. | Apr 2019 | 20 | 16 |  | Apr 2026 | Executive Director of Workforce & OD | Workforce & OD Committee |
| 4 - The health board is a great place to work where all staff feel valued and work together towards a common goal | 89 (3071) | Healthcare Nursing Staff Levels (HMPS) There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. | Nov 2022 | 20 | 20 |  | Apr 2026 | Executive Director of Nursing & Patient Experience | Workforce & OD Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 53 (1762) | Welsh Language Standards Risk decreased from 15 Failure to fully comply with all the requirements of the Welsh Language Standards, as they apply to the University Health Board. | Apr 2019 | 15 | 12 |  | Apr 2026 | Executive Director of Nursing & Patient Experience | Quality & Safety Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 85 (2561) | Non-Compliance with ALN Act Decreased from 20 The Health Board is currently at risk of not reliably and consistently fulfilling the following duties: • Prompt provision of information requested by Local Authorities (Section 65) • Prompt response when asked if there is a relevant NHS treatment or service likely to be of benefit in addressing a learner’s needs (Section 20) • Securing the treatment or service identified by the Health Board in response to the Section 20 request • Notifying the Local Authority of pre-school children likely to have ALN (Section 64) | May 2022 | 25 | 15 |  | Apr 2026 | Executive Director of Allied Health Professions & Health Sciences | Quality & Safety Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 90 (2796) | Subject Access Request Risk If the Health Board is non-compliant with the UK General Data Protection Regulation (UK-GDPR), then there is a risk of Information Commissioner’s Office (ICO) enforcement action being taken against SBUHB, as well as reputational damage and the potential for claims. | Jan 2023 | 20 | 20 |  | Apr 2026 | Director of Digital | Digital, Data Research & Innovation Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 92 (3444) | Finance: Forecast Deficit Risk Forecast deficit is not met due to (1) insufficient progress on run rate reduction, (2) the saving targets required across all areas are not achieved. | Jun 2023 | 20 | 25 |  | Apr 2026 | Executive Director of Finance | Performance & Finance Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 93 (3448) | Finance: Reduced capital funds Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2024/25. | Jun 2024 | 20 | 12 |  | Apr 2026 | Executive Director of Finance | Performance & Finance Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) If we fail to have an approvable Integrated Medium-Term Plan (IMTP) for 2026/27 then we will not meet our statutory duty to break even and may lose public confidence. | Oct 2025 | 20 | 20 |  | Apr 2026 | Executive Director of Planning, Partnerships & Performance | Performance & Finance Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 106 (TBC) | Emissions Reduction If we do not identify funding and implement appropriate actions effectively and in a timely way, there is a risk that the Health Board will not achieve the emissions reduction targets set by Welsh Government which could result in failure and potential reputational damage in the eyes of Welsh Government and the wider public. | Oct 2025 | 20 | 20 |  | Apr 2026 | Executive Director of Planning, Partnerships & Performance | Performance & Finance Committee |
| 5 - The health board is a resilient, sustainable and responsible organisation | 107 (TBC) | EPRR & Recovery If the health board lacks adequate and effective emergency preparedness, planning, response and recovery at both corporate and operational levels, there is a risk that it may not be able to respond and recover promptly, efficiently, or effectively to a major incident, business continuity, or critical incident. This could lead to: Negative impacts on patient care delivery in both acute and non-acute settings; Potential harm or injury to patients and/or staff; Non-compliance with statutory obligations under the Civil Contingencies Act 2004; Legal actions and financial penalties; Reputational damage and diminished public trust. | Oct 2025 | 25 | 20 |  | Apr 2026 | Executive Director of Planning, Partnerships & Performance | Performance & Finance Committee |

| Datix ID Number: 843 Date Opened: April 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 3 Risk Target Date: 31/03/2026 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a great place to work where all staff feel valued and work together towards a common goal |  |  | SRR Ref: 4.1 | Director Lead: Tina Ricketts, Director of Workforce and OD Assuring Committee: Workforce & OD Committee |  |  |  |
| Risk: Recruitment of consultant medical & dental staff in hard to fill roles. Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard-to-fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 4 = 20 Current: 4 x 4 = 16 Target: 4 x 3 = 12 |  |  |  | Rationale for current score: National shortages of numbers in some areas can lead to: - Inability to recruit sufficient numbers of trainees to fulfil rotas on all sites - Inability to attract non training grades to complete rotas - Inability to fill Consultant grade posts in some specialties with adverse effects on patient safety and employer relations. Inability to recruit sufficient registered nursing staff. Risk score has been reviewed and reflects current position across services as a whole. Services with particular difficulties are listed under the Assurance section. Where risk at service level is significant and/or interdependencies could lead to service collapse, these will be escalated separately. |  |  |  |
|  |  |  |  | Rationale for target score: This remains a challenge and is also a national problem. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Regular monitoring of recruitment position with reports to Executive Team and Board via Medical Director and Medical Workforce Board. - Specialty based local workforce boards established to monitor and control specific issues. The Health Board Workforce & OD Committee will seek assurance of medical workforce plans to maintain services. - Engagement of the Deanery about recruitment position. - Weekly workforce delivery meetings with Executive Medical Director to review progress against critical medical and clinical posts - Working with specialist agency and head-hunters to improve chances to fill hard to recruit posts - Working with a marketing agency to develop a branding and attraction campaign for the health board. - Consideration of the RPO (Recruitment Process Outsourcing) model. - Implemented the CESR (Certificate of Eligibility for Specialist Registration) framework to grow our own consultants - Revised Consultant Development Programme, sponsored by the Medical Director. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Medical training initiatives pursued in a number of specialties to ease junior doctor recruitment | Service Group Medical Directors |  | 31/03/2026 |
|  |  |  |  | The Medical Workforce Group continues to monitor recruitment and junior doctor’s rotas. | Executive Medical Director |  | 31/03/2026 |
|  |  |  |  | Continue to recruit internationally where appropriate. | Director W&OD |  | 31/03/2026 |
|  |  |  |  | Continue to work with head-hunters | Director W&OD |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - General situation monitored through W&OD Committee - Regular communication with Deanery - Ongoing and targeted recruitment campaigns - Monitoring by Service Group teams and specialty based local workforce boards - Monthly workforce planning and deployment taskforce meetings with service groups - Weekly workforce delivery meetings with CEO as above - Areas currently experiencing recruitment difficulties are: mental health, oncology, anaesthetics, acute care physicians, care of the elderly, pathology and haematology. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Locum cover Adequate supply of doctors who can work in this country Ability to flexibly deploy doctors in training. Dedicated work between workforce and finance to review and confirm budgeted medical workforce establishment by service group to confirm SIP and vacancy factor. |  |  |  |
| Additional Comments / Progress Notes 28/10/2025: The Health Board is considering introducing a Medacs Bank which will include a Recruitment Process Outsourcing (RPO) offer which could help with some hard to fill consultant roles. |  |  |  |  |  |  |  |

| Datix ID Number: 739 Date Opened: Apr 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 4 Risk Target Date: N/A |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.4 | Director Lead: Raj Krishnan, Interim Executive Medical Director Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Healthcare Acquired Infection (HCAI) Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 4 x 5 = 20 Target: 4 x 5 = 20 |  |  |  | Rationale for current score: Health Board incidence of key Tier 1 infections per 100,000 population above All Wales rates, indicating Health Board’s population at greater risk of infection. High occupancy rates & frequent ward moves associated with increased risk of infection transmission. Lack of decant facilities compromises environment deep cleaning & decontamination and planned preventative maintenance programmes. |  |  |  |
|  |  |  |  | Rationale for target score: There is a need for financial investment to provide adequately maintained & clean environments which will facilitate good IPC & minimise infection risks. Improved governance structures for IPC and antimicrobial stewardship will drive improved local ownership and embed responsibility for these priorities for all levels of staff. Adequately maintained & clean environments facilitate good IPC & minimise infection risks. Reduced occupancy & frequency of patient moves mitigate against infection transmission. Compliant ventilation systems and water safety minimise infection risks. Access to timely data on infections, training, antimicrobial stewardship, cleaning at ward/unit/practice level enables Service Groups to identify areas for focused QI programmes, drive improvement, & effectively measure outcomes. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Policies, procedures, protocols and guidelines supplement the National Infection Control Manual. - Strengthened IPC governance structures, with clear lines of reporting and improved scrutiny and clarified accountability. - Corporate infection prevention & control service and Public Health Wales Microbiology provide specialist advice and support for Health Board staff. - Surveillance of infections, with early identification of increased incidence, and instigation of controls. - Funding is available to provide the cleaning hours outlined in the (2009) National Standards of Cleanliness. - Engineering controls for water safety, ventilation, and decontamination. - Antimicrobial stewardship programmes and systems of monitoring and feedback. - Key nosocomial infections reported and investigated as incidents via Datix. - Mandatory ESR IPC training compliance achieved >80%. Infection prevention & control related training programmes provided. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | To undertake a financial and quality impact assessment of implementing the 2025 National Healthcare Cleaning Standards. | Head of Facilities & IPC |  | 31/07/2026 |
|  |  |  |  | Healthcare Associated Infection Improvement Plans are being developed | IPC and Service Group Leads |  | 31/07/2026 |
|  |  |  |  | Revised: To maintain 80% compliance with IPC mandatory training (Levels 1 & 2) in all staff groups. | Service Group Directors |  | Complete |
|  |  |  |  | Achieve reduction in Tier 1 infections to meet de-escalation criteria for intervention targets | Service Group Directors |  | 31/03/2027 |
|  |  |  |  | Drive improvements in antimicrobial prescribing | Service Group Directors |  | 31/07/2027 |
| Assurances (How do we know if the things we are doing are having an impact?) - Clear Corporate and Service Group IPC Assurance Framework in place. - Ongoing monitoring of infection control rates, with weekly feedback corporately and to the Service Groups. - The Infection Prevention & Control Strategic Group (IPCSG) reports to the Quality and Safety Committee. The group monitors the progress of the Health Board and Service Groups Infection Prevention Improvement plans, monitors infection rates and receives assurances from the service groups and sub-groups and identifies key areas to drive improvements. The Quality and Safety Committee receives. - IPC, antimicrobial stewardship, decontamination and cleaning audit programmes. - Compliance and validation systems for water safety, ventilation systems and decontamination. - Annual completion of IPC Level 2 mandatory training for all HB staff. - Service group Medical Director led HCAI case review meetings take place: to determine if the infection episodes were avoidable, and to identify where improvements can be made to achieve better patient outcomes. |  |  |  | - Poor condition of the hospital estate requires investment. - Ensure improved Corporate and Service Group oversight of the compliance with ventilation, water safety, decontamination and cleaning. - Challenges to sustain cleaning workforce and the necessary finding to implement the 2025 National Healthcare Cleanliness Standards. - High occupancy rates & frequent ward moves associated with increased risk of infection transmission. Additional beds introduced to wards as a result of the “UEC Test of Change” pilot, further reducing the space between beds. - High activity limits access for planned preventative maintenance and necessary HTM validation/compliance checks. - Lack of single room availability, leading to delays in isolating patients with infections and increasing risks to patient contacts and infection outbreaks occurring. - Increased numbers of clinically optimised patients remaining in hospital leads to increased length of stay, increased risk of over-occupancy and over-crowding, with consequence of increasing risks of acquisition of infection. - Antimicrobial prescribing, relating particularly to total volume of antibiotics, with the SBUHB having second highest total volume of antibiotics prescribed in primary care in Wales. - Lack of decant facilities compromises environment deep cleaning & decontamination and planned preventative maintenance programmes. - Varying levels of IPC responsibility embedded across all disciplines and groups, with variable medical engagement at all levels in infection prevention-related Quality Improvements programmes. |  |  |  |
| Additional Comments / Progress Notes HCAI Q4 position to March 20th, 2026. • C. difficile – 10 hospital onset cases (target 6). * Combined (hospital onset and community onset) cumulative total –207 cases. • Staph. aureus – 2 hospital onset cases (target 3). * Combined cumulative total - 121 cases. • E. coli - 3 hospital onset cases (target 4). * Combined cumulative total - 260 cases. • Klebsiella spp. - 0 hospital onset cases (target 4). * Combined cumulative total – 103 cases. • Pseudomonas aeruginosa - 0 cases (Not included within targeted interventions) * Combined cumulative total – 26 cases ESR IPC training Compliance achieved >80% 28/04/2026: Action completed – To maintain 80% compliance with IPC mandatory training (Levels 1 & 2) in all staff groups. |  |  |  |  |  |  |  |

| Datix ID Number: 1043 Date Opened: Apr 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 36 Risk Target Date: 31/03/2030 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Research & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 3 x 3 =9 |  |  |  | Rationale for current score: C - Inability to find records for patients could delay care/increase length of stay over 15 days. Could also mean patients receive incorrect treatment. Increased risk of fire where records are stored outside of the medical record libraries. L - we know this happens from incidents raised |  |  |  |
|  |  |  |  | Rationale for target score: C - The increased development and adoption of the digital record will reduce the need for the paper health record being available at the point of care. L - The increased development and adoption of the digital record, will reduce the amount of paper required to be stored and managed. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - There is a plan in place to increase the functionality of the electronic record to document patient care. The delivery of the plan is overseen by the Digital Leadership Group (DLG) and progress provided to Management Board. (Supported by individual project boards as appropriate). - Records managed by the Medical Records libraries are Radio Frequency Identification (RFID) and location tracked. - Medical Record libraries are regularly risk assessed for fire by health and safety. - Alternative offsite storage arrangements have been identified. - All records must be documented on the Information Asset Register (IAR). |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Allow for new process to stabilise and evaluate benefits of new centralised unit. | Head of Health Records & Clinical Coding |  | 29/05/2026 |
|  |  |  |  | Consider impact of Infected Blood Compensation Authority (IBCA) embargo on the acute records service and provide options for the health board to consider and mitigate the risk relating to storage and its associated financial pressures. | Head of Health Records & Clinical Coding |  | 29/05/2026 |
|  |  |  |  | Review the benefits of the commercial document scanners. Further evaluate the financial impact of the purchase. | Head of Health Records & Clinical Coding |  | 31/07/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - RFID has been implemented for the acute record improving the management and storage of records - Health Records performance reports developed in line with RFID technology - Monitoring complaints and incident reporting. - Electronic record is being implemented in accordance with the plan e.g. implementation of Welsh Nursing Care Record (WNCR), Electronic Test Requesting (ETR), Hospital Electronic Prescribing and Medicines Administration (HEPMA). |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Investment required supporting the delivery and operational costs of the Digital strategy. - Reliance on Digital Health & Care Wales (DHCW) for delivery of the solution for a fully electronic patient record. - Impact of the Infected Blood Enquiry on the Health Boards ability to destroy notes. - Attainment of the Tier 1 Health Board target for clinical coding completeness which relies on the timely availability and quality of the Paper record and electronic sources. - Process for ensuring clinical adoption of electronic ways of working and cessation of adding information to the paper record that is already available electronically needs to be agreed and enforced by the Health Board. - Impact of the infected Blood Inquiry on the health board’s ability to destroy notes and the change in the records code of practice is being reviewed by the Director of Digital. |  |  |  |
| Additional Notes 13/04/2026 – Reviewed and no further updates required. |  |  |  |  |  |  |  |

| Datix ID Number: 1763 Date Opened: Apr 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 52 Risk Target Date: 31/05/2026 |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, fairer and more prosperous lives |  |  | SRR Ref: 1.1 | Director Lead: Richard Thomas, Director of Communications and Engagement Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Impact Assessment Requirements The Health Board does not have sufficient skills & resource in place to undertake integrated impact assessments in line with strategic service change and policy development. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 4 = 16 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: - Current lack of required skills / staff to deliver requirements across the organisation. - Risk lowered to 12 because new Integrated Impact Assessment process developed and being tested across a range of issues and incorporated into Policy on Policies and Corporate Governance processes in line with Strategic Equity Plan.. |  |  |  |
|  |  |  |  | Rationale for target score: - All of these areas need to have adequate resourcing and robust processes / policies in place for the organisation to make robust plans, engage public confidence and meet our statutory and public duties. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Robust policies and processes in place for Impact Assessment and now integrated into corporate governance approach. - EIA responsibilities incorporated into wider Integrated Impact Assessment process. - Development of Strategic Equality Group across organisation to support processes. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Refreshed: Roll out Impact Assessment process across organisation. Integration of process into Board decision-making and corporate governance processes. | Assistant Director of Insight, Charity & Engagement & DICE |  | 31/05/2026 (Risk expected to reduce to target when complete) |
| Assurances (How do we know if the things we are doing are having an impact?) Advice on Integrated Impact Assessment available across organisation supported by robust policies and procedures, overseen by Strategic Equality Group. Intranet page created to provide clarity on process / forms across organisation. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Participation from across organisation in Strategic Equality Group. |  |  |  |
| Additional Comments / Progress Notes 14/05/2026: Risk reviewed & updated. |  |  |  |  |  |  |  |

| Datix ID Number: 1762 Date Opened: Apr 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 53 Risk Target Date: 30/04/2028 |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Elizabeth Rix, Executive Director of Nursing Assuring Committee: Health Board (Welsh Language Group); Quality & Safety |  |  |  |
| Risk: Welsh Language Standards Failure to fully comply with all the requirements of the Welsh Language Standards, as they apply to the University Health Board. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 3 = 15 Current: 4 x 3 = 12 Target: 3 x 3 = 9 |  |  |  | Rationale for current score: As a consequence of an internal assessment of the Standards and their impact on the UHB, it is recognised that the Health Board will not be fully compliant with all applicable Standards. This position has been confirmed/verified via an independent baseline assessment. There is a risk of a compliance notice being issued in relation to Standard 96. An action plan has been implemented to increase compliance by July 2026. If this does not achieve the desired outcome then recording of Welsh language skills on ESR will be mandated. Risk score reduced (March CRR cycle) following identification of funding to support translation software. Our five year plan in relation to Standard 110 has been published, but progress against all of the priority areas within the plan is inconsistent. Progress against Standards 96 and 110 are key for the organisation to make progress in improving the availability of linguistically appropriate person-centred care and delivering on the requirements of these elements of the WLS. Consistent and embedded progress is required in relation to both these areas. |  |  |  |
|  |  |  |  | Rationale for target score: Working through its related improvement plan the likelihood of noncompliance will reduce in some areas as awareness and staff training in response to the Standards, is raised. Progress on the wider Welsh Language Standards (WLS) relies on a number of inter-dependencies including digital solutions, workforce and systems processes. As a result a target risk score of 9 is considered to be reasonable. The target date is set to reflect the need to embed the Standard 110 workplan and to improve our position in relation to Standard 96, both of which are enablers for other WLS. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - An independent baseline assessment of the Health Board’s position against the Standards has been undertaken. This is in addition to the Health Board’s own self-assessment. - Work to implement the recommendations in the above baseline assessment was completed in 2023. - An online staff Welsh Language Skills Survey has been launched. This resulted in a response rate of 15%. - In November 2025 Management Board agreed to mandate the recording of Welsh language skills on ESR in order to support our compliance with Standard 96 - this is yet to be enacted. - We have a record of staff Welsh language skills for 58% of our staff and continue to work to improve this. - Close constructive working relationships are in place with the Welsh Language Commissioner’s Office - Strong networks are in place amongst Welsh Language Officers (WLO) across NHS Wales to inform learning and development of responses to the Standards. - Proactive communication and marketing activity is being undertaken across the Health Board to raise awareness of Welsh language compliance, customer service standards and training opportunities. - Plan to provide clinical consultations through the medium of Welsh launched in 2024 (Standard 110 and Standard 110a) – this is progressing well within some areas, though more focussed work is required in stroke services, care of the elderly and children and young people’s services. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Engage with service and professional groups to increase the percentage of staff who have recorded their Welsh language skills on ESR. | Welsh Language Lead |  | 31/07/26 |
|  |  |  |  | WLDG workplan to be developed | WLDG members |  | 31/07/26 |
| Assurances (How do we know if the things we are doing are having an impact?) - Compliance with Statutory requirements outlined in Welsh Language Act and related Standards. - Meetings with the Welsh Language Commissioner. - Self-Assessment against the requirements of More Than Just Words. - Production of an Annual Report. - Reporting to QSG - Outcome of compliance spot checks - Welsh Language Delivery Group has been re-established and met in September 2025; a quarterly programme of meetings has been established. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Formal and regular reporting to the Board will recommence with the production of the next annual report. Incorporation of relevant Welsh Language Standards into ward assurance processes. Welsh Language Delivery Group attendance to be monitored to ensure appropriate engagements. |  |  |  |
| Additional Comments / Progress Notes 13/05/2026: Standard 96 – recording staff skills on ESR mandated from 01/05/2026 |  |  |  |  |  |  |  |

| Datix ID Number: 2159 Date Opened: September 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 64 Risk Target Date: N/A |  | Current Risk Rating 5 x 4 = 20 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.2 | Director Lead: Claire Osmundsen-Little, Director of Finance Assuring Committee: Quality & Safety Committee |  |  |
| Risk: Health & Safety (H&S) Infrastructure Insufficient resource and capacity of the health, safety and fire function within SBUHB to maintain legal and regulatory compliance for the workforce and for the sites across SBUHB. |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 4 = 20 |  |  |  | Rationale for current score: The Health Board received 12 Health & Safety Executive (HSE) improvement notices during 2019-20 covering various Health & Safety legal breaches covering a range of areas. There is the potential for future multiple notices for not meeting legal requirements based on current available resources. Due to retirement resources in the team has reduced and the risk level increased to 20. The Health Board has also received letters of fire safety matters; these could lead to enforcement if compliance is not achieved. There are currently insufficient resources to appropriately monitor and manage health & safety throughout the organisation, this includes, violence and aggression/case management, manual handling, fire and respiratory protection, with the risk score remaining at 20. |  |  |
|  |  |  |  | Rationale for target score: There is a need for financial investment to fully understand the Health Board’s current compliance. Phase 1 will enable the Health Board to undertake such audits/assessments to understand current baseline, with phase 2 providing the minimum resources to implement a sustainable health and safety provision to support the legal requirements of the Health Board and demonstrate that suitable resources are in place to undertake the roles and responsibilities of the department, also to undertake suitable and sufficient training, provide corporate overview/audit to ensure practices are being employed in the workplace. Target score refreshed to reflected position expected pending funding agreement (following which it could be re-assessed). |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |
| - Assistant Director of Health and Safety in post to support strengthening and develop the H&S function to support the organisation. Business case submitted for additional resources. - Health and Safety Operational Group and the Health and Safety Committee monitor compliance. Refreshed the Fire Safety Group with additional controls in place. - Fire risk assessments (FRA) are being prioritised to reduce the number of FRA overdue and to bring up to date. However, due to leavers and recruitment, resource levels have fluctuated along with compliance levels that are continually monitored. - Fire training in place and fire wardens in place - Review undertaken of fire risk assessment schedule and frequency requirements, with the revised schedule to be introduced in Q2 2026/27. Prioritisation over the next 12 months is on sleeping risk areas to maintain 100% compliance in these areas, and other non-sleeping risk areas are regularly reviewed, with the frequency of these being reviewed based on risk level and will be implemented in Q2 2026/27. - Policies and procedures in place. - Governance structure in place, with clear lines of reporting and improved scrutiny for groups and committee |  |  |  | Action | Lead | Deadline |
|  |  |  |  | Having completed staffing structure review, next action is to work through Health Board governance processes to ensure affordability and to agree a risk-based, phased approach to implement any agreed structure going forward. | Assistant Director of Capital and H&S | Complete |
|  |  |  |  | Refreshed: Updated costing and phasing of implementation to be presented to the Performance & Finance Committee in Q1 2026. | Assistant Director of Capital and H&S | Complete |
|  |  |  |  | Paper was presented to the Performance & Finance Assurance Group on 23/04/2026 for review and approval. | Assistant Director of Capital and H&S | Complete |
|  |  |  |  | Phase 1 will incorporate skill mixing of overall WTE, this includes current vacancies. Following approval now received for phase 1 in PFAG, recruitment will progress, with a target date of August to fulfil recruitment to complete phase 1. The Recruitment to implement Phase 2 could commence in Q4 2026/2027, pending approval for additional resources identified for Phase 2. | Assistant Director of Capital and H&S | 31/08/2026 (Phase 1) |
| Assurances (How do we know if the things we are doing are having an impact?) - Monitoring through the appropriate group/committees (H&S committee) to receive assurance and or identify gaps for key compliance and adherence to applicable legislation. - Site visits/tours undertaken by Health & Safety and Fire team to identify compliance and gaps in compliances. However, this is generally on a reactive basis. - The Service Groups provide an exceptions report through the Health & Safety Operational Group. Quarterly reporting through the Health Board governance structures. - Ongoing monitoring of incidents to prioritise resources. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Health and safety, capital and estates now sit under the Director of Finance portfolio, that has been through a restructure for the senior positions, resulting in the merger of two Assistant Director posts (AD Capital Planning & AD Health & Safety). Included in the submission was an updated H&S structure indicating a phased approach to implementation. Agreement of funding not yet secured for structure to address gaps below: - Challenges to undertake any audits to understand compliance levels due to resources. - Challenges to adequately support service groups in the provision of appropriate training and support. - Increase in training requirements through national initiatives and directives i.e. Section 116/120 (Criminal Justice Act), new powers to act, plus Protection of Premises Act 2025 (Martyn’s Law). - Increased demand from service groups i.e. to provide appropriate levels of training, support and auditing in all areas (Manual Handling; Violence & Aggression/Case Management; Health & Safety, Fire Safety and Fit Testing). Health & safety support and guidance. - Increased activity from regulated bodies i.e. Fire and Rescue services. - Challenges to respond to audits/inspections undertaken by regulatory/advisory bodies i.e. HIW. - Implementation of All Wales systems i.e. All Wales ligature risk assessment programme. - Limited training programme in place to support managers/supervisors in health and safety training i.e. Managing safely or equivalent. - Approval to resource identified resources to implement a more sustainable health & safety structure. |  |  |
| Additional Comments / Progress Notes 14/05/2026: No changes in risk score. Resource progressing through the Health Board governance process. However, current target score refreshed to reflect position i.e. PFAG approval of phase 1, with requirement to explore internal resource first (this will depend on appropriate knowledge, skills and qualifications). Phase 2 paused: this will be reviewed pending approval of funding. |  |  |  |  |  |  |

| Datix ID Number: 1834 Date Opened: November 2019 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 66 Risk Target Date: 28/12/2026 |  | Current Risk Rating 5 X 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.3 | Director Lead: Raj Krishnan, Interim Executive Medical Director Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Access to SACT (Systemic Anti-Cancer Therapy) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 2 = 10 |  |  |  | Rationale for current score: Demand for SACT continues to exceed current service capacity. Ongoing workforce challenges persist within the Chemotherapy Day Unit (CDU) and Pharmacy Technical Services (PTS), impacting service delivery. Patient waiting times remain elevated, with a continued number of breaches against SACT Key Performance Indicators (KPIs). The introduction of new cancer diagnoses and NICE-approved treatments necessitates the implementation of additional SACT regimens, further straining resources. Approval has been granted for additional treatment chairs, and initial recruitment to posts successful. Training of staff is essential prerequisite before this expansion can be operationalised. It is likely to take until Feb 2026 to fully train. Improved performance from Q4 24/25 to Q1 25/26 remaining steady therefore score remains at 20. |  |  |  |
|  |  |  |  | Rationale for target score: Harm will always be at level of 5 due to the impact delayed treatment can have on a patient’s prognosis. However the action being undertaken to increase capacity and therefore access to SACT make the likelihood of delays less so. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Review of scheduling by staff to ensure all chairs used appropriately. - A daily scrutinizing process in progress to micro-manage individual cases, deferrals etc. - Changes made to prescribing & authorising processes to improve workflow for PTS reducing potential delays to supply and administration of treatment. - Responsibility for checking bisphosphonate prescriptions in CDU moved to nursing staff to free up Pharmacy capacity allowing them to focus on key clinical tasks within Pharmacy. - Joint project with Nuclear Medicine to streamline pathways and prioritise SACT patients appropriately halved the average time waiting for MUGA/EDTA tests required before starting SACT. - Increased homecare capacity - Adopted principles from UK SACT board publication: General Principles to Support Systemic anti-Cancer Therapy Aseptic Pressures September 2023 |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Recruiting to posts (dependency on recruitment process changes) | Divisional Manager (Cancer) |  | 30/06/2026 |
|  |  |  |  | Training of new staff (full competency) | SACT Training Team / Pharmacy |  | 31/12/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - To support increased demand, additional funding has been secured to expand the nursing establishment, ensuring appropriate staffing levels during the unit’s core operating hours. - Training has begun for SACT passport. - Waiting times are tracked against the new SACT metrics, which are based on treatment intent rather than average waiting times, providing a more outcome-focused measure. These metrics are reported through our Cancer Performance Report to Welsh Government, the Management Board, and internally via governance structures within NPTSSG, where Oncology services are hosted. - Patient experience continues to be monitored through the Friends and Family Test and the Welsh Cancer Patient Experience Survey, in line with our Putting Things Right (PTR) procedures. - The SBU Capacity Task and Finish Group meets monthly to analyse demand and capacity gaps. Common delay themes are identified and reviewed monthly, with a quarterly report presented to the SACT Consultant Meeting and the Divisional Business Meeting to inform service planning. - Current breach trends are primarily linked to CDU capacity constraints and SACT booking delays, as evidenced in quarterly reporting. Work is ongoing to explore new models of care in addition to the approved posts to address these issues. Welsh SACT performance metrics – P2 to start within 14 days. P3 to start within 21 days |  |  |  | Gaps in assurance (What additional assurances should we seek?) Workforce requirements have and continue to be mapped to identify the additional capacity needed to meet both current and projected future demand for SACT services. While initial funding has been secured to support the first phase of this work, it does not guarantee the sustainability of future capacity. This marks the beginning of a phased approach to workforce planning and service development. Ongoing staffing pressures require training staff to support clinical service delivery, which is reducing capacity to progress training in the nursing team, whilst pharmacy backfill is impacting on training in these roles. |  |  |  |
| Additional Comments / Progress Notes 19/02/2026 Performance remains steady with mitigations put in place for Xmas being successful. No change to risk score at present (discussed at SACT performance meeting) PTS backfill posts progressing which when filled will reduce delays in additional chairs being clinical. 3 Nurses recruited (however newly qualified so extended training) Tiered training adopted to accelerate nursing competence. Tier 1 3 months, full training 6 months. Current SACT trained nurses : CDU - 13/16, HDU - 14/16, Ward 12 - 21/36. 20/03/2026: - There were a number of late deferrals in February with no clear or consistent underlying cause identified. This is not specific to SBUHB with work ongoing with the WCN team to understand contributory factors and implement mitigations - HCSW have not been fully recruited into, however, due to the limited training required compared to pharmacy and nursing, this is not currently impacting our ability to open chairs - Recruitment to backfill for pharmacy gaps as a result of earlier recruitment is still in progress. This needs to be resolved before the additional chairs can become clinical. |  |  |  |  |  |  |  |

| Datix ID Number: 1832 Date Opened: May 2021 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 80 Risk Target Date: TBC |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.8 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Transfer of Clinically Optimised Patients Risk that we fail to significantly reduce the number of Clinically Optimised Patients in hospital beds. A deficit in the availability of appropriate community / domiciliary care results in unacceptable delays in discharging patients from acute hospital beds. As a result, patients can decompensate and never gain the independence that could have been available from an early discharge. The use of surge capacity across the Health Board to support UEC flow is directly impacted by the clinically optimised patient group remaining in acute beds for prolonged periods of time waiting for interventions or care in the community. Lack of access to same day domiciliary care/emergency placements in the community hinders ability to avoid admission and associated harms. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: - Sustained levels of clinically optimised patients (COPs) leading to overcrowding within ED and other front door assessment services, as a direct result of lack of downstream flow, therefore resulting in delays admitting patients. - The number and length of stay of the clinically optimised patient cohort drives the use of alternative capacity solutions such as surge capacity, use of non-designated bed spaces and other sub-optimal clinical areas such as waiting rooms. Recent closure of surge capacity and growth in the Clinically Optimised cohort is resulting in extreme UEC pressures and periods of BCI. - Constraints in relation to all patient flows out of Morriston to a more appropriate clinical setting, identified and included in an expanded risk. - Delay in discharge for clinically optimised patients can result in deterioration of their condition, deconditioning and exposure to delay related harms associated with hospital admission. - Increase in demand for Pathway 1 and increase in bed day utilisation continues. |  |  |  |
|  |  |  |  | Rationale for target score: Targeted reduction of Clinically Optimised patients remains a priority for the HB in order to minimise risk of avoidable harm to patients within the HB and in the wider community. The impact of this patient cohort remaining in hospital beds when they do not require any health intervention drives risk across the UEC pathway for patients accessing urgent and emergency care services. The output of poor flow results in overcrowding of the ED and other front door service areas thus preventing timely ambulance handover, timely access to urgent care and delayed admission to an acute bed. The target score reflects a marked reduction in the likelihood of avoidable harm for the COP cohort and those patients on an unscheduled care pathway, resulting from improvements to the timeliness of discharge from wards expected following the effective implementation of actions agreed. NB while the actions listed below have defined target dates, they are reliant upon our partners to delivery effectively and on time. NB Failure to achieve a reduction in the number and bed day consumption of the clinically optimised patient cohort also presents as a financial risk to the Health Board as it drives the use of unfunded capacity and workforce solutions to manage demand. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - One of the measures under targeted intervention is to see a reduction in pathway of care delays, which specifically supports the reduction in the number of clinically optimised patients. - Review is undertaken on a patient-by-patient basis – with explicit action agreed in order to progress transfer to appropriate clinical setting. - Critical constricts in relation to access/time delays for social workers and assessment for package of care and social placement part mitigated through Health Board funding of Social Work posts. - Daily escalation meetings are held with health and social service colleagues to ensure the requirements of the patients are reviewed and patients are pulled through the system where possible. - Planned transfer of 30 COP patients (Pathway 3/Pathway1) from Morriston to Singleton 5th Jan 26 achieved. Plan to close AMU surge based on this transfer of patients has not been delivered due to Winter pressures and Business Continuity status however, working towards closure end Jan 26. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Work programme and governance structure agreed by local partnership (health board & local authorities) to work up sustainable D2RA model to be actioned as part of the wider Health Board organisational change programme. | Associate Director PCCT |  | 31/03/2026 potential slippage to Sept 26 |
|  |  |  |  | Recent communication between Executive Directors, Chairs and Council Leaders due to the growing COP position and the needs to take down unfunded capacity due to the extreme financial deficit of the Health Board, resulting in 4 key actions being agreed. | CEO |  | 30/04/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - Patient level dashboard allows breakdown by delay type - Regular (weekly) COP reviews and escalations - Shared vision with NPT & Swansea LA CEOs agreed and governance structure with Executive Directors for sign off - POCD reporting into the UEC and Communities and Older Persons Boards. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Capacity and demand exercise required to inform reshaping of community services Specific demand and capacity broken down by D2RA pathways required – current support from Deloittes to review Pathway 2. |  |  |  |
| Additional Comments / Progress Notes 26/01/26: Deloitte continue to work on Pathway 2 analysis and savings opportunities-delayed due to a disruption in the Deloitte support personnel and a gap in provision. 24/03/2026: A deteriorating COP position and high patient risk across the UEC pathway. Minimal traction in terms of patient movement and discharge from hospital. Action closed - Formal agreement through Communities and Older Persons Board to proceed to OCP for health employees to deliver the D2RA hub and recruitment into Swansea LA, with a limited offer from NPT LA. |  |  |  |  |  |  |  |

| Datix ID Number: 2561 Date Opened: May 2022 |  | Risk score decreased from 20 Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 85 Risk Target Date: 30/09/2026 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Christine Morrell, Director of Therapies & Health Sciences Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Non-Compliance with ALN Act The Additional Learning Needs and Education Tribunal (Wales) Act 2018 (the ALN Act) places several statutory duties on Health Boards. Failure to fulfil specific operational requirements in the necessary timescales would cause a breach of these duties. Additional detail regarding these duties and the relevant sections of the Act is provided below (Additional comments). The Health Board is currently at risk of not reliably and consistently fulfilling the following duties: - Prompt provision of information requested by Local Authorities (Section 65) - Prompt response when asked if there is a relevant NHS treatment or service likely to be of benefit in addressing a learner’s needs (Section 20) - Securing the treatment or service identified by the Health Board in response to the Section 20 request - Notifying the Local Authority of pre-school children likely to have ALN (Section 64) The consequence of the Health Board not meeting its operational requirements under the ALN Act within the timescales required is non-compliance with multiple statutory duties. Additional consequences include parent / carer and young peoples' dissatisfaction leading to complaints and legal challenge; children failing to access the multi-agency support that they need with their learning needs, leading to poor outcomes; and reputational impact. From April 2027, it is anticipated that formal reporting to Welsh Government on compliance with ALN Act KPIs will be introduced, with performance measured against an 80% target. This will introduce a performance risk as well as a statutory compliance risk for the Health Board, with potential consequences including failure to meet performance requirements, challenge from Welsh Government and further reputational impact. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 4 x 3 = 12 |  |  |  | Rationale for current score: Performance against Section 65 and Section 20 duties has improved. There has been improved compliance in percentage terms and a reduction in the total number of beaches. However, there continue to be breaches and performance is not reliably and consistently above 80%. There remain gaps in assurance regarding the Health Board’s statutory duty to secure ALP and its duty to notify LAs of pre-school children. In view of the above, risk likelihood has been downgraded to ‘probable’ (risk incidents likely to occur more than once weekly – 4). Risk consequence remains major (multiple breaches of a statutory duty – 4) |  |  |  |
|  |  |  |  | Rationale for target score: With sustained performance progress and completion of activity required to address gaps in assurance, a target risk score of 12 is believed to be achievable, with a reduced frequency of risk events and improved performance in percentage terms. Given multiple demands on the relevant operational services, it is expected that some breaches of the Health Board’s ALN multiple statutory duties under the ALN Act will remain. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Designated Educational Clinical Lead Officer (DECLO) is in post, providing a single point for direction and co-ordination of the Health Board’s activity under the ALN Act and fulfilling the Health Board’s statutory requirement (Section 61) - Operational processes through which the Health Board fulfils its statutory duties under the ALN Act are in place, - Accurate and reliable data is available to all relevant operational colleagues via a digital infrastructure. This enables Services to monitor their compliance with the requirements of the ALN Act. There is ongoing dialogue with Digital colleagues to iteratively improve the digital system. - The Health Board has an ALN Steering Group, chaired by the Deputy Director for Allied Health Professions and Health Sciences, ensuring oversight at a senior level within all impacted operational and corporate areas. - The Health Board also has an ALN Operational Group, chaired by the DECLO, to co-ordinate activity required to address the risk. The Operational Group has an ALN workplan and reports are made to the Steering Group regarding progress. - There is close and ongoing collaborative working with Local Authority Education partners, including their involvement in the ALN Steering and Operational Groups as noted above. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Revise processes through which the Health Board fulfils its duty under Section 64 of the ALN Act and ensure that accurate and reliable data is available. | DECLO |  | 30/06/2026 |
|  |  |  |  | Establish process through which Health Board fulfils its legal duties with local college partners | DECLO |  | 30/06/2026 |
|  |  |  |  | Ensure reliable data capture for securing additional learning provision (Therapies) | Head of SLT |  | 30/09/2026 |
|  |  |  |  | Completion of outstanding ALN Audit action | DDAHPHS |  | 30/07/2026 |
|  |  |  |  | Embedding and consolidation of current operational mechanisms and reporting requirements | DECLO |  | 30/09/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - The Health Board has accurate and reliable data via a digital infrastructure to monitor compliance with Section 65 and Section 20 duties. Data is available to all relevant operational and corporate colleagues. - Data shows an improving picture of timely responses to requests for involvement under Sections 65 Section 20 of the Act. Performance was at above 80% for 3 of the last 4 months for Section 65 requests and for 3 of the last 5 months for Section 20 referrals, with the number of breaches decreasing and an overall trajectory of improvement. - Data shows that the Health Board is fully compliant with its duty to decide whether additional learning provision needs to be secured in Welsh. - The Health Board has confirmed in response to a DHCW impact assessment that it will be able to produce the performance reporting data required for a trial reporting period to commence September 2026, with formal reporting to be introduced in April 2027. - There is regular, data-based reporting on compliance with the ALN Act through the Patient Safety and Compliance Group. ALN-impacted Service Groups also report on their compliance at a Service Group level. - Compliance data for all ALN-impacted Service Groups is regularly reported through the Health Board’s ALN Steering Group, enabling regular and in-depth analysis of compliance data and any challenges. - An Audit has been carried out by Audit and Assurance Services. While this provided an overall ‘limited assurance’ rating, progress in completing management actions that were identified in response to this audit has progressed under oversight of the Mental Health Legislation Committee. |  |  |  | Gaps in assurance (What additional assurances should we seek? - Data is required to enable assurance to be provided that the Health Board is fulfilling its statutory duty to secure additional learning provision. However, it should be noted that no Health Board in Wales is currently able to provide this assurance; that activity in SBUHB is more advanced than elsewhere in Wales towards providing this assurance - Data is required to provide assurance that the Health Board is fulfilling its statutory duty to notify Local Authorities of pre-school children likely to have ALN. - A process has not yet been established between the Health Board and its Further Education partners regarding how Section 20 duties are operationalised, though dialogue is ongoing and no cases have been identified where this has impacted negatively on a young person with ALN. - One management action from the ALN audit remains outstanding. |  |  |  |
| Additional Comments Statutory ALN duties are as follows (with performance KPIs asterisked): - Designated Education Clinical Lead Officer (DECLO) in place to provide co-ordination and oversight (Section 61) - Timely response (with 6 weeks) to Local Authority-issued requests for information or help (Section 65)* - Timely response (within 6 weeks) where a matter is referred by a relevant Education body asking if there is a relevant NHS treatment or service likely to be of benefit in addressing a child’s learning needs (Section 20)* - Where additional learning provision is identified in response to the above referral, the duties: - to decide whether the provision is required in Welsh*, - to take all reasonable steps to secure the provision in Welsh if so, - and to secure the provision (Section 20-21) - Notification to Local Authority where a pre-school child is identified as being likely to have ALN (Section 64) Progress Notes 01/05/2026: R&A note: Risk fully reviewed & refreshed by lead. |  |  |  |  |  |  |  |

| Datix ID Number: 3071 Date Opened: November 2022 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 89 Target Risk Date: TBC |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a great place to work where all staff feel valued and work together towards a common goal |  |  | SRR Ref: 4.1 | Director Lead: Elizabeth Rix, Executive Director of Nursing Supporting Director: Deb Lewis, Chief Operating Officer Assuring Committee: Workforce & OD Committee |  |  |  |
| Risk: Healthcare Nursing Staff Levels at HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is because the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the June 2022 HIW governance review. In addition, there is no head room built into the Prison nursing establishment, so periods of sickness, leave and study render the roster short. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 2 x 2 = 4 |  |  |  | Rationale for current score: Consequence major – unable to fully deliver on the recommendations of HIW due to low healthcare staffing numbers, further impacted during periods of sickness or absence as no headroom. Recommendations also raised in Prison & Probation Ombudsman reports. Likelihood expected – suboptimal care provided on a daily basis. |  |  |  |
|  |  |  |  | Rationale for target score: Consequence minor – With sufficient staffing numbers the prison will be able to deliver on HIW recommendations and fully implement the actions in the Health Delivery Plan. Likelihood unlikely – With full establishment and headroom, suboptimal care is less likely. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| Daily communication with the Governor about the availability and priority of healthcare nursing staff. Pharmacy technician role established – can administer drugs to support nursing establishment. Agreed that Health Care Support Workers to be 2nd checkers for CD drugs and to support substance withdrawal monitoring (awaiting accreditation). Bank and agency staff are used in a limited way, when skillset allows. E-roster implemented and scrutinised with regular reporting to Service Group Patient Safety & Compliance Group. Escalation for overtime and additional hours to fill shortfalls. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Review of staffing in prison. Royal College of Psychiatrists Substance Misuse and Mental Health Baseline assessment completed – analysis of outcome and agreement of further action next. (Following financial deep dives) | Deputy Head of Nursing |  | Complete |
| Assurances (How do we know if the things we are doing are having an impact?) Prison feedback and complaint process Progress reporting on action plans through Service Group PS&C Group, and Health Board Q&S structures (via Patient Safety & Compliance Group). |  |  |  | Gaps in assurance (What additional assurances should we seek?) Implementation and reporting of clinical audits. Audit framework for HMP Swansea in development - Clinical Pathways/Audits and Health Promotion groups taking forward. |  |  |  |
| Additional Comments / Progress Notes 25/02/2026 - Vacancies appointed to. An additional 1.5 WTE Band 5 within budget also identified following finance review now added to TRAC for approval. Discussion with GND regarding rotation for future student stream liners to HMP. Review of actions of HNA and MHSMU ongoing. Identification of e learning for staff to complete. Gap analysis to be undertaken for HEIW Inclusion Health Competency and Education Framework in conjunction with the workforce plan. 15/05/2026: Action complete: Service Group now has a consolidated action plan for Royal College of Psychiatrists Substance Misuse and Mental Health Baseline and PHW Health Needs assessment for HMP Swansea that is monitored through Prison Partnership Board. Service has 2 WTE student streamliners proposed for September 2026 above establishment to support staffing. Further review of risk to be undertaken in May. |  |  |  |  |  |  |  |

| Datix ID Number: 2796 Date Opened: January 2023 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 90 Target Risk Date: TBC |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Research & Innovation Committee |  |  |  |
| Risk: Subject Access Request Risk If the Health Board is non-compliant with the UK General Data Protection Regulation (UK-GDPR), then there is a risk of Information Commissioner’s Office (ICO) enforcement action being taken against SBUHB, as well as reputational damage and the potential for claims. Due to insufficient resources and inconsistent processes across Swansea Bay University Health Board, there is a risk that Subject Access Requests (SARs) will not be fulfilled in compliance with UK-GDPR Article 15, resulting in potential breaches of personal data which could cause distress and lead to a loss of public and government confidence in the Health Board’s trustworthiness and legal standing. Additional Potential Consequences: - Regulatory Enforcement: ICO may impose fines up to 4% of annual turnover for serious breaches. While the ICO has not historically issued fines for SAR breaches, this may change, especially as enforcement activity increases. Recent public reprimands issued by the ICO to another NHS Trust and several public bodies signals heightened regulatory scrutiny. There is also potential for Enforcement Notices to be issued by the ICO, requiring organisations to take corrective action when areas of failure have been identified. - Operational Disruption: Staff diverted from priority tasks to manage SARs, affecting service delivery. - Legal Exposure: Increased risk of litigation & claims from individuals with compromised data rights. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 4 = 16 |  |  |  | Rationale for current score: C – This is assessed to be Major (score 4) under the Governance & Assurance risk domain of health board policy. Failure to comply with SAR requirements or mis-sharing of sensitive information in these areas could result in multiple complaints, loss of public confidence, negative media coverage, and/or criticism by Welsh government. L- The probability of one of these potential consequences occurring is currently considered to score 5 (expected – greater than 50% chance) due to a backlog and/or delays of SARs in a number of different areas. These delays are often the result of waiting for approval to release from Health Care Professionals. 2024/25 statistics showing 65% of SARs were released without full clinical approval. Certain areas have experienced surges in requests following media coverage, with further increases expected. The complexity and sensitivity of these cases, combined with limited resources and inconsistent processes, make delays and errors expected. While the risk of an ICO fine remains low, public reprimand remains a stronger possibility, and the frequency of breaches, solicitor correspondence, complaints, ICO involvement and claims for financial compensation is already high and likely to escalate. |  |  |  |
|  |  |  |  | Rationale for target score: C – As above L – Completion of tasks within the SAR Action Plan will lead to greater consistency in how SARs are managed across the Health Board, along with clearer guidance. There will also be an electronic redaction system in place to help support the initial redaction process, providing finance is available. Completion of the Action Plan will lead to recommendations, the implementation of which will be resource dependent meaning that there will come a time when all has been done that is possible with the resources available. For this reason, the target likelihood score is currently a 4 instead of a 3. Additional resources would allow the organisation to make significant improvements to the process by which SARs are managed. Being able to adequately comply with legal requirements reduces the likelihood of enforcement action and fines from the ICO, as well as minimising the risk of reputational damage. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Approved SAR Policy: Provides a formal framework for consistent SAR handling. - Dedicated SAR Lead (Band 7 IG Manager): Ensures operational oversight and coordination. - Defined Governance Roles: Senior Information Risk Owner (SIRO), Caldicott Guardian, and Data Protection Officer (DPO) roles are in place and active. - Legal and Risk Advice: Accessed for complex SARs to ensure lawful and appropriate handling. - Escalation to Information Governance & Cyber Assurance Group (IGCAG): Enables timely intervention and oversight of emerging issues - SAR Working Group monitoring: Tracks delivery of actions and feeds into governance structures. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Implement detailed Action Plan in line with the timescales outlined within the Plan | Data Protection Officer/Head of Health Records |  | 31/03/2027 |
| Assurances (How do we know if the things we are doing are having an impact?) - Bi-monthly reporting to Digital, Data, Research & Innovation Committee (DDRI): Provides regular oversight and visibility at committee level. - IGCAG oversight: Chaired by the SIRO and attended by key governance leads. - Escalation reports to Management Board and DDRI: Ensures senior leadership awareness. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Internal audit report identified the requirement to invest in resources to address gap in assurance. |  |  |  |
| Additional Comments Background and Context: The Health Board faces a sustained increase in both the volume and complexity of SARs, driven by technological advancements, expanded data availability, and evolving communication practices (e.g. use of WhatsApp and non-corporate email channels). This surge has outpaced existing capacity, including that of professional and expert staff, with many requests exceeding statutory response times and lacking adequate redaction or clinical review. The fragmented nature of record-keeping—spanning paper files, multiple systems, and sensitive content— and inconsistent handling procedures across departments further complicates timely and compliant disclosures. During the 24/25 financial year, the acute SAR team processed 8,652 requests for data. This excludes other areas of SBUHB who manage their own SAR. Each SAR application may involve multiple requests for Health Care Professionals (HCPs) to approval the release of information. The 8,652 applications resulted in 9,102 requests to HCPs to approve, with an additional 4561 released without specific approval based on an ‘open consent’ given previously. Of the requests to approve, 48% (4,366) did not reply within 7 days and therefore this data was released without approval. Therefore only 35% of all SAR requests are released with full HCP oversight. The acute SAR team note that of the 8,652 requests into them, 124 were unable to be completed within the 28-day mandatory timescale. Of these 124, 104 were relating to Children and Young People (CYP) and 18 related to complex email enquiries. Whilst these figures may not appear significant in comparison to the total annual requests received, it is important to recognise that the time required to address these CYP and complex emails is considerable and places an excessive pressure on the organisation, e.g. A large email search may result in 10,000-15,000 emails, all requiring oversight and review, often taking weeks to complete for each request. During 2024/25, SBU received 10 SAR complaints from the public, an additional 3 SAR complaints from the ICO, and reported 1 SAR breach to the ICO. Progress Notes 10/04/2026 - Risk has been reviewed. It is proposed to split the SAR Action Plan into two separate plans to enable IG to concentrate on organisation wide actions. Moving forward it is proposed that there will be an Acute Health Records Action Plan which will become owned by the Access to Health Records Team and there will also be an IG Modernisation Action Plan (owned and managed by IG). This proposed approach will be taken to the next IGCAG meeting. |  |  |  |  |  |  |  |

| Datix ID Number: 3444 Date Opened: June 2023 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 92 Risk Target Date: TBC |  | Current Risk Rating 5 x 5 = 25 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: 5.1 | Director Lead: Claire Osmundsen-Little, Director of Finance and Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Forecast Deficit Forecast deficit is not met due to (1) insufficient progress on run rate reduction, (2) the saving targets required across all areas are not achieved. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 4 = 20 Current: 5 x 5 = 25 Target: 5 x 1 = 5 |  |  |  | Rationale for current score: - Delivery of the deficit plan is predicated on a combination of savings and run rate reductions - Consequence is significant as failure to deliver the plan could impact service delivery if cost reduction required later in the year - A deficit plan is a failure to meet a statutory duty |  |  |  |
|  |  |  |  | Rationale for target score: - The consequence will not change given the importance of financial delivery and its relationship with the delivery of the Health Board’s recovery and sustainability plan - Reducing likelihood to 1 supports a confidence that the deficit plan will be delivered. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| The Health Board is doing the following: - Accountability Letters and Budgetary Management Framework issued to all budget holders in May 2026, which set the expectation and budget for 2026/27. - Introduced in Q3 of 2024/25 the Health Board has put in place further oversight via the Recovery & Sustainability Board, which reported directly to PFC and is chaired by the CEO. This Board is held bi-weekly. - Supporting the R&S Board is the R&S Team, which since 2025/26 has dedicated resource to support the programmes of work agreed for 2026/27. In 2026/27 this has been strengthened with the creation of a Delivery Unit, within which R&S will operate, which has a dedicated Director.. - Continued transparent exchange of position with NHS Executive & Welsh Government, with both weekly and monthly meetings with the NHS Executive. - Standard Day 5 Finance Reports on Variable Pay, Savings Performance and Flash report published via SharePoint site. - Variable Pay is being reported weekly to Informal Execs, alongside the Staff in Post report from ESR to track wider WTE position of the Health Board. - The Health Board has continued with its strategic external partner (Deloitte) for April/May and has ensured there is a clear handover plan to support the £65m savings.. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Extension to commissioning of external support (Deloitte), in collaboration with Welsh Government, which commenced on 14th July 2025. Provide further support for establishment of a sustainable position into 2026/27. | Director of Finance |  | 30/05/2026 |
|  |  |  |  | Refreshed: Establishment of Delivery Unit, with dedicated Director to oversee the delivery of £65m savings required in 2025/26. | Director of Finance |  | 30/05/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board financial performance is reviewed and monitored through: - WG Monthly Monitoring Returns and letter signed by CEO and DOF - Monthly financial performance meetings - Monthly performance meetings (New 2025/26) - Performance & Finance Committee - Independent Member briefings - Recovery & Sustainability Board - Routine reporting to Board of most recent monthly position and financial forecasts - Weekly meetings with the NHS Executive - Escalation Meetings with NHS Executive - Face to Face meetings with Director Finance for NHS Wales |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 13/05/2026: Board Development session planned for 18/05/2026 in relation to the 2026/27 plan to address answers to the questions from WG (17th April 2026). |  |  |  |  |  |  |  |

| Datix ID Number: 3448 Date Opened: June 2024 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 93 Risk Target Date: 31/03/2027 | Current Risk Rating 4 x 3 = 12 |
| --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: 5.1 | Director Lead: Claire Osmundsen-Little, Director of Finance and Performance Assuring Committee: Performance & Finance Committee |  |
| Risk: Reduced Capital Funds Reduced National NHS funds available for major capital schemes requiring a restricted Capital Plan for 2026/27. |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 4 = 20 Current: 4 x 3 = 12 Target: 5 x 1 = 5 |  |  |  | Rationale for current score: - The Health Board has received a 12.3% uplift to its opening discretionary capital allocation for 2026/27 of £15.6m and £29.6m for approved capital schemes within the All-Wales Capital Programme. - The funding available within the Capital Resource Limit (CRL) will not meet the demands for capital investment. Discretionary capital is deployed to replace ageing medical devices & equipment; to address backlog maintenance of premises; and to support small scale, non-National service improvements with capital investments - The outcome of the 2024 national capital prioritisation exercise means some major capital scheme business cases are on hold. A number of high-risk priority schemes will require funding support from WG, including estate stabilization for the Cefn Coed site and in particular Acute Adult Mental Health In-patients services. - Whilst the current requests for replacement of medical equipment and digital devices/network are not causing concern due to the substantial end of year slippage funding received from Welsh Government in 2025-26, there are likely to be more requests for estates backlog maintenance beyond the initial resources. - Potential consequences of this risk are the inability to achieve the ambitions set out within health board plans; the potential failure of ageing equipment leading to service disruption; the exposure to potential environmental health & safety risks. |  |
|  |  |  |  | Rationale for target score: The target score expresses the aspiration of the health board for addressing this risk. The target date indicated above reflects the point which the current actions are anticipated to reduce the risk, though knowledge of the actual funding available is required to reduce it further and this is not available until some months into the financial year. |  |

| Controls (What is currently in place to manage the risk?) | Further Actions (What more are we going to do to address the risk?) |  |  |
| --- | --- | --- | --- |
| The Health Board is doing the following: - Regular dialogue with Welsh Government regarding capital requirements. - Clear communication and reporting of the capital position, the risks and limitations. - Close management of all schemes to ensure slippage is understood along with the impact on service. - Clear prioritisation of any new requirements recognising the current constraints. | Action | Lead | Deadline |
|  | Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk-based basis. | Director of Finance | Monthly through the financial year as plan is dynamic |
|  | Examine the specific prioritisation and phasing of capital investment to meet health board objectives through the Executive Capital Management Group. | Director of Finance | Bi-Monthly |
|  | Maintenance of risks through the Capitalisation Prioritisation Group should additional WG funding become available later in the year. | Assistant Director of Finance (Strategy & Planning) | On-going |
|  | Fix in-year CRL position with Welsh Government. | Assistant Director of Finance (Strategy & Planning) | 30/10/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board capital position is reviewed and monitored through: - Quarterly capital prioritisation group - Performance & Finance Committee quarterly finance report - Capital, Land and Assets Sub-Committee of the Performance & Finance Committee - Capital & Estates Board - Executive Capital Management Group - Monthly Monitoring Returns to Welsh Government. | Gaps in assurance (What additional assurances should we seek?) Reporting on impact of constraints to the capital programme on service delivery. |  |  |
| Additional Comments / Progress Notes 13/05/2026: Risk reviewed & updated. |  |  |  |

| Datix ID Number: 3571 Date Opened: October 2023 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 96 Risk Target Date: TBC |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  |  | SRR Ref: 5.1 | Director Lead: Marie Davies, Director of Planning, Partnerships & Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Failure to Develop an Approvable IMTP (statutory compliance) If we fail to have an approvable Integrated Medium-Term Plan (IMTP) for 2027/28 then we will not meet our statutory duty to break even and may lose public confidence. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: The Health Board does not have a WG approved IMTP and has been placed in enhanced monitoring for Finance, Strategy and Planning following the inability of the Health Board to submit a balanced IMTP since March 2023. Given the All-Wales financial context, the Health Board was not able to submit an IMTP in March 2026. It has instead developed an Annual Plan 26/27 set in a three-year context. |  |  |  |
|  |  |  |  | Rationale for target score: The target remains to develop a financially balanced IMTP so that we meet our statutory duties. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - As per the Welsh Government de-escalation criteria for Strategy and Planning, work is well underway to update the Health Board’s clinical services strategic plan. - The Health Board has refreshed and published its Organisational Strategy - As per the Welsh Government de-escalation criteria for Strategy and Planning, work has been undertaken to assess the Health Board against the planning maturity matrix and develop an action plan in response. This has been reported via the Board Planning & Partnerships formal report and feedback from Welsh Government in February 2026 reflected the “positive improvement journey” and agreed with the Health Board’s scoring. - Delivery of financial recovery, productivity and sustainability actions through agreed Recovery and Sustainability plans owned by executive and programme leads is reported to the Recovery and Sustainability Board. - Delivery of transformation, redesign and major change actions through approved System Programme Plans are monitored through the System Programme Boards. - Delivery of operational and service level actions through Service Delivery Groups as part of normal business activity will be monitored through the Monthly Performance Reviews and Integrated Performance Reporting - The Annual Plan Oversight Group has been superseded by the Integrated Planning and Performance Review Meeting which takes on a quarterly basis and is chaired by the CEO with the purpose of providing formal management oversight to the delivery of the Annual Plan, and to act as a forum for future planning discussions. - The process for development of the 2026/27 plan focussed on developing the total savings opportunities pipeline. - A process for Development of the Annual Plan 2027/28 has been approved by the Exec Board 22.04.26 - Plan development will continue to be subject to robust challenge and scrutiny through regular briefings to Independent Members, Performance and Finance Committee (now meeting twice a month, once informally and once formally) and with detailed oversight from the Board itself. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Refresh Clinical Services Strategic Plan | Executive Director of Planning, Partnerships & Performance/ Medical Director |  | 30/11/2026 |
|  |  |  |  | Recovery and Sustainability Board to continue to focus on savings delivery and now shift to a more sustainable approaches in the longer term. A new monthly performance review regime and Executive Team members to oversee thematic savings workstreams and support Service Groups to meet targets. | Executive Director of Finance and Performance |  | Complete |
|  |  |  |  | Establishment of the ‘Delivery Unit’ | Director of Delivery |  | 30/06/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - The strength of the plan is demonstrated by delivery which is monitored through the System Transformation Boards, Recovery & Sustainability Board and The Service Delivery Group Monthly Performance Reviews and Integrated Performance Report. - Improvement in planning will be reflected in the 2026 self-assessment against the WG Planning Maturity Matrix. |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 29/04/2026: Register entry reviewed & updated. |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: May 2024 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 100 Risk Target Date: 31/03/2027 |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, fairer and more prosperous lives |  |  | SRR Ref: 1.1 | Director Lead: Marie Davies, Director of Planning, Partnerships & Performance Assuring Committee: Population Health Committee |  |  |  |
| Risk: A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners at the Public Services Board (PSB) and/or Regional Partnerships Board (RPB), there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 3 = 12 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: Currently the likelihood of non-delivery of partnership priorities that meet expectations is possible. |  |  |  |
|  |  |  |  | Rationale for target score: The occurrence of non-delivery of partnership priorities will reduce with an improved partnership approach within the Health Board, although given the complex nature of partnership working it is unlikely to completely eradicate the risk. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Senior Health Board leadership is now embedded across the West Glamorgan Regional Partnerships Board (WGRPB) governance to improve visibility and decision making, and the internal Strategic Partnerships Group the Population Health Committee – both established in 2023, provide oversight for external partnerships. - Collaborative Partnerships Framework has been agreed by SBUHB Management Board, setting out a Health Board approach to Partnerships. - The Annual Plan 2026/27 outlines clear priorities for working with PSB, RPB Board and governance and leadership arrangements have been strengthened to support delivery - The Director of Planning, Partnerships meets weekly with Directors of Social Services to align work programmes and develop trusted relationships. Updated RPB governance was signed off in Dec 2025 to focus on 3 key programmes of work aligned to HB priorities: Older Peoples , Regional Commissioning and Mental Health - A Partnerships Tracker has been developed and presented to the Audit Committee. The Partnerships Tracker will provide greater oversight of the health board’s statutory duties and requirements, and a report will go to Audit Committee three times a year. The tracker is accessible to Audit Committee members and sessions have been held to demonstrate how it works. - A regular update on the Tracker, including any additions/amendments is taken to Audit Committee, (the latest one will be May 2026). - A series of ‘deep dives’ of the Health Board’s key partnerships has been put in place for independent members on a bi -weekly basis from April 2026. - Specific and targeted reporting for some areas in the Health Board with an interest in external partnerships including Primary Care & Therapies, Mental Health & Learning Disabilities and Children & Young People. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Evaluation of internal strategic partnership arrangements to ensure that tools and resources continue to be effective and improve partnership and collaboration. | Executive Director of Planning & Partnerships |  | 31/03/2027 |
| Assurances (How do we know if the things we are doing are having an impact?) Strategic Partnerships Group (SPG) in place and provides oversight of partnership discussions, including the WGRPB and the Public Service Boards (PSB). Regular updates and assurance are provided to Health Board via the Director of Planning and Partnerships Management Board report. Collaborative Framework and the Partnerships Tracker are both tools developed to support the Health Board become a better partner with greater oversight. |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 29/04/2026: • Children & Young People – The establishment of the Women, Children & Young People’s Care Programme Board will provide increased visibility and strategic leadership in these key priority areas. A workshop in December was co-chaired by the Executive Director of Nursing and the Chief Operating Officer and the first meeting took place 27/04/2026. The CYP Steering Group will now be established, providing a mechanism for partnership related discussion in relation to Children & Young People. |  |  |  |  |  |  |  |

| Datix ID Number: 443 Date Opened: May 2025 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 104 Risk Target Date: 31/03/2027 |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital Data & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Failure to meet Tier 1 targets in Clinical Coding Completeness Because: The volume of new inpatient episodes exceeds the available clinical coding staff capacity; There are difficulties recruiting and retaining a sufficient number of trained clinical coding staff to address the gap, and clinical information is not always of sufficient quality or completeness electronically the Discharge Advice Letter (DAL), to support swift coding. There is a risk that: Clinical notes for inpatient episodes will not be coded in a timely way. Resulting in: The non-achievement of the Tier 1 Welsh Government target (which is that 95% of inpatient activity should be coded within 30-days of discharge); Insufficient coded data to support effective service planning for population health needs; Inadequate data being available for mortality review/quality and safety purposes, with increased risk of failure to spot variance that are negatively impacting levels of patient care and potentially causing avoidable deaths; Negative impact on accuracy of analysis to understand how resources are being allocated and used at Health Board level and national level (programme budgeting); Delays in claiming case mix sensitive contract lines with Joint Commissioning Committee (JCC), Hywel Da and Cwm Taff (circa £70m per annum value in total) due to lack of coding data. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 3 =12 |  |  |  | Rationale for current score: C - Insufficient coding data will negatively impact service planning for population health needs and inadequate data being available for mortality review/quality and safety purposes. This could result in failures at spotting patterns of variance that are negatively impacting levels of patient care and potentially causing avoidable deaths. Clinically coded activity is also used to understand how resources are being allocated and used at Health Board level and national level (programme budgeting), and therefore a reduction in coding completeness will impact on the accuracy of this analysis. It is also used to claim case mix sensitive contract lines with JCC, Hywel Da and Cwm Taff of circa £70m per annum with lack of coding data impacting on the timeliness in making these claims. L - Tier 1 target is currently not being met on a regular basis. |  |  |  |
|  |  |  |  | Rationale for target score: C - Insufficient coding data will negatively impact service planning for population health needs and inadequate data being available for mortality review/quality and safety purposes. This could result in failures at spotting patterns of variance that are negatively impacting levels of patient care and potentially causing avoidable deaths. Clinically coded activity is also used to understand how resources are being allocated and used at Health Board level and national level (programme budgeting), and therefore a reduction in coding completeness will impact on the accuracy of this analysis. It is also used to claim case mix sensitive contract lines with JCC, Hywel Da and Cwm Taff of circa £70m per annum with lack of coding data impacting on the timeliness in making these claims. L – Increase in what can be coded electronically, unit centralisation, greater staff retention and the development of an auto-coding model will lead to increased capacity and a reduction in likelihood for targets not being met. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - A three-year coding modernisation plan has been approved by executive board on 26th February 2025. This plan will see the implementation of an auto-coding solution and a re-banding of the clinical coding department within existing budgets to attain Tier 1 targets by 27/28. - The coding management team assess the staffing complement on a daily basis to ensure resources are deployed in the most efficient and effective manner, in line with demand and clinical coding priorities. - There is a comprehensive training programme in place for new Trainee Coders. - The Clinical Coding Departments raise incidents when clinical information is missing from the patient’s health records and prevents the activity being coded in a timely manner. These incidents are highlighted at the Directorate Business Meetings held on a bimonthly basis as part of the Clinical Coding Key Performance Indicators. - Clinical coding staff performance continues to be monitored and discussed during the monthly Clinical Coding Managers Meetings, which are chaired by the Head of Health Records & Clinical Coding, and an update is also reported and presented on the Health Board Performance Scorecard. - An App has been developed by Digital Intelligence that shows any relevant data relating to a patient episode from different systems including Signal, Theatre Operative Management System (TOMs), Electronic Pre-operative Assessment (EPOA) and the DAL in one place. This will reduce the number of systems a clinical coder needs to log into. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Recruitment of outstanding Coding Department posts | Head of Health Records and Clinical Coding |  | 01/07/2026 |
|  |  |  |  | Auto-coding model in production for two specialties | Head of Digital Intelligence Programmes |  | 30/05/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - Attainment of the Tier 1 Health Board target for clinical coding completeness which relies on the timely availability and quality of the paper record and electronic sources. Coding 95% of in-patient activity within 30 days of discharge is a tier 1 Welsh Government target that is currently not being achieved regularly within SBU – with an average of circa 74% for 24/25. Performance is reported to Digital Business Meeting every 6 months, and to Digital, Data, Research & Innovations Committee via a Coding Paper. - Episodes are coded from paper and electronic sources; the ability to code from electronic sources improves the timeliness & accuracy; approximately 52,000 episodes of 150,000 episodes are coded from electronic sources currently. This is reported to Digital Business Meeting every 6 months, and to Digital, Data, Research & Innovations Committee via a Coding Paper. - An Audit has been carried out by NHS Wales Assurance and Audit Services of the Coding Department was completed in June 2024 with a result of limited assurance. In response a twelve-point action plan was developed and implemented. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Investment required supporting the delivery and operational costs of the Digital strategy. - Replacing qualified coders who have left the department with trainees reduces productivity - the only mitigation against this is an auto-coding product to increase productivity and re-banding across coding department to put staff at same bandings as NHS England and help staff retention – the investment required for this is yet to be funded. - The Quality of Discharge Summary provision and standard of clinical information available at the point of coding requires improvement to assist with prompt and accurate coding. There continues to be missing clinical information at the point of coding, preventing accurate and timely coding. - Incomplete DALs. |  |  |  |
| Additional Comments / Progress Notes Supplementary Notes: - Coding 95% of in-patient activity within 30 days of discharge is a tier 1 Welsh Government target that is currently not being achieved regularly within SBU – with an average of circa 74% for 24/25. - Contract coders and overtime have been used to achieve that 75% average which has stopped due to the current financial situation of the Health Board. - Retaining and recruiting qualified coding staff is a big challenge due to higher bandings in England and the availability of digitised record to allow home working. - 7 WTE qualified coders have been lost to English Health Boards or DHCW in the last 3 years due to higher bandings with a further 2WTE retiring. This has resulted in circa 44% of the current coding WTE being trainees/unqualified. Currently, there are 3 coding vacancies (March 2026). 13/04/2026: Risk reviewed and updated actions. |  |  |  |  |  |  |  |

| Datix ID Number: 3114 Date Opened: May 2025 |  | Date Last Reviewed: Apr 2026 |  | HBR Ref Number: 105 Risk Target Date: 31/12/2026 |  | Current Risk Rating: 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.3 | Director Lead: Matt John, Director of Digital Supporting Director: Chris Morrell, EDAHPHS Assuring Committee: Digital, Data & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Significant increased cost for the replacement Pathology System LIMS If the national Laboratory Information Management (LIMS) 2.0 programme is unable to secure funds from Welsh Government for the overrun into Q1 and Q2 FY 2026/27, then there will be significant additional cost across NHS Wales which could impact the Health Board’s financial plans in 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. There is also an emerging financial risk associated with access to legacy data (see Gaps in Assurance). |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 4 x 4 = 16 Target: 4 x 1 = 4 |  |  |  | Rationale for current score: Consequence – Additional costs could be in region of approximately £1m for the Health Board depending on the length of delay. Costs for Q1 and Q2 are £0.49m, these costs are on the basis of Blood Sciences go-live in July and Blood Transfusion in September. Pathology and digital are working closely with DHCW to meet these ambitious timescales. Any delays to go-live will incur additional costs. Likelihood – probable (10-50% chance currently) – due to being off-track on project and ambitious dates in the back-up plan. |  |  |  |
|  |  |  |  | Rationale for target score: Consequence as above Likelihood will be negligible if effective system / mitigations put in place in time |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| The national team have approached Welsh Government for Q1 and Q2 costs National costs for Q1 and Q2 FY 2026/27 total £4.5m across Wales, with £0.49m apportioned to SBUHB. The national team have approached Welsh Government to request funding. The national team have asked Health Boards to request the same funding through local governance processes, in case Welsh Government funding is not confirmed. Configuring and testing the new LIMS system SBUHB is live with Cellular Pathology and were the first users of the system in Wales. For Blood Sciences, there are 196 critical defects that must be resolved and / or mitigated against before go-live; the national programme is aiming to have fixes in place by the 1 June 2026 ready for Health Board testing. The current Blood Sciences go-live date in the national plan is July. The project team and the Blood Transfusion service remain concerned about the delivery of the Blood Transfusion module in LIMS 2.0. The national plan (first published mid-January 2026) is indicating a go-live in September. The plan needs to undergo further consultation with Health Boards to assure the ambitious dates being proposed are realistic and that resources can be made available to meet the September go-live. Paramount to the go-live will be assurance that the system configuration supports clinical workflow and importantly, regulatory requirements. Should Blood Transfusion go-live be delayed further, SBUHB will need to continue to use the current LIMS 1.0. The supplier, Intersystems, have waived their costs until end of August but they will begin again from September onwards at £69k per month. DHCW will not be passing on any costs. Pursuing only a ‘Minimal Viable Product’ to avoid scope-creep SBUHB Pathology Services are only seeking to pursue a safe replacement system, known as a ‘Minimal Viable Product’. This is to eliminate the possibility of testing timescales being extended. Other Health Boards and Trusts report they are following the same approach. Challenging the supplier and Digital Health and Care Wales for their technical delivery The supplier is responsible for addressing any defects identified during testing. Digital Health and Care Wales (DHCW) are responsible for delivering some of the technical integrations (in addition to co-ordinating the national programme). The SBUHB Project Team, through the programme governance, challenge the supplier and DHCW to deliver on their commitments. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Ensure financial risk is included in the Health Board financial plan for 26/27, and work with the national team to: - Secure funding from Welsh Government for Q1 and Q2. - Determine the financial impact of the legacy data access requirements. | Director of Digital |  | 30/06/2026 |
|  |  |  |  | Continue to work in collaboration with other NHS Wales organisations to challenge supplier delivery to support go-live dates before the end of Q2. | SBUHB Project Team |  | 30/09/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) National Programme Board SBUHB, together with all Health Boards, Trusts and the supplier belong to the national LIMS Programme Board. The Programme Board receives updates on testing activities, including metrics showing the number of outstanding system issues. It is chaired by the Executive Director of Allied Health Professions and Health Science for Aneurin Bevan University Health Board. SBUHB Project Team A Project Manager is in place to manage the SBUHB Project Team on daily basis. Operational Delivery Network LIMS 2.0 Sub-Group SBUHB work in regional partnership with Hywel Dda University Health Board (HDUHB) and hold a joint, monthly Operational Delivery Network LIMS 2.0 Sub-Group, which receives reports from the SBUHB and HDUHB Project Managers, along with Programme Managers from the supplier and Digital Health and Care Wales. This group is jointly chaired by the SBUHB Clinical Lead for Laboratory Medicine and HDUHB Head of Pathology Service, who are also Senior Responsible Officers for the SBUHB and HDUHB projects. Morriston Management Board The SBUHB project regularly reports progress to the Morriston Management Board. Digital, Data, Research and Innovation Committee The SBUHB project regularly reports progress to the Digital, Data, Research and Innovation Committee. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Quantifying additional costs for legacy data access The national LIMS programme has confirmed that extended access to legacy data - specifically TCL 2016, the Legacy Data Repository (LDR), associated scanned images, and the legacy data viewer - falls outside the existing TCLE upgrade contract and will attract additional cost. Programme Board members noted that these costs relate to continued safe access to historical data beyond the lifetime of TCL 2016, and are required to meet patient safety, operational, and legal obligations. DHCW is currently developing the technical design and cost model, including the licensing charges from the supplier for continued use of TCL 2016 and the legacy viewer, Azure hosting costs for the TCL and LDR databases, and ongoing support and maintenance. The Programme Board reported that these additional costs are unavoidable and not a result of programme delay; rather, they arise from requirements not captured in the original 2023 contract. Early Programme Board feedback in March indicated that each Health Board should expect further financial impact once DHCW had finalised infrastructure requirements and supplier costings within the following weeks. However, costs remained unavailable in the 14 April national LIMS Programme Board where national team commented that costings were expected to be available by the end of April. |  |  |  |
| Additional Comments / Progress Notes The current go-live schedule is tabulated below: Tranche; Discipline; Go-live date. 1; Technical deployment only; October 2025. 2; Cellular Pathology/Andrology; January 2026. Mortuary; March 2026. 3; Public Health Wales/Microbiology/Cervical Screening; June 2026. 4; Blood Sciences/Point of Care Testing/Newborn Screening; July 2026. 5; Blood Transfusion; September 2026 proposed. User Acceptance Testing sign-off User Acceptance Testing across Wales was originally expected to take place across the two months of September and October 2024. However, a significant number of issues in the system, coupled with partial delivery of integrations between the LIMS and national systems managed by Digital Health and Care Wales, were identified early in the process. Maintaining the availability of Pathology staff to undertake testing across an extended duration, alongside maintaining service delivery, has also been challenging. Blood Transfusion services in other part of Wales SBUHB Blood Transfusion are the only Blood Transfusion service in Wales that have successfully migrated onto the current LIMS system. Pathology resource for testing Testing is reliant on the knowledge and skills of Health Board staff whose availability is limited, having to manage testing alongside operational service delivery. With a national shortage of Biomedical Scientists, there is no readily available external resource to support this process. 27/04/2026 – Updated with an increased count of critical defects in Blood Sciences (196, up from 181), and a later date for the supplier to deliver fixes (1st June, late from 23rd March). Public Health Wales Microbiology go-live, including for Microbiology labs located in Swansea, will be 22nd June (previously set for 18th May) due to outstanding defects. Target date for action to confirm Q1 & Q2 funding moved two months later (from 30/04/2026 to 30/06/2026) to reflect that the national team request to Welsh Government for funding is unlikely to be responded to until after the Senedd elections. The quantification of costs for legacy data access has not yet been provided by the national team; this is being monitored at the national LIMS Programme Board where SBUHB are represented. |

| Datix ID Number: TBC Date Opened: October 2025 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 106 Risk Target Date: N/A |  | Current Risk Rating: 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Marie Davies, Director of Planning, Partnerships & Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Emissions Reduction If we do not identify funding and implement appropriate actions effectively and in a timely way, there is a risk that the Health Board will not achieve the emissions reduction targets set by Welsh Government which could result in failure and potential reputational damage in the eyes of Welsh Government and the wider public. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 5 = 20 |  |  |  | Rationale for current score: Consequence: 4 – based on Governance and Assurance domain outcome of: Low performance rating (low confidence of external stakeholders and Welsh Government connected to potential delay slippage/delay in delivery of targets) Likelihood: 5 – The 2025 target has been missed, see ‘Targets explained’ in ‘Additional comments’. This makes achieving the 2030 target less likely. |  |  |  |
|  |  |  |  | Rationale for target score: Likelihood: 5 - Funding is not available and updated DSDP was not costed, passing unknown costs onto the Health Board to implement. Revised DSDP still has a majority focus on buildings without allocated funding to enable. Revised DSDP still has a majority focus on buildings without allocated funding to enable. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Board leadership is provided by the Executive Director of Planning and Partnerships. There is a supporting governance structure in place. - There is a Climate Action Plan (CAP) 2026-2030, approved 27 February 2026. - Implementation is managed by the action’s owners through their local arrangements. Assurance is brought to the quarterly Sustainable Swansea Bay Steering Group meeting. Support is available to the action owners from the Sustainability Team and through a quarterly Climate Knowledge Exchange. - Measures required to achieve emissions reduction objectives are integrated into other strategies and plans, including Estates Strategy; IMTP; Quality Strategy; Sustainable Travel Strategy; Healthy & Sustainable Catering Strategy; Value Based Healthcare Strategy, People Strategy; Population Health Strategy. - The organisation’s carbon emissions is one of the Health Board’s strategic indicators. - The Health Board’s Green Group provides a forum for sharing across services and to learn from other case studies in Wales. - Climate change & decarbonisation is a component part of the prioritisation for Capital Projects across NHS Wales organisations. - Currently building in climate and sustainability into the Clinical Services Plan. - Health Board takes part of the wider Welsh Government Health and Social Care Climate Emergency Programme governance through membership and participation on: - Buildings, Estates, Land Use Planning Programme Board – 1 member - Transport and Procurement Programme Board – 1 member - Approach to Healthcare Programme Board – 2 members - Adaptation Programme Board – 2 members - Community of Experts – 4 members - Adaptation Accelerator Programme – 2 members - The Health Board has contracted three ‘Sustainability Clinical Leads’ including an ED (Emergency Department) Consultant, a Consultant Anaesthetist, and NAU (Neurology Ambulatory Unit) Manager. They are driving sustainable healthcare work in the health board including Green ED, Greener Theatres, Green Group and other initiatives as well as wider NHS Wales and Royal College networks. - Participation on the Public Services Boards in Swansea and Neath Port Talbot sharing best practice and investigating opportunities for collaboration. - Appropriate lead within the CAP will meet with potential funders and partners, and ongoing sourcing of funding / collaboration opportunities identified |  |  |  | NHS Wales Shared Services Partnership led: Working with suppliers on carbon reduction plans. NWSSP require any contract over £5 million have a Carbon Reduction Plan, that can then provide a more accurate emissions factor supporting calculation. Furthermore, there is a Health Board responsibility not to over purchase items and ensure stock is utilised prior to reorder to remove any waste/expiry of dates. | Director of Planning, Partnerships & Performance (SRO, but action led by NWSSP) |  | 2030 |
|  |  |  |  | Currently building in climate and sustainability into the Clinical Services Plan. | Assistant Director of Planning & Partnerships |  | TBC – CSP completion timeline |
| Assurances (How do we know if the things we are doing are having an impact? |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| - Annual carbon emissions data: This is reported to Welsh government annually, based on a financial year. There are three emissions measures reported. The Health Board has some success in meeting the target for Scope 1 and 2 emissions, but the scope 3 emissions are off target. See Additional Comments at foot of this template for definition of measures and performance figures. - CAP Delivery Plan & RAID (Risks Actions Issues & Decisions) log: Implementation of the CAP is reviewed and updated quarterly as an assurance element to SSBSG. - DSDP Delivery Plan & RAID log: Implementation of the DSDP is reviewed and updated quarterly as an assurance element to SSBS. DSDP elements are amber/red due to external constraints, particularly around funding. - DSDP reporting and benchmarking: DCR process replaced by DSDP reporting, with bi-annual the 1st report focuses on a deep dive into 4 initiatives, risks, and issues. The format of the second report has not been confirmed. The first report on the updated DSDP was approved by Management Board in March 2026, recognising red and amber risks – predominantly due to funding. - Benchmarking: An annual review is undertaken within SBU against progress in the wider health sector and other relevant developments in sustainability and climate related work. This highlights that the Health Board is aware of work, but it can be hard to replicate. This will be partially addressed through the established Sustainable Healthcare Working Group. - Annual CAP reporting: Progress report and assurance to Welsh Government around local Health Board actions as detailed in the CAP being undertaken in addition to those in the DSDP. This report is not required in 2025/26. - NWSSP internal audit review: Audit conducted for period Sep-23 to Apr-24 reported with ‘Limited assurance’ due to Welsh Government not having any dedicated funding stream. This risk has been continuously reflected in the DCR reporting process to WG. In addition, periodic updates are provided internally to the Head of Compliance which informs reporting to Audit Committee. Other Health Boards, bar Powys, also received a ‘Limited Assurance’. |  |  |  | - Source of emissions: The Health Board has made significant reductions on the emissions from the Estates with the RE:Fit programme and development of the solar farm powering Morriston Hospital. However, most Health Board emissions are indirect, predominantly from the Supply Chain, and harder to reduce. - Funding stream: The SBU Climate Action Plan (CAP) has been developed to be achievable cost neutrally. However, the NHS Wales Decarbonisation Strategic Delivery Plan (DSDP), published in 2021, was developed by the Carbon Trust and directly targets emissions from buildings. However, suitable resource to implement the actions was not provided by Welsh Government or NHS Wales to support delivery of the plan. There is an expectation that additional funding be absorbed into Health Board financial plans. This is not feasible, recognising decarbonising buildings costs more than £60 million. |  |  |  |
| Additional Comments: Targets Explained: Public Sector Emissions Reporting: Annual carbon emissions reporting to Welsh Government calculating emissions associated with Health Board Activities (based on financial year). • Scope 1: Direct emissions from owned or controlled sources including natural gas, fleet, fluorinated gases and anaesthetic gases • Scope 2: Indirect emissions from the purchase and use of electricity • Scope 3: All other indirect emissions that occur in the upstream and downstream activities of an organisation this includes supply chain, business travel, commuting, waste, water, and processes associated with electrical distribution and extracting fossil fuels. Context: Climate Emergency was declared by Welsh Government in 2019, leading to the Net Zero Wales ambition for the Welsh public sector to collectively reach net zero by 2030. In response NHS Wales developed a ‘Decarbonisation Strategic Delivery Plan (DSDP)’ (published in 2021). The Health Board has some success in meeting the target for Scope 1 and 2 emissions, largely driven by the development of the solar farm and Re:Fit energy efficiency programme managed by Estates. This is despite new categories being added since establishment of the baseline including kerosene, fluorinated gases and anaesthetic gases. A total of 79% of the Health Board’s emissions are part of the supply chain – emissions reductions in this space will be dependent on suppliers actively working on reducing their own emissions and sharing this information with the Health Board. NWSSP is leading on this with all contracts over £5million requiring a carbon reduction plan. Annual carbon emissions data is reported to Welsh government annually, based on a financial year. This calculates emissions associated with health board activities (and so reflects outcome of activities aimed at managing risks to delivery). Most recent performance (2024/25) against WG revised 2018/19 baseline is: Scope; 2018/19* (tCO2e); 2024/25 (tCO2e); % difference. 1; Direct emissions from owned or controlled sources incl. natural gas, gas oil, kerosene, fleet, fluorinated gases, anesthetic gases; 26,123.40; 23,433.44; -10.30. 2; Indirect emissions from the purchase/use of electricity incl. grid electricity. 3; All other indirect emissions (up/downstream) incl. supply chain, commuting, homeworking, business travel, water, waste, well to tank and transmission and distribution (grid); 110,063.30; 150,792.27; +37.01. Total; 136,186.70; 174,225.71; +27.93. *Readjusted baseline from WG, based on the change in footprint: ABMU to SBU Increases in 2024/25 were mostly from: - Natural Gas: Number of cold weather days and increase in natural gas used to heat - Oil: Oil leak and refill od tank required - F—gas: F-gas accidental release at Morriston and system requiring refill - Supply chain: Change in emissions factors for the supply chain and revised methodology by NWSSP - Commuting: Increase in number of staff, this utilises a Welsh Government estimation from the number of staff in the Health Board - Homeworking: New category, not included prior to 2024/25, utilises an estimate similar to commuting utilising a Welsh Government estimation from the number of staff in the Health Board Emissions calculations do not take into account the level of service intensity/capacity delivered by the Health Board. 2025 target, -16% emissions reduction across NHS Wales: Target was passed in 2025 with emissions across NHS Wales increasing by over 20% - as reported in the BBC. There has been no communication from Welsh Government on this. However, this doesn’t take into consideration the different data sources from the baseline to now, improved data efficiency, or increases in services provided/footfall. 28/04/2026: Risk reviewed & updated |

| Datix ID Number: TBC Date Opened: October 2025 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 107 Risk Target Date: N/A |  | Current Risk Rating: 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Marie Davies, Director of Planning, Partnerships & Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Emergency Preparedness, Resilience and Response, (EPRR) and Recovery If the health board lacks adequate and effective emergency preparedness, planning, response and recovery at both corporate and operational levels, there is a risk that it may not be able to respond and recover promptly, efficiently, or effectively to a major incident, business continuity, or critical incident. This could lead to: Negative impacts on patient care delivery in both acute and non-acute settings; Potential harm or injury to patients and/or staff; Non-compliance with statutory obligations under the Civil Contingencies Act 2004; Legal actions and financial penalties; Reputational damage and diminished public trust. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 4 = 20 |  |  |  | Rationale for current score: The current score is aligned with the Wales Risk and Preparedness Register and reflects the Health Board’s compliance with statutory obligations under the Civil Contingencies Act and NHS Wales EPRR standards. It also considers assurance processes in place, including regular audits, training compliance, and business continuity planning. These controls provide a robust framework for preparedness; however, residual risk remains due to external dependencies, inter-agency coordination challenges, supply chain vulnerabilities, and the evolving nature of threats such as cyber incidents, climate-related events, and public health emergencies. It also aligns with the EPRR risk register. Including the risk linked to EPRR resource. Where there is a team of 2 to coordinate resilience across the health board. |  |  |  |
|  |  |  |  | Rationale for target score: The target score reflects the ongoing nature of the actions and control measures required to strengthen organisational resilience. These activities, such as maintaining EPRR training compliance, strengthening governance structures, robust risk and lessons management and embedding business continuity arrangements across services, are essential to sustaining current levels of preparedness. Without these controls in place, the current risk score would escalate to 25. Maintaining the current risk score depends on the continued implementation of these measures, alongside improvements in interoperability with partner agencies, enhanced assurance processes, and investment in key risk mitigation areas including cyber security, supply‑chain resilience, utilities resilience, and climate‑adaptation planning. This ongoing programme of work supports effective preparedness, coordinated response, and timely recovery during major incidents or emergencies, ensuring alignment with national standards and statutory requirements. While a reduced target score is not indicated the organisation remains committed to continuous improvement through regular exercising and testing of plans, applying lessons identified from incidents, and sustained engagement with internal and external stakeholders. These ongoing activities ensure resilience remains dynamic and responsive to evolving risks. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - There is an Executive Director nominated as lead for Civil Contingences (the Director of Planning, Partnerships & Performance). - A comprehensive business continuity management (BCM) process is in place, allowing services to assess and manage risks across the five key business continuity (BC) areas (premises, people, service, utilities, and supplies) and implement suitable mitigations. The BC framework serves as a guide for departments to develop their own specific BC procedures. - An overarching Strategic BC Procedure outlines the management processes, escalation protocols, and response structures to ensure effective command, control, and coordination during a significant disruption. In addition, each Service Delivery Group has an overarching Tactical BC Procedure outlining the tactical management processes, escalation protocols and response structures for effective command and control and coordination. - A Emergency Preparedness, Resilience, and Response (EPRR) strategy and program is in place to oversee and ensure enhanced assessment, preparedness, prevention, response, and recovery strategies. These aim to ensure there is the capacity and capability to be resilient, prepared and for staff to have the right skills and to have the correct plans to safely and effectively respond and recover from emergencies. This has been shaped by consideration of lessons identified from previous emergency incidents and exercises; the management of shared risks; and the impacts outlined in the EPRR risk and preparedness register. - The organisation has fully established emergency preparedness, resilience, and response (EPRR) measures, with the EPRR work and training programs aligned to meet Civil Contingency statutory requirements. Oversight is provided by the EPRR Oversight Group. - A range of emergency response protocols, including a major incident procedure, has been developed. To support, there is a suite of emergency procedures at national and regional levels to address and mitigate national, regional, and local risks as effectively as possible. These risks are identified in the Health Board EPRR Risk and Preparedness register and aligned to National Risk Register, Wales Risk and Preparedness Register, Local Resilience Forum (LRF) Community Risk Register, and respective local authority risk registers. - The Health Board actively participates in the NHS Executive Health Emergency Planning Advisory group and its sub-groups, which provide a platform for discussing and advancing NHS emergency preparedness and planning policies. Additionally, the HB is involved in the Wales Resilience Partnership Group and South Wales Local Resilience Forum and contributes to various pan-Wales/regional groups. The Health Board works closely with local partners and is a member of both Neath Port Talbot and Swansea Local Authority risk groups. - The HB EPRR arrangements are aligned to the HB Strategic vision and objectives. EPRR not only helps the HB to comply with the legal requirements but also reinforces the delivery of high-quality, safe, and equitable services, as well as supports the long-term sustainability and resilience of the organisation. - There is a holistic approach to building, strengthening, and maintaining the EPRR work programme with consideration to leadership and governance (and ensuring these are up to date to ensure clear accountability), training and workforce development, scenario planning and exercises, risk management, community engagement and continuous improvement, including the conduct of regular audits and assurance checks against NHS Wales EPRR standards. This allows delivery of care to be of high quality, efficient, resilient, and adaptable during times of crisis. - Exercising & Continuous Improvement: Scheduling regular internal training and exercises simulations; capturing lessons identified from incidents and exercises and integration into plans. |  |  |  | Amended: Training & Competency: ⦁ Ensure full compliance with EPRR training requirements for all relevant staff. ⦁ Refresher training and scenario-based learning for key roles. There is a relentless drive to ensure there is 100% compliance for Gold and Silver Command training, currently this target has not been met despite a number of training sessions offered. This has been escalated vai SDG Directors and Executive Board. Furthermore, completion of this training has been included as a recommendation as essential in the recent debrief report following 3 episodes of declared business continuity incidents due to operational pressures. | Executive Director of Planning and Partnerships |  | 31/03/2026 date extended to 31/07/2026 |
|  |  |  |  | Amended: Business Continuity Management: ⦁ Embed and test business continuity plans across all critical services. ⦁ Ensure plans include critical resilience and alternative arrangements. This target has not been met despite additional training and support. An extension has been offered for full completion by 30.04.26. This has been escalated via the SDG Directors and Executive Board. Furthermore, completion of service business continuity procedures has been included as a recommendation in the recent debrief report following 3 episodes of declared business continuity incidents due to operational pressures. During disruption, it is essential that services can remain to function. | Executive Director of Planning and Partnerships |  | 31/03/2026 date extended to 31/07/2026 |
|  |  |  |  | HB National Power Outage (NPO) Framework: Support Estates Directorate to develop a HB wide NPO Framework The draft Framework, now termed loss of utilities, is complete and will be discussed for approval in the HB EPRR Oversight Group; 07.05.26 and will be submitted to Executive Board and Health Board for approval. | Executive Directors of Planning and Partnerships / Finance |  | 30/07/2026 |
| Assurances (How do we know if the things we are doing are having an impact? |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| - The EPRR Strategy Group is responsible for overseeing the strategy and implementation of the EPRR work plan. It operates under the coordination of the corporate Strategy Directorate, with the programme focused on achieving Civil Contingency responsibilities, conducting thorough risk assessments, and facilitating training, exercises, and lessons learned. A digital dashboard is in place to support the monitoring of the EPRR work programme. - The HB delivers various exercises to test the effectiveness of current arrangements and response procedures and key training programmes. A comprehensive HB training and exercise strategy is established, covering operational, tactical, and strategic response levels. - Local procedures (including Major Incident and Emergency Response procedures) are regularly reviewed to incorporate the latest UK and national guidance, as well as lessons identified from actual events. Following each live incident, a debrief is conducted, and the findings are documented in the SBUHB lessons identified register. - As part of the EPRR Work Programme and within the Digital Dashboard, the EPRR Strategy Group monitors and ensures that all business continuity procedures are kept up to date. Identified gaps in business continuity management are taken forward by the respective Service Delivery Group and cross cutting services EPRR - The EPRR Strategy Group oversees the HB EPRR risk register, which includes the necessary mitigations for consequence management. This informs the EPRR work programme and training and exercising strategy. - Risks associated with health included in the Wales Risk and Preparedness Register are included on the South Wales Local Resilience Forum Risk Register and the specific health risks are discussed in the Loal Resilience Health Group. This work informs multi-agency, regional resilience, and response arrangements. - The EPRR Strategy Group currently provides annual updates to the Management Board, with a summary to the Health Board. This includes presenting the Major Incident Procedures, which are reviewed each year, submitting the NHS Executive Annual Report for approval, and offering a comprehensive EPRR update. The update covers challenges, achievements, and other emergency response arrangements. - The six statutory duties shape the overarching EPRR work programme, with progress monitored through the Digital Dashboard and discussed at the EPRR Strategy Group. Indicator of achievement of 2025/26 objective is: As a Category 1 Responder organisation under the Civil Contingencies Act 2004, HB meets the six statutory duties. Assurance of this is provided through the NHS Executive Annual Report, which is signed by the HB CEO and presented to the Management Board. The report also includes an update on the delivery of the HB EPRR work programme. - Business Continuity audit report - Additionally, to support the HB EPRR Training and Exercising Strategy, HB takes every opportunity to participate in national and regional exercises. These exercises are then discussed in the various resilience forums, as mentioned earlier. |  |  |  | - EPRR is a corporate function and must be recognised as a vital, cross-cutting service to ensure EPRR considerations are integrated into all HB operations. Progress is being made in this area, but further work is needed. Service Delivery Groups must designate appropriate managerial resources to take on EPRR responsibilities within their respective services. These individuals should have the necessary seniority to make decisions and drive the required work programme forward. Additionally, EPRR mapping has been undertaken for the HB Strategic vision and objectives evidencing where HB-wide work programmes need to incorporate resilience, with EPRR clearly defined as a critical pillar in supporting these efforts. However, further clarity is needed regarding the specific gaps or challenges hindering the full integration and effectiveness of EPRR within these processes. |  |  |  |
| Additional Comments / Progress Notes 27/04/2026: Risk reviewed and progress against actions recorded narratively above. |  |  |  |  |  |  |  |

| Datix ID Number: 4334 Date opened: December 2025 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 108 Risk Target Date: 31/03/2029 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Data, Research and Innovation |  |  |  |
| Risk: WCCIS/Connecting care - Provision of an Integrated Health Record for MH&LD and PCT If the Connecting Care programme fails to deliver a digital solution that meets the operational, clinical, and reporting needs of Mental Health & Learning Disabilities (MH&LD) and Community & Therapies services, Then wider MH&LD, Community and Therapies teams will lack access to timely, accurate, and shared information across care settings, resulting in fragmented service delivery, limited availability of high-quality data for performance monitoring and informed decision making, increased duplication of effort, and elevated clinical and governance risks. This includes the potential for further Regulation 28 reports, as previous Prevention of Future Deaths (PFD) notices have explicitly cited the absence of an integrated electronic system as a contributing factor to avoidable harm. Without a fit-for-purpose solution, the Health Board may be unable to fulfil the actions required under Regulation 28, particularly around effective information sharing and risk management across agencies. Whilst the issue facing current users across integrated teams from the loss of WCCIS will be largely mitigated through the approved procurement of replacement solutions through the strategic partnership with the supplier, there remains to be 3,000 users across MH&LD and PCT who continue to provide services without an appropriate digital solution to support them. The provision of a solution is a core component of the SBU Digital Strategy. A recent independent review of Mental Health and Learning Disability services at SBUHB identified the lack of a single digital solution as a critical barrier to safe and effective care, highlighting that fragmented systems and manual processes are contributing to clinical risk, delayed interventions, and repeated Regulation 28 reports due to inadequate access to shared electronic records. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: Likelihood – The Health Board have procured Rio as an Electronic Patient Record (EPR) for users in integrated teams that currently use WCCIS on the Swansea Council Contract. The strategic partnership to develop and inform Access Intelligent Care Platform (AICP) which is an integrated shared care record, is in place and will serve the integrated teams using WCCIS as well as teams in Mental Health and Learning Disabilities that were predominantly using paper. The wider roll out of an EPR for the 3,000 users across MH&LD and PCT will require additional funding and procurement activities. We continue to work with the National Connecting Care programme to inform the development of a shared care record, including funding to support a wider roll out across Community and Mental Health. Consequence – there would continue to be a significant impact on quality of care and capacity of the MH&LD and PCT teams. The organisation would fail to address the requirements of Regulation 28 reports and there would continue to be a lack of quality data to allow performance monitoring and informed decision making on service transformation. This has a wider impact on the health service provision across the health board, including secondary care. |  |  |  |
|  |  |  |  | Rationale for target score: Likelihood – If the health board introduce a solution for the wider community and mental health teams, then it is unlikely the consequence associated with system failure or not replacing the new system will occur and some reduction in risk level may be possible. Consequence – the consequence of not having a digital solution to support integrated teams and the wider community and MHLD teams will remain the same. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Local Programme Board has been established and is responsible for the delivery of Rio for paper-based teams and integrated WCCIS users. - Development of the business case for an EPR for wider roll out to Community and MH/LD. - Regional Program Board is in place to ensure HB and councils are working together and align implementation of solutions. - DHCW National Program Board is in place to deliver national approach. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Implement the new interim solution | Director of Digital |  | 31/12/2026 |
|  |  |  |  | Business case completed and approved for the provision of an Electronic Patient Record for the whole of Community and MH&LD | Director of Digital |  | 31/03/2027 |
| Assurances (How do we know if the things we are doing are having an impact?) - Digital leadership group will have oversight of the delivery of the actions of the Local Program Board and reports to Management Board - Digital, Data, Research and Innovation Committee will have oversight of the overall plan and act as escalation route to Health Board if required. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - The national approach has been delayed and is difficult to influence in terms of scope and timelines for delivery - The route to obtaining national funding to support the Health Board is not clear. |  |  |  |
| Additional Comments The Welsh Community Care Information System (WCCIS) was developed to provide staff across health and social services with a single system and shared electronic record to enable delivery of more effective and efficient services. It is used by health board teams within mental health and community services, in addition to local authority social services teams, but the system is now end of life, it is anticipated that it will be discontinued from September 2027. SBUHB users are mainly operating within Integrated Teams and access the solution via the Swansea Council’s contract with the system provider. - A business case for an interim solution to address the immediate needs of the current SBUHB users of WCCIS (integrated teams) was presented to and approved by Management Board on 19th December 2024. - The Health Board are continuing to support the National Program in the process for acquiring a longer-term solution - The procurement of the interim solution was completed at the end of 2025/26 and project implementation has commenced. - In September 2025 WG confirmed approval of funding to DHCW of the first year costs in the National OBC. Funding is only available in 2025/26 and a proportion of the funding is available to SBUHB to support the interim solution for integrated teams and next steps. There has been no formal commitment from WG of funding in future years. 19/03/2026 - Risk has been reviewed. The paper based teams for MHLD are on track to go live 24th March 2026. Manual migration of caseloads is underway to support this go live. The ongoing recruitment for phase 1 has been held up with recruitment restrictions; this has been escalated. Progress is ongoing with WCCIS Data Migration, Data Migration1 (demographics) has completed testing, Data Migration 2 (referrals) has commenced. Discussions are ongoing with Swansea Council and the supplier regarding the delay to implementation. 10/04/2026 - The paper-based teams for menta​l health LD went live on the 24th of March ​ |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: Mar 2026 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 109 Risk Target Date: TBC |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.8 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Access to Planned Care If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to meet the non-urgent physical and mental health needs of adults and children, there is a risk that we will be unable to improve access to timely, safe, effective, and person-centred planned care, resulting in a potential for patient harm, increases in length of stay, placement of patients in unsuitable places, and a negative impact on patient & staff experience |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 4 = 16 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: - TBC |  |  |  |
|  |  |  |  | Rationale for target score: - TBC |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Specialty level capacity and demand models set out the baseline capacity and identify solutions to bridge the gap in 2025/26. - Planned care trajectories have been developed (and shared with Welsh Government). - Processes are in place to monitor performance against those trajectories internally (and with Welsh Government as part of Targeted Intervention). - There is focused intervention within the 10 specialties with the longest waits to support delivery. - Long waiting patients are outsourced to the independent sector, where it is appropriate to do so. - Additional activity is being delivered on weekends (via insourcing), which is working towards reducing the wait for outpatient appointment to below 26 weeks. - There is ongoing internal and external validation of waiting lists - All long waiting patients receive clinical reviews to ascertain continued need for surgery. - Complaints and concerns in respect of waiting times are monitored to identify issues and trends. - A Planned Care Programme Board and the associated transformation programmes are in place across outpatients and theatres to develop services. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | The Clinical Committee which has been set up to support the Planned Care & Cancer Board (PCCB) will ask clinical leads from each of the services managed under the PCCB to review their arrangements against ‘optimal practice’ as determined by the national Clinical Implementation Network (CIN) and to present their findings to the PCCB. | Chief Operating Officer / Assistant Director of Ops Planned Care & Cancer |  | 28/02/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - A Targeted Intervention (TI) dashboard presents live data on performance to support monitoring by COO, performance and operational teams. - Weekly monitoring meetings chaired by the Assistant Director of Performance review/monitor progress against delivery plans. - Updates on metrics such as validation, clinical reviews, complaints & concerns are fed into Planned Care Board. - There are highlight reports that go to Planned Care Board on each of the programme streams. |  |  |  | Gaps in assurance (What additional assurances should we seek?) There is scope to improve assurance that Health Board processes are optimised. |  |  |  |
| Additional Comments / Progress Notes 30/03/2026: Risk transferred from former Strategic Risk Register Entry following Exec Team discussion. |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: Mar 2026 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 110 Risk Target Date: TBC |  | Current Risk Rating 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.8 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Access to Cancer Care If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to provide timely diagnosis and treatment of adults and children, there is a risk that we will be unable to improve provision of safe, effective, and person-centred cancer care, resulting in a potential for patient harm, poor outcomes, and a negative impact on patient & staff experience. This will impact not only on SBU patients but those of partner organisations depending on this health board as a regional centre for cancer care. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 4 x 3 = 12 |  |  |  | Rationale for current score: - TBC |  |  |  |
|  |  |  |  | Rationale for target score: - TBC |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Processes are in place to manage each individual case on the Single Cancer Pathway (SCP), with enhanced monitoring & weekly monitoring of action plans for top 6 tumour sites. - Initiatives are in place to protect surgical capacity to support Single Cancer Pathways. - Performance discussions by tumour-site focus on compliance with the following targets: - First outpatient appointment by Day 10 - Deliver a decision to treat (DTT) by day 31 - Outsourcing solutions are in place to support pathology turnaround times for urgent suspect cancer. - The COO is leading targeted discussions with most pressurised tumour sites to understand barriers to complying with national optimal pathways for cancer - Cancer improvement group meets monthly. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | New Assistant Director of Operations is reviewing governance arrangements and their operation to ensure they perform optimally. | COO |  | 28/02/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - A Targeted Intervention (TI) dashboard presents live data on performance to support monitoring at tumour site and health board scrutiny meetings. - Weekly Targeted Intervention monitoring meetings chaired by Cancer Services to review compliance with the 62 day pathway and track backlog volumes. - Bi-weekly Cancer meetings chaired by the Deputy Chief Operating Officer review NOP adherence and delivery of 62 day target - Planned Care & Cancer Board chaired by COO reviews Cancer Performance information. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Assurance of optimal effectiveness of control arrangements. |  |  |  |
| Additional Comments / Progress Notes 30/03/2026: Risk transferred from former Strategic Risk Register Entry following Exec Team discussion. |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: Mar 2026 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 111 Risk Target Date: TBC |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.4 | Director Lead: Liz, Rix, Executive Director of Nursing & Patient Experience Assuring Committee: Quality & Safety |  |  |  |
| Risk: Listening to People If we do not listen to and act upon the issues raised by people there is a risk that matters of concern to them will continue unaddressed, resulting in dissatisfaction, the potential for poor outcomes, greater regulatory intervention and loss of public trust and confidence. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 3 x 3 = 9 |  |  |  | Rationale for current score: - TBC |  |  |  |
|  |  |  |  | Rationale for target score: - TBC |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Putting Things Right framework. Complaints performance reporting. - Early resolution services (e.g., PALS) People’s Experience Framework. Compliments. - Stakeholder engagement structures (ARG, Bay Youth, MVP, BAME) - Community engagement events |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Implementation of framework once received. | Executive Director of Nursing & Patient Experience |  | 01/04/2026 |
|  |  |  |  | EDON review of concerns processes within service groups to look for potential improvements | Executive Director of Nursing & Patient Experience |  | 31/12/2025 |
| Assurances (How do we know if the things we are doing are having an impact?) - Divisional complaints handling - Service group quality and safety group oversight - Friends and Family and All Wales questionnaire data at service group level - Delivery of People’s Experience Framework - Directorate of Insight Communication & Engagement (DICE) reports to Patient & Stakeholder Experience Group (PSEG) - Llais membership of PSEG - Service group reporting to Patient Safety & Compliance Group (PSCG)(bi-monthly) - Patient Feedback Team reporting to PSCG (bi-monthly) - Beacon dashboard scrutiny (monthly in Exec Huddle) - Weekly executive quality and safety huddle - PSCG reporting to corporate Quality & Safety Group - Quality & Safety group reporting to Management Board and Quality & Safety Committe - Welsh Risk Pool Annual Assessment - Internal audit of People’s Experience Framework - Llais thematic reports |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Revised PTR framework being issued in 2025. - Number of overdue concerns within service groups. |  |  |  |
| Additional Comments / Progress Notes 30/03/2026: Risk transferred from former Strategic Risk Register Entry following Exec Team discussion. |  |  |  |  |  |  |  |

| Datix ID Number: 4842 Date Opened: Mar 2026 |  | Date Last Reviewed: Apr 2026 |  | CRR Ref Number: 113 Risk Target Date: TBC |  | Current Risk Rating 5 x 3 = 15 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Data, Research & Innovation |  |  |  |
| Risk: Sustainability and Refresh of Digital Systems and Infrastructure If the organisation is unable to sustainably support, maintain, refresh and replace its digital systems, devices and infrastructure in a timely manner, there is a risk that ageing and legacy technologies will become increasingly unstable, insecure and costly to support. This may increase the likelihood of system failures, cyber security vulnerabilities and unplanned disruption to clinical and corporate services. Contributing factors include capital and revenue funding constraints, extended refresh cycles, ageing infrastructure and systems, accumulating technical debt, and the ongoing need to support business‑as‑usual services while maintaining safe and reliable digital operations. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 3 = 15 Target: 5 x 2 = 10 |  |  |  | Rationale for current score: Consequence - Failure or significant degradation of digital systems, devices or infrastructure would have a major impact on patient safety, clinical service delivery, cyber security, business continuity and organisational reputation. Many core clinical and corporate functions are critically dependent on reliable, secure and available digital services, meaning the consequence of failure remains high. Likelihood - The likelihood of occurrence is currently material due to elements of the digital estate remaining ageing or approaching end of life, some refresh requirements not yet fully funded, and ongoing reliance on legacy systems pending replacement. Although controls are in place to manage and prioritise risk, extended refresh cycles and funding constraints mean disruption or increased cyber exposure remains plausible. |  |  |  |
|  |  |  |  | Rationale for target score: Consequence - The potential consequence of digital service failure remains high due to the critical nature of digital systems in supporting care delivery and organisational operations. Likelihood - The likelihood is expected to reduce as a result of continued delivery of funded technology refresh programmes, improved asset lifecycle management, strengthened cyber resilience for legacy systems, and clearer long‑term planning for infrastructure and device replacement. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Cyber Security Policy in place, supported by mandatory cyber security training for staff - Programme in place to manage and track legacy digital systems, devices and infrastructure - Multi‑year capital plans established for technology refresh, including networks, servers and end‑user devices - Risk‑based prioritisation approach to ensure highest‑risk systems and assets are addressed first - Digital feed into the annual capital plan and leverage the Welsh government national slippage programme - Active monitoring, patching and protection of networks, systems and infrastructure - Immutable backup solutions in place with defined recovery processes - Service‑level Business Continuity Plans in place, supported by EPRR arrangements to manage digital outages - Formal review process for major digital incidents, including lessons learned and follow‑up actions - Digital strategy and supporting roadmaps in place, including infrastructure and sustainability considerations |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Continue delivery of the technology refresh programme, prioritising end‑of‑life and unsupported assets | Director of Digital |  | 31/03/2027 |
|  |  |  |  | Review the 10-year financial plan for digital systems and infrastructure with Finance and incorporate into the 27/28 IMTP | Director of Digital |  | 30/09/2026 |
|  |  |  |  | Key systems to be reviewed for legacy and cyber security risks | Director of Digital |  | 31/12/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - Regular reporting on delivery of technology refresh programmes and capital schemes to DDRI and DSMG - Reduction in the number of unsupported or end‑of‑life systems and devices - Improved cyber security compliance and reduced critical vulnerabilities through NIS annual assessment - INFRAM assessment - Trend analysis showing infrastructure‑related incidents or service outages reported to the Business Meeting and DSMG - Oversight through Digital governance structures and assurance committees |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Confirmation of funding for future refresh cycles beyond current planning horizons |  |  |  |
| Additional Comments / Progress Notes 30/03/2026: Risk transferred from former Strategic Risk Register Entry following Exec Team discussion. 30/04/2026: Risk content refreshed |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: April 2026 |  | NEW RISK Date Last Reviewed: April 2026 |  | HBR Ref Number: 114 Risk Target Date: TBC |  | Current Risk Rating 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.7 | Director Lead: Deb Lewis, Chief Operating Officer Supporting Director(s): Tina Ricketts, Director of Workforce & OD; Liz Rix, Executive Director of Nursing Assuring Committee: Quality & Safety Committee for Information: Workforce & OD |  |  |  |
| Risk: Mental Health & Learning Disabilities Staffing If workforce shortages and fragility persist across Mental Health and Learning Disabilities services (vacancies, sickness, turnover, reliance on temporary staff and insufficient skill mix), then services will be unable to deliver safe staffing and consistent therapeutic input across community, crisis and inpatient pathways. This may lead to avoidable harm (including self-harm/suicide risk), increased restrictive practice, delayed access and extended length of stay, deteriorating staff wellbeing and retention, failure to meet national quality expectations and performance standards, and increased regulatory, financial and reputational impact. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 3 = 15 |  |  |  | Rationale for current score: Current score reflects sustained gaps in key professional groups and registered nursing establishments, variable staffing fill and reliance on temporary staffing in high-acuity settings. This reduces continuity of therapeutic engagement and increases risk of incidents, restrictive interventions, delayed discharge and deteriorating access performance. Controls reduce (but do not remove) the likelihood of harm through escalation and prioritisation processes. Inherent Risk: 5 x 5 = 25 (Catastrophic consequence; Likelihood is expected without controls due to sustained vacancy/absence and skill-mix gaps). Current Risk: 5 x 4 = 20 (Catastrophic consequence; Likelihood reduced but probable given current mitigating controls but ongoing fragility). |  |  |  |
|  |  |  |  | Rationale for target score: Target score assumes a remodelled model of care that reduces reliance on inpatient capacity, clarifies safe caseload/workload triggers, strengthens MDT capacity (including psychology/AHPs), and improves recruitment/retention so that staffing fill rates stabilise and temporary staffing reduces. Residual consequence remains major due to inherent clinical risk and demand volatility, but likelihood reduces to possible. Target Risk: 5 x 3 = 12 (Catastrophic consequence; Likelihood reduction to possible once remodelled pathways, strengthened MDT capacity and stabilised staffing). |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Establishment review and safer staffing oversight (including escalation where staffing falls below agreed thresholds). - Recruitment and retention activity for hard-to-fill roles (including international recruitment where appropriate) and use of temporary staffing controls. - Clinical escalation, bed/capacity management and daily operational oversight of staffing and acuity. - Workforce wellbeing support, mandatory training arrangements and supervision frameworks (where in place). - Mental Health Transformation Programme governance and workstreams (including service redesign/model of care development). |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Agree and implement a MH&LD workforce stabilisation plan (priority roles, recruitment pipeline, retention offers, sickness reduction actions) aligned to the remodelled clinical model. | ED Workforce & OD / COO |  | Q2 2026/27 |
|  |  |  |  | Reduce agency and bank dependency through phased milestones (roster optimisation, substantive recruitment, incentive packages, internal staff bank expansion) and monthly exception reporting to Exec. | ED Workforce & OD / ED Finance |  | Q4 2026/27 |
|  |  |  |  | Complete and approve the remodelled clinical model and demand/capacity plan (including safe caseload/workload triggers, pathway redesign and reduced reliance on inpatient beds where appropriate). | COO / MH&LD Clinical Leadership |  | Q3 2026/27 |
|  |  |  |  | Strengthen MDT therapeutic capacity (psychology, OT, SALT and other AHPs) and clinical supervision arrangements; implement a skills/competency framework for priority pathways. | ED Nursing / EDAHPHS / COO |  | Q2 2027/28 |
| Assurances (How do we know if the things we are doing are having an impact?) - Quality and safety intelligence: incidents/SIs, restrictive practice, violence/aggression, complaints and safeguarding themes triangulated with staffing and acuity. - Monthly workforce metrics (vacancy, sickness, turnover, staffing fill, reduction in temporary/agency staff spend) with exception escalation. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Need clearer Board-level assurance on whether current staffing and skill mix is safe and sustainable against the remodelled model of care (including agreed safe caseload thresholds and ward staffing templates). Independent assurance is required on effectiveness of mitigation (not just activity), including: measurable improvement in therapeutic contact/continuity; reduction in restrictive practice; improved access/flow; and reduced staff harm/absence. |  |  |  |
| Additional Comments / Progress Notes 06/05/2026: This is the first draft of CRR risk: This risk captures the cumulative impact of workforce fragility on delivery of safe and effective MH&LD care and the dependency on timely service remodelling to reduce pressure on inpatient and crisis pathways. 13/05/2026: Risk agreed by Executive Board and current score of 20 indicated. |  |  |  |  |  |  |  |

| Datix ID Number: TBC Date Opened: April 2026 |  | NEW RISK Date Last Reviewed: April 2026 |  | HBR Ref Number: 115 Risk Target Date: TBC | Current Risk Rating 5 x 4 = 20 |
| --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.7, 3.2 | Director Lead: Claire Osmundsen-Little, Director of Finance Supporting Director(s): Deb Lewis, Chief operating Officer; Liz Rix, Executive Director of Nursing Assuring Committee: Performance & Finance Committee Committee for Information: Quality & Safety |  |
| Risk: Mental Health & Learning Disabilities Estate If the condition, configuration and security of the mental health inpatient, crisis and community estate (including ligature risks, blind spots, backlog maintenance, ageing infrastructure, water/heating/ventilation vulnerabilities and inadequate seclusion and Section 136 facilities) cannot be stabilised and improved at pace, then the Health Board may be unable to provide safe, therapeutic and dignified care. This may result in serious harm or death (including self-harm/suicide risk), increased violence/aggression and restrictive practice, service disruption or temporary closure/decant due to infrastructure failure, failure to meet statutory health & safety requirements, national standards and HIW expectations, and significant regulatory, financial and reputational impact. |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 3 = 15 |  |  |  | Rationale for current score: Current score reflects that significant environmental hazards and infrastructure fragility remain across parts of the MH estate (including ligature and observation challenges, inadequate therapeutic space and privacy, and maintenance/security concerns). While interim controls reduce risk, incidents and near misses remain likely and the residual consequence is major given the patient cohort and potential for serious harm and regulatory action. Inherent Risk: 5 x 5 = 25 (Catastrophic consequence; Likelihood is expected without controls due to known high-risk environments and infrastructure vulnerabilities). Current Risk: 5 x 4 = 20 (Catastrophic consequence; Likelihood reduced but probable due to residual ligature/observation risks, security incidents and backlog maintenance despite mitigations). |  |
|  |  |  |  | Rationale for target score: Target score assumes delivery of an agreed estates stabilisation plan (including highest-risk ligature and observation mitigations), improved security arrangements, and implementation of an interim reconfiguration/decant solution while the long-term reprovision business case progresses. Consequence remains major due to inherent clinical risk, but likelihood reduces to possible as environmental hazards and infrastructure failure risk reduce. Target Risk: 5 x 3 = 15 (Catastrophic consequence; Likelihood reduction to possible once stabilisation works and interim/long-term solutions materially reduce environmental hazards and business continuity risk). |  |

| Controls (What is currently in place to manage the risk?) | Further Actions (What more are we going to do to address the risk?) |  |  |
| --- | --- | --- | --- |
| - Environmental and ligature risk assessments/audits with prioritised mitigation actions (including observation and practice controls where estates fixes are not immediately possible), with site-level action tracking. - Estates maintenance response, backlog maintenance prioritisation and statutory compliance processes for the MHLD estate, with escalation of critical infrastructure defects (water/heating/ventilation/electrical) and infection prevention considerations. - Additional controls include: security measures and incident response (e.g., access control, management of break-ins); seclusion/Section 136 governance and compliance monitoring; quality and safety walkarounds; and transformation programme estates workstream governance and options appraisal for interim/long-term solutions. | Action | Lead | Deadline |
|  | Deliver an MHLD inpatient, crisis & community estates stabilisation plan focused on highest-risk ligature / observation hazards, sanitation, privacy/dignity and therapeutic environment improvements, with funded milestones and weekly oversight. | Interim ED Finance / COO (MH&LD) | Q2 2026/27 |
|  | Implement a violence reduction, restrictive practice reduction and staff safety plan in inpatient, crisis and community settings (training compliance, de-escalation capability, incident learning and environmental mitigations). | ED Nursing / MH&LD Service Group | Q3 2026/27 |
|  | Complete options appraisal and decision on interim reconfiguration/decant (including Section 136/crisis suite and compliant seclusion provision), with patient experience, equality, workforce and business continuity impacts explicitly assessed. | Interim ED Capital & Estates / COO (MH&LD) / ED Planning | Q3 2026/27 |
|  | Implement an estates business continuity and security resilience plan for MHLD sites (priority utilities, fire/water ingress mitigation, access control, anti-intrusion measures and tested decant/contingency arrangements). | Assistant Director Estates / Local Security Management / COO (MH&LD) | Q4 2026/27 |
| Assurances (How do we know if the things we are doing are having an impact?) - Environmental risk assurance: routine ligature/environmental audit compliance, actions closed on time, and independent validation/walkaround assurance for highest-risk areas. - Quality and safety intelligence linked to environment: incidents/near misses (self-harm, violence/aggression, restrictive practice), HIW feedback, complaints/patient experience themes and staff safety metrics, triangulated with estates defects and security incidents. | Gaps in assurance (What additional assurances should we seek?) - Board-level assurance is required that (1) the highest-risk environmental hazards are identified consistently and reduced in a measurable way; (2) there is a clear, costed and deliverable stabilisation plan to bridge to an interim and long-term solution; and (3) the risk of service disruption from infrastructure failure (utilities, flooding/water ingress, fire safety, security) is understood and controlled. Independent assurance should evidence impact, not only activity (e.g., reduction in ligature risks, fewer environmental-driven incidents, improved privacy/dignity and therapeutic space, and improved HIW compliance at across sites. |  |  |
| Additional Comments / Progress Notes 06/05/2026: This risk captures the compounding quality, safety and business continuity threat created by the condition, configuration and security of the MHLD estate and the dependency on stabilisation works and interim/long-term reprovision. 13/05/2026: Risk agreed by Executive Board and current score of 20 indicated. |  |  |  |

| Datix ID Number: TBC Date Opened: May 2026 |  | NEW RISK Date Last Reviewed: May 2026 |  | CRR Ref Number: 116 Risk Target Date: N/A (See Target Score Rationale) |  | Current Risk Rating 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  | SRR Ref: 2.7 | Director Lead: Executive Director of Nursing and Patient Experience Supporting Director: Executive Medical Director Assuring Committee: Quality and Safety Committee |  |  |  |
| Risk: Maternity Services Site There is a risk that women and birthing people requiring emergency obstetric intervention and/or escalation to intensive care will experience delay, clinical deterioration or poorer outcomes because obstetric services are not co-located on the same site as ITU facilities (the only perinatal service without co-located ITU in the UK), emergency services and acute specialties at Morriston Hospital. This may affect the timeliness of access to critical care, multidisciplinary decision-making, transfer arrangements and the organisation’s ability to provide care in line with best practice expectations for critically ill women in childbirth. Potential consequences include avoidable harm to mothers and babies, delays in treatment, increased reliance on emergency transfer and escalation processes, regulatory concern, reputational damage and failure to meet expected maternity safety standards. It additionally, requires the movement of teams from the Singleton site when these transfers are required or deliveries occur at Morriston, leaving Singleton site vulnerable without senior cover out of hours (the same consultant covers gynaecological emergencies and that leaves the Labour without senior cover). Specialists such as surgeons, vascular access specialists, and cardiology are also unable to cross-cover Singleton to assist critically unwell women on site due to rota restrictions. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 5 x 4 = 20 |  |  |  | Rationale for current score: The current score remains very high because the absence of co-located obstetric and ITU services creates an inherent time-critical safety vulnerability for a small but high-risk cohort of women requiring urgent escalation. Although mitigation arrangements exist, the service model still depends on rapid recognition, senior decision-making, stabilisation and transfer between sites or services, with residual risk relating to delay, communication, capacity and operational reliability. None of the mitigations reduce the risk significantly and as escalation is dependent upon finding additional clinical teams and goodwill or displacing the risk between Singleton / Morriston sites. |  |  |  |
|  |  |  |  | Rationale for target score: Target score reflects effect of current actions. However, following consideration of the options appraisal there may be opportunities to identify further action to reduce score and indicate lower target. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Current controls include consultant-led obstetric care at [Singleton Hospital], obstetric anaesthetic support, established escalation procedures for acutely unwell women, access to general ambulance transfer, involvement of senior maternity, anaesthetic and critical care staff in complex cases, use of maternal early warning systems, emergency drills/training, incident reporting, and governance oversight through maternity safety and quality arrangements. However, none of these mitigations reduce the risk significantly and as escalation is dependent upon finding additional clinical teams and goodwill or displacing the risk between Singleton / Morriston sites. - Services undertake and evidence simulation testing of emergency scenarios involving severe maternal deterioration, including transfer to critical care, and implement learning from debriefs and incidents. (This has a limited effect on risk level.) |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Complete a multidisciplinary review of the current obstetric critical care escalation pathway, including triggers for escalation, roles, decision points, transfer arrangements and documented clinical handover standards. | Head of Midwifery / Clinical Director for Women and Children / Critical Care Lead |  | Completed (April 2026) |
|  |  |  |  | Develop a longer-term options appraisal and risk reduction plan for sustainable access to critical care for obstetric patients, including estate/service model options and dependencies on strategic capital planning. | Executive Director of Nursing and Patient Experience / Medical Director / Capital Planning Lead |  | 31/03/2027 |
|  |  |  |  | There is an OCP underway to split the Obstetric & Gynaecology consultant rota so that a dedicated Gynaecology consultant is available out of hours to attend Morriston gynaecology emergencies, thereby sparing Obstetric cover at Singleton. | Directorate Manager & Clinical Director O&G |  | 30/11/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - A quantified assurance framework is in place covering response times, transfers, maternal critical care activity, incidents, near misses, compliance with escalation policy and exception reporting to the Quality and Safety Committee. - Regular review of serious incidents, near misses, transfers and deterioration events involving obstetric patients. - Audit of compliance with escalation and transfer pathways, outcomes from multidisciplinary simulation, and committee review of maternity safety metrics and exception reports. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Further assurance is required on the timeliness and reliability of access to critical care for obstetric emergencies, the adequacy of enhanced maternal care capability, transfer response standards, out-of-hours resilience, and whether the current configuration can consistently meet recognised maternity and critical care expectations. Longer term options to address risk need to be developed. |  |  |  |
| Additional Comments / Progress Notes |  |  |  |  |  |  |  |

Risk Score Calculation

For each risk identified, the LIKELIHOOD & CONSEQUENCE mechanism will be utilised.  Essentially this examines each of the risks and attempts to assess the likelihood of the event occurring (PROBABILITY) and the effect it could have on the Health Board (IMPACT).  This process ensures that the Health Board will be focusing on those risks which require immediate attention rather than spending time on areas which are, relatively, a lower priority.