Engagement Plan for Gorseinon Hospital

Proposed Engagement Period 1 September – 19 October 2026 (8 weeks)

This allows for the proper preparation of engagement materials in multiple formats and addresses Llais feedback regarding engaging during August

PREPARATORY WORK

| Due Date | Activity |
| --- | --- |
| 27.7.26 | Draft engagement plan / timeline for Llais |
| 27.7.26 | Draft engagement document |
| 27.7.26 | Executive Team consider engagement plan, proposal and IIA |
| 31.7.26 | Complete Llais proforma for permanent transfer of beds including IIA |
| 30.7.26 | Amend engagement document with internal comments |
| 31.7.26 | Send engagement document and revised engagement timeline to Llais |
| 10.8.26 | Preparation of the distribution lists for engagement |
| 12.8.26 | Executive Team consider engagement document, plan and feedback from Llais |
| 4.9.26 | Translation of documents into - Welsh - Audio - BSL - Easy Read (3 weeks required) – send off by 14.8.26 |
| 26.8.26 | Exec Board meeting to sign off final engagement document, plan and timescale (if not achieved on 12.8.26) |
| 28.8.26 | Development of display boards including QR code for feedback to be on display at: - Gorseinon Hospital - Singleton Hospital - Mobile set for drop in events |
| 28.8.26 | Development of slide deck for standard presentation to staff / public / stakeholders |
| 28.8.26 | Development of leaflet on engagement with QR code for printing |

ENGAGEMENT ACTIVITY

| Due Date | Activity |
| --- | --- |
| 1.9.26 | Start of public engagement |
| 1.9.26 | Information goes live on internet |
| By 1.9.26 | Distribution of Engagement Materials to: - Politicians (MPs, MS, County Councillors, Town and Community Councillors) - Third sector network - SRG, HPF, PF - BaYouth - Older Peoples Network Swansea - Swansea Disability Network - Sensory Impairment Groups – Swansea Deaf Club, Sight Loss Group - RPB Peoples Forum - Carers Forum - Swansea Carers Centre - Groups / individuals on the stakeholder list |
| From 1.9.26 | Inclusion in Comms channels e.g. - Abi’s Midweek Message - Intranet bulletin - Team Brief - Cascade within Service Groups |
| From 1.9.26 | Set up Display Boards - Gorseinon - Singleton Hospital |
| w/c 14.9.26 | 2pm – 7pm X1 Face to Face Drop in Gorseinon area |
| w/c 21.9.26 | 2pm – 7pm X1 Face to Face Drop in Swansea City Centre |
| w/c 28.9.26 | Mid-point review with Llais |
| w/c 28.9.26 | X1 online conversation am / pm |
| w/c 5.10.26 | X1 online conversation evening |
| w/c 5.10.26 | Last push to encourage responses |
| TBC | Staff engagement activities |
| 19.10.26 | Engagement closes |

CONSCIENTIOUS CONSIDERATION

| Due Date | Activity |
| --- | --- |
| 20.10.26 – 2.11.26 | Review of the feedback from engagement |
| 3 Nov | Share feedback / update with Llais |
| 9 Nov | Engagement report and revised IIA included in ET paper |
| 11 Nov | Exec Team consider outcome of engagement, revised IIA & feedback from Llais |
| 13 Nov | Development of Board paper on outcome of engagement and subsequent proposed decision including mitigations |
| 19 Nov | Board papers published |
| 26 Nov | Board consideration of outcome of engagement and subsequent decision including IIA and mitigations |
| 27 Nov | Decision is shared with stakeholders and people who responded to the engagement |

The above plan is subject to agreement with Llais.