| Meeting Date | 31 July 2025 |  | Agenda Item |  |  | 6.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Health Board |  |  |  |  |  |
| Report Title | Mental Health Transformation |  |  |  |  |  |
| Report Author | Melanie Walker / Nerissa Vaughan |  |  |  |  |  |
| Report Sponsor | Deb Lewis |  |  |  |  |  |
| Presented by | Melanie Walker/Nerissa Vaughan |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To provide the Health Board with; - A general update on the Mental Health Transformation Programme - A detailed overview of the estates components of the programme - including an assessment of the existing estate, a summary of previous consultations and the work plan for addressing the estate risks |  |  |  |  |  |
| Key Issues | In February 2025 the Board received In Committee the initial findings of the Independent Expert’s review of the Health Board’s Mental Health Services. There were a number of serious concerns raised in the report and a number of immediate, medium term and long- term actions were recommended. At a Special Board in June 25 an update was given on actions that had been completed or were in progress. The paper raised a number of serious concerns about the estate and environment. This paper gives a further update on the overall Transformation Programme. One of the approved recommendations of the report was to develop proposals to consider options for an interim solution to address the safety and quality of the adult and older people’s inpatient estate ahead of a new business case for the permanent reprovision of inpatient services. The aim was to address the serious concerns. This paper provides an update to the Board on the work around the development of an overall estates plan associated with the Transformation Programme to give context to the interim solution and provides an update on the immediate works being undertaken to address the estate risks. The aim is to bring a more comprehensive assessment of the interim solution options to the meeting of the Board in September seeking approval to proceed. It will also seek approval to proceed with the development of a Business Case for the Permanent solution alongside. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the update on the work being undertaken on the overall Mental Health Transformation Programme - CONSIDER the existing position in relation to the Mental Health Services’ estate - CONSIDER the previous consultation exercises undertaken with the commitments made by the Health Board - ENDORSE the work currently being undertaken to address the risks associated with the Mental Health Services’ estate - APPROVE that a more comprehensive paper is developed on the Interim Solution – Temporary Moves, providing a full option appraisal, capital and revenue considerations and seeking approval to proceed on the preferred option |  |  |  |  |  |

Mental Health Transformation

- INTRODUCTION

In February 2025 the Board received In Committee the initial findings of the Independent Expert’s review of the Health Board’s Mental Health Services. There were a number of serious concerns raised in the report and a number of immediate, medium term and long term actions were recommended. At a Special Board in June 25 an update was given on actions that had been completed or were in progress. The report raised a number of serious concerns about the estate and environment This paper gives a further update on the overall Transformation Programme. One of the approved recommendations of the report was to develop proposals to consider options for an interim solution to address the safety and quality of the adult and older people’s inpatient estate ahead of a new business case for the permanent reprovision of inpatient services. The aim was to address the serious concerns. This paper provides an update to the Board on the work around the development of an overall estates plan associated with the Transformation Programme to give context to the interim solution and provides an update on the immediate works being undertaken to address the estate risks.  The aim is to bring a more comprehensive assessment of the interim solution options to the meeting of the Board in September seeking approval to proceed. It will also seek approval to proceed with the development of a Business Case for the Permanent solution alongside.

- BACKGROUND

  - Mental Health Transformation Programme

Given the urgency of some of the challenges faced by the Health Board and the need for a focused internal programme of work, the Board supported the proposal that an Organisational Transformation Programme should be developed to mobilise actions across the Health Board to enable rapid improvements in Quality and Safety and be the main driver of the necessary short to medium improvement in mental health services described in the Independent Expert’s paper to the Board in February. An update on the establishment of the Programme was given to the Board in June.

The programme structure is set out in the diagram below:

A Project Initiation Document has been developed and been agreed by the Executive Team. The workstreams have multi-disciplinary membership and are chaired by leaders from across the organisation. Most of the workstreams have now been formally established. Two of the workstreams – Informatics and Estates are currently working in a temporary Task and Finish model, given the complexity of the challenges facing these workstreams. The aim is to establish these as formal workstreams as soon as possible.  The risks identified in the revised Service Group risk register form part of each of the workstreams work programme. There is a driver group which is chaired by the Board’s independent expert.  The purpose of the driver group is to ensure connection and challenge between the workstreams and that the necessary changes deliver at pace.  This group will report into the Health Board’s Programme Board.

Since the update provided to the Board in June significant progress has been made in the Informatics Task and Finish group. As the Board is aware, currently Mental Health and Learning Disability patient and service data is largely managed through paper records and manual systems. Mental Health and Learning Disability services were not included in the Health Board rollout of the Electronic Patient Record. Waiting list management is largely a manual collation of data.  Whilst some of these limitations are as a result of national priorities and decisions, it has been recognised that the Health Board needs to rapidly improve its mental health and learning data collection and analysis supported by the development of an appropriate electronic system. The Task and Finish group was established to undertake an assessment to gain a comprehensive understanding of the current landscape, including the number and variety of data sources in use and the specific reporting requirements tied to each.

An initial baseline assessment has been completed to understand the current state of both digital and paper-based processes in use across Mental Health teams, which includes the following.

- Reporting requirements

- Data source e.g. Access Database, excel spreadsheet, WCCIS

- Estimated number of monthly referrals

- No of patients on the caseload

- Number of WTE staff in each team

A short – term Improvement Plan has been developed which risk assesses and prioritises the various teams with the aim of moving them from paper based to an electronic system. The longer term plan is to migrate to the Rio system which is currently being procured.

The use of the Health Care Professional (HCP) module of WPAS as an interim solution has been agreed for the Crisis Resolution Team and the SPOA Team with a  go live on September 1st, 2025. These teams were considered the highest priority and posed the highest risk.

Implementing the HCP module across both teams as an interim solution ahead of the longer-term solution will provide the following benefits.

- It will provide data to underpin planning and performance across Mental Health services.

- It will enable the teams to move away from the use of access databases, excel spreadsheets and manual processes which are inefficient, error prone and difficult to manage.

- It will enable teams to standardise processes, improve data accuracy and reporting solutions.

- It will provide an invaluable opportunity for learning, including building digital confidence across teams which will inform the smooth transition to the longer-term solution.

- It will address the immediate operational pressures caused by using outdated systems and manual processes.

The remaining teams have been prioritised with detailed implementation plans being developed for sign off at the next Task and Finish Group.

The Service Redesign Group has also begun work. The programme has been divided in two (Planned, Unscheduled) to support this. The priority areas have been agreed as follows;

- SPOA

- Home Treatment/Crisis Teams

- Community Services including the Community Mental Health Teams

This work spans agencies and it is essential that this is done in a multiagency, multi disciplinary environment. Membership of the workstream includes Local Authority membership. This work will also link to RPB governance.

The Quality and Safety workstream has met and agreed it’s key deliverables these are;

- Identify quality and safety metrics for MHLD services to be used at the Departmental Service Group, Corporate and Board level

- Ensure processes are in place to oversee incident reporting and concerns management

- Detailed assessment of mortality within the service

- To identify and mitigate risks to patient safety and/or provision of high quality services

- The development of a clear risk register and ongoing process to maintain accuracy and relevance

- Improvement in the oversight of the coroner process and recommendations

- To oversee the timely delivery of Improvement Plans relating to external regulators (e.g. Healthcare Inspectorate Wales, Public Services Ombudsman)

- The development of a Quality Management System to support the service and promote a culture of continuous improvement and learning

The Workforce workstream is not as advanced – the membership has been agreed and draft Terms of Reference have been developed. The key deliverables will be agreed at it’s first meeting during July.

The activity supporting estates is covered in the latter part of the paper.

  - Overview of the existing estate

None of the existing estate is compliant with the Royal College of Psychiatrists’ Standards for Inpatient Mental Health Services or the standards which are described in the recently published All Wales Mental Health and Wellbeing Strategy. Much of the estate is in visibly poor condition and not fit for purpose but even the estate which appears to be more modern has a number of deficits. Overall, the accommodation is often cluttered, does not provide adequate heating/cooling control or provides accommodation which is difficult to nurse with poor observation. There are ligature risks in all areas and insufficient alarm raising capacity. There is also insufficient availability or single en-suite rooms in much of the estate and often inadequate bathroom facilities. Disabled access is problematic in the oldest estate.

Adult Mental Health Services

- Acute Adult Mental Health Services (AMHS) are provided over 3 wards, two at Cefn Coed and one at Neath Port Talbot hospital – there are in 54 beds in total.

- Section 136 Suite is provided in rooms in Ward F, Neath Port Talbot Hospital

- Psychiatric Intensive Care is provided through 4 beds at Princess of Wales Hospital, Bridgend.

- Perinatal Mental Health Services are provided through 6 beds in a dedicated unit at Tonna Hospital

Tawe Clinic - Cefn Coed Hospital:

Cefn Coed Hospital is one of only two remaining functional mental health hospitals from the 1930s in the UK. Most of the wards have been decommissioned and isolated from the active estate. A small area of the oldest site remains operational, providing treatment wards (Wards Clyne and Fendrod) for adults of a working age. The two wards provide 33 beds.

The supporting infrastructure (water and heating) as well as some of the patient accommodation was upgraded during 2016. This addressed the most pressing estate issues (i.e. immediate risk of failure) and was intended to extend the life of the site by 5 years. The age and structure of the building, with the extensive presence of asbestos, coupled with the antiquated infrastructure means that further extensive upgrade is not considered feasible. The estate and environment is of very poor quality and does not provide a therapeutic environment in which to receive or provide care.

Ward F, Neath Port Talbot Hospital

This provides the third Adult Mental Health inpatient ward in 21 beds.  It is provided in newer accommodation being situated within Neath Port Talbot Hospital which is a PFI facility. The ward also provides the Section 136 Suite and Seclusion Suite. The fabric of the building is good and there en-suite facilities and outside spaces for patients. There are, however, design issues with the ward with poor lines of sight, ligature risks and a very small isolated Section 136 suite which is not fit for purpose. The bathroom facilities are shared with the Seclusion Suite. This is also isolated from the main ward and poses safety risks for patients and staff. Both these areas have poor temperature control and adequate ventilation.

The ward operates as an initial assessment ward with onward patient movement to Cefn Coed following assessment.  Due to the lack of disabled access in Cefn Coed, a number of patients remain for their entire stay at Ward F.

Psychiatric Intensive Care is provided in 4 beds at the Princess of Wales Hospital in Bridgend through the LTA with Cwm Taff Morganwg Health Board.

The Perinatal Mental Health Unit (Uned Gobaith) is located at Tonna Hospital providing 6 beds. This unit delivers Regional Services to the South Wales population and are commissioned by JCC. The clinical services provide high quality modern care. The Unit was set up as a temporary solution in repurposed accommodation. Whilst the design of the unit has been imaginative, there is a lack of space and layout compromises have been made. It’s geographical location is remote and the unit is isolated in relation to other mental health services.

Older Peoples Mental Health Wards

- The Older People’s Mental Health Services (OPMHS) are provided over 4 wards on 2 sites. Suite 2, Tonna Hospital and Ysbryd y Coed, Cefn Coed Hospital. There are 78 beds in total

Tonna Hospital

Tonna Hospital was first commissioned and opened in 1991. From opening it has provided In-patient Older Adult Mental Health Services. The facility currently provides the Older Peoples Mental Health Service for the Neath/ Port Talbot population. There are 18 beds. The accommodation is dated and doesn’t aid the delivery of modern Older People’s Mental Health Services – mixing functional mental health with dementia care. It is crowded and has limited ensuite facilities. Bathroom facilities are limited.

As part of the Covid response in 2020, there was a need to maximise acute beds on acute hospital sites. This resulted in Older People’s Mental Health services being consolidated on the Tonna Hospital site from Ward G in Neath Port Talbot Hospital. This enabled a reduction of sites from 3 to 2.

Ysbryd y Coed – Cefn Coed Hospital

Ysbryd y Coed at Cefn Coed Hospital has 3 wards and a total of 60 beds. The facility was opened in the early part of the millenium and currently provides the Older Peoples Mental Health Service for the Swansea population. The accommodation is in a newer facility at the back of the Cefn Coed site away from the original building. The infrastructure to support the facility is independent of the original building. Whilst it is newer estate, it has not been well maintained and there are design faults with the building’s roof which are being repaired. The wards have a large footprint and are of a design which was fashionable at the time of construction but which does not reflect modern best practice. The ward design does not enable good observation of patient care and are, therefore, difficult to nurse. The wards are expansive in nature, making it difficult for elderly people to navigate.

Substance Misuse Inpatient Services

- Substance Misuse Inpatient Services are provided in a dedicated unit of 5 beds on Ward F, Neath Port Talbot Hospital.

Calon Lan Inpatient Substance Use Detox Unit:

This facility is situated in Ward F in Neath Port Talbot Hospital. It provides inpatient planned detox services (both alcohol and drugs) and are commissioned by the Area Planning Board. The accommodation is in modern purposed designed facilities.  It’s location, however, is unusual as most facilities of this nature are co-located with physical health services (acute medicine and gastroenterology) due to the medical needs of the cohort of patient. A national review of Inpatient Detox is due to commence.

  - Overview of Previous Consultations

There have been a large number of consultations undertaken by the Health Board on Mental Health Estate Improvements of which the Board needs to be aware.

These consultations are detailed below;

- Public consultation on proposals for adult mental health acute assessment facilities - Neath Port Talbot Hospital (Nov 2013 – March 2014)

- Engagement to develop the Western Bay Regional Partnership Board Adult Mental Health Strategic Framework (Nov 2016 – Nov 18)

- Engagement on Experience of OPMHS in Swansea & NPT and Proposed Permanent Closure of 14 beds at Tonna Hospital - Feb 2020

- Public engagement on proposed changes to Older People’s Mental Health Services in Swansea Bay (June – Jan 2022)

- Engagement on Changing for the Future – Our Proposal for the future location of Adult Acute Mental Health Assessment Beds in SBUHB (Jan – April 2022)

As a result of the consultations there were a number of themes which emerged and should be noted;

- The importance of community - based care as the preferred means of supporting people with an acute mental health problem was roundly endorsed.

- There was agreement that there was the need to provide facilities that are modern, fit for purpose and offer improved service user experiences in terms of dignity, respect and safety.

- Agreement that improved facilities are required to replace Cefn Coed Hospital

- Agreement that providing single rooms and private toilet facilities is a requirement for helping to deliver gender sensitive services; to treat people with dignity and respect, and to help people to feel safe when in hospital, which improves their recovery.

- Agreement that concentrating resources on a single site to improve equity of services is helpful although questions about how much of a difference centralisation would make were raised.

- In general terms the intention of moving to a single unit was understood but there were a number of responses where people believed that better facilities and improved outcomes should be delivered through having hospital beds closer to where people lived.

- There were specific concerns about a single integrated site for Older People’s Mental Health Services and objections to proposals that sought to achieve this.

- Concern that the additional travel for people who need to be admitted to hospital will result in a burden that may not be offset by the improved facilities and care that are anticipated

- Concern that the community services are not sufficiently resourced to provide care that reduces the need for hospital admissions and that the number of acute beds will be insufficient for future demand (both in terms of cost and time taken to travel).

- Concerns over any reduction in bed base

- Concern that there may not be sufficient physical space on any specific site or indeed the potential to provide safe external and therapeutic environments for clients.

- Some people felt that travelling further to receive appropriate care was acceptable but that the currently available transport was inadequate and consequently people in hospital will not receive supportive visits from family and friends that aid recovery.

- Concern about impacts of any new build unit on the surrounding environs – road infrastructure, congestion and local amenities

- Green space for patient’s was stressed as were facilities such as Cafés, quiet meeting areas for visiting, sufficient car parking

- Integrated units were seen as a way of joining up working across the organisation as well as improving partnership with other agencies.

- THE DEVELOPMENT OF THE MENTAL HEALTH TRANSFORMATION PROGRAMME - ESTATES PLAN

The Estates workstream (which is currently operating as a task and finish group to rapidly develop the work plan) has developed a work plan which is divided into 3 components;

- Short term essential improvements to the estate to mitigate the highest risks and improve the environment for patients and staff

- Interim solution (temporary moves) to reconfigure the estate to ensure that use of the best estate is maximised and that pathways are reconfigured to improve patient care

- Long term solution – to design and build a purpose built, fit for purpose Adult Mental Health and Older People’s Mental Health facility. This will reinvigorate the existing work that has been undertaken on the previous Outline Business Case and bring this to fruition

The aim is to cover an 8 year period, recognising that a purpose built facility will take time to develop from business case to build, commissioning and then opening. It is not considered feasible to remain in the existing estate for this length of time and a temporary solution is, therefore, needed to cover this interim period. Even this temporary solution will take time to deliver and a short- term programme has, therefore, been developed which addresses some of the highest risks and makes improvements to the worst of the environment. Alongside all of this will be the commencement of the longer- term work on the permanent solution.

Short term essential improvement

The following is included in the short- term programme funded through Transforming Estate Fund (TEF)

- Replace the Uned Gobaith roof (Tonna Hospital)

- Upgrades to the Seclusion Suite (Neath Port Talbot Hospital)

- Upgrades to the door entry system (Caswell Clinic)

- Upgrades to the Nurse Call system

- Drainage Repairs

- External assessment of ligature risks

- Upgrades to the Tawe clinic – these include;

- Improvements to the court yard areas

- Replacement of flooring

- Upgrades to the kitchen areas

- Bedroom Repairs

- Bathroom Upgrades

- Lighting replacement

- Window repairs

- Encasement of TVs

- Ligature Risk improvements

- Replacement of old and broken furniture

Procurement has already begun on this work and it is intended that these are delivered over the course of 2025/26. The external assessment of ligature risks was undertaken over the period 18-21st July. The report is awaited.

Interim Solution – Temporary Moves

Work has commenced on assessing the potential options available to the Health Board to relocate services in the interim – in advance of a purpose designed permanent solution.

This has been a complex exercise and further work is required on refining the options and ensuring there has been engagement upon them. A paper will come to the meeting of the September Board which describes these in more detail and will propose a preferred option and seek approval to proceed.

The objectives of the option development have been as follows;

- Improving the quality of the environment for patients

- Improving the sustainability of the estate

- Reducing the fragmentation of clinical pathways

- Improving the adjacencies of clinical services

- Consolidation of sites

- Enhancing the workforce model to ensure that staff are deployed as effectively as possible.

- Enhancing the workforce model to ensure that staff are supported in their skills and professional development

- Reducing the current safety risks to patients

It should be noted that the Interim solution is not intended to be permanent and none of the options offers a perfect solution.

There have been a number of considerations and constraints when developing the options – these are detailed below;

- Physical space considerations – ensuring that the ward areas are able to accommodate the required number of beds/facilities without altering the overall footprint (due to time and cost)

- Ensuring that services are appropriately co-located whilst trying to minimise the travel requirements for patients and their families

- Reducing the decant requirements to simplify the programme and expediate the delivery

- Balancing the needs of Older People’s Mental Health Services against Adult Mental Health Services

- Reducing the disruption to staff whilst ensuring that patient care needs are maximised

- Delivering the programme as quickly as possible but still meeting the objectives as described

- Ensuring that services are delivered as efficiently as possible

- Maximising and altering the best of the estate whilst recognising that these are not purposed designed facilities

- Recognising the estate infrastructure (water ,heating, building structure) constraints of  the Cefn Coed site

Long term solution – to design and build a purpose built, fit for purpose Adult Mental Health and Older People’s Mental Health facility.

The Mental Health Transformation Programme includes a Service Redesign Workstream. This has commenced on developing a revised service model along with modernising service provision to reflect the evidence base and best practice. This will inform the future state and with it the facility requirements.

The Estates Workstream has revisited the previous SOC and associated consultation work (as described above) and following Health Board approval, will start to develop a revised business case to support the Long Term Solution

A paper will come to the meeting of the September Board to seek approval to progress the development of a revised business case and recommence discussions with Welsh Government on the process required around this.

- GOVERNANCE AND RISK ISSUES

The Board received an update from the Independent Expert at it’s June meeting. This highlighted the known risks associated with the Health Board’s Mental Health Services. The report highlighted the risks associated with the Estate and this paper describes the programme of work intended to address these.

- FINANCIAL IMPLICATIONS

The short- term essential improvements described earlier in this paper are funded through approved TEF funding. The Interim Solution - Temporary moves options are currently being refined and fully costed. These will be presented to the Board in September. The Long Term solution will be subject to a business case and costed in line with these requirements.

- RECOMMENDATION

The Board is asked to:

- RECEIVE the update on the work being undertaken on the overall Mental Health Transformation Programme;

- CONSIDER the existing position in relation to the Mental Health Services’ estate;

- CONSIDER the previous consultation exercises undertaken with the commitments made by the Health Board;

- ENDORSE the work currently being undertaken to address the risks associated with the Mental Health Services’ estate; and

- APPROVE that a more comprehensive paper is developed on the Interim Solution – Temporary Moves, providing a full option appraisal, capital and revenue considerations and seeking approval to proceed on the preferred option

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| There are significant risks to Quality of Care highlighted in the initial findings of the Independent Expert in her report to In- committee meeting in February. The Mental Health Transformation Programme has been set up to address these risks. This paper updates on the main programme and specifically highlights the mitigations to the risks associated with estate |  |  |  |
| Financial Implications |  |  |  |
| The committed expenditure identified in the paper is covered under the TEF funding received by the Health Board. The interim and permanent solutions will be subject to a capital business case. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Mental Health Act compliance. |  |  |  |
| Staffing Implications |  |  |  |
| Unknown at present |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The paper contributes to the delivery of the Seven Wellbeing Goals. |  |  |  |
| Report History |  | Previous reports on Mental Health Transformation were taken to the In – committee meeting of the Board in February 2025 with an update to the Board in June 2025 |  |
| Appendices |  | None |  |