# Swansea Bay University Health Board (SBUHB)

Minutes of the Special Board Meeting

held on 17 February 2026 at 1:30pm

| Present: |  |  |
| --- | --- | --- |
| Jan Williams | (JW) | Chair |
| Stephen Spill | (SS) | Vice Chair |
| Abigail Harris | (AH) | Chief Executive Officer |
| Anne-Louise Ferguson | (ALF) | Independent Member |
| Andrew Griffiths | (AG) | Independent Member |
| Martin Lloyd | (ML) | Independent Member |
| Reena Owen | (RO) | Independent Member |
| Patricia Price | (PP) | Independent Member |
| Tina Ricketts | (TR | Executive Director of Workforce & OD |
| Gill Richardson | (GR) | Executive Director of Public Health |
| Liz Rix | (LR) | Executive Director of Nursing and Patient Experience |
| Nuria Zolle | (NZ) | Independent Member |

| In Attendance: |  |  |
| --- | --- | --- |
| Helen Annandale | (HA) | Associate Board Member |
| Lee Davies | (LD) | Executive Director of Strategy and Planning, Hywel Dda UHB |
| Pat Dunmore | (PD) | Associate Board Member |
| Matthew John | (MJ) | Director of Digital |
| Raj Krishnan | (RK) | Deputy Executive Medical Director |
| Alun Llewelyn | (AL) | Associate Board Member |
| Hazel Lloyd | (HL) | Director of Corporate Governance |
| Ian Macdonald | (IM) | Assistant Director of Finance |
| Carys Richards | (CER) | Senior Corporate Governance Manager |
| Karen Stapleton | (KS) | Deputy Director Strategy |
| Craige Wilson | (CW) | Deputy Chief Operating Officer |

| Apologies: |  |  |
| --- | --- | --- |
| Jean Church | (JC) | Independent Member |
| Alison Clarke | (AC) | Deputy Director of Therapies and Health Science |
| Marie Davies | (MD) | Executive Director of Planning and Partnerships |
| Richard Evans | (RE) | Executive Medical Director & Deputy Chief Executive |
| Deb Lewis | (DL) | Chief Operating Officer/Executive Director of Primary Care & Community and Mental Health & Learning Disabilities |
| Nicola Matthews | (NM) | Independent Member |
| Christine Morrell | (CM) | Executive Director of Therapies and Health Science |
| Charlotte Rees | (CR) | Independent Member |
| Richard Thomas | (RT) | Director of Insight, Communications and Engagement |

| Observers: |  |  |
| --- | --- | --- |
| Rose Turrell | (RoT) | Service Planning Manager (RJC) |

| Acronyms |  |  |  |
| --- | --- | --- | --- |
| SBUHB | Swansea Bay University Health Board | MoU | Memorandum of Understanding |
| RJC | Regional Joint Committee | WG | Welsh Government |
| WRP | Wales Risk Pool | HDUHB | Hywel Dda University Health Board |

The meeting began at 13:30.

| Minute Ref: | Agenda Item |
| --- | --- |
| PART 1. PRELIMINARY MATTERS |  |
| 1.1 Welcome and Apologies |  |
| 026/26 | JW extended a warm welcome to all attending the meeting welcoming particularly: Councillor Alun Llewellyn, joining the Board as the Associate Board Member (local government); Helen Annandale, Associate Board Member (chair of the SBUHB Health Professionals Forum); and Lee Davies, the Executive Director of Strategy and Planning for Hywel Dda University Health Board (HDUHB). JW expressed the Board’s gratitude to LD for forgoing annual leave to join the meeting. JW set out the role of the Board as the Governing Body of the organisation, meeting on a bimonthly basis, with an agenda that covered the breadth of the Board’s responsibilities. There were occasions when the Board had to meet outside the normal meeting cycle, to consider specific issues; this special meeting would receive a report on the Regional Cellular Pathology Programme. The Board received apologies as recorded above. |
| 1.2 Declaration of Interests |  |
| 027/26 | Charlotte Rees had registered a conflict of interest and sent her apologies. There were no other declarations of interest outside those already on the register. |
| PART 2. REGIONAL CELLULAR PATHOLOGY PROGRAMME |  |
| 2.1 Regional Cellular Pathology Programme |  |
| 028/26 | JW welcomed LD and invited him to provide a summary of the proposal; he drew attention to: - Work undertaken over the past year by SBUHB and HDUHB in response to significant estate and workforce challenges facing both health boards in the delivery of cellular pathology services. - The joint work had resulted in the initial identification and shortlisting of two sites, with a third site added subsequently. Detailed technical and non-technical assessments of all three sites had included consideration of both capital and revenue financial implications and indicative timescales. - The papers sought support for the proposed preferred site of the Bay Campus and approval to submit the proposal to Welsh Government (WG). JW advised that the Regional Joint Committee (RJC) had considered the proposals at an extraordinary meeting on 16 February 2026, had endorsed the preferred site and agreed to recommend it to both Boards; the HDUHB Board would consider the same proposal at a Board meeting on 18 February 2026. She thanked LD for his summary of the work to date and invited questions: NZ indicated that, as she was not a member of the RJC, she had not had an earlier opportunity to consider the documents; she sought some additional information on the alignment of the proposal with SBUHB strategic and workforce objectives. LD provided some additional background: - The undertaking of a full assessment of the technical and non-technical implications of each site, as set out in the report. - A joint HDUHB and SBUHB workshop; this had considered the options in some detail prior to consideration by the Regional Joint Committee on 16 February 2026. External experts had supported the work. - Each site had advantages and disadvantages: the Bay Campus had lower capital costs as two of the floors already had existing laboratories and required no additional work. - The non-technical assessment had identified advantages associated with co-location on a University site; this supported a key objective of the project- to develop a Centre of Excellence to support the recruitment of pathologists, in short supply across the UK, and a challenging recruitment environment. - An economic assessment had also supported the Bay Campus. - Taken in the round, the consensus at the workshop was that the Bay Campus be the preferred option. JW confirmed that the Board was not asked to sign up to any revenue consequences at this stage. A series of recommendations framed the future opportunities to mitigate revenue costs; these included exploiting digital and technical developments, enhanced productivity and efficiency, and capital opportunities. JW thanked Huw Thomas, Executive Director of Finance, HDUHB, for his assistance. NZ confirmed that the additional information, together with the support of both Executive Teams, gave her assurance. SS invited LD to provide an outline of the indicative timescales. LD emphasised the degree of urgency in progressing the matter, given the current estate risks; the preferred option would need a total implementation time of 24 months. Subject to approval, WG would receive the submission in the following week, with the Business Justification Case and other processes completed during 2026/27, subject to WG agreement and funding. Construction work would follow in 2027/28. JW thanked LD for the further detail and invited questions. AH extended her thanks to LD, IM and their teams for their intensive work to date; it reflected exemplary regional joint working. JW agreed and also extended her thanks to the SBUHB and HDUHB staff involved in the work; she regarded it as a blueprint for future RJC projects. JW also suggested the circulation of RJC meeting papers to all Board members, for information and ease of reference. Action: HL She also suggested to HA that the Health Professionals Forum might welcome a presentation on the project. HA agreed and JW asked IM if he would organise this. Action: IM JW extended her thanks to SS and to Eleanor Marks, Vice Chair of HDUHB, for their roles in maintaining Board level oversight of the project . The Board: - CONSIDERED the work undertaken on the site options appraisal and the recommendation from the recent Regional Cellular Pathology workshop for a preferred Laboratory Site. - APPROVED the submission of the paper, identifying the preferred site, to Welsh Government by 20 February 2026, ACKNOWLEDGING the endorsement by the Regional Joint Committee (RJC) on 16 February 2026. |
| 2.2 Pathology Memorandum of Understanding report |  |
| 029/26 | Introducing the report, HL drew attention to the redrafted Memorandum of Understanding (MoU) initially approved by SBUHB and HDUHB in March 2025; section three of the report set out the main updates to the structural and governance arrangements, with the leadership arrangements forming part of the 2026/27 service specification. The RJC meeting on 16 February RJC had endorsed it, for presentation to both Boards for approval. On behalf of JC, JW asked for confirmation that indemnity and liability clauses would set out clear responsibilities in the event of any mishaps. Responding, HL confirmed that, following selection of the preferred site option, revised documentation would set out contractual arrangements, working with the Wales Risk Pool (WRP) to cover the next stage of work. JW extended her thanks to HL and colleagues in HDUHB for their work on this key governance matter. The Board: - APPROVED the redrafted Transitional Memorandum of Understanding (Appendix A), for Regional Pathology services ACKNOWLEDGING the endorsement of the RJC meeting on 16 of February 2026. |
| Next SBUHB Board Meeting: (Special) Thursday 26 February 2026 |  |

The meeting concluded at 13:52.