| Meeting Date | 27 November 2025 |  | Agenda Item |  |  | 5.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | SBUHB Board Meeting |  |  |  |  |  |
| Report Title | Organised for Success Programme |  |  |  |  |  |
| Report Author | Tina Ricketts, Director of Workforce & OD |  |  |  |  |  |
| Report Sponsor | Tina Ricketts, Director of Workforce & OD |  |  |  |  |  |
| Presented by | Tina Ricketts, Director of Workforce & OD |  |  |  |  |  |
| Freedom of Information | Closed |  |  |  |  |  |
| Purpose of the Report | This report seeks approval of the Terms of Reference (v7) of the Organised for Success programme. The Organised for Success programme has been set up to enable the Health Board to be organised in the most effective way to delivery in year and medium terms improvements. It will set us up so we can be successful for the populations we serve and for our colleagues across the organisation. This Programme is a key enabler in the delivery of the savings benefit associated with headcount reduction (as identified by the Recovery and Sustainability Board) and will include a management restructure of our clinical services and corporate functions. |  |  |  |  |  |
| Key Issues | Prior to the appointment of the new Chair and Chief Executive, the Health Board had a period of instability with the majority of executive posts being covered on an interim basis. In addition, the Health Board has had to rely on a command-and-control leadership style to address immediate issues such as the maternity service review, mental health service review and financial turnaround. This has impacted on the culture of the Health Board with signs of low trust amongst the workforce with some staff reporting that they do not feel empowered to make change. There is variability in leadership and management capability and capacity with pockets of good practice but a number of areas where improvement is needed as evidenced by the staff survey results and key workforce metrics. Our current operating model is locality based. Patients and staff regularly report that this model is not fit for purpose and is detrimental to both patient experience and the best use of resources. The Board recognises that a culture change programme is required but we must first ensure that our services are organised in the best way for our patients. We must also ensure that our leaders have the right capacity and capability to deliver our challenging agenda and to lead the required cultural change. In response, the Organised for Success Programme has been developed which will focus on the following: Phase 1 - which is underway, includes the review of executive director portfolios, the deputy structure (the tier below the executive team) and will explore the opportunity for joint appointments to support regional working with Hywel Dda. This phase will also include the development of a Delivery Unit which will house the Health Boards PMO, transformation, improvement, performance and business intelligence capability. Phase 2 - will see a restructure of our clinical services moving away from a locality-based model to a thematic care group structure. The restructure will reduce the number of management layers and will also ensure appropriate spans of control. We will also consider whether we move away from an operationally led leadership model to a clinically led model. Phase 3 – will consider the wrap around support that each care group needs to deliver on their priorities and will consider how we organise our corporate services so that they meet the needs of the Health Board but are sustainable into the future. There are 5 enablers to the programme: - Leadership and management development framework - Programme communications and engagement plan - Performance Management Framework - Accountability Framework - Single Improvement Methodology We are still modelling how these enablers will interface with the programme. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Board members are asked to: - APPROVE the Organised for Success Programme terms of reference - APPROVE the governance structure for the programme as set out in the report |  |  |  |  |  |

ORGANISED FOR SUCCESS PROGRAMME

- Introduction/ Background

Following from feedback from staff, there is a recognised need to review how we are organised so that we are best placed to respond to the challenges we face in the most effective and efficient way, balancing short-term actions required to ensure delivery of in-year targets, and our longer term goals as set out in our refreshed strategy, Better Health, Better Care, Better Lives.

We also know from both internal and external feedback (including internal and external audit, independent reviews) that we don’t yet have the right operating framework in place that aligns planning, performance, accountability and delivering – from Board through to front line services.

From recent reviews it has become evident that some clinical services (e.g. Emergency Department, Perinatal and Mental Health) need a period of enhanced management oversight to improve patient and staff experience at pace. Furthermore, staff survey results and other workforce metrics, such as high sickness absence rates, indicate that there is variability in the capacity and capability of managers across the health board impeding on our ability to deliver our strategic objectives and priorities.

Our clinical services plan will be the vehicle through which we review and refresh our plans for how best to configure and delivery our clinical services – recognising the need to delivery more care through integrated community services which provide care closer to home, increase digitally enabled care, and focus more of our resources on population health management through better prevention and early intervention to tackle the widening health inequities in our communities.

Our workforce has grown by c2,200 over the last five years despite a large proportion (c26%) of our services transferring to a neighbouring health board. We are currently delivering services in a way that is unaffordable with a current cost reduction requirement of around 8% in 2025/26 and similar for 2026/7. This requires us to be more radical and injecting more pace in to transforming our services, so they are sustainable – in terms of quality and safety, cost and workforce. Our current pay bill is unaffordable and needs to reduce by a minimum of 10% to ensure we remain sustainable into the future. This requires short term action to significantly reduce what it costs to delivery our services and medium-term service transformation, building on the successes we see every day.

The Organised for Success programme has therefore been set up to support us to be organised in the most effective way to delivery in year and medium terms improvements. The programme is a key enabler in the delivery of the savings benefit associated with headcount reduction (as identified by the Recovery and Sustainability Board), which will include a management restructure of our clinical services and corporate functions.

This programme of work will review executive portfolios, service group structures and management spans of control and will make recommendations on how we organise ourselves for success. The programme will also bring together our PMO, transformation and improvement capability through the establishment of a Delivery Unit.

- Terms of Reference

The terms of reference of the programme are set out in appendix 1 for approval. These have been updated to include feedback from the Management Board in September 2025.

The following diagram sets out the 3 phases of the programme:

There are 5 key enablers of this programme:

- The leadership and management development framework which will set out the required leadership competencies and behaviours

- A communications and engagement plan for the programme

- The Performance Management Framework which will need to be refreshed to ensure clarity on the driver and watch metrics for each care group

- The Accountability Framework which will need to be refreshed along with the Standing Orders and Standing Financial Instructions

- A Single improvement methodology will need to be adopted so we have a consistent approach to reducing waste and improvement

We are still modelling how these enablers will interface with the programme.

The lead for each phase of the programme is set out in the table below.

Table 1: Leads for each phase of the progamme

| Phase | Description | Proposed Lead |
| --- | --- | --- |
| A | Executive Portfolios | Chief Executive officer |
| B | Deputy/ Tier 2 Management Structure | Director of Workforce & OD working with each of the Executive Directors |
| C | The Establishment of a Delivery Unit | Director of Workforce & OD working with Deloitte |
| D | Joint Posts across the Regional Partnership | Chief Executive officer |
| E | The establishment of a new care group structure | Chief Operating Officer |
| F | A review of the care group leadership structure – confirming the Triumvirate Leadership model (e.g. operationally led or clinically led) | Director of Workforce & OD working with the Executive Team |
| G | A review of the number of divisions or directorates within each new care group to ensure spans of control are reasonable and equitable. This will include a review of the specialities and services managed under each of the care groups to ensure they are organised in the best way for our patients | Chief Operating Officer working with the Care Group Tri’s |
| H | A review of the number of management layers within the new care groups with the aim to have a maximum of 6 layers, where appropriate, from Board to front line staff with a focus for this programme on the top 4 layers (Tri, Division, Directorate, speciality/ service) | Director of Workforce & OD working with Chief Operating Officer |
| I | A review of the wraparound support for each new care group (e.g. HRBP, Finance BP) to ensure this is reasonable and equitable | Director of Workforce & OD |
| J | A review of corporate functions sitting in/ out of care groups to ascertain the most appropriate design of the function (e.g. hub and spoke, centralised) | Director of Workforce & OD |

The governance structure for the programme is set out in the diagram below. The Formal Executive Team Meeting will be the Steering Group for the programme with key decisions being made by the Board. The Management Board will receive regular progress updates and will be consulted and engaged on key decisions.

- Care Group Structure Early Thinking

Our early thnking is that we move from locality based Service Groups to Thematic Care Groups as set out in the diagram below:

In this proposed model, the Accountable Officer will be a clinician, supported by operational director and nursing director. This reflects our commitment to a clinically led model, where multidisciplinary teams are empowered to lead service design, delivery and improvement, aligned to patient pathways, in ways that best meet the needs of patients and communities.

The proposed structure better aligns delivery to the Welsh Government’s transformation programmes and national direction

- Key Risks

The Board should be aware of the following risks:

| Key Risks | Current risk rating | Mitigating Actions | Risk Owner |
| --- | --- | --- | --- |
| There is a risk that the implementation of the programme will be delayed due to lack of programme management capacity | 12 | Interviews for Programme Manager scheduled for 4th November | Director of Workforce & OD |
| There is a risk that the challenging timelines of the programme will not be met due to senior colleagues not seeing this programme as a priority/ not releasing the required resource | 12 | The resourcing of the programme will be overseen by the Steering Group. The establishment of a central delivery unit has been incorporated in phase 1 of the programme. This will be responsible for ensuring that all key HB programmes are adequately resourced. We will work with HEIW and Hywel Dda to explore available resources outside of the Health Board | Director of Workforce & OD |
| There is a risk that the operational performance of the Health Board is negatively impacted as colleagues become distracted with the programme/ associated organisational change processes | 9 | Operational performance will be overseen by the central delivery unit. The establishment of a delivery unit has been incorporated in phase 1 of the programme. | Chief Operating Officer |
| The programme will require a restructure of our budgets and corporate systems (e.g. the Electronic Staff Record System). There is a risk that this may limit the capacity of the corporate teams to work on other priorities. | 12 | Two planning groups have been set up with one focused on the restructure of our budgets and corporate systems. Regular updates on progress will be provided to the Steering Group. The impact on other priorities will be managed through the delivery unit. | Director of Workforce & OD |

- Recommendations

Board members are asked to:

- APPROVE the Organised for Success Programme terms of reference

- APPROVE the governance structure for the programme as set out in the report

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The aim of phase 2 of the programme is to structure our services to improve patient experience. Currently services are structured on a geographical basis. |  |  |  |
| Financial Implications |  |  |  |
| The financial savings from the programme have not yet been quantified as we are still working through potential scenarios including the impact of the pay protection policy. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| An equality and diversity impact assessment will be undertaken for each phase of the programme. |  |  |  |
| Staffing Implications |  |  |  |
| The aim of the programme is to see a reduction in management tiers and equity in spans of control where possible. Staffing implications are still being scoped. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| As set out in the report. |  |  |  |
| Report History |  | Not applicable |  |
| Appendices |  | - Organised for Success Terms of Reference |  |