DATED _______________________________________________

TRANSITIONAL

Memorandum of Understanding

between

SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD

and

HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD

OPerational delivery network South-West Wales Regional Pathology 2024/2025

CONTENTS

____________________________________________________________

CLAUSE

1.	Background	3

2.    Definitions…………………………………………………………………………………………….4

3.	Key objectives for the Project	4

4.	Contributions…………………………………………………………………………………………5

5.	Principles of Collaboration	6

6.	Project Governance	6

7.    Reporting…………………………………………………………………………….……………….9

8.	Quality Governance arrangements…………….……………………………………….………..10

9.	ODN Policies………………………………………………………………………………...…..…10

10.	Clinical Guidelines…………………………………………………………………………..……..11

11.	Roles and Responsibilities……………………………………...……………...…………………11

12.	Employment of Staff…………………………………………………….…………………………14

13.	Escalation……………………………………………………………………….……….………….15

14.	Risk Management…………………………………………………………………….……………15

15.	Intellectual Property………………………………………………………………………………..16

16.	Data Protection and Information Governance…………………………………………………..16

17.	Term and Termination……………………………………..……………………..……………….16

18.	Variation……………………………………………………...……………………………………..16

19.	Charges and Liabilities………………………..…………………………………..………………16

20.	Ownership of Assets……………………………………………………………….………………17

21.	Procurement………………………………………………………………………...…………….. 17

22.	Host Health Board - Duty of Care…………….………………………………………………….17

23.	Management of Concerns………………………………………………………….……………..17

24.	Audit…………………………………………………………………………………………………18

25.	Effect of ODN on SBUHB's Core Functions…………………...………………………………..18

26.	Status…………………………………………………………..……………………………………18

ANNEX

ANNEX A The Project	21

ANNEX B Information Sharing Protocol	22

ANNEX C Pathology ODN Board and Pathology ODN Operational Board terms of reference	23

ANNEX D Contributions	24

This Transitional MoU is dated _______________________________________

Parties

SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD of One Talbot Gateway, Baglan Energy Park, Baglan, Port Talbot, SA12 7BR (SBUHB)

HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD of Corporate Offices, Ystwyth Building, Hafan Derwen, St David’s Park, Jobswell Road, Carmarthen, SA31 3BB (HDUHB)

- Each a Health Board and together the Health Boards as the context requires.

Background

- 1.1	On 22nd November 2022, SBUHB and HDUHB submitted a Report to their respective Boards to take forward the development of an Operational Delivery Network (ODN) as the management model for South-West Regional Pathology Services (“Service”). The Report recommendations were approved in both public Board meetings, confirmed in minutes. HDUHB agreed to collaborate with SBUHB to establish the ODN. The re-designed regional pathology service (“Project”) will bring together two organisations; SBUHB and HDUHB laboratory-based services under one umbrella. The ODN will also lead on behalf of the organisation in the commissioning of microbiology services for the region. Currently, these are provided in the majority of instances by Public Health Wales (PHW). This change will facilitate delivery of a new regionalised and co-located service model, supported by integrated management and a joint Health Board workforce. It is planned that a regional pathology hub laboratory will be created at Morriston Hospital via Welsh Government investment through the capital business case process. This investment case will also propose refurbishment of existing laboratories not on the Morriston site to provide fit for purpose local services to meet relevant service models. This hub and spoke network will work consistently across the region. The proposed hub laboratory will incorporate regional services for cellular pathology, laboratory medicine, microbiology, immunology and specialist reference units and precision medicine laboratories.

- The term “Laboratory Medicine” is used throughout the document to refer to the discipline known as Blood Sciences in Hywel Dda, as well as any equivalent service created by the amalgamation of SBUHBs Laboratory Medicine and HDUHB’s Blood Sciences services.

  - Major aspects of the case for change to develop the Project are based on workforce fragility (which has now reached a critical phase), future proofing for demand and developments in service delivery, financial efficiencies and estates with significant backlog maintenance and of a design that is not fit for purpose to deliver modern laboratory services in the majority of cases. The pathology service must be developed to meet service user’s changing expectations in respect of high quality, safe and efficient health care services and the delivery of these services as close to home as possible. The pathology service must embrace competitiveness and a commissioner-led focus. It requires strong local clinical leadership and a business orientated management infrastructure, focusing on productivity by matching the workforce to activity, workflow and the roles and functions that are needed to deliver the ODN, through improving systems and processes and realising the benefits of new technology. The ODN will be a partnership between participating organisations, working collaboratively to achieve its common goals and purpose.

This is a transitional Memorandum of Understanding (“Transitional MoU”) and its purpose is to outline the accountability arrangements and resulting responsibilities of the Health Boards in respect of the transitional ODN model, to act as the (transitional) hosting agreement between the Health Boards and to bridge the gap before the Health Boards enter into the MoU for the ODN which will come into effect after the transitional phase has completed, when the final details of the ODN have been agreed. This Transitional MoU should be read in conjunction with the Report to SBUHB’s Board dated 22nd November 2022. This Transitional MoU is between SBUHB and HDUHB only. There will be a separate agreement with PHW regarding PHW’s role in respect of the Microbiology Services that PHW will be providing in connection with the ODN. It is envisaged that other MoUs will be required in respect of the ODN.

The ODN will be hosted and managed by SBUHB. This hosting role is entirely separate from the role of SBUHB as a provider of pathology services and all references to SBUHB throughout this Transitional MoU (unless otherwise stated) refer to SBUHB’s role as host of the ODN. SBUHB will ensure a clear distinction between its day-to-day operational responsibilities, as a health care provider for its local population and its responsibilities as the host of the ODN.

The Health Boards have agreed to work together on the Project detailed in Annex A.

The Health Boards wish to record the basis on which they will collaborate with each other on the Project. This Transitional MoU sets out:

the key objectives of the Project;

the principles of collaboration;

the governance structures the Health Boards will put in place; and

the respective roles and responsibilities the Health Boards will have during the Project.

Definitions

- “Data Protection Legislation” means all applicable data protection and privacy legislation in force from time to time in the UK including the retained EU law version of the General Data Protection Regulation ((EU) 2016/679) (UK GDPR); the Data Protection Act 2018 (DPA 2018) (and regulations made thereunder) and the Privacy and Electronic Communications Regulations 2003 (SI 2003/2426) as amended; and

"Intellectual Property Rights” means any and all patents, trade marks, service marks copyright, moral rights, rights in design, know-how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether now or in the future subsisting in the United Kingdom or any other part of the world together with all or any good will and accrued rights of action;

- “Programme of Work” means the development of the Pathology ODN in its Transition period (up to March 31st 2025). This includes;

- The development of the leadership team and any associate staff changes to existing pathology leadership structures.

- The process by which pathology staff transfer from existing employers to the ODN under the hosted arrangements.

- The programme management of the development of the network via the existing programme management arrangements and resources.

- Develop and agree a commissioning arrangement to include a service specification, commissioning method and financial consideration of investment and risk approach

- Ensuring the parallel production of the capital business case for the Hub Laboratory and spoke refurbishments continues to reflect the changing regional nature of pathology service provision and that the regional management team fully engage with the capital business case process to produce a robust, region OBC for the capital infrastructure to support the network in future years.

Key Objectives for the Project

- The Health Boards shall undertake the Project to achieve the following Key Objectives:

- The Project will deliver high quality pathology services to SBUHB and HDUHB. The Project will take a whole system collaborative approach to ensuring the delivery of safe and effective services across the patient pathway, adding value stakeholders. There will be improved cross-organisational multi-professional clinical engagement to improve clinical care.

- The Project will provide equity of access to pathology services for patients within SBUHB and HDUHB Health Board areas (and those served from neighbouring Health Boards)

- The Project will cover Cellular Pathology, Mortuary, Immunology and Laboratory Medicine.

- The Project will have a single management team (the Pathology ODN Operational Group), a single consultant lead (Network Clinical Director) and laboratory service staffing hosted by SBUHB.

- The management team will be established with clear accountability arrangements for the operational delivery of services.

- There will be a joint mechanism in place to oversee the strategic direction, annual planning and performance delivery of the Project, via the Pathology ODN Board and the Pathology ODN Operational Group.

- The Project will have a single budget set against specifications agreed by the Health Boards.

- There will be investment in the Project by the Health Boards and joint investment in the capital infrastructure where necessary.

- The assets for the Project will remain on each Health Board’s balance sheet.

- The provision of service support facilities across the ODN laboratory network will be determined via the Service Specification for the Pathology ODN. This will include responsibility and accountability for estates and facilities management, financial management, IT equipment and support and Human Resources support including Occupational Health

- The quality and safety and finance and performance committees of each Health Board will review, at least annually, a report for the joint service on its quality and safety performance and its operational and financial performance. Escalation of this reporting will be more frequent should it be necessary.

- Services will be accredited to meet regulatory standards. In particular, the Human Tissue Authority (HTA) regulations to ensure human tissue is used safely and ethically, and with proper consent.

- The Lead Director (named Executive of Host Organisation) will be responsible for the quality governance for the Service across the region.

- A digital first approach will be taken to the development of the regional service delivery model.

- The service model will enhance the resilience and sustainability of the Service.

- 4.	Contributions

- 4.1	The Health Boards acknowledge that the current position with regard to the Project and the contributions already made or to be made (financial and otherwise) are as detailed in Annex D to this Transitional MoU.

- 5.	Principles of Collaboration

5.1	The Health Boards agree to adopt the following principles when carrying out the Project (Principles):

collaborate and co-operate. Establish and adhere to the governance structure set out in this Transitional MoU to ensure that activities are delivered and actions taken as required;

be accountable. Take on, manage and account to each other for performance of their respective roles and responsibilities set out in this Transitional MoU;

be open and transparent. Communicate openly about major concerns, issues or opportunities relating to the Project to inform good decision-making and to minimise risk;

learn, develop and seek to achieve full potential. Share information, experience, materials and skills to learn from each other and develop effective working practices, work collaboratively to identify solutions, eliminate duplication of effort, mitigate risk and reduce cost;

adopt a positive outlook. Behave in a positive, proactive manner;

adhere to statutory requirements and best practice. Comply with applicable laws and standards including public procurement rules, data protection and freedom of information legislation. In particular, the Health Boards agree to comply with the requirements of the Information Sharing Protocol attached to this Transitional MoU in Annex B;

act in a timely manner. Recognise the time-critical nature of the Project and respond accordingly to requests for support;

manage stakeholders effectively;

deploy appropriate resources. Ensure sufficient and appropriately qualified resources are available and authorised to fulfil the responsibilities set out in this Transitional MoU. In particular the parties agree to make the contributions detailed in Annex D to this Transitional MoU;

act in good faith to support achievement of the Key Objectives and compliance with these Principles;

be mutually supportive, respecting the statutory status and independence of all participating organisations; and

be valued at the highest levels within the ODN, with visible leadership, clear lines of accountability and a coherent collaborative approach.

- Project Governance

- 6.1	Overview

As a non-statutory organisation without legal identity, the ODN does not in itself possess constitutional rights, but rather it will fall under the governance arrangements of its host organisation, SBUHB. Commissioners will continue to be accountable for the commissioning of services and providers will continue to be accountable for the delivery of services. Each Health Board would either be separately or collectively accountable for the commissioning of services.

The Health Boards will have in place appropriate governance arrangements and Schemes of Delegation as may be necessary and required in order to carry out their respective functions within the ODN.

The ODN will be accountable to SBUHB for all arrangements pertaining to the running of the ODN. This will include, but not be limited to, employment of staff to work within the ODN, provision of all employment HR and corporate services, accommodation and training.

The governance structure defined below provides a structure for the development and delivery of the Project.

- 6.2	Guiding Principles

The following guiding principles are agreed. The Project's governance will:

provide strategic oversight and direction;

be based on clearly defined roles and responsibilities at organisation, group and, where necessary, individual level;

align decision-making authority with the criticality of the decisions required;

be aligned with Project scope (and may therefore require changes over time);

leverage existing organisational, group and user interfaces;

provide coherent, timely and efficient decision-making; and

correspond with the key features of the Project governance arrangements set out in this Transitional MoU.

- 6.3	Recruitment of ODN Leadership Team in connection with the Transitional ODN

- The ODN Leadership Team acts as a resource, co-ordinator and facilitator for all its stakeholders to achieve a collaborative approach to safe and equitable and effective specialised pathology services. It consists of the following membership:

| - ODN Post | - Roles and Responsibilities |
| --- | --- |
| - Regional Pathology Network Director | - To be operationally responsible for the delivery of the Pathology ODN and all of its associated services. |
| - Regional Pathology Network Clinical Director | - To be the Consultant level Clinical Director of the Pathology Network. To work alongside the Network Director to provide senior leadership, operational accountability and resource management. To lead on Quality and Safety for the Network. |
| - Pathology Transformation Programme Director | - A fixed term post linked to the establishment of the Network and not required for recurrent running of the service once established and senior leadership team in place. |
| - Designated Individual for Mortuary Services (i.e. the individual designated in a licence under the Human Tissue Act 2004) | - Responsible for the duties set out in Section 18 (Duty of the designated individual) of the Human Tissue Act 2004. |
| - Regional Mortuary Manager | - Responsible for the operational running of Mortuary services in both Health Boards under the direction of the Mortuary services MOU |

- 6.4	Provider Organisations within the Transitional ODN

- The following organisations shall perform the following ODN functions:

| - Organisation | - Function |
| --- | --- |
| - Swansea Bay University Health Board | - ODN host organisation and commissioner of the ODN |
| - Hywel Dda University Health Board | - Commissioner of the ODN |
| - Public Health Wales | - Provider of majority microbiology services in region. Commissioned by HDUHB and SBUHB |
| - A Regional Collaboration for Health (ARCH) | - Joint Health Board and Swansea University programme supporting change in service delivery i.e. the formation of the ODN |

- 6.5		Governance Structure

- Pathology ODN Delivery Board

- (a)		The Pathology ODN Delivery Board provides overall strategic oversight and direction to the Project. The Board meets on a monthly basis and is the main decision-making body, being responsible for leading the ODN, considering current and future strategy, ratifying ODN guidelines and overseeing the work needed to deliver its annual programme of work and meet its agreed aims and objectives. This group will consist of:

SBUHB:

Chief Operating Officer (Lead Director)

Director of Therapies and Health Sciences

Director of Finance

Medical Director’s Office representative

Workforce Director representative

Network Director, Pathology ODN

Network Clinical Director, Pathology ODN

Programme Director, ARCH Pathology (Transitional ODN only)

HDUHB:

Director of Therapies and Health Sciences

Director of Operations

Director of Finance

Medical Director’s Office representative

Workforce Director representative

    - The Pathology ODN Delivery Board shall be managed in accordance with the terms of reference set out in Annex C to this Transitional MoU.

- Pathology ODN Operational Group

  - The Pathology ODN Operational Group will provide strategic management at Project and workstream level. The Pathology ODN Operational Group shall meet monthly. It will provide assurance to the Pathology ODN Board that the Key Objectives are being met and that the Project is performing within the boundaries set by the Pathology ODN Board.

  - The Pathology ODN Operational Group consists of representatives from each of the Parties. The Pathology ODN Operational Group shall have responsibility for the creation and execution of the programme of work and deliverables, and therefore it can draw technical, commercial, legal and communications resources as appropriate into the Pathology ODN Operational Group. The core Pathology ODN Operational Group members are:

Network Director, Pathology ODN

Network Clinical Director, Pathology ODN

Service Manager, Cellular Pathology, Pathology ODN

Clinical Director, Cellular Pathology, Pathology ODN

Service Manager, Laboratory Medicine, Pathology ODN

Clinical Director, Laboratory Medicine, Pathology ODN

Quality and Safety Lead, Pathology ODN

Training Lead, Pathology ODN

Service Group Director, Morriston Hospital

Pathology Workforce Manager

Pathology Finance Manager

  - The Pathology ODN Operational Group shall be managed in accordance with the terms of reference set out in Annex C to this Transitional MoU.

Reporting

Project reporting shall be undertaken at three levels:

    - Pathology ODN Operational Group: minutes and actions will be recorded for each Pathology ODN Operational Group meeting. Meetings will be held on a monthly basis. Any additional reporting requirement shall be at the discretion of the Pathology ODN Operational Group.

    - Pathology ODN Delivery Board:  Reporting shall be monthly, based on the minutes from the Pathology ODN Operational Group highlighting: Progress within the current period; issues being managed; issues requiring help (that is, escalations to the Pathology ODN Board) and progress planned next period and/or aligned with the frequency of the Pathology ODN Board meetings.

- iii)	Organisational: the Pathology ODN Delivery Board should report every 2 months via an agreed standardised format to both Health Boards Management Board/Executive Team and committees. A Quarterly report should be prepared for each organisations Quality and Safety committee highlighting any issues within the period. The ODN Delivery Board should prepare an annual review covering the previous 12 month period, highlighting activity, performance, quality and safety and workforce issues should be shared with SBUHB and HDUHB Management Board/Executive Team  and to the appropriate committee before public board reporting.

- This Transitional MoU does not affect any existing reporting arrangements currently in place.

Quality Governance Arrangements

The ODN will not have statutory responsibility for clinical governance arrangements within each Health Board. The ODN will be responsible for ensuring regular and complete reporting into the Pathology ODN Operational Group on clinical governance matters relating to the ODN.

Both Health Boards will provide the information requirement outlined in the [name of document], thus enabling the ODN to be compliant with reporting requirements.

- Both Health Boards will provide confirmation to the ODN that Quality governance information and incidents have been reported to their respective Health Board’s Quality and Safety Committee.

ODN Policies

During the Transition period the ODN will develop and seek agreement on policies relating to the operational running of the network and clinical and organisational governance. These include (but are not limited to) the following:

Quality Governance Policy

Information Sharing Protocol / Data Sharing Agreement (Annex B)

Quality statement and reporting matrix

Activity and performance matrix

Service specification

Commissioning specification and process

- Development and approval of the above will be required prior to the Transnational ODN moving to the permanent MOU agreement.

The policies will be accessible on the SharePoint website of each Health Board.  New policies and updates to existing policies will be developed and approved through the ODN governance structure.  Each Health Board will be responsible for ensuring it has a process in place for receiving and implementing notifications of new policies and updates to existing policies.

Clinical Guidelines

All clinical guidelines have been developed collaboratively with the process of development having been approved by the Pathology ODN Operational Group. Each Health Board should acknowledge access to the guidelines.

The ODN will update the clinical guidelines as required and provide notification to the Health Boards. Both Health Boards are responsible for having in place a system of receiving updates to clinical guidelines.

Roles and responsibilities

The Health Boards shall undertake the following roles and responsibilities to deliver the Project:

| Activity | SBUHB | HDUHB |
| --- | --- | --- |
| Governance and Finance |  |  |
| Host organisation | Lead | Assure |
| To have in place appropriate governance arrangements and a Scheme of Delegation as necessary and required to enable the ODN to carry out its functions | Mutual | Mutual |
| To hold and manage the budget for the ODN making payments and receiving income as necessary | Lead | Assure |
| To be the legal entity which enters into agreed procurement arrangements to include, but not restricted to, procurement contracts, quotations, terms of engagement etc. commissioned by the ODN for example, in respect of the refurbishment of laboratories in satellite hospitals to modernise and create fit for purpose pathology services. It is anticipated (although not yet decided) that the ODN may procure as a network during the transitional form, in order to improve purchaser power and to provide consistent equipment in all sites over time (existing contracts pending/ending in the next financial year will be reviewed) | Lead | Assure |
| To be authorised to appoint lawyers and other professional advisors and to agree the terms and conditions from time to time on behalf of the ODN | Lead | Assure |
| In fulfilling its obligations and responsibilities under this Transitional MoU, the Health Boards shall not be required to act contrary to their statutory powers and duties, Standing Orders and Standing Financial Instructions, Welsh Government approval requirements, corporate governance requirements generally, procurement requirements (for example, the Public Contracts Regulations 2015 or the Procurement Act 2023) or any legal obligations not covered elsewhere under this clause 11 | Mutual | Mutual |
| Responsibility for ensuring that the Pathology ODN Board is accountable to the organisations represented on its board | Lead | Assure |
| Accountability for the commissioning of providers for the delivery of services | Mutual | Mutual |
| Service Specification |  |  |
| Draft the Service Specifications for Cellular Pathology, Mortuary, Immunology and Laboratory Medicine, prior to the operational date of the ODN and develop the Service Specifications as required | Mutual | Mutual |
| Strategic Planning |  |  |
| Provide professional and clinical leadership across the ODN | Lead | Assure |
| Host a risk register and undertake risk management across the ODN | Lead | Assure |
| Develop an annual working plan for an approved programme of work for the ODN to deliver against the quality and delivery framework and report through the governance structure progress against the programme of work | Lead | Assure |
| Contribute towards evaluation of the ODN | Lead | Assure |
| To provide effective linkage into commissioning groups | Lead | Assure |
| Produce quarterly and annual reports | Lead | Assure |
| Undertake comparative benchmarking and audit across the ODN for quality control purposes | Lead | Assure |
| Procurement of Service Providers for the delivery of Services – eg appointment of a Supply Chain Partner to support capital planning | Lead | Assure |
| Outsourcing of activity – regional basis | Lead | Assure |
| Operational Delivery |  |  |
| Implementation of ODN wide digital systems to support pathology i.e. LIMS 2.0 national roll out of new pathology system as a region scheduled for completion in February 2025 | Lead | Assure |
| Develop coordinated patient clinical pathways throughout the Service over a wide area (as a minimum, the geographic areas of both Health Boards) to ensure access to high quality, safe and efficient pathology services | Lead | Assure |
| Ensure improved access and equity of access to pathology services | Lead | Assure |
| Responsibility for monitoring of day-to-day capacity across the ODN, agreeing and working to an escalation plan (with agreed thresholds for escalation triggers) both within and across the ODN to monitor and manage surges in demand for pathology services | Lead | Assure |
| Support capacity planning and activity monitoring for collaborative matching or demand and supply | Lead | Assure |
| Ensure the quality of the ODN is monitored and subject to a process of continuous quality improvement through clinical audit | Lead | Assure |
| Responsibility for performance management of the ODN in line with the Services Specification(s) | Lead | Assure |
| Develop and implement ODN standardised operating policies and procedures | Lead | Assure |
| Joint recruitment i.e. medical workforce and generally to posts | Lead | Assure |
| Advanced Practice BMS development | Lead | Assure |
| Training – standardisation and movement of trainees and trainers between sites where relevant | Lead | Assure |
| Development of single quality systems | Lead | Assure |
| Tactical (local) Advice and Support to Commissioners |  |  |
| Provide local information, data and intelligence to support performance monitoring of the ODN (i.e. clinical reports, process measures, key performance and quality indicators, case-mix standardised outcomes, workforce data etc.) | Lead | Assure |
| To provide ongoing programme management of a phased implementation across the ODN | Lead | Assure |
| Develop, through the Digital Sub-group, a shared IT system that can ‘communicate’ or ‘interface’? between Health Boards | Mutual | Mutual |
| Improved Quality and Standards of Care |  |  |
| Deliver a clinical governance framework including a process for incident reporting with follow up action plans and network morbidity and mortality review. This includes collaborative serious incident investigation. | Lead | Assure |
| Deliver an ODN-wide training and education programme encompassing the whole patient pathway prioritising key areas | Lead | Assure |
| Implement a clinical informatics system for the ODN | Lead | Assure |
| Ensure on-going service improvements and best practice models are embedded and contribute to improved quality performance | Lead | Assure |
| Monitor and provide advice on improvements to clinical services and commissioners | Lead | Assure |
| Use clinical process and clinical outcome measures to compare and benchmark providers | Lead | Assure |
| Deliver an annual quality improvement and audit programme | Lead | Assure |
| Partnership Development |  |  |
| Engage with staff during the Transitional MOU period to ensure staff are full informed and engaged on the development of the Pathology ODN and where appropriate consulted upon any formal changes that might arise. This will include regular briefing to and attendance of Staff Side Partnership meetings in both organisations from the Pathology team in liaison with local Workforce representatives. | Mutual | Mutual |
| Engagement with third sector organisations | Lead | Assure |
| Linkage with any other relevant ODNs (national/local level) | Lead | Assure |
| Enhance relationships with other health boards in Wales to ensure the ODN reaches optimal effectiveness | Lead | Assure |
| Embed communication strategy and key communication deliverables | Lead | Assure |
| Monitoring and performance management of active engagement by members in the ODN to improve performance against agreed outputs | Lead | Assure |
| Participation in relevant national policy or guideline development | Lead | Assure |

- For the purpose of the table above:

Lead: the Health Board that has principal responsibility for undertaking the particular   activity, and that will be authorised to determine how to undertake the activity. The Lead must act in compliance with the Objectives and Principles at all times, and consult with the other Health Board in advance if they are identified as having a role to Assure the relevant activity;

Assure: the Health Board that will defer to the Lead on a particular activity, but will have the opportunity to review and provide input to the Lead before they take a final decision on any activity. All assurance must be provided in a timely manner. Any derogations raised must be limited to raising issues that relate to specific needs that have not been adequately addressed by the Lead and/or concerns regarding compliance with the Key Objectives and Principles.

Mutual: both Health Boards share equal responsibility for undertaking the activity.

Within 3 months of the date of this Transitional MoU the Health Board with the Lead role for any aspect of the Project shall develop a delivery plan for that part of the Project which shall identify the following:

the key milestones for the delivery of the Key Objectives;

what employees (other than employees identified in this Transitional MoU) will be required to work on the Project;

whether any staff will need to be seconded from one Health Board to the other;

what staff will require access to the premises of the other Health Board;

TUPE implications; and

Each delivery plan must be approved by the Pathology ODN Operational Group prior to being implemented.

- 12.	Employment of Staff

12.1	The working assumption is that  when the ODN takes effect (and not during the phase of this Transitional MoU) it is anticipated that there will be a “relevant transfer” for the purposes of the Transfer of Undertakings (Protection of Employment) Regulations 2006 (as amended) (“TUPE”) i.e. the ODN function for pathology services is formed by transferring existing staff into the ODN host organisation (SBUHB) and the assumption is that TUPE will apply to staff who are in scope to transfer under TUPE at the commencement of the provision of the pathology services. Any new posts are appointed to SBUHB as ODN posts and therefore, TUPE on commencement of services will not apply to these new posts.

In the event that the Transitional MoU proceeds to the MoU for the ODN, the existing employer, will be responsible for any TUPE arrangements (e.g. the obligation to inform and consult with appropriate representatives (where appropriate) and provide Employee Liability Information under regulation 11, TUPE) and in respect of re-tendering and the handover of services. . If and when the provision of pathology services under the ODN expires or terminates pursuant to applicable contracts, SBUHB, as the employer under the ODN, will be responsible for the application of TUPE (e.g. the obligation to inform and consult with appropriate representatives (where appropriate) and provide Employee Liability Information under regulation 11, TUPE) and in respect of re-tendering and the handover of services.

As part of the transitional phase/this Transitional MoU, the Health Boards shall agree which services are to be transferred to the ODN and consequently, which staff are in scope to TUPE transfer. This information will be used to inform the MoU for the ODN and will be captured in the ODN Service Specification as and when developed.

- 12.2	SBUHB shall be responsible for the appointment of staff in line with the posts agreed through the Pathology ODN Operational Group.

12.3	New staff appointed to work within the ODN will be employed by SBUHB, they will be entitled to be treated as any other SBUHB employee.  They will be expected to abide by all SBUHB policies, procedures and guidance including, but not limited to, fire safety and health and safety procedures. ODN staff will benefit from access to all applicable policies and procedures including training and development.

12.4	The ODN staff will be accountable for their performance to the Service Group Director, Morriston Hospital who, for this role, is accountable to the ODN Senior Responsible Officer Director in SBUHB.

12.5	The ODN core team will be situated in Morriston Hospital but with the expectation that they work across the Network flexibly to meet the needs of the service and provide a visible presence in all sites.  Some posts in the Network will be Regional roles, i.e. working across or being responsible for services across multiple sites. ODN staff will require practice rights in both Health Board organisations regardless of their normal ‘base’ site as they could be required to work across the network as part of their roles. In the transitional phase and prior to any TUPE transfer, those staff who have been identified as working across both Health Board sites will be given practice rights to practice within both sites. Such rights will be supplemental to the staffs’ existing contracts (via a collateral contract or “side letter”), which will bridge the gap prior to implementation of the MoU for the ODN and the TUPE transfer. On the relevant TUPE transfer date, the side letter will remain in force (for the duration of the contract or for as long as cross-site practice rights are necessary), to provide for cross-site practice rights where applicable to those staff who are required to practice within both Health Board sites.

12.6	ODN staff members will be expected to maintain professional CPD, complete all mandatory training and uphold competencies in line with the requirements of the role. ODN staff will be subject to all SBUHB HR policies including annual appraisals/PADR and disciplinary processes ODN staff in training will be expected to work in the geographic areas of both Heath Boards, as part of their training.

- 13.	Escalation

- 13.1	If either Health Board has any issues, concerns or complaints about the Project, or any matter in this Transitional MoU, that Health Board shall notify the other Health Board and the Health Boards shall then seek to resolve the issue by a process of consultation. If the issue cannot be resolved within a reasonable time, the matter shall be escalated to the Pathology ODN Operational Group, which shall decide on the appropriate course of action to take. If the matter cannot be resolved by the Pathology ODN Operational Group within [28] days, the matter may be escalated to the Pathology ODN Board for resolution. At this stage of escalation, the CEOs of both organisations should be notified of the dispute with a view to resolution.  If the CEOs cannot resolve the dispute, it will be escalated to Welsh Ministers for resolution.

- 14. 	Risk Management

- 14.1	A risk management arrangement and process will be established in the event of closure of the ODN. This will include an assurance process to ensure risks are identified, analysed, evaluated, controlled, monitored and communicated appropriately.

- 14.2 	A quality assurance process will be undertaken to ensure consistency of standards and quality of care across the ODN. This will include ODN facilitated external/internal peer review undertaken as appropriate.

- 14.3 	There will be an ODN escalation plan and structures established in the event of a major incident / surge with links to appropriate organisations for effective emergency preparedness, resilience and response arrangements.

- Intellectual Property

The Health Boards intend that notwithstanding any secondment any Intellectual Property Rights created in the course of the Project shall vest in the Health Board whose employee created them (or in the case of any Intellectual Property Rights created jointly by employees of both Health Boards in the Health Board that is Lead Health Board noted in clause 11 above for the part of the Project that the Intellectual Property Right relates to).

Where any Intellectual Property Right vests in either Health Board in accordance with the intention set out in clause 15.1 above, that Health Board shall grant an irrevocable licence free of charge to the other Health Board to use the Intellectual Property Rights for the purposes of the Project.

Each Health Board shall retain all title, right and interest in and to its respective Intellectual Property Rights.

Property Rights created prior to the effective date of, or outside the scope of, this Transitional MoU (“Background IP”).  Save as expressly granted under this clause 15 or as otherwise agreed herein, nothing in this Transitional MoU shall be construed as a transfer, licence and/or assignment from one Health Board to the other of ownership of, title, right or interest in and to its respective Background IP.

Data Protection and Information Governance

16.1	The Health Boards agree to comply with the requirements of the Information Sharing Protocol and to enter into a Data Sharing Agreement as applicable, as attached to this Transitional MoU in Annex B.

- 17.	Term and Termination

- 17.1	This Transitional MoU shall commence on the date of signature by both Health Boards, and subject to clause 17.3, shall expire on 31 March 2025 or on completion of the Project, whichever is the latest.

- 17.2	If the Project is not completed by 31 March 2025, the ODN Delivery Board shall propose the time period of extension for the Transitional MOU for decision by both Health Boards in their March 2025 meetings.

- 17.3	Either Health Board may terminate this Transitional MoU by giving at least six months' notice in writing to the other Health Board at any time.

- 18.	Variation

18.1	This Transitional MoU, including the Annexes, may only be varied by written agreement of the Pathology ODN Board.

- Charges and Liabilities

Except as otherwise provided, the Health Boards shall each bear their own costs and expenses incurred in complying with their obligations under this Transitional MoU.

The Health Boards agree to share the costs and expenses arising in respect of the Project between them in accordance with the Contributions Schedule set out in Annex D to this Transitional MoU to be developed by the Pathology ODN Operational Group and approved by the Pathology ODN Board within three months of the date of this Transitional MoU.

Both Health Boards shall remain liable for any losses or liabilities incurred due to their own or their employee's actions and neither Health Board intends that the other Health Board shall be liable for any loss it suffers as a result of this Transitional MoU.

Ownership of Assets

All assets (including intellectual property rights) acquired by SBUHB in connection with the ODN shall belong to SBUHB but be held upon trust for the ODN.

SBUHB shall, to the extent it is legally entitled to do so, transfer ownership and any other rights in such assets to such party or body as a commissioner shall require and within such timescales as are reasonably required.

In the event that any income is derived from such assets or from their disposal, such revenues shall be regarded as part of the ODN income and accounted for accordingly.

Procurement

21.1	When existing contracts, which have been entered into separately by each Health Board, have expired, it is envisaged that new contracts will be entered into for the benefit of the ODN by adopting a joint approach, for example, SBUHB will act as the lead procurer for goods, services and works that are required by the Health Boards.

21.2	Existing (separate) contracts entered into by the Health Boards will remain in force until their expiry date (unless such contracts may be lawfully terminated, for example, because of contractor default, insolvency etc. or where the Health Boards have a right to terminate at will on written notice). Upon expiry, the approach in clause 21.1 above will be adopted.

21.3	Where contract terms permit and subject to the public procurement rules in force at the time, in order to be in a position to re-procure jointly, a Health Board may extend (or not, as the case may be) any existing contract to align its expiry date with a corresponding contract entered into by the other Health Board.

Host Health Board - Duty of Care

SBUHB shall be responsible for ensuring that all reasonable skill, care and diligence are exercised in carrying out those services which it is required to perform under the ODN as the host Health Board, properly and efficiently in accordance with this Transitional MoU and its overall responsibilities under the National Health Service (Wales) Act 2006 and all other appropriate legislation.

SBUHB shall keep the ODN informed of any reasonably foreseeable or actual changes in circumstances which are likely to affect its ability to comply with the terms of this Transitional MoU as the Host Health Board.

Management of Concerns

- 23.1	Where a matter is received into the ODN and is regarded as an individual concern (as defined in The National Health Service (Concerns, Complaints and Redress Arrangements) (Wales) Regulations 2011 (“Redress Regulations”)), SBUHB will only be responsible for the management of those concerns where qualifying liability (as defined in the Redress Regulations) in tort is established, which relates to its geographical area of responsibility and arises from its own resident population. In such circumstances, the Chief Executive of SBUHB will be responsible for investigating and responding to the concern in accordance with the Redress Regulations. For the avoidance of doubt, complaints or matters which are not Concerns or Complaints (as defined in the Regress Regulations) but which otherwise relate to the performance of this Transitional MoU, are dealt with under clauses 23.5 and 23.6 of this Transitional MoU23.2 	Individual Concerns or Complaints received into the ODN and relating to patients resident outside SBUHB’s geographical area of responsibility will be referred to the Chief Executive of the health board in the appropriate geographical area no later than two (2) Working Days of becoming aware of that Concern or Complaint.23.3	Where a Concern or Complaint involves the exercise of functions by both SBUHB and HDUHB, the Health Boards shall co-operate for the purposes of co-ordinating the handling and consideration of the Concern or Complaint in accordance with the Redress Regulations and shall ensure that the person who notified the Concern or Complaint receives a co-ordinated response to the Concern or Complaint that he or she has notified. This duty to cooperate includes a duty for each Health Board to:

agree which Health Board shall take the lead in:

          - co-ordinating the handling and consideration of the Concern or Complaint; and

          - communicating with the person who notified the Concern or Complaint;

provide information relevant to the handling and consideration of the Concern or Complaint which is reasonably requested by the other Health Board; and

to ensure that it is represented at any meeting reasonably required in connection with the handling and consideration of the Concern or Complaint.

- 23.4	In respect of the performance of this Transitional MoU, both Health Boards shall and shall procure that their staff shall be required to comply with the duty of candour introduced pursuant to the Health and Social Care (Quality and Engagement) (Wales) Act 2020 and any Guidance issued in relation to the implementation of this duty and the 2020 Act, where an outcome triggers the duty of candour procedure.

- 23.5	Where a matter is considered to be a review of funding decisions it will be dealt with in accordance with the Review Process set out in the All Wales Policy for Making Decisions on Individual Patient Funding Requests.

- 23.6	If either Health Board receives any formal inquiry, complaint, claim or threat of action (which is not a Concern or Complaint (as defined in the Regress Regulations) from a third party (including, but not limited to, claims made by a supplier or requests for information made under the Freedom of Information Act 2000) or under the Data Protection Legislation in relation to the Project (“Receiving Health Board”), such inquiry, complaint, claim or threat of action shall be dealt with by that Receiving Health Board, having regard to its internal policies and procedures and all relevant law. Where either Health Board receives a formal inquiry, complaint, claim or threat of action from a third party which requires information from the other Health Board prior to responding, the other Health Board shall assist and cooperate in a timely manner to enable the requesting Health Board to comply with its information and other disclosure obligations. If the Health Board providing the information to assist the other Health Board considers that the information is confidential or otherwise not in its interests or in the public interest to disclose, it shall have the opportunity to make representations to the requesting Health Board and both Health Boards shall attempt to reach agreement as to what information is disclosable. The requesting Health Board shall have absolute discretion as to what information, provided by the other Health Board, may be disclosed when responding to a formal inquiry, complaint, claim or threat of action from a third party. In all cases, the Receiving Health Board shall report the matter to the Pathology ODN Operational Group.

Audit

SBUHB will provide an effective independent internal audit function as a key source of its internal assurance arrangements. This will be in accordance with NHS Wales Internal Auditing Standards and any other requirements determined by the Welsh Government.

SBUHB will ensure that relevant external audit arrangements are in place which give due regard to the functions of the ODN.

Effect of ODN on SBUHB’s Core Functions

In the event of SBUHB’s determining (acting reasonably) that the performance by SBUHB of its obligations under this Transitional MoU is having a detrimental effect on SBUHB’s ability to fulfil its core functions, SBUHB may instruct the ODN Senior Responsible Officer and SBUHB’s Chief Executive to review the operation of this Transitional MoU.

In carrying out a review of this Transitional MoU further to clause 25.1 above, the ODN Senior Responsible Officer and SBUHB’s Chief Executive shall consider the source and manner of any detriment identified by SBUHB’s Board further to clause 25.1 and shall put forward such amendments and variations to this Transitional MoU and the associated governance arrangements between the ODN and SBUHB as they may consider appropriate.

SBUHB’s Board shall consider the recommendations made further to clause 25.2 and may recommend to the ODN Senior Responsible Officer and the Chief Executive of SBUHB that this Transitional MoU and the associated governance arrangements are amended accordingly.

Status

This Transitional MoU is not intended to be legally binding, and no legal obligations or legal rights shall arise between the Health Boards from this Transitional MoU. The Health Boards enter into the Transitional MoU intending to honour all their obligations.

Nothing in this Transitional MoU is intended to, or shall be deemed to, establish any partnership or joint venture between the Health Board, constitute either Health Board as the agent of the other Health Board, nor authorise either of the Health Board to make or enter into any commitments for or on behalf of the other Health Board.

| Signed for and on behalf of SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD |  |
| --- | --- |
| Signature: | ............................................ |
| Name: | ............................................ |
| Position: | ............................................ |
| Date: | ............................................ |
| Signed for and on behalf of HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD |  |
| Signature: | ............................................ |
| Name: | ............................................ |
| Position: | ............................................ |
| Date: | ............................................ |
| CONTACT POINTS |  |
| SBUHB |  |
| Name: | ............................................ |
| Office address: | ............................................ |
|  | ............................................ |
| Tel No: | ............................................ |
| E-mail Address: | ............................................ |
| HDUHB |  |
| Name: | ............................................ |
| Office Address: | ............................................ |
|  | ............................................ |
| Tel No: | ............................................ |
| E-mail Address: | ............................................ |

The Project

Project overview

The South West Wales Pathology Programme has two key components:

- The development of a single Regional Pathology service via an Operational Delivery Network (ODN) approach, with Swansea Bay as the host organisation.

- The development of a Hub Laboratory Centre of Excellence on the Morriston Hospital site to provide fit for purpose modern laboratory service for the region and local laboratory refurbishments via Welsh Government Capital investment processes.

This MOU focusses on the development of the Operational Delivery Network (ODN). The Business Case for development of the Hub buiding and local laboratory refurbishments has separate governance led by SBUHB.

The development of the ODN aims to provide stability and sustainability to pathology service across the region. Developing critical mass of service delivery, joint training and quality management systems, single digital information systems and collective recruitment for hard to recruit to roles will all contribute to decreasing risk with current service delivery methods. The balance of risk between the organisations does need to be considered as part of the establishment of the network and arrangements with regard for example capital investment in retained local laboratory services outside of any investment secured by the capital process will need to be considered i.e. significant backlog maintenance to existing buildings.

One of the key aims of the network is to ensure consistency of service delivery to the regional population regardless of their location. This will be achieved through the implementation of digital pathology solutions where possible, the development of a robust regional transport and logistics network and the timely analysis and reporting of investigations. Developing consistent service models and equipment and processes in all laboratories will also shore up business continuity through the movement of samples in the event of any laboratory down time in any site.

Background

To progress the transformation plan for Pathology services in South West Wales, the Health Boards agreed the need to create a Regional Pathology service model. This approach, new for NHS Wales but not across the United Kingdom would enable joint recruitment, collaborative development of service plans, standardisation of approach, equipment and facilities and the benefits of consolidation. A number of possible options of how a regional management model could operate that would be underpinned by a strong governance framework and an agreed set of principles were considered.

A Joint Executive meeting between SBUHB and HDUHB was held on 24th November 2021; these points were discussed and a subsequent visioning workshop was held on 29th November 2021, chaired by the then CEO of Swansea Bay UHB.

A Regional Pathology Task and Finish (T&F) Group convened in 2022, chaired by Andrew Carruthers COO HDUHB, and supported by Christine Morrell as SRO for the ARCH Regional Pathology Transformation Programme. The group considered their options for the management model and undertook an appraisal and sought advice from NHS Wales Legal and Risk services. The detail of the decision making process is covered in the November 2022 paper considered by both Health Boards (see Appendix). The conclusion was the development of an Operational Delivery Network (ODN) for Pathology services with an aim to be operational by Q4 2022/23,

Following the establishment of the ARCH Pathology team in early 2023/24 the task of delivering the ODN model moved forward at pace. The terms of reference of the T&F group were revised to form an ODN Transition Board and sub groups established to consider implications for Finance and Commissioning, Workforce and Digital services. It addition, Legal & Risk advice has been retained to work with both HB governance teams on the Memorandum of Understanding and legal agreements required to deliver the network.

To date the following developments have been agreed:

- Development and agreement of a Mortuary MOU for the Region. This has facilitated closer working between the mortuaries and the appointment of a regional mortuary team, joint training processes and rotations.

- Development and agreement of joint regional management structure and job descriptions and person specifications for those roles

- Baseline assessment of performance, resources, quality/accreditation, compliance and workforce for the region

- Review of existing logistics and transport arrangements

- Continued development of regional Digital Cellular Pathology pilot in the region

- Staff engagement in all laboratories in the region to develop the identity and culture of the regional service and understand the current strengths and challenges on each individual site.

- Appointment of a single Designated Individual (DI) for the regional mortuary service following the retirement of the current HDUHB post holder. This has been achieved by appointment of the same individual to take responsibility for both Health Board licenses, although licenses still remain separate.

Current work is focussing on:

- Development of a regional ‘compliance’ team structure to combine functions in both organisations in pathology, IT, Quality, Health and Safety and Training

- LIMS 2.0 roll out regionally by February 2025. To ensure that the region has a consistent pathology digital system with replicable supporting processes in both health boards

- Consideration of the regional recruitment and training of non-consultant medical staff to histopathology

- Development of a Transitional Pathology Regional MOU for consideration by both Boards to support the development of the regional management team and integrated service change

- Development of the Service Specification and commissioning arrangements for the Pathology service for consideration by both organisations.

The proposal therefore is to continue to regionalise the service via the Transition Board but also move into the territory over the next 12 months of harmonising workforce arrangements. Once the commencement date of the Network is agreed by both Boards the process of appointing into the senior leadership team and subsequent TUPE transfer of staff into the new service model will commence.

Transitional MOU

This transitional MOU has been developed by a task and finish group established under the leadership of the ARCH Programme Director with input from NHS Wales Shared Services – Legal and Risk, and SBU and HDUHB Governance Teams. The group has met monthly to develop the attached draft MOU for the Transition period.

The Transitional MOU takes the same form as the proposed final MOU but with the following differences:

- Transitional MOU only covers the period to April 2025. It has no permanence as the organisations will need to agree to the formal MOU once developed for the recurrent networked service

- The ToR for the ODN will be developed during the Transition period and therefore this annex and others are under development through the Transition period

- The

The Transitional MOU seeks to support:

- Development of the Service Specification for the Pathology ODN

- Development of Commissioning arrangements including quality management and assurance

- Support to start implementing the leadership team for the regional service

- Information and data sharing of staff information and clinical service information

Information Sharing Protocol

The Health Board Information Governance Teams will work with the ARCH Programme Team and ODN Board to develop and approve an Information Sharing protocol between the organisations.

This is already in place for the separate Mortuary MOU and will form the basis of the overall Pathology Protocol.

A DPIA has been undertaken to assist in the development of the protocol

Pathology ODN Delivery Board Terms of Reference

(a) Remit:

In Transition phase the ODN will have two key tasks:

- To develop and approve the various documents that will finalise the Pathology ODN formation and seek approval via public board. This will include: service specification and commissioning approach, MOU (permanent), TUPE arrangements, assurance and monitoring processes

- To appoint to the Network Director roles

The Board will also oversee the Operational Group and shape the regional service provision and assurance through this transition phase.

(b) Membership Decision-making:

SBUHB:

Chief Operating Officer (Lead Director)

Director of Therapies and Health Sciences

Director of Finance

Medical Director’s Office representative

Workforce Director representative

Network Director, Pathology ODN

Network Clinical Director, Pathology ODN

Programme Director, ARCH Pathology (Transitional ODN only)

HDUHB:

Director of Therapies and Health Sciences

Director of Operations  (Transition Chair)

Director of Finance

Medical Director’s Office representative

Workforce Director representative

(c) Meetings:

The meeting will take place monthly

Papers will be circulated one week in advance

Meetings will routinely take place via MSTeams or in person if required

Quoraum will be three representatives from each organisation.

Pathology ODN Operational Group Terms of Reference

(a) Remit:

The Pathology ODN Operational Group will provide a regional focus to operational service management and operational delivery.

The group will develop a standing agenda through the Transition phase to ensure oversight of Pathology operational matters on a Regional footing.

This should include (but not be limited too):

- activity and performance information,

- accreditation updates,

- quality and safety information and;

- financial performance.

The group will be cognisant of the developing service and commissioning specification for Pathology and will be charged with developing information in the Transition phase to ensure the delivery of the commissioned service can be monitored and assurance provided to the ODN Board

The group will also be charged with developing the Pathology ODN annual plan, detailing service developments and improvements as well as developing any investment cases for Board approval.

(b) Decision-making:

- Network Clinical Director, Pathology ODN (Chair)

- Network Director, Pathology ODN

- Service Manager, Cellular Pathology, Pathology ODN

- Clinical Director, Cellular Pathology, Pathology ODN

- Service Manager, Laboratory Medicine, Pathology ODN

- Clinical Director, Laboratory Medicine, Pathology ODN

- Quality and Safety Lead, Pathology ODN

- Training Lead, Pathology ODN

- Service Group Director, Morriston Hospital

- Pathology Workforce Manager

- Pathology Finance Manager

(c) Meetings:

The meeting will take place monthly; 2 weeks following/prior to the ODN Board.

Papers will be circulated one week in advance

Meetings will routinely take place via MSTeams or in person if required

Quoraum will be one of each of the Network Director, Cellular Pathology, Laboratory Medicine lead roles and workforce and finance representatives.

Pathology ODN Transitional Sub Groups

Three sub groups have been established to support the development of the ODN: Finance and Commissioning; Workforce and OD and Digital. All contain representatives from respective departments in both Health Boards, the ARCH Pathology Team and Service leads from both Health Boards.

The ARCH Pathology Team provide business support to the sub groups and the transition board. The host organisation will take on secretariat of these groups following the establishment of the ODN. The ARCH Pathology team will be disbanded at this stage

Contributions

The Finance and Commissioning Sub Group are tasked with developing the Service Specification and Commissioning arrangements for the ODN. The ODN Board will have to approve these in Transition prior to any decision to fully establish the ODN. This will confirm the resource responsibilities and risk sharing on commencement of the ODN and assurance and monitoring arrangements.