The following are highlights of the Quarter 2 achievements by area.

Information on achievements have been reported as part of the Highlight Reports provided for APOG on 10th October 2023.

UEC / Six Goals

Programme 1 – Co-ordination, signposting & alternatives to admission

Atrial Fibrillation Redesign

- 38 practices signed up to AF framework

- Referral criteria developed for ECHO service and PAF clinics

- Activity underway re: improved access to one stop clinics for AF by clinical professionals with specialist interest in AF

- Staff recruitment completed and full complement of staff to be in post from 20/11 to provide new community based echo service for newly diagnosed AF patients

Heart Failure Redesign

- Dashboard to monitor progress in development

- Recruitment – all business case posts have been recruited

- Training with clinical competencies ongoing

- Secured clinical spaces across region to expand service

Diabetes redesign

- 29 practices are engaged with the programme. Planning in progress to commence delivery in Cwmtawe and Bay Cluster

Programme 2 – Integrated Front Door

SDEC:

- Current SDEC model in place – rapid testing period and perfect fortnight completed. Plans to further integrate AMU and SDEC in to an Acute Hub. SDMU (SAU) model progressing as part of same day emergency care offer

- Triage for AMU and SDEC within SDEC and all-walks ins coming through SDEC

- Perfect fortnight completed – successfully decompressed yellow zone and anecdotal improvements in flow from ED

- SDMU (SAU) nursing workforce and recruitment plans mapped and underway in readiness for anticipated business case sign off and go live.

Care home rapid response:

- Project operational

- Pharmacy reviews for all residents at the agreed care homes continue to be rolled out

- Rapid response element of project operational

- Baseline data collated and compared to monthly performance data

Programme 3 – Acute Hospital Flow and discharge

SAFER/ Red2Green/ D2RA:

- Phase 1 completed - further work taking place re; D2RA, preventing deconditioning and criteria led discharge. Patient flow team at MGH to work across SBUHB

- Criteria Led Discharge launched

- Plan developed re collection of pre-COP red reason code

- System requirements being confirmed to carry out change to Signal re; D2RA measures reporting

Stroke Pathway Improvements

- SBAR submitted to management Board in July and has since been approved – recruitment in line with SBAR underway.

- Some performance improvements seen to date

Improvements to repatriations/ transfers for patients requiring specialist rehab (neuro/ stroke/ orthopaedics):

- Repatriation improvements forms part of broader MGH patient flow initiatives

- Current activity includes scoping of how repatriations can be improved

Embed centralised acute admissions model at Morriston:

- Work ongoing to embed all acute admissions at MGH

- Rapid improvement project (AMU/ED) – ambulatory patients accessing acute hub via SDEC entrance (triage within SDEC)

- Removal of ‘fit to sit’ in yellow zone

- PAT Team working in AMU

Programme 4 – Integrated discharge

Extend sanctuary service provisions:

- Bid submitted to RPB for capital improvements to improve the environment within the Forge Centre. Approval from RPB for £90k – capital project manager identified.

- Work is ongoing is ongoing with capital estates to agree a plan and schedule timeline to undertake work

Ensure implementation and reporting of all D2RA pathways (in conjunction with SAFER roll-out) from the hospital to community with right community services in place (right-sizing infrastructure to deliver model)*:

- D2RA conversations underway at ward level re; D2RA terminology used in ward rounds. D2RA data is currently only reported for the Home First service. Work underway re; finalising Signal system change requirements so as to be able record & report all discharges

Implementation of a Single Point of Access/ Integrated Discharge Hub for all community services:

- Model for IDH agreed and implementation to commence with target implementation of Q3. Project roll out began on 4th September

- Improvement project started on 4th Sept with roll-out of Patient Assignment Team (PAT) within AMU. PAT to date have joined AMU at Board rounds to have focussed push on discharges. In this time 179 discharges have taken place (Pathway 0 = 127/ 71%; Pathway 1 = 29/ 16%; Pathway 2 = 8/ 5%; Pathway 3 = 15/ 8%)

Provide additional EMI beds

- Pilot approved in June 23 subject to ongoing review – increase in EMI capacity (8 beds) in place for 23/24.

- Pilot subject to ongoing review – pilot began June 23 (running until March 24)

Ty-Olwen: Commission 4 inpatient beds:

- Ty Olwen has 12 beds operational (2 additional beds commissioned)

- Social worker recruitment underway to move to 14 beds

Planned Care

Waiting times

- The Health Board’s position has improved with good steady progress against the 52-week and 104-week targets. The 52-week outpatient target set for the end of October is on track to be achieved.

- Revised trajectories for clearing 99% of 104 weeks (all stages) by the end of March 2024 have been developed but are still dependent on securing the necessary funding from Welsh Government to achieve

- Stage 5 waits continuing to decrease with additional scrutiny in place, however reliance on outsourcing/insourcing contracts to deliver ministerial target

Mental Health & Learning Disabilities

Milestones Completed

3 x milestones have now been completed.

- MHLD_001 111 Press 2 in place providing 24/7 access into mental health services experiencing a MH Crisis.

Completed

- MHLD_0024 (a) Repurposing of Cardigan Ward as an admission, assessment and treatment ward complete.

Completed

- MHLD_030 Patients have access to Public Health Wales Physical Health Screening Programmes in Forensic Services. Completed

The majority of the GMOs are progressing well and are on track.  These include:

- Improvement in 111 Press 2 response times and call rates

- Expansion of Adult Sanctuary Service into NPT

- Construction to start on Seclusion Suite for Taith Newydd

- Successful roll out of WCP & HEPMA across adult inpatient areas

- Continued work on development of implementation plan for Dual Diagnosis Strategy

- Implementation of hybrid medical model within medium secure services

Digital

- Development of a coherent digital roll out plan to enable the digitisation of the Mental Health and Learning Disabilities service; the plan is sequenced in such a way as to maximise the system benefits, to provide digital systems support to the areas of greatest flow pressures within the Service Group and to enable roll out of wider systems. The implementation of HEPMA and WCP across Cefn Coed is now complete, this has been a very positive experience for the HEPMA and WCP teams and has been well supported by all health professionals within the mental health service.

- The Signal team have added mental health fields and sections to Signal and implemented in Mental Health wards F, Fendrod and Clyne.

- User requirement workshops have been held with key health professionals to develop a local specification to support the procurement of an ePMA system from the National ePMA multi-vendor framework. Following approval at the Clinical Reference Group (CRG) and the HEPMA board an invitation to tender has been issued.

- Electronic Test Requesting (ETR) uptake has reached 77% in secondary care and 89% in primary care, towards an aim of 90%. The focus has been on Paediatric outpatients and neonatal services, which went live in July. The Radiology department are evaluating the current use of electronic Radiology requesting, with a view to making this available to AMU followed by Paediatric outpatients.

- Phlebotomy Module pilot in NPT inpatients remains dependent on a fix from the LIMS supplier. This has taken an extended period of time for the LIMS supplier to assess and has been escalated to DHCW as the LIMS contract holder. The assessment has been returned and DHCW are raising the Purchase Order for work on the fix to begin.

- National Data Resource – engaging with the national programme to understand how the future capabilities could support the sharing of data between applications and business intelligence. The local Steering Group has reviewed a proposal for a Local Data Resource.

- Discussions pertaining to the implementation of Welsh Emergency Department System (WEDS) continue with the DHCW Chief Executive in light of the strategic review commissioned to evaluate the WEDS platform.  The local SBUHB project board and National Programme are actively working towards establishing next steps.

- The SAFER dashboard, allowing measurement and comparison of the SAFER principles performance on each ward across hospital sites has been launched during this period.

- ED, Outpatient and Referral Self-service Dashboards using the admission activity self-service template have been launched, enabling oversight of this key performance measure to support improvement and highlight good practice.

- The Urgent Emergency Care App containing numerous UEC reports in a single-entry place has been launched. Daily and weekly reports have also been scheduled via the app and are emailed to relevant parties, supporting proactive management.

- The Fracture Discharge Service measures have been added to the Virtual Wards dashboard, enabling performance to be measured.

- The Digital and Data Literacy module on the manager’s pathway has continued to be delivered during this period, supporting staff at many levels to understand and maximise use of available data.

- The upgrading of the Wireless infrastructure has begun in Q2, this works involves the replacement of approximately 1200 Wireless Access Points that are ceiling mounted every 3 metres across the whole hospital site. We are currently at 35% completed.

- Work has continued with migration of data from the old SAN/VMWARE environment to the new environment (which was procured at the end of the 22/23 financial year). Work was due to complete by the end of QTR 2 but it will now continue into the first few weeks of QTR 3.

Cancer

Cancer Services: (Divisional Lead – Adel Davies Pugh, SRO- Ceri Gimblett)

Radiotherapy:

- SABR expansion all documentation completed – next phase to begin Oct 2023

- CT Recommissioning Business case reviewed at BCSG and BCAG in September.  To go to Senior Meeting October 4th. If final approval granted recruitment to commence immediately.

Haematology:

- Business Case approved by Management Board in July 23 to strengthen the middle grade tier of doctors and CNS provision within Haematology

- Successful appointment of CLL CNS and has commenced in post and has started clinic.

- Successful appointment of 3 WTE CNS Coordinators currently going through recruitment checks with imminent start dates.

- Successful appointment of 2 WTE Senior Clinical Fellows – both require MTI Programme and so the service is working closely with the Royal College and Medical HR. Expected start date in Jan 24.

- 3 WTE Junior Clinical Fellows are currently out to advert with a closing date of 4th October.

AOS:

- 5 day acute oncology service in place at Morriston supported with 5 day Acute Oncology Haematology Assessment Unit (AOHAU) at Singleton.

- SBAR agreed by team for SMT Oct 23

- RAG rated action plane in place with teams to support the requirements against the 'Service Specification of Acute Oncology Services for the NHS in Wales'.

OG Cancer Surgery Service and non-resection surgery service (Divisional Lead – Mollie Kearns, however this project is led via RSSPP (SBUHB and CVUHB partnership)

- Milestones developed for Q2-Q4 following recent meetings held between clinical leads in SBUHB and CVUHB.

- Draft pathway developed based upon SW Peninsular model and circulated for discussion across surgical community.

Consultant AHP Cancer Post (Divisional Lead, Helen Annandale, PCT Service Group)

- Successful recruitment to post in Sept - anticipated start date at end of Q3.

Primary Care, Communities and Therapies (PCT)

- 11 out of 18 GMOs are on track with a further 4 on track for year-end recovery

Children & Young People

16 of the 24 GMO’s are on track in quarter 1. The main achievements to note are:

- Capital funding has been approved by Welsh Government in support of necessary adaptions required to enable the relocation of the Paediatric Sexual assault referral centre (SARC). This will allow the Paediatric SARC to be relocated to SA1 site alongside the Adult SARC.

- The SBUHB neonatal service has benefited from a funding uplift as a result of the WHSSC reconfiguration of cot capacity across South Wales. The formal outcome and funding has now been received. Nursing and Medical staffing establishments will be enhanced on a recurrent basis, along with therapy and Psychology support. Robust recruitment and retention strategies are underway.

- The Welsh Government Neurodivergent Improvement programme has been launched, Childrens services representatives nominated and attending meetings, keen to participate in developing a national model.

- A multi-agency Delivery Plan for Children & Young People’s Emotional & Mental Health Delivery Plan has been developed in collaboration with WGRPB.

- All vacant paediatric dysphagia speech and language therapy posts now appointed with staff taking up posts. SBUHB have instigated a working group to develop in house competencies based on All Wales Adult Dysphagia competencies.

Workforce

The following highlights some of the key milestones that have been delivered in Q2:

Goal 1: Planning Our Workforce

- We have launched a new Workforce Planning SharePoint site on the Health Board’s intranet hub sites

- We have launched a new programme of work to record funded baseline establishments on our Electronic Staff Record (ESR) system, working in partnership with finance. This programme of work is planned to take place in 2023/24 and roll over into 2024/25

Goal 2: Attract and Recruit our Workforce

- We have expanded our Central Resourcing Team in readiness for them to support more service groups with Nursing and Health Care Support Worker recruitment activities in Q3

Goal 3: Engage and Retain Our Workforce

- We completed phase 3 of our Big Conversation staff engagement programme in July 2023 which involved 7 engagement workshops with 130 senior leaders attending to engage on the One Bay Way vision. This Method will now be closed for Q3

- Good progress is being made in the development of a new SharePoint site for managers to access HR policies and processes

- Good progress is being made for our retention initiatives, which will be moving to implementation phase in Q3

Goal 4: Equality, Diversity and Inclusion

- Our main workforce policies continue to be translated by the Welsh Language team and made available on the intranet site

Goal 5: Health and Wellbeing

- All Occupational Health and Wellbeing staff have been trained on the new Occupational Health system and the system has gone live

- We have exceeded our Q2 targets in the number of staff trained in REACT and suicide prevention and stress awareness

Maternity

MAT_009- Continuity of Carer- Workforce review and plan to be developed

UPDATE- Community OCP began on Monday 11th September with proposals for new team structure, Band 7 managers for each team and teams structured in line with PCTG clusters to allow for better cross cover for clinics and home visits.  If agreed this will support our aim of women being seen by no more than 2 midwives in the community and support us in reopening community services by redirecting staff and patients from Singleton back into the birth centre and home births.

MAT_008- Mechanisms for recognising themes and trends in care ‘failings – red flags NICE maternity staff reporting and responding

Quality & Safety

| Area | Achievements |
| --- | --- |
| Falls | - Falls rates per 1000 bed days under 4 (national average 5.8) - Falls framework updated for engagement - Falls audit completed in Older Person’s Mental Health services on all sites- this will lead to a QI plan in Q3 - Community falls scoping exercise complete and fed back to service group for their action - HB wide reconditioning campaign undertaken throughout August |
| Infection Prevention and Control | - IPC lead for care homes recruited - IPC audit programme agreed - Following number of pseudomonas cases in SGH, process put in place to inform IPC of positive water samples |
| End of Life Care | - Digital intelligence discussions ongoing, plans for development of some measures in Sept 2023. - Palliative Care Project started in July 2023 (Safe Care Collaborative Community Work stream project). - Recent bespoke training has taken place across Morriston, NPT&S and P,C&T service groups. Care home train the trainer is ongoing. Up to August 2023 21% of HB staff have received EOLC training. - A&FCP notifications in WCP are increasing - Feedback obtained from clinicians after the Treatment Escalation Plan pilot in ED and AMU, changes are to be made to the Treatment Escalation Plan. |
| Suicide Prevention | - Sharing HOPE 747 staff engaged since April 2022 - Social platforms Swansea NHS site on Facebook, Twitter and YouTube = 3.7k views as at end of May 2023. - There have been several Sharing HOPE sessions in ITU Morriston Hospital for high-risk trauma these sessions are ongoing throughout the year. - New combined REACT & Suicide Prevention Training including newly qualified induction nurses Total trained from Sep 2022 = 841 - A bespoke REACT & Suicide Prevention training was delivered to Primary Care staff during there BT4L (Protective time for learning). Total trained in March 2023 = 263 - Child Health bespoke session was delivered since June 23 where 27 people attended in total. - Between Mar 22 to August 2023 – 5.76% of cases reported suicidal thoughts in the previous 7 days of initial contact. - Between Jan 22 to August 2023 – 3% of cases reported thoughts to end life. - Level 3 Suicide Prevention training for Mental Health professionals (This has been successfully piloted and will be rolled out across the MH division) |
| Sepsis | - Morriston sepsis leads are in discussion with digital planning to provide a digital solution and a focussed piece of work in SDMU looking at training. - NPTSSG are looking at using existing Signal options to improve communication around sepsis and a targeted training programme. - Awareness campaign including drop-in training sessions, ward-based training sessions and use of sepsis notice board displays are being used across the HB. |
| Nutrition and Hydration | - Agreement of QI projects to be undertaken as part of QP - Engagement with Improvement Cymru to provide coaching as part of QI project to increase accurate weighing of patients |
| Pressure damage | - Agreement of SRO - Agreement of QI projects to be undertaken as part of QP |
| Quality, safety and improvement capacity and capability | - Posts being recruited to - Community of Practice held - Patient Safety Congress event held |