| Meeting Date | 30 November 2023 |  | Agenda Item |  |  | 3.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Swansea Bay University Health Board Estates Strategy Update |  |  |  |  |  |
| Report Author | Simon Davies, Interim Director of Capital Planning & Estates. Ian MacDonald, Assistant Director of Finance |  |  |  |  |  |
| Report Sponsor | Darren Griffiths, Executive Director of Finance and Performance. Activing Deputy Chief Executive |  |  |  |  |  |
| Presented by | Darren Griffiths, Executive Director of Finance and Performance. Activing Deputy Chief Executive |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this document is to present progress on delivery of the Health Board’s approved Estates Strategy, which identified the infrastructure requirements to support the future healthcare service needs and striving to obtain business continuity. The Strategy also set out the scale of work needed to address the urgent and significant backlog maintenance works following completion of the 6-facet condition survey undertaken in 2022. |  |  |  |  |  |
| Key Issues | The Estates Strategy highlights the opportunities associated with developing the existing estate in line with the clinical service plan and development control plans, whilst managing the Health Board’s high and significant backlog maintenance risks including electrical systems, ventilation systems, heating systems, fire and medical gas installations. The 10-year strategy highlighted an indicative capital funding requirement of £812m to address prioritised capital projects within our development control plans, including historical and current poor condition of the aged estates with estimated backlog maintenance figures of approximately £102m. A risk assessed approach has been taken to highlight the important first steps that need to be undertaken to deliver the strategy. This will need to be underpinned by a Long Term Financial Model which shows how the revenue model for the Health Board is structured to support the changes in clinical model and estate configuration. The report sets out the progress made to date in key areas and the further work required as aspects of the Strategy are translated into delivery plans to meet the requirements of the Strategy. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - - NOTE progress on implementation of the approved Health Board Estates Strategy, including acquisitions, disposals, and business cases. - NOTE progress on the Private Finance initiative (PFI) Exit and alternative financing models. - NOTE progress with the priorities for Mental Health and Learning Disabilities (MH&LD) and Primary, Community and Therapy Services (PCCS) - NOTE progress with the plans for the prioritised Morriston business continuity plans for ward refurbishment and roof replacement. - NOTE the next steps and reporting plans through the Performance & Finance Committee. |  |  |  |  |  |

SWANSEA BAY UNIVERSITY HEALTH BOARD ESTATES STRATEGY

- INTRODUCTION

The Health Board’s Estates Strategy was approved by the Health Board in May 2023. The development of the Estates Strategy is a key enabler for delivery of the Health Board’s Clinical Services Plan (CSP), however the NHS in Wales faces unprecedented challenges balancing the management of the current estates condition against other competing priorities within existing capital funding constraints.

In general terms we have reported to Board that 75% of our existing Estate is more than 30 years old including the Morriston Nucleus template with a number of other areas built in the 1960’s making it challenging when developing/maintaining the Estate to support our existing and future clinical needs.

66% of the Estate is described within our 6 facet survey condition of being poor, in a bad condition and the Strategy Acknowledges that we must address these areas (mainly wards and theatres) or the facilities could become unavailable for clinical care.

This is a risk that we will have to manage, especially within our older wards and theatres which means that we will have to carry out a reactive approach to immediate repairs to maintain business continuity of services whilst also planning to address these challenges through our pre-planned maintenance and painting programme.

This Estate Strategy has been developed to consider the beginning of a new 10-year asset cycle, which will look to renew and optimise significant parts of the acute sites, alongside improving access for key services. It will provide a strategic framework for estate development and management which demonstrates that it has responded to and identifies the facilitation requirements that meet the Swansea Bay University Health Board CSP, to align the clinical accommodation to the prevailing service and strategic objectives alongside the overall development control plan.

The initial stage of the Strategy is clear in the main objective is to maintain business continuity in the current climate of limited capital funding being available. Specialist Estates Services (SES) Capital Audit have just completed a report for Audit Committee on our Estates Strategy and highlighted the risk around capital funding constraints.

In the short to medium term the health board has utilised a combination of All-Wales capital funding, targeted Estates Facilities Advisory Board (EFAB) Funding, planned reactive maintenance and discretionary funding to address identified high priority areas including successfully secured EFAB funding of £7.9m over 2023-24 to 2024-25 to date to tackle high / significant backlog priorities.

- BACKGROUND

A priority for the Strategy is to increase estate utilisation and efficiency by decreasing some of the estate and its backlog maintenance costs, whilst still managing to improve the environment. It is also important that the Health Board can provide assurance that its health estate is well managed operationally and is safe and secure for patients and staff and appropriate and sustainable to support current and future needs as identified in the clinical services plan maintaining business continuity.

As previously mentioned, the delivery of these plans will require financial investment, alongside changes in working practices and will present a challenge to the organisation as we strive to implement change and ensure our infrastructure is fit for our future.

Whilst the complexities of the work identified seems enormous, do nothing is not an option and we have identified good practices in place to understand the requirement and put together both planned preventive maintenance works and reactive maintenance works including future capital work plans (new build) being undertaken in order to further reduce the overall backlog maintenance costs for the Health Board including.

2.1 	Disposals and Acquisitions

Cefn Coed Hospital Site

Board approval has been given to acquire ownership of the land and building at Ty Maes y Gruffydd, Cefn Coed. This area of land is required as part of the development of the new Adult Acute Mental Health Unit. Agreement on the transfer of ownership has been reached with Welsh Ambulance Trust (WAST) and Welsh Government (WG).

The planned longer-term disposal of surplus parts of the Cefn Coed site which is included in the Swansea Council Local Development Plan (LDP) is continuing. Around the time of the of the adoption of the current LDP, a masterplan was developed for the residential redevelopment of the parts of the site surplus to NHS operational requirements. This included demolition and redevelopment to provide c350 new-build homes on the site.

The Cefn Coed site Masterplan needs to be updated to reflect the preferred location for the new Adult Acute Mental Health Unit (AMHU). This shift away from an entirely residential development will and the need to work with clinicians regarding the AMHU requirements has resulted in the site not coming forward for development during the current LDP period.  However, the progress which has been made stands the site in good stead to provide homes and an AMHU during the future LDP period, albeit that the scale of residential development will be reduced, and the site is therefore more appropriate for a reduced housing allocation of c170 rather than a Strategic Site. The future disposal plan will need to run alongside the development of the new AMHU.

Garngoch

Board approval has been given to declare part of the Garngoch Hospital site surplus to requirements. Approval will now be sought from WG to proceed with the disposal process which will be undertaken under the auspices of the NHS Wales Estates code (2018). The capital receipt will be retained by the Board.

Phillips Parade

Phillips Parade is a Health Board owned property near the city Centre in Swansea. The building is suitable for ambulatory care and would suit either a GP practice or other Health Boards service which are ambulatory in nature. There are a number of competing priorities for the provision of health care from this building and this is currently being worked through; any permission to change use or dispose of the asset will be a matter for Board consideration and approval.

2.2	Morriston Hospital

Morriston Hospital Front Entrance

Following the construction of Tawe ward in the main front entrance of Morriston Hospital during the Pandemic we are now in a position where we can reinstate this area and enhance the appearance back to a proper main entrance with enhanced services including the re-provision of; Discharge Lounge, Phlebotomy (for in-patients and out-patients), outpatient Lung Function Suite.

This will also bring back the open plan patient / visitors waiting area and create a dedicated, protected staff welfare area. Other benefits include the opening up and increasing the footfall through the commercial premises, Costa, Subway and WH Smiths. The Health Board has commenced the detailed design and subject to the successful conclusion of discussions with WG on providing upfront capital investment to undertake the re-instatement works, we hope works can commence in January 2024 and complete in June 2024, should WG funding be granted in the next few weeks.

Progressing with City Deal

The Campuses project being led by Swansea University and delivered in partnership with Swansea Bay University Health Board (UHB), Hywel Dda UHB and Swansea Council, is one of 9 projects under the Swansea Bay City Deal.

The Campuses business case previously approved by the Health Board, was approved by the Swansea Bay City Deal in October 2021 and subsequently by Welsh and UK Governments in December 2021.  Delivering the project has been delayed by an extended period of negotiation between the Swansea Bay City Deal, Local Authorities and Swansea University over details in the primary funding agreement which includes a wide range of elements far broader than health.

Following agreement of the primary funding agreements, the Health Board recently received a draft of the secondary funding agreement between Swansea University and the Health Board. An initial legal review of the agreement has taken place by the Health Board and agreement of the final secondary funding agreement is nearing completion.

Once finalised the agreement will allow funding to be released from the City Deal for the Institute of Life Sciences (ILS) Innovation Centre at Morriston (Refurbishment of the Morriston Management Centre) for Swansea University £1.250m and a contribution of £0.960m to the design fees for the proposed new Morrison Hospital Access Route.

Ward Refresh Works

The Capital and Estates teams have been working closely with the Morriston Service Group Director and operational team to identify a decant space to carry out general maintenance works, undertake the rolling painting programme and other essential works.

The short-term requirement will facilitate decant areas to undertake works from the approved £7.9m funding (2023/24 & 2024/25) from the EFAB. Good progress has been made with most of the Morriston Hospital main corridor flooring being completed and works will be commencing shortly in Morriston Hospital on the replacement of the fire alarm, replacement of call systems on Wards A, B, C and D and the highest priority roofing patch repair on Wards R, S, T and V will be completed this financial year. Until December 2023, TAWE ward will be utilised as a decant area where required.

The Morriston and Singleton Service Groups are working to facilitate the availability of future decant wards that can initially be used to facilitate EFAB works during Q4 2023/24 and 2024/25. The availability of decant wards would allow our thinking to evolve in how we can undertake a programme of major ward refurbishments in the medium to long term, beyond the current 2-year EFAB funding award. As highlighted in the Estates Startegy, this programme will need to factor in the highest business continuity risks in Morriston related to: -

- Roof coverings - risk of water ingress through the fabric of the roofing systems in the oldest parts of Morriston Hospital. Whilst underlying roof structures have been assessed as safe, the external fabric of the roof is at risk of failure of a scale which could result in an unsustainable loss of bed capacity.

- Inadequate ward configuration for single rooms & bed spacing and mechanical and engineering infrastructure improvements within the main theatres.

2.3	Update on All Wales Capital Schemes

Table 1 below provides an update with the major business cases identified in the 10-year capital investment plan included in the Estates Strategy. The Health Board is actively working on an unprecedented number of major capital investment business cases.

Table 1 - Major Business Case Portfolio

There are 13 cases at various stages of development for a range of investment related to enabling projects, maintenance of our existing estates and service transformation. Most of the business cases are progressing to plan, although increasing costs mean we are reviewing the scope and design of 3 cases to ensure they deliver within budget estimates. These are Regional Pathology, Regional PET-CT and Dan-y-Deri.

Co-location of Burns cubicles at General ICU.

The Welsh Government recently approved £7.7m capital funding to undertake works for the Burns ICU areas. These essential works are primarily to allow the co-location of the Burns Critical Care with General ICU to mitigate long-standing workforce issue. At the same time the capital works to create 3 new burns cubicles in ICU North, is allowing a full refurbishment of this area and also an upgrade of theatre 7 with replacement of the air handling unit.

Cancer and Diagnostics

Positive discussions have been taking place with WG about commencing a business case for the provision of a 2nd CT-SIM at the South-West Wales Cancer Centre (SWWCC). Subject to business case approval by WG and agreement to the revenue funding from both Swansea Bay and Hywel Dda Health Boards, the high level-plan would see the machine coming on-line in May 2025, to provide extract capacity and resilience.

2.4	Other

Morriston Access Route

We have compiled our development control plans (DCP) for each site supporting our clinical service plan which shows quite a challenging capital programme with various capital projects at different business case stages. It’s worth noting that one of the key planning conditions within Swansea Local Authority Local Development Plan, states that any future expansion of services on the Morriston site will require a new access route coming off the M4 junction 46 mitigating traffic congestion on the existing road Infrastructure. We have completed around 40% of the design works but are waiting on approval of the next tranche of design fee funding from WG in order to complete the design and planning application.

Carbon Reduction

Following on from the opening of the first Solar Farm in NHS Wales in 2022, we are delivering exciting, innovative, and transformational carbon reduction projects that currently lead the way in the UK and Europe with phase 2 solar farm expansion and battery storage currently on site with an anticipated completion date of February 2024. We have completed high-level assessments of Morriston and Singleton hospital sites on how we can de-steam and decarbonise the estate and shared with WG. As these schemes are more about reducing carbon rather that also cost reduction, the likelihood of any central government funding support is looking less promising. We are also developing plans for our Neath Port Talbot hospital site with our PFI partners to develop a decarbonisation strategy for the site.

Mental Health & Learning Disabilities

Discussions have commenced on the requirements for modernised estate for Swansea City Centre. Further work will be required to assess the priorities for the current estates and how future developments can link into the proposed Swansea Wellness Centre and also other developments being undertaken by the local authority. There is a requirement for a MH & LD service model to shape the buildings in this area.

Primary & Community Services

A prioritised list of improvements required for the primary and community services estate is under discussion. This will likely require a mixture of discretionary/EFAB funding to undertake backlog maintenance issue, as well as more transformational schemes linked to the delivery of integrated health and social care hubs, utilising the WG Integration Rebalancing Care Fund (IRCF) being managed through the West Glamorgan Regional Partnership Board. There is a requirement for a primary care and community services model to shape buildings in this area.

2.5	Neath Port Talbot PFI Hospital

Whilst the PFI contract has 6 years and 9 months remaining before hand back to the Health Board, the small project team within the Health Board has implemented a proactive monitoring approach to both the service and comprehensive contract provisions regarding performance management and handback. Significant challenges facing the project team prior to expiry are current disputes and asset condition, ongoing relationships at an operational level and performance issues regarding outstanding deductions.

The next 2 years will be critical for the Health Board to address KPI performance standards, significant life cycle works and asset condition to make sure that the hospital is handed back to the Health Board in Estates condition B.

Working alongside WG and NHS Wales SES, we have been successful in being accepted onto the UK Infrastructure Projects Authority (IPA) PFI Expiry Health Check Programme. The Health Board team met with the panel of PFI experts in September 2023 and we are expecting to shortly receive the initial Expiry Health Check report. This will be an important item of expert advice as we plan to exit the Health Board’s largest financial contract and will help us identify and prioritise the additional programme of work and resources required (will likely include financial, building and legal advice) to support a successful exit.

2.6	Equality Impact Assessment

When the Board approved the Estates Strategy at the end of May 2023 it was agreed that an Equality Impact Assessment be undertaken. Whilst this work has commenced it has not been able to conclude this in time for the Board meeting. The overall strategy will be Quality Impact assessed and detailed individual assessments will be made in each individual development as is good practice.

2.7	Next Steps

Disposals

The Health Board is open to agreeing the appropriate disposal of assets which are not needed strategically as enablers for resource availability although the current assessment is that the financial scale of available disposals would not make a material contribution to the overall strategy. In addition to the proposed disposals contained in this paper, candidate sites are being identified for residential housing developments as part of the new Swansea Local Development Plan (LDP) due to come into place in late 2024. We will also need to consider the same requirements for the NPT LDP.

Alternative Financing Models

Very early discussions have taken place with WG on two aspects of alternative financing models. Discussions with the Capital & Estates team from the WG Health & Social services department on alternative funding models, including the Mutual Investment Model MIM took place in September 2023. A follow up meeting with WG Central Finance is being arranged. Discussions have also taken place with the WG Energy Services division on alternative financing models for Energy Performance Contracts. The Board should note that whilst discussions with WG departments will continue, given the current financial climate, the market for these alternative financing models is now less attractive to commercial investors, with significant issues around affordability linked to high interest rates.

Morriston Ward & Roof Business Case

Further work on the implementation plans and business cases for the Morriston Ward Refurbishment and Roof Replacement programme will be taking place with the Morriston and Singleton Service Delivery Units. The plan would be to have a more detailed plan available during Q4 and to commence discussions with WG on the scope of the business case. Importantly this scheme would see major internal refurbishment carried out allowing ward environments to be made fit for purpose with increased cubicle numbers and modern, fit-for-purpose environments. The rate and scale of cubicle development will reduce the numbers of beds per ward template and so this case will consider the bed model for Morriston Hospital and whether further decant/permanent ward space will be required to meet future need. This may not result in more physical beds but appropriately spaced beds in improved modern environments of care.

Mental Health & Learning Disabilities

Development of a MH&LD service model to shape buildings in this area.

Primary Care & Community Services

Development of a PC&CS service model to shape buildings in this area.

PFI

Consider recommendations of PFI Expiry Health Check and consideration of resources required to develop a project structure.

Quality Impact Assessment

Completion of the quality impact assessment.

- RISK AND GOVERNANCE

The Estates Strategy has been prioritised based on a balance of business continuity risk and the requirement to modernise services though our Clinical Services Plan.

The routine oversight of the strategy and providing progress updates is now a matter for the Performance and Finance Committee with regular updates to the Board as required; currently every 6 months.

The environment of estates is a risk register entry on our Health Board Risk Register, at level 16, and the Performance and Finance Committee oversee this risk on behalf of the Board.

- FINANCIAL IMPLICATIONS

This Estates Strategy reflects the Clinical Services Plan and 6 Facet Survey undertaken in 2022. Very high-level capital investment estimates in advance of any detailed designs suggest a significant investment of £812m over a 10-year period. All investments will be subject to the normal programme and project business cases and discussions with Welsh Government on affordability.

The investment plan highlights the priority enabling projects required for the critical backlog maintenance estates issues identified from the Morriston Hospital 6-facet survey on wards and theatres. The impact of investment in several key schemes from the 10-year plan towards the significant backlog maintenance.

The high-level capital investment of £812m into the estate over the next 10-years is a significant undertaking that will require the support of Welsh Government. We have already been successful in securing £7.9m investment through the NHS Wales Estate Funding Advisory Board (EFAB), which will allow us to start to address some of the very urgent backlog maintenance issues.

- RECOMMENDATION

Members are asked to: -

- NOTE progress on implementation of the approved Health Board Estates Strategy, including acquisitions, disposals, and business cases.

- NOTE progress on the PFI Exit and alternative financing models.

- NOTE progress with the priorities for MH&LD and PCCS

- NOTE progress with the plans for the prioritised Morriston business continuity plans for ward refurbishment and roof replacement.

- NOTE the next steps and reporting plans through the Performance & Finance Committee.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Engineering systems within the two main acute sites have a direct impact on the experience patients, visitors and staff alike. As engineering services are past their normal lifecycle their reliability is adversely affected which has a direct impact on the delivery of services. |  |  |  |
| Financial Implications |  |  |  |
| A high level 10-year capital investment plan has been produced. The plans include projects that will reduce the level of the backlog maintenance identified in the recent 6 facet survey. Projects will require business cases to show the impact on both capital and revenue investment. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| N/A |  |  |  |
| Staffing Implications |  |  |  |
| N/A |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| If the Health Board do not address the condition of the engineering services within the Estate, there is increased likelihood that we could have system failures that adversely affect the provision of clinical services. |  |  |  |
| Report History |  | Board Development briefing 9th January 2023 Board Estates Strategy Task & Finish Group (February to May 2023). Board sign off Estates Strategy May 2023. |  |
| Appendices |  | Estates Strategy Document In resources – Estates Strategy detailed analysis and survey work. |  |