| Meeting Date | 30 November 2023 |  | Agenda Item |  |  | 3.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Update on Voluntary Sector Recommissioning |  |  |  |  |  |
| Report Author | Joanne Abbott-Davies, Asst Director of Insight, Engagement & Fundraising, DICE Nicola O’Sullivan, Head of Engagement, DICE Nerissa Vaughan, Interim Director of Strategy |  |  |  |  |  |
| Report Sponsors | Richard Thomas, Director of Insight, Communications & Engagement Nerissa Vaughan, Interim Director of Strategy Darren Griffiths, Director of Finance |  |  |  |  |  |
| Presented by | Nerissa Vaughan, Interim Director of Strategy |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This paper outlines the progress made with implementing voluntary sector recommissioning, highlights some changes to the approach and outlines the revised timeline going forward. |  |  |  |  |  |
| Key Issues | The Health Board is undertaking recommissioning of all its voluntary sector services for the first time. Whilst significant progress has been made on implementing the initial stages of this programme, further changes have arisen which means that the programme’s timetable needs to be revised. This paper outlines the proposed revisions which have been developed jointly by Procurement, Strategy and DICE, in partnership with the voluntary sector, to address these issues and safeguard the continuity of voluntary sector services within this process. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - Note the progress made to date with the Voluntary Sector recommissioning - Note the changes which have occurred and their impacts on the implementation programme - Approve the revised process proposed for the programme - Approve rolling over existing SLAs for 2024-25 - Approve the revised timescales proposed for the programme - Approve the financial commitments for 2024-25 |  |  |  |  |  |

UPDATE ON VOLUNTARY SECTOR RECOMMISSIONING

- INTRODUCTION

This paper outlines the progress made with implementing voluntary sector recommissioning, highlights some changes to the approach and outlines the revised timeline going forward.

- BACKGROUND

The Health Board is undertaking recommissioning of all its voluntary sector services for the first time.  This is a complex process and requires development of a novel approach for both Procurement and the Health Board as well as needing to work in partnership with the sector.

Whilst significant progress has been made on implementing the initial stages of this programme, further changes have arisen which means that the programme timetable needs to be revised.

This paper outlines the proposed revisions which have been developed jointly by Procurement, Strategy and DICE, in partnership with the voluntary sector, to address these issues and safeguard the continuity of voluntary sector services within this process.

- PROGRESS TO DATE

The Health Board decided to recommission voluntary sector services as most of the existing arrangements were historic and had not been subject to a market testing process which left it open to challenge regarding demonstrating value for money.

The recommissioning was initially planned in 2017 but had to be postponed due to the implications of Bridgend Boundary Change and the need to disaggregate commissioned services.  The process restarted in early 2020 but again had to be paused due to the pandemic. In January 2021, the Health Board agreed to a revised timescale for the recommissioning process with it planned for completion by end March 2023.

We have worked closely with the voluntary sector and engaged extensively and will continue to do so to ensure the process is as voluntary sector friendly as possible, while still offering a compliant assured process for the Health Board.

Feedback from the sector informed the decision to proceed with a Dynamic Purchasing System (DPS). This offers a two-stage process where providers initially apply to get on the framework (Phase 2) subject to passing the due diligence test, ensuring they have adequate systems and processes in place to enable them to do business with the Health Board. Organisations on the framework are then able to respond to service specifications (Phase 3) and participate in the mini competition process (Phase 4) where they complete applications to tender for services within particular lots. All submitted applications will be evaluated and organisations will be advised as to whether or not their submission was successful.

To date the following milestones have been achieved:

- Steering Group established to oversee process with elected representation from the voluntary sector and all Delivery Groups and service leads for specific service areas.

- Workshops held with the sector to ensure that the recommissioning process is designed in such a way to enable full participation whilst providing the Health Board with the assurances it needs.

- Support provided to the sector by Councils of Voluntary Services to ensure all organisations are equally able to participate in the process, irrespective of their size and organisational capacity.

- Agreement of “lots” to ensure that all current and future needs for voluntary sector commissioning can be met using the Health Board framework (attached as Appendix A).

- The Due Diligence Process has been completed, with two opportunities for voluntary sector organisations to join the Health Board framework.  This has resulted in 96 organisations applying and following clarification and supplying further information, all organisations met the due diligence requirements.

- Development of specifications for the majority of “lots” but some difficulties experienced in relation to mental health ones particularly due to lack of ownership of these, mainly Tier 0/1 services, within the Health Board.

- Workshops held with the sector looking at draft specifications to ensure feedback can be incorporated into final versions where appropriate.

- ISSUES

Progress has been hampered by the lack of dedicated time to carry out this work, making progress on this recommissioning process extremely challenging alongside other responsibilities.

The West Glamorgan Regional Partnership Board (RPB) has now agreed a new Emotional and Mental Wellbeing (E&MW) Strategy, focusing on a move to prevention and early intervention. The provision of Tier 0/1 services, some of which were within the recommissioning programme for the Health Board, now fall within the remit of this E&MW Strategy, so it will be important that the implications of the new Strategy are considered in recommissioning tier 0/1 mental health services.  As a result, we have concluded that it makes sense for the recommissioning of Tier 0/1 mental health services to be done in conjunction with the RPB and in line with the new E&MH Strategy, alongside the distribution of Mental Health Improvement monies on a pooled funding basis.  The detailed timelines are being worked through with the RPB currently.

Delays in clarifying this position as well as a lack of capacity to take this work forward means that the established timeline agreed by the Board has been delayed, meaning that the conclusion of the recommissioning programme with all the resulting contracts in place by end of March 2024 is now not possible.

Therefore a revised timeline has been developed which is realistic for the sector, allows the Health Board to ensure the process is implemented appropriately without disruption to these services.  Our priority always has been, and remains, to make sure that the process is done well, in partnership with the sector, rather than at a pace which makes this impossible.  We are also very conscious that we need to ensure we do not destabilise the sector through this process because of its critical role in supporting the people we serve.

There will be a need to work through the detail of these changes with our RPB colleagues and the sector.  The Commissioning department from the Strategy Directorate and the Engagement department from DICE will work together to take this work forward in partnership with Procurement and the sector.

Proposed Way Forward

- Revised Timescale

Finalisation of Phase 1 Specifications

Mini competition & evaluation of Phase 2 services incorporating lessons learnt

Health Board Approval & Contract Award

Negotiation & Handover Arrangements

Finalise performance management framework

Taking these changes into account and bearing in mind the delays outlined above a revised timeline is proposed as outlined below:

Nov-Dec 2023	      Jan – March 2024	      April – June 2024	July – September 2024	    Oct – Dec 2024    Jan – Mar 2025

Mini Competition & Evaluation of Phase 1 services

Application of Lessons Learnt

Finalisation of funding allocations to lots Specifications

Finalisation of Phase 2 Specifications

Phase 1 – testing the process with 4 services (lots 12 & 14)

Phase 2 – implementing process following lessons learnt with remaining lots

This will mean that the new commissioning arrangements will come into operation from 1st April 2025 rather than 1st April 2024 as originally proposed, but will ensure that the programme can be completed effectively and appropriately, in partnership with the Regional Partnership Board and the voluntary sector.

- GOVERNANCE AND RISK ISSUES

The voluntary sector has had these proposed changes to timescales discussed with them, and while there is concern about the delay in implementation there is also relief that the revised timeline will allow sufficient time for proper transfers of services and service users if required to occur with minimum disruption.  A briefing was held with over 45 organisations to outline the revised timeline being proposed and the sector were supportive of this proposed approach and rolling over the SLAs for 2023-24.  Overall the primary concern is ensuring the process is right and gives the sector every opportunity to participate appropriately, rather than necessarily adhering to the original timeline.

- FINANCIAL IMPLICATIONS

As outlined previously, there are significant pressures on the voluntary sector.  While the cost of living rises have affected all sectors, the impact on the voluntary sector has been exacerbated by the long-time flat funding for services despite many organisations now paying the living wage in Wales which has increased their baseline costs.  Many of these organisations are small and have few options about how to achieve efficiencies.  A recent letter has been sent to the Minister for Social Justice from Third Sector Support Wales outlining the particular challenges facing the sector and the level of fragility due to short-term funding and the implications of financial settlements across the public sector in Wales (attached as Appendix B).  In 2023-24 an uplift of funding for the sector of 4% was agreed to help address this.  It is proposed that the same uplift should be applied in 2024-25 from underspends in the existing voluntary sector budget; the budget will not overspend as a result of this proposal.  To align with the new timeline for recommissioning from April 2025, existing service level agreements with voluntary sector organisations will need to be extended to end at this time rather than April 2024 as was originally agreed.

The overall voluntary sector budget will neither be uplifted for inflation nor subject to cost improvement requirements. The intention for this model is that it will incentivise the assessment of existing services and whether they can be more effectively delivered by voluntary sector services. Any decommissioned service funding will then transfer to the voluntary sector budget allowing the budget to grow and deliver efficiencies for further developments.

Recognising the funding model, in preparing the Annual Plan for 2024-25 Service Delivery Groups and the sector will work with the Strategy Commissioning Directorate to identify services which can be transferred from the Health Board to the voluntary sector, supporting the principle that the Health Board should focus on providing services and staff which only it can.  As part of this it is believed that efficiencies of a minimum of 3% can be realised from these transfers due to differential pay rates between the public and voluntary sectors.

As future services will be commissioned for three years, it will be necessary for an uplift each year to be incorporated into the recommissioning process with the financial model above being used to create the financial headroom to incorporate this.

- RECOMMENDATION

Members are asked to:

- Note the progress made to date with the Voluntary Sector recommissioning

- Note the changes which have occurred and their impacts on the implementation programme

- Approve the revised process proposed for the programme

- Approve the revised timescales proposed for the programme

- Approve the financial commitments for 2024-25

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| This procurement process and implementation of the Strategic Framework will ensure that services are provided to a high quality, are safe and patient experience is monitored. |  |  |  |
| Financial Implications |  |  |  |
| These are outlined above |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Legal guidance on procurement will be followed |  |  |  |
| Staffing Implications |  |  |  |
| None. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The actions outlined in the report support the five ways of working outlined in the Act. Swansea Bay UHB is working collaboratively with partner organisations to identify improved ways of working to support the longer-term strategic vision of the organisations involved. Changes to services should reflect the needs of the local population and so should have positive impacts for future generations. |  |  |  |
| Report History |  | The Board considered a previous report in January 2020, September 2020 and February 2022 |  |
| Appendices |  | Appendix A – List of Lots / Specifications Appendix B – Letter to Jane Hutt from Third Sector Support Wales |  |

Appendix B

Current Position with Lots & Specifications

| Description | No of Specs | Comments (where appropriate) |
| --- | --- | --- |
| 1. Admission, Avoidance & Discharge Support | 2 | Phase 2 |
| 2. Adult Mental Health | N/A | Aligned to the Emotional and Mental Wellbeing Strategy – to be taken forward in partnership with RPB |
| 3. Cancer & Palliative Care including Young People | 2 | Phase 2 |
| 4. Carers | 1 | Phase 2 |
| 5. Children & Young People | 4 | Excluding Emotional and Mental Wellbeing services – to be taken forward in partnership with RPB Phase 2 |
| 6. Emergency Response | 0 | No funding currently allocated to this lot |
| 7. General Information, Advice, Support & Counselling | 3 | Phase 2 |
| 8. Learning Disabilities | 0 | No funding currently allocated to this lot |
| 9. Lifestyle Change & Population Health | 0 | No funding currently allocated to this lot |
| 10. Older People Mental Health & or Dementia | N/A | Aligned to Emotional and Mental Wellbeing Strategy – to be taken forward in partnership with RPB |
| 11. Participation, Coproduction and Facilitation | 0 | Councils of Voluntary Services role in supporting sector being excluded from process via the exemption process |
| 12. Stroke | 1 | Included in Phase 1 to test process |
| 13. Substance Misuse | N/A | Agreed lead will be with Area Planning Board Commissioning Team |
| 14. Violence Against Women and Men, Domestic Assault, Sexual Violence & Sexual Health | 3 | Included in Phase 1 to test process |
| 15. Green initiative | 0 |  |
| 16. Transport | 0 | No funding currently allocated to this lot |
| 17. Amplifying quiet voices | 0 | No funding currently allocated to this lot |
| Totals | 4 12 | Stage 1 Stage 2 |