Appendix B: Swansea Bay University Health Board

Anti-Racist Wales Action Plan

November 2023 Update

| Goal | Actions | Impact | Lead | Target Date | Output and progress |
| --- | --- | --- | --- | --- | --- |
| - SBUHB will be anti-racist, and will not accept any form of discrimination or inequality for employees and service users. | Utilise the Insight function to bring together information and intelligence from complaints, concerns, patient feedback, patient groups, staff experience, external reports etc. This will provide an overview of staff and patient experience around race and be used to further inform and develop the action plan. | The insight will help provide a baseline around staff and patient experience around race across the Health Board. This will inform future priorities and actions around race. | Director of DICE | Dec 2022 | The Health Board has established a Patient and Stakeholder Experience Group where feedback is shared to learn and consider opportunities to share good practice across the organisation. Sources include: Service Delivery Units; departments; quality and safety; patient experience; concerns and complaints; the staff experience; stakeholder and public engagement feedback, including external reports from organisations such as Llais (formerly CHC) Representation from the Accessibility Reference Group attends this meeting. While the group is in its infancy, the value and importance of the group is recognised and the group is committed to supporting the embedding of human rights and equalities across the organisation. |
|  | Establishment of Strategic Equality, Diversity and Inclusion Group (SEDIG) to develop, implement and monitor a strategic approach to ensuring human rights and equalities, including race are embedded across the Health Board. | The strategic approach of embedding human rights and equalities across the organisation will enable a high level consistent approach where there are commonalities and a tailored approach where appropriate. | Director of DICE | Jan 2023 | The Strategic Equality and Belonging Group was formally established on the 24/04/23. Membership includes representation from across the health board, together with representation from the Regional Partnership Board, local CVS’s and protected characteristic group representatives where possible. While the group is in its infancy, it is committed to embedding human rights and equalities across the organisation. |
|  | Adopt a Human Rights Approach to empower staff and patients and embed this across the organisation and develop a plan on how this will be implemented. Explore the potential of developing a Health Board wide commitment / charter around our commitment to human rights and equalities for staff and patients. Map and reiterate how human rights and equalities wraps around and informs the Health Board commitments and values. | Further embedding human rights and equalities into Health Board mechanisms means this approach influences and informs day to day practice across the organisation | Director of DICE | Sept 2023 | The original intention was to establish the SEDBG by Jan 2023. The group did not commence until late April 2023. We will align our strategic equality objectives and human rights with the Health Board’s 10-year vision The One Bay Way. The Health Board is a partner in the Swansea Human Rights City approach. Health Board staff have completed British Institute of Human Rights (BIHR) training to support this work. |
|  | Develop anti-racism action plan for employment as a specific part of the wider approach to equality, inclusion and diversity. Progress will be monitored and reported via IMTP and Annual Plan, and the Joint Executive Team process with Welsh Government. Gather written commitment/ video messages from CEO and other senior leaders endorsing support and commitment around anti-racism not only around staff but also access to services etc | Implementation of anti-racism action plan will reduce people’s experience of racism during recruitment, career progression and whilst working. Visible evidence of development in the behaviours exhibited by Board members/Service Group Triumvirates. | Director of Workforce and OD Director of Workforce and OD/ Director of Insight, Comms & Engagement | Dec 2022 From Dec 2022 for Board Members | SBUHB Anti-racist Workforce Action Plan (Sharepoint.com) launched at the end of Black History month with Director of WOD presenting it at the Team Brief on 2nd November 2023. The next Strategic Equality Diversity and Belonging Group Meeting (SEDBG) will be held on 29th November 2023. With a new interim CEO appointed, there is an opportunity to capture and share their commitment. Conversations have taken place to schedule messages from the Executive Directors regarding equalities and human rights for the coming year. |
|  | All Board members and Service Group Triumvirates to undertake an anti-racist education programme and implement and report progress against personal objectives to meet vision of an anti-racist Wales. | Visible change, where required, in decision making, evidencing that anti-racism, equality, diversity and inclusion have been considered and acted upon. Visible and transparent allies and leadership providing confidence to workforce and service users that any forms of structural racism is being proactively addressed. | Director of Workforce and OD / Director of Corporate Governance | From Dec 2022 for Board Members Date TBA for Service Groups Triumvirates | Anti-racist training was delivered to Board members by Prof Uzo Iwobi, CEO of Race Cymru Council and Dr Heather Payne from Welsh Government at the February 2023 Board Development session. |
| - Staff will work in safe, inclusive environments, built on good anti-racist leadership and allyship, supported to reach their full potential, and ethnic minority staff and allies, both empowered to identify and address racist practice. | Require anti-racist leadership at all levels and report demonstrable progress in driving anti-racism at all levels by: - appointing Executive Equality Champions and Cultural Ambassadors; - implementing a leadership and progression pipeline plan for Black, Asian and Minority Ethnic staff; - providing Ethnic Minority Networks appropriate levels of resource and access to the Board. | More visible representation and allies at all levels, clear leadership pipeline for Black, Asian and Minority Ethnic staff and thriving networks supporting and acting as a critical friend to Management Board as well as the Board. More effective mechanism to address gaps in attainment. | CEO/Chair/ Director of Workforce and OD | Sept 2023 | Welsh Government indicated their intention to issue a role description for the Executive Equality Champion. We are awaiting the issuing of this document Work is ongoing to progress this work Further development of the staff network is taking place and we are currently working on appointing into the key officer roles identified. |
|  | Establishment of SEDIG | This group will include representation from across the protected characteristic groups in addition to representation from the Stakeholder Reference Group (SRG), Accessibility Reference Group (ARG), Staff Side representation and Co-Production. This will enable the group to consider cross-cutting themes from a broad human rights perspective whilst also providing the opportunity to consider issues specific to a protected characteristic group. Review protected characteristic networks that exist across the Health Board and ensure there is consistency in the approach to supporting existing groups and the establishment of others. Learn from good practice around Equality Impact Assessments / Impact assessments and update the Health Board approach to developing these, ensuring the most up to date approach and evidence is being utilised to inform services and policies. | Director of DICE Director of DICE Director of DICE | Jan 2023 July 2023 July 2023 | The Strategic Equality and Belonging Group was formally established on the 24/04/23, a few months later than anticipated. While the group is in its infancy, it is committed to embedding human rights and equalities across the organisation. Work is ongoing to ensure consistency of approach towards staff networks across the organisation. We have updated our external stakeholder database to reflect existing community groups and networks we can communicate with, gather feedback from, provide updates to as part of our continuous engagement approach We are exploring the potential of aligning the Equality Impact Assessment with the Health Board Quality Impact Assessment process |
|  | Continuation of funding for the Outreach Team | The Outreach Team, consisting of three members of staff has been funded to the end of March 2023 through TTP WG Funding. The Team has proven invaluable in reaching into minority communities where voices are seldom heard. The community links, knowledge and relationships developed has proven invaluable and the investment in this work will continue to build on these strong foundations. The information and intelligence from this work can inform the Human Rights and Strategic Equality Group and Health Board. | Director of DICE | Dec 2022 | Funding was secured for 2023/24 to continue this invaluable work and we are exploring ways to fund this work for 2024/25 |
|  | Ongoing use of the insight function to inform human rights and equalities work | The insight function will bring together information from across the Health Board, such as staff experience, patient experience, concerns, complaints, compliments together with including external reports. This intelligence can be used to provide a baseline of current experience and be part of an ongoing mechanism to identify issues for action as they arise. | Director of DICE | Ongoing | The Health Board has established a Patient and Stakeholder Experience Group where feedback from across the organisation and from external sources is shared to learn from and share good practice across the organisation. This is a relatively new group and will continue to evolve and embed this work in the future. Existing DICE funding is being used to appoint to an Insight role. |
|  | Ensure anti-racism is embedded into ‘the Big Conversations’ and Quality Improvement work streams and action plans. | Based on the lived experience of staff which will form part of ‘the Big Conversation’. | Assistant Director Workforce & OD / Executive Director of Nursing | From Oct 2022 | Conversations are taking place with the ‘Our Big Conversation’ and Quality Improvement leads to ensure and understand how anti-racism is embedded / evidenced Cultural conversations continue with the cohorts of Internationally Educated Nurses. The feedback ahs led to changes being made to improve the experience of future cohorts. |
|  | Ensure external communications supports a Human Rights and Equalities Approach and communications and engagement approaches are inclusive. | Messaging to patients, staff and communities will be relevant and inclusive and provide a sound basis for further engagement | Director of DICE | Ongoing | Whenever the Health Board undertakes public engagement, consideration is given to ensure the opportunity to participate and share views is as accessible as possible. Different, targeted approaches, taking into account different needs and preferences are taken to gather the views of the seldom heard / those with quiet voices to make sure their voices are heard. Proactive external communications and PR regularly undertaken around ED&B friendly issues eg speech therapy for trans community. |
|  | Work with HEIW and other NHS organisations the Health Board’s Outreach Team, local equalities networks to co-design anti-racist education programmes with Black, Asian and Minority Ethnic people. This will include setting a requirement for all NHS Staff, NHS Volunteers and students to complete redesigned anti-racist education programmes. Co-design Human Rights and Equalities training with other NHS organisation, partners and organisations with expertise and lived experience. | Consistent, fit for purpose educational intervention offered to all staff, students and volunteers. Visible mandated education providing confidence to workforce that organisation is serious about human rights, equalities and anti-racist principles. Visible evidence of development and change in the exhibited behaviours of those who have participated in education programme e.g. Staff more confident to be allies and call out discrimination, including racism. Staff more confident in complaining about discrimination, including racist incidence by colleagues, patients and public | Director Workforce & OD / ADWOD / Director of DICE | Dec 2023 | We continue to work with HEIW who are leading this piece of work We continue to work with HEIW who are leading this piece of work Work is ongoing regarding supporting staff to feel more confident about complaining about discrimination. |
|  | SBUHB to commit involvement in Academi Wales Aspiring Board Members Programme, ensuring education, mentoring and support to participants who will be from a Black, Asian and minority ethnic background. | Increase in number of people from Black, Asian and minority ethnic background who are able to evidence more effectively their ability to undertake the role of a non-executive member. Increased ethnic diversity on Boards “building a robust pipeline” of future Black, Asian and Minority Ethnic Board Members | Director Workforce & OD / Director Corporate Governance | From Dec 2022 | We continue to work with Academi Wales who are leading this piece of work |
|  | Ensure that SBUHBs commitment to be a values and behaviours driven, anti-racist organisation is embedded into key messages at induction. Coaching and Mentoring will be available for staff and will be an integral part of our talent pathways and coaching and mentoring strategy. This will include mutual mentoring with a focus on lived experience. Ensure all leadership and management training supports a human rights and equalities approach, is anti- racist and where appropriate includes messages of how to manage / lead in a non-discriminatory and anti-racist way. Ensure that talent schemes are designed to attract applicants from ethnic minority communities. This will include the implementation of our new Talent Management Strategies aimed at internal staff development ie Talent Gateway, Tiers 1-3 Talent and succession programme. This action will cover internal programmes and external recruitment to schemes. | Visible mandated education across all levels providing confidence to workforce that organisation is serious about human rights, equalities and anti-racist principles and behaviours Staff are supported to access coaching and mentoring support as required, and bespoke to their personal goal and development. Visible anti-racist leadership and management development that reinforces messages and behaviours at every opportunity. Ethnic minority staff will experience outcomes comparable with non-ethnic minority colleagues, when working for SBUHB. | Director Workforce & OD | From Dec 2022 | Wales led Virtual Induction is constantly being reviewed and evaluated to ensure up to date and appropriate messaging. Coaching and Mentoring now sits with Widening Access, Equality and Inclusion. Work is being carried out to broaden the number of coaches in the organisation and work has started to develop mentoring pathways. Leadership and management programmes are constantly being reviewed and evaluated to ensure up to date and appropriate messaging Work is ongoing to progress this work |
| - Data in relation to race, ethnicity and intersectional disadvantage will be routinely collated, shared and used transparently, to level inequalities and provide assurance that the NHS Wales is an anti-racist and safe environment for staff | Improve workforce data quality and prepare for the introduction of WG Workforce Race Equality Standard (WRES) | High quality workforce data, underpinned by a culture where staff can be safe, and confident to provide ethnicity data and speak up against racist discrimination and practice | Director Workforce & OD / Associate Head of Workforce | Sept 2023 | Workforce Race Equality Standard (WRES) update. Profession Anton Emmanuel met NHS Wales Equality Managers on 25th May 2023 with Welsh Government. Lessons were leant from WRES in England and update on the ongoing work in Wales. We are currently awaiting roll-out of the system. The ESR team have been involved in the Welsh Government table top exercise as part of preparation work, which has improved understanding of the process. |