## Slide 1
PCT INTEGRATED DISCHARGE ACTION PLAN
Notes: This slide can be used for presentations which are from a health board-wide perspective or for a whole HB audience as the graphic device to the right of the slide includes all four service group colours and red for the corporate team.

## Slide 2
INTEGRATED DISCHARGE ACTION PLAN
WORKSTREAM 1- Refreshed Pathways of Care Action Plan
WORKSTREAM 2- Pilot Integrated Discharge Hub (Morriston)
WORKSTREAM 3- Improved Data and Performance Management
Notes: The purple line indicates Morriston Hospital Service Group, so this slide can be used for matters which relate to MHSG.

## Slide 3
Set Up Delivery Improvement
AUGUST/-OCTOBER
MAY
JUNE/JULY

## Slide 4
WORKSTREAM 1 –
POCD ACTION PLAN
Reduction in Top 5 Delays
Improved Flow
Sustainable Improvement across all actions
Shared Ownership/Accountability (HSC)
Refreshed Action Plan
Daily COP Review & Challenge
Organisational ownership of actions
Monthly Oversight
Fortnightly Accountability/Assurance
Agreed Improvement Targets:
Assessment
Allocation
Review
Reduce ‘unknowns’
GOAL
METHOD
OUTCOME
Notes: The blue line indicates Mental Health and Learning Disabilities (MHLD), so this slide can be used for matters which relate to MHLD.

## Slide 5
WORKSTREAM 2 –
PILOT IDH MORRISTON
PILOT new Integrated Discharge Hub in Morriston
Create Operational Model that can be scaled to Singelton & Neath
Implement referral form for wards
Implement IDH live Inbox
Establish MDT ‘Live’ Triage
Professional Decision Maker
Reduce time to allocate pathway
Speed up referral process
Streamline process
Simple Approach
Improve Flow into Community Pathways
GOAL
METHOD
OUTCOME
Notes: The blue line indicates Mental Health and Learning Disabilities (MHLD), so this slide can be used for matters which relate to MHLD.

## Slide 6
WORKSTREAM 3 –
IMPROVED DATA & PERFORMANCE MANAGEMENT (HF )
Improved capability for data reporting
Improved operational performance data
Ability to target improvement activity
Accurate data for Demand & Capacity Modelling
Completion of 16 SIGNAL functional requirements
Removal of ‘On Hold’ List
Ability to record ED/OPAS/WAST referrals
Ability to record ‘In Reach’ activity
Ability to run performance reports
Improve time to complete assessment
Compliance with 24/48HR targets
Accurate Data
Improved Performance Management
GOAL
METHOD
OUTCOME
Notes: The blue line indicates Mental Health and Learning Disabilities (MHLD), so this slide can be used for matters which relate to MHLD.

## Slide 7
GOVERNANCE
SBUHB UEC BOARD
WEEKLY TARGETED INTERVENTION MTG
POCD ACTION PLAN GROUP
POCD/IDH OPERATIONAL GROUP
HOME FIRST OPERATIONAL ASSURANCE GROUP
ASSURANCE
OVERSIGHT
TACTICAL DELIVERY
OPERATIONAL DELIVERY
Notes: The red line indicates the corporate team, so this slide can be used for corporate matters.