| Meeting Date | 23 July 2024 |  | Agenda Item |  |  | 3.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Clinical Outcomes and Effectiveness Report |  |  |  |  |  |
| Report Author | Sharon Rağbetli, Clinical Audit & Effectiveness Manager |  |  |  |  |  |
| Report Sponsor | Dr Raj Krishnan, Acting Executive Medical Director |  |  |  |  |  |
| Presented by | Dr Raj Krishnan, Acting Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides an overview of the work of the Clinical Outcomes and Effectiveness Group (COEG), providing a summary of performance with; Audit Plans for 2022/23 and 2023/24, compliance with and the response to, published mandated national audits/registries and on mortality through the Learning from Deaths Panel. |  |  |  |  |  |
| Key Issues | - Progress against clinical audit, outcomes and effectiveness is overseen on a monthly basis by the COEG and report to the Quality and Safety Group; - Progress against the service groups’ identified audits for 2022/23 has now reached 87% and 41.5% for 2023/24 - 16 overdue responses to NICE (National Institute for Clinical Excellence)/HTW (Health Technology Wales) guidance or national audit/registry publications were escalated to the Quality and Safety Group |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the progress made within all clinical audit areas; - NOTE the outstanding Welsh Government proformas and responses to NICE/HTW Guidance are escalated to the Quality Safety Group; - NOTE the achievement of completing 87% of the 22/23 Audit Plans and 41.5% for 2023/24; - NOTE the number of Level 3 mortality Reviews closed since February 2023. |  |  |  |  |  |

CLINICAL OUTCOMES AND EFFECTIVENESS REPORT

- INTRODUCTION

The health board’s hierarchy of audit activities, as established in 2021, lists five levels. The five levels as set out in the Clinical Audit and Effectiveness Policy are:

- Level one - mandated national audits and registries;

- Level two - a small number of HB (health board) Audit Priority Topics (Level 2),

- Levels three and four - audit Plans at Service Delivery Group and Department levels

- Level five - emergent necessary ad-hoc topics.

This report provides an update on delivery of and progress with audit plans at each level.

In addition, it provides an update against the NHS Delivery Unit and Welsh Government National Learning from Deaths Framework. This was adopted by the HB to support local processes established to screen, review and provide feedback on any queries or concerns identified by the Medical Examiners (ME) Service and/or the bereaved and forms a key part of the clinical outcomes work. The approach enables the HB to address any concerns and themes that emerge from the data collected, supported by a customised dashboard.

2.      BACKGROUND

Patient outcomes and clinical effectiveness is part of the remit of the Quality and Safety Group but is discharged through the Clinical Outcomes and Effectiveness Group (CEOG). COEG meetings on a monthly basis to report progress on each of the areas of focus as well as receive presentations on the lessons learned from various audits. It then reports to the Quality and Safety Group on a bi-monthly basis.

Assurance is also required at a board-level as to the progress and improvement around clinical audits, outcome and effectiveness. As such a regular report is provided to the Quality and Safety Committee.

- GOVERNANCE AND RISK ISSUES

3.1	Mandated National Audits/Registries (Level 1)

The health board is required to participate in the Welsh Government mandated list of topics.  The list has not been refreshed for a number of years, though some of the topics listed have evolved, more recently the Care at the End of Life project moving from time-limited to continuous.

At the May 2024 Clinical Outcomes and Effectiveness Group (COEG), members noted that there were still a number of responses to the quarterly update yet to be received on the list of mandated topics and these were to be escalated to the service groups.

During the meeting, the lead for the National Audit of Care at the End of Life updated on progress and the practicalities in issuing cases for review across the patch. The service groups were in agreement that while it may not be possible to meet all requirements for the case-note review section of the project this cohort, that it was important to firm up the mechanism and plans for moving forward.

    - Assurance Proformas

Whilst Welsh Government no longer requires the completion of two-stage assurance proformas following publication of mandated national audits/registry topics, the HB retained its own internal process as an assurance mechanism for the COEG.  Table 1. below details the number of Assurance Proformas issued and the responses received by Audit Year;

| Assurance Proformas Returned |  |
| --- | --- |
| 1st April 23 – 31st March 24 | 1st April 24 to 10th May |
| 29/39 (74%) | 3/4 (75%) |

Table 1.

As at the May COEG meeting, no assurance responses needed to be redirected and therefore no exceptions were noted.

Of the 5 MBBRACE – UK topics previously escalated, all were subsequently completed.

1 response on National Oesophageal Cancer Audit previously escalated, remains outstanding.  This will be followed-up by the Associate Medical Director for Professional Concerns and Quality and Safety to ensure action.

Breaches of the eight-week timescales are escalated to the Quality and Safety Group by the COEG as part of the governance route and for onward management.

3.1.2 Responses to Key National Guidance and Publications

Responses to newly issued/updated NICE (National Institute for Health and Care Excellence) and/or Health Technology Wales (HTW) guidelines are also reviewed by COEG. Since 1st April 2023 90/113 (80%) responses have been completed.  This is an improvement from 73% reported in the last paper.  The latest compliance data for responses to key national guidance and mandated national audit/registry topic publications, shows that the 8 week target had been breached for;

| - IPG757 Maximal cytoreductive surgery for advanced ovarian cancer – previously escalated to Quality and Safety Group |  |
| --- | --- |
| - IPG768 Irreversible electroporation for treating prostate cancer – previously escalated to Quality and Safety Group - Health Technology Wales - Virtual reality distraction therapy – previously escalated to Quality and Safety Group - NG158 Venous thromboembolic diseases: diagnosis, management and thrombophilia testing – previously escalated to Quality and Safety Group - NG126 Ectopic pregnancy and miscarriage - NG235 Intrapatum care - NG192 Caesarean birth - NG229 Fetal monitoring in labour - NG12 Suspected cancer - Assurance Proforma National Oesophago-gastric cancer audit - QS75 Neonatal infection - IPG774 Vaginal transluminal endoscopic hysterectomy and adnexal surgery for benign gynaecological conditions - IPG778 Percutaneous thrombectomy for intermediate risk or high risk pulmonary embolism - Health Technology Wales – Digital wound management tools - Health Technology Wales – Robot-assisted thoracic surgery - Health Technology Wales – Low energy contact X-ray brachytherapy These have been escalated to the Quality and Safety Group for action to be taken. |  |

    - NCEPOD (National Confidential Enquiry in Patient Outcome and Death) Studies

NCEPOD Study into ICU (intensive care unit) Rehabilitation is running in Morriston with no issues.

3.2   Health Board Priority Topics (Level 2)

A number of topics are identified by the Executive Medical Directors Department in order to generate data for the HB (health board) and to support healthcare professionals in training in evidencing participation in audit and quality improvement activities Progress with the HB Priority topics is indicated in the table below;

|  | Cases |
| --- | --- |
| Consent to Treatment Round 1 | 646 |
| Consent to Treatment Round 2 | 319 (up from 267) |
| Antimicrobial Stewardship Round 1 | 2 |
| Antimicrobial Stewardship Round 2 | 87 (up from 70) |
| Do Not Attempt Cardiopulmonary Resuscitation Round 1 | 203 |
| Do Not Attempt Cardiopulmonary Resuscitation Round 2 | 64 (up from 17) |
| Care in the Last Days of Life Round 1 | 91 |
| Care in the Last Days of Life Round 2 | 20 (up from 18) |

Table 2.

Update presentations on each of the Level 2 topics are scheduled into the COEG meetings regularly, in addition to progress being discussed as a standing agenda item.

The Lead for Care in the Last Days of Life indicated that due to the change in design of the National Audit of Care in the Last Days of Life to run continuously, the topic could be removed as duplication.  Discussions to be had with areas experiencing lower volumes of deaths to explore need.

3.4   Service Delivery Group and Department Plans (Level 3 and Level 4)

COEG is updated at each meeting as to progress and issues by the Clinical Audit team, who support the Service Delivery Groups by contacting project contacts with a view to gaining updates and completion summaries and action plans. The Audit team reported at the last meeting that due to competing priorities and reduced capacity, the figures were largely static as there had not been the time or resource to request updates.

Completion of the 2022/23 Audit Plan currently stands at 87% and 41.5% for the 2023/24 plan.

Table 3. provides the current status by Service Delivery Group for 2022/23 and 2023/24;

| Service Delivery Group | Audit Plans |  |
| --- | --- | --- |
|  | 2022/23 | 2023/24 |
| Mental Health and Learning Disabilities | 12 (100%) | 6 (40%) |
| Morriston | 51 (88%) | 8 (32%) |
| Primary Care, Community and Therapies | 11 (100%) | 11 (61%) |
| Singleton and Neath Port Talbot | 14 (70%) | 7 (41%) |
| Totals | 88 (87%) | 44 (41.5%) |

Table 3.

Completion on the 2023/24 Plan has improved from 37% to 41.5% and the 2022/23 Plan has improved from 78.6% to 87%.

  - Emergent Necessary Ad-hoc Topics (Level 5)

Service Delivery Groups and Departments/Specialties are able to add audit activities in year as needed.  These include Medical Student topics that cannot be pre-planned, additional regional/national projects not included on the Level 1 list etc.

  - Mortality and Medical Examiner (ME) Service Reviews

The group receives monthly updates on the work of the Learning from Deaths Panel regarding progress with reviews, themes generated and compliments received.  A new report template for use by Service Delivery Groups will take into account the cases referred to the service groups for further investigation and also summarise associated actions.

It was noted that the issue of expanding reviews into Primary Care hinged on having a robust system in place to support.

For April 2024, a total of 185 deaths were recorded.  Whilst a total of 50 referrals were received during April, these referrals would include cases from older time periods as the ME Service work through their caseload.  74% of referrals did not need to progress past Level 1;

- 24 cases were closed

- 9 cases are already subject to existing processes and feedback is awaited

- 4 cases have been shared with teams to discuss and provide feedback on

13 cases are progressing to Level 2 for review and discussion by the Learning from Deaths Panel.

Level 3 Proportionate Investigation has been split into three sub-sections;

- 3a – Close referral and email relevant team for information purposes only

- 3b – Close referral and email relevant team requesting feedback from discussions with individuals/team

- 3c – Proportionate Investigation

This approach has been in place since January 2023.  Chart 1. illustrates the total number of Level 3 reviews completed since February 2023

Chart 1.

Communication with the patient/family remains the most frequently reported concern by the bereaved while DNACPR (do not attempt cardio-pulmonary resuscitation) form partially completed was the most frequently reported issue by the ME Service;

Chart Chart 2.

45 compliments forwarded by the ME Service were shared with various wards across the HB; 1 for Neath Port Talbot, 1 for Gorseinon, 8 for Singleton, 7 for Community and the remaining 28 for Morriston.

- FINANCIAL IMPLICATIONS

There are no financial implications relating to this report.

- RECOMMENDATIONS

Members are asked to:

- NOTE the progress made within all clinical audit areas;

- NOTE the outstanding Welsh Government proformas and responses to NICE/HTW Guidance are escalated to the Quality Safety Group;

- NOTE the achievement of completing 87% of the 22/23 Audit Plans and 41.5% for 2023/24;

- NOTE the number of Level 3 mortality Reviews closed since February 2023.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Compliance with national topics provides an opportunity to benchmark performance for quality, safety and patient experience, while the appropriate identification and planning of necessary local priorities can support improvements and provide assurance. The Learning from Deaths approach supports learning to ensure that patients at the end of life and their loved ones have the best possible experience. |  |  |  |
| Financial Implications |  |  |  |
| None |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None. |  |  |  |
| Staffing Implications |  |  |  |
| None. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Long term the aim is to continue to embed a new culture in terms of the prioritisation of audit and improvement activities, while balancing the need to meet requirements placed on doctors and healthcare professionals in training. Generating themes and learning from deaths will contribute towards striving to give patients at the end of their life and their loved ones, the best possible experience. |  |  |  |
| Report History |  | Quarterly report to the committee |  |
| Appendices |  | Nil |  |