| Meeting Date |  |  | Agenda Item |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Strategy Implementation Plan Update |  |  |  |  |  |
| Report Author | Angharad Higgins, Head of Quality & Safety |  |  |  |  |  |
| Report Sponsor | Lesley Jenkins, Acting Deputy Director of Nursing |  |  |  |  |  |
| Presented by | Angharad Higgins, Head of Quality and Safety |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To provide an updated position on all actions within the Quality Strategy, which have been revised in line with the findings of the Internal Audit report on our Quality Management System. |  |  |  |  |  |
| Key Issues | - Plan revised following Internal Audit report - Action leads contacted to ask for updates - Management Board approval on 4.7.24 of whole plan updates going forward - Format of plan under review to facilitate easier updating |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Note to contents of this report - Be assured by the progress noted |  |  |  |  |  |

QUALITY STRATEGY IMPLEMENTATION PLAN UPDATE- JUNE 2024

- INTRODUCTION

The Health Board quality Strategy was launched in March 2023, following a period of organisation and stakeholder engagement.

Delivery of the strategy is supported by a 5 year implementation plan, focussed around the four key quality ambitions set out in the strategy, namely:

- Safe and Reliable Care

- An Organisation Our Patient and Communities Can we Proud Of

- Empowered Staff

- High Quality Services Now and in the Future

Actions within the implementation plan were identified by service leads and reflect those set out within service group and specialty work-plans. Updating the implementation plan is co-ordinated by the Corporate Quality, Safety and Improvement Team. Delivery of the plan is undertaken at service level.

An internal audit review of the Health Board’s Quality Management System was undertaken in March 2024 and reported in June 2024. This report made the following recommendations

| Recommendations |  |  | Priority |
| --- | --- | --- | --- |
| 2.1a 2.1b | The Quality Strategy Implementation Plan should be reviewed and redesigned to focus on improvement goals that are relevant and achievable. The Implementation Plan should incorporate SMART criteria to define success and provide realistic timescales for delivery. |  | High |
| 2.2 | Performance reporting of deliverables within governance arrangements should provide effective oversight of progress with delivery of the Implementation Plan that clearly defines risks and enables prompt action to be taken where issues are escalated. |  | Medium |
| Agreed Management Action |  | Target Date | Responsible Officer |
| 2.1a 2.1b | To have a thorough review of the Goals and Actions within the Quality Strategy Implementation plan and bring an update in July for Q&S Group. The review to use SMART criteria in order to clarify realistic timescales and successes | July 2024 | Head of Q&S / Deputy Head of Q&S/ Acting Project Lead |
| 2.2 | Performance reporting of deliverables should clearly identify progress, risk and actions. Implementation Plan documentation to be reviewed and adjusted to address this. | July 2024 | Acting Project Lead |

Management Board received a paper in July 2024 that described how the implementation plan required a ‘top to toe’ review in order to ensure SMART targets and clear ownership of actions.

- BACKGROUND

The current strategy has been reviewed by the Quality, Safety and Improvement Team and designated leads within the plan. A full breakdown of the plan is included as Appendix 1.

The status of actions is as follows:

| Quality Ambition | No updates Received | Actions Completed | Actions Not Started | Actions On-Track | Actions Off-Track | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Safe & Reliable Care | 4 | 2 | - | 13 | 7 |  |
| An Organisation Our Patients & Communities Can Be Proud Of | 3 | 7 | 7 | 1 | 0 |  |
| Empowered Staff | 1 | 6 | - | 5 | 0 |  |
| High Quality Services Now & in the Future | 2 | 1 | 1 | 4 | 0 |  |

Off-track actions are listed as follows

Safe and Reliable Care

- GOVERNANCE AND RISK ISSUES

There is a risk of non-achievement of the health board’s strategic objectives which is detrimental to the quality of service delivery. This risk is amplified by a lack of recent updates against aspects of the implementation plan and unclear ownership for some actions within the plan.

The Quality, Safety and Improvement Team are undertaking the following actions to improve governance and reduce risk around the Quality Strategy Implementation Plan:

- Contact all leads individually to ask for timely review of their actions

- Quarterly ‘whole plan’ updates to QSG

- Revision of the reporting tool to include risks to delivery

- FINANCIAL IMPLICATIONS

There are no direct financial implantations related to this report.

- RECOMMENDATION

The Board/Committee is asked to note the report.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Financial Implications |  |  |  |
| None identified |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None identified |  |  |  |
| Staffing Implications |  |  |  |
| None |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Quality Strategy includes a long term view for the quality and safety of our services. |  |  |  |
| Report History |  | Quality and Safety Group July 2024 |  |
| Appendices |  | Appendix 1- Quality Strategy Implementation Plan |  |