| Meeting Date | 13 July 2023 |  | Agenda Item |  |  | 4.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Board Effectiveness Action Plan |  |  |  |  |  |
| Report Authors | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan |  |  |  |  |  |
| Key Issues | - The board is required to undertake an annual self-assessment of its effectiveness in terms of governance and internal controls. The findings of the most recent self-assessment were presented to the September 2022 meeting of the board. A proposed action plan was also presented to this meeting, which was agreed. - A report on progress against that action plan was last received by the Committee in May 2023. This report provides a further update. - At the time of reporting, a total of 35 actions were identified as complete by the relevant lead executive; these are highlighted green in the Action Plan, and represents an increase of one since the last report. For the remaining seven actions, it has not been possible to complete these within the original target dates. - With regard to the four actions outstanding from the previous year’s plan, three of these are now reported as closed. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE progress made as detailed within the updated Board Effectiveness Action Plans included at Appendix 1 and Appendix 2 - AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead. |  |  |  |  |  |

BOARD EFFECTIVENESS ACTION PLAN

- INTRODUCTION

1.1	The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan.

2.	BACKGROUND AND CONTEXT

2.1	The board is required to undertake an annual self-assessment of its effectiveness in terms of governance and internal controls.

2.2	The findings of the most recent self-assessment were presented to the September 2022 meeting of the board. A proposed action plan was also presented to this meeting, which was agreed.

2.3	A report on progress against that action plan was last received by the Committee in May 2023. This report provides a further update.

3.	STATUS UPDATE

3.1	Since the last meeting of the Committee, the action plan has again been circulated to all lead executives with a request that they provide updates on the actions assigned to them. A copy of the updated action plan has been included at Appendix 1 for information.

3.2	At the time of reporting, 35 of the 42 actions contained within the current plan were identified as complete by the relevant Lead Executive, and these have been highlighted green in the Appendix. The following action has been reported as complete since the last update to the Committee:

| No | Action | Progress |
| --- | --- | --- |
| 34 | Review and strengthen systems to ensure the formal sign-off of budget delegation/accountability letters. | Aligned to the revised Health Board Budgetary Management approach approved by performance and Finance Committee, accountability letters were issued in June 2023 for Financial Year 2023/24 to all Executive Directors and Service Group Directors, which clearly set out both the recurrent budget brought forward from 2022/23, the investment agreed by the Board as part of the 3 Year Financial Plan (2023-2026) and the 2023/24 savings targets. The letter requires the recipients to reply within a set deadline and responses will be monitored and where no reply is received follow up correspondence will be issued. |

3.3	There are a further seven instances where it has not been possible to complete actions within the original target dates. These are highlighted red in the Action Plan.

3.4	In addition to the above, four ongoing actions were carried over from the previous year’s plan, of which one remains in progress. An update has been included at Appendix 2 for information.

4.	FINANCIAL IMPLICATIONS

4.1	There are no direct financial implications arising from the recommendations in this report.

5.	RECOMMENDATIONS

5.1	Members are asked to:

- NOTE progress made as detailed within the updated Board Effectiveness Assessment Action Plans included at Appendix 1 and Appendix 2

- AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead.

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☐ |
|  | Effective Care |  |  | ☐ |
|  | Dignified Care |  |  | ☐ |
|  | Timely Care |  |  | ☐ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Ensuring the board carries out its business appropriately and aligned with standing orders is a key factor in the quality, safety and experience of patients receiving care. |  |  |  |  |
| Financial Implications |  |  |  |  |
| There are no direct financial implications arising from this paper |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| There are no direct legal implications arising from this paper |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no direct staffing implications arising from this paper |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| The development of the board will provide a robust and sustainable organisation to support the communities it services. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix 1: Appendix 2: | Board Effectiveness Action Pan 2022/23 Board Effectiveness Action Pan 2021/22 Outstanding Actions |  |