HEALTH BOARD RISK REGISTER

June 2024

HEALTH BOARD RISK REGISTER

SUMMARY OF ASSESSED RISKS

| Impact/Consequences | 5 |  | 75: Whole Service Closure | 53: Compliance with Welsh Language Standards 66: Access to Cancer Services – SACT | 16: Access to Planned Care 60: Cyber Security 69: Adolescents being admitted to Adult MH wards 81: Midwifery Staffing Levels 93: Finance: Reduced capital funds 98: Overall condition/compliance and suitability of Health Board Estate 99: Failure to implement the population health strategy approaches at the required scale. 101: Industrial Action (HCSW) New | 01: Access to Unscheduled Care Service 50: Access to Cancer Services 92: Finance: Forecast Deficit |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 |  |  | 37: Operational and strategic decisions are not data informed 51: Nurse Staffing Levels Act (Section 25B) 52: Impact Assessment Requirements 94: CAMHS failure to meet required standards of performance | 27: Digital Transformation 36: Paper Record Storage 43: DOLS/LPS Authorisation & Compliance Reduced from 20 61: Paediatric Dental GA Service 64: H&S Infrastructure 90: GDPR Subject Access Requests 91: Mental Health Capacity Act (MCA) | 03: Recruitment of Consultant Medical and Dental Staff 04: Healthcare Acquired Infection 63: Screening for Fetal Growth Assessment in line with Gap-Grow (G&G) 80: Transfer of Clinically Optimised Patients 85: Non Compliance with ALN Act 89: Healthcare Nursing Staff Levels (HMP) 96: Failure to Develop an Approvable IMTP |
|  | 3 |  |  |  | 100: Partnerships & Collaboration |  |
|  | 2 |  |  |  |  |  |
|  | 1 |  |  |  |  |  |
| C X L |  | 1 | 2 | 3 | 4 | 5 |
|  |  | Likelihood |  |  |  |  |

Risk Register Dashboard

| Strategic Objective | Risk Reference | Description of risk identified | Initial Score | Current Score | Trend | Controls | Last Reviewed | Scrutiny Committee |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 People of Swansea Bay live healthier, equitable and more equal and prosperous lives | 52 (1763) | Statutory Compliance: Engagement & Impact Assessment The Health Board does not have sufficient resource in place to undertake engagement & impact assess in line with Statutory Duties | 16 | 12 |  |  | June 2024 | Performance & Finance Committee |
| 1 People of Swansea Bay live healthier, equitable and more equal and prosperous lives | 99 | Failure to implement the population health strategy approaches at the required scale This arises from risk of a failure of the organisation to understand and act on the provisions of the strategy for building whole of system actions across the 4 pillars; and the consequent lack of systems and processes to support the delivery of population health improvements. | 20 | 20 |  |  | June 2024 | Population Health & Partnership Committee |
| 1 People of Swansea Bay live healthier, equitable and more equal and prosperous lives | 100 | A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners, there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. | 12 | 12 |  |  | June 2024 | Population Health & Partnership Committee |
| 2 Care is high quality, safe, efficient, and delivers the best possible outcomes for people | 75 (2522) | Whole Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 20 | 10 |  |  | June 2024 | Performance & Finance Committee |
| 2.1 Care is high quality, safe, efficient, and delivers the best possible outcomes for people | 4 (739) | Healthcare Acquired Infection Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve national infection reduction goals. | 20 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.1 Care is high quality, safe, efficient, and delivers the best possible outcomes for people | 51 (1759) | Nurse Staffing (Wales) Act (Section 25B wards) Risk of Non Compliance with the Nurse Staffing (Wales) Act There is a risk we may not meet these requirements fully due to increased acuity, unplanned staff absence and vacancies. The potential impact of this maybe non-compliance with the ‘Act’, poor patient outcomes and experience, and suspension of services. | 16 | 12 |  |  | June 2024 | Workforce OD & Digital Committee |
| 2.1 Care is high quality, safe, efficient, and delivers the best possible outcomes for people | 53 (1762) | Welsh Language Standards Failure to fully comply with all the requirements of the Welsh Language Standards, as they apply to the University Health Board. | 15 | 15 |  |  | June 2024 | Health Board (Welsh Language Group) |
| 2.1 Care is high quality, safe, efficient, and delivers the best possible outcomes for people | 101 | Industrial Action (Healthcare Support Workers) (In Committee Risk) Due to inconsistencies in the bandings of healthcare support workers across the UK and NHS Wales at a band two and three level, action is being taken in partnership with Unison and the RCN to address inequalities against the context of limited financial resource availability. [Full description In Committee] | 20 | 20 | New | New | June 2024 | Workforce OD & Digital Committee |
| 2.2 Primary & Community Care | 89 (3071) | Healthcare Nursing Staff Levels (HMPS) There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. | 20 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.3 Mental Health & Learning Disability Services | 43 (1514) | DoLS Risk reduced from 20 Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty/Liberty Protection Safeguards within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. | 16 | 16 |  |  | June 2024 | Quality & Safety Committee |
| 2.3 Mental Health & Learning Disability Services | 91 (3432) | There is a risk that assessments under the Mental Capacity Act (MCA) are not undertaken and recorded as required. Where the UHB fails in its statutory duty to enact the MCA appropriately this could result in harm to vulnerable individuals, and/or unlawful deprivations of liberty, leading to litigation. Such cases could incur significant financial penalties, cause distress to staff members and patients, and risk damage to the organisations reputation. | 16 | 16 |  |  | June 2024 | Quality & Safety Committee |
| 2.3 Mental Health & Learning Disability Services | 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 20 | 12 |  |  | June 2024 | Performance & Finance Committee |
| 2.4 Urgent & Emergency Care | 1 (738) | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 20 | 25 |  |  | June 2024 | Performance & Finance Committee |
| 2.4 Urgent & Emergency Care | 80 (1832) | Transfer of Clinically Optimised Patients A deficit in the availability of appropriate community / domiciliary care results in unacceptable delays in discharging patients from acute hospital beds. As a result, patients can decompensate and never gain the independence that could have been available from an early discharge. | 20 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.5 Planned Care | 16 (840) | Access to Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 16 | 20 |  |  | June 2024 | Performance & Finance Committee |
| 2.5 Planned Care | 61 (1587) | Paediatric Dental GA Service – Parkway Safety risk of general anaesthetic procedures performed on children outside of an acute hospital setting. | 15 | 16 |  |  | June 2024 | Quality & Safety Committee |
| 2.6 Cancer Care | 50 (1761) | Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 20 | 25 |  |  | June 2024 | Performance & Finance Committee |
| 2.6 Cancer Care | 66 (1834) | Access to Cancer Services (SACT) Delays in access to SACT treatment in Chemotherapy Day Unit. | 25 | 15 |  |  | June 2024 | Quality & Safety Committee |
| 2.7 Children & Young People Services | 69 (1418) | Adolescents are being admitted to adult mental health wards Risk related to adolescent patients being admitted to Adult MH inpatient wards – Inappropriate settings potentially resulting in 'Safeguarding Issues'. The WG has requested that Health Boards identify Secondary Care inpatient facilities for the care of adolescents. In Swansea Bay University Health Board Ward F NPT Hospital is the dedicated receiving facility with one bed identified. | 20 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.7 Children & Young People Services | 85 (2561) | Non-Compliance with ALN Act There are risks to the Health Board’s ability to meet its statutory duties and establish the effective collaborative arrangements required by the ALN Act, which is being implemented through a phased approach. | 25 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.8 Maternity Services | 63 (1605) | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). | 12 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 2.8 Maternity Services | 81 (2788) | Critical Staffing Levels: Midwifery Unplanned absences resulting from long and short-term sickness, alongside maternity leave, have resulted in critical staffing levels, which undermine the ability to maintain the full range of expected services safely, increasing the potential for harm, poor patient outcomes and/or choice of birthplace. Poor service quality or reduction in services could impact on organisational reputation. | 25 | 20 |  |  | June 2024 | Quality & Safety Committee |
| 3 Care is delivered in safe and appropriate settings | 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legal and regulatory compliance. | 20 | 16 |  |  | June 2024 | Quality & Safety Committee |
| 3 Care is delivered in safe and appropriate settings | 98 (3692) | Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. | 20 | 20 |  |  | June 2024 | Performance & Finance Committee |
| 4 The delivery of care is supported by innovative digital solutions | 27 (1035) | Digital Transformation to Deliver Sustainable Clinical Services Inability to deliver sustainable clinical services due to lack of resources to deliver sustainable Digital Transformation and services. There are insufficient resources to invest in the delivery of the SBU Digital strategy; support the growth in utilisation of existing and new digital solutions; replace existing technology infrastructure or software at the end of its useful life. | 16 | 16 |  |  | June 2024 | Workforce OD & Digital Committee |
| 4 The delivery of care is supported by innovative digital solutions | 36 (1043) | Storage of Paper Records Failure to provide adequate storage facilities for paper records then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. | 20 | 16 |  |  | June 2024 | Workforce OD & Digital Committee |
| 4 The delivery of care is supported by innovative digital solutions | 37 (1217) | Information Led Decisions Risk that operational and strategic decisions are not data informed. | 16 | 12 |  |  | June 2024 | Workforce OD & Digital Committee |
| 4 The delivery of care is supported by innovative digital solutions | 60 (2003) | Cyber Security (In Committee Risk) The level of cyber security incidents is at an unprecedented level and health is a known target. | 20 | 20 |  |  | June 2024 | Workforce OD & Digital Committee |
| 4 The delivery of care is supported by innovative digital solutions | 90 (2796) | Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs) and other requests for disclosure of personal data The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of subject access /access to health records requests received from requestors. The ICO are already involved with a number of breaches and complaints in this area and there is the potential for future enforcement action if significant improvements are not made. | 16 | 16 |  |  | June 2024 | Workforce OD & Digital Committee |
| 5 The Health Board is a great place to work where staff feel valued and work together towards a common goal | 3 (843) | Recruitment of Consultant Medical and Dental Staff Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard to fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. | 20 | 20 |  |  | June 2024 | Workforce OD & Digital Committee |
| 6 The health board is a resilient, financially sustainable and responsible organisation | 92 (3444) | Finance: Forecast Deficit Risk Forecast deficit is not met due to insufficient progress on COVID cost reduction, savings identification, run rate reduction and the potential for new in-year pressures. | 20 | 25 |  |  | June 2024 | Performance & Finance Committee |
| 6 The health board is a resilient, financially sustainable and responsible organisation | 93 (3448) | Finance: Reduced capital funds Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2023/24. | 20 | 20 |  |  | June 2024 | Performance & Finance Committee |
| 6 The health board is a resilient, financially sustainable and responsible organisation | 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) Failure to have an approvable IMTP for 2024/5 then we will lose public confidence and breach legislation. | 20 | 20 |  |  | June 2024 | Performance & Finance Committee |

Risk Schedules

| Datix ID Number: 738 Health & Care Standard: |  |  | HBR Ref Number: 1 Risk Target Date: 30/09/2024 |  | Current Risk Rating 5 x 5 = 25 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Urgent & Emergency Care |  | BAF Ref: 2.4 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance and Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 5 x 5 = 25 Target: 3 x 4 =12 |  |  | Rationale for current score: The UEC system continues to see high demand, with ambulance attendances in particular being higher than seen previously. This is coupled with reduced flow out of hospital beds due to an imbalance of acute / community / care service provision. These factors are resulting in unacceptable delays in patients accessing UEC services and therefore the risk score remains high. |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: The HB is currently under escalating performance monitoring from WG (Targeted Intervention or TI) for delivery of UEC services. The improvement plan developed as a response to TI and that already included in the HB annual plan is to implement models of care that reflect best practice and focus on areas that will benefit patients, staff and the UEC system most. The implementation of this plan will improve patient flow, length of stay and reduce emergency demand. |  |  |  |
| Date added to the HB risk register 26.01.16 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| Five main areas of work within the plan: - Frailty strategy – approved via Management Board - Grip & control operational management - Senior decision makers at front door services - Pathway of care delays (PoCD) - Home First - ACT - Interface with local authority - Reconfiguration of Emergency Dept In addition to BAU improvement actions: - Continued focussed roll-out of 6-Goals schemes of work - D2RA / Trusted assessor model - SAFER - Criteria-led discharge - Continuous Flow Model (CFM) - Robust SDEC model |  |  | Action | Lead |  | Deadline |
|  |  |  | Review of senior decision making capacity within SDEC and AMU | GMD Morriston SG |  | 30/07/2024 |
|  |  |  | Implementation of 7-day community services such as VW | Interim EMD |  | 30/09/2024 |
|  |  |  | Monitoring of Continuous Flow Model continues to be implemented despite the challenge of flow. It will be monitored over 12 month period. | COO |  | 30/09/2024 |
|  |  |  | Criteria led discharge roll out | Corporate patient flow team |  | Progress: Rolled out in Medicine. Other specialties to follow by 30/09/2024. |
| Assurances (How do we know if the things we are doing are having an impact?) - Urgent & Emergency Care Board is meeting monthly chaired by the COO. - Six Goals programme reviews the pan on a monthly basis |  |  | Gaps in assurance (What additional assurances should we seek?) The need to deliver sustained service. |  |  |  |
| Additional Comments / Progress Notes 08/05/2024: Risk assessment rationale, controls and actions fully refreshed. Focus on the implementation of the Frailty strategy, to be operational during September 2024. |  |  |  |  |  |  |

| Datix ID Number: 843 Health & Care Standard: |  |  | HBR Ref Number: 3 Risk Target Date: 31/03/2025 | Current Risk Rating 4 x 5 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The Health Board is a great place to work where staff feel valued and work together towards a common goal |  | BAF Ref: 5 | Director Lead: Sarah Jenkins, Interim Director of Workforce and OD Assuring Committee: Workforce OD & Digital Committee |  |  |  |
| Risk: Recruitment of consultant medical & dental staff in hard to fill roles. Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard to fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 4 x 5 =20 Target: 4 x 3 = 12 |  |  | Rationale for current score: National shortages of numbers in some areas can lead to: - Inability to recruit sufficient numbers of trainees to fulfil rotas on all sites - Inability to attract non training grades to complete rotas - Inability to fill Consultant grade posts in some specialties with adverse effects on patient safety and employer relations. Inability to recruit sufficient registered nursing staff. - The situation has improved around the recruitment of junior staff but there are many hard to fill consultant posts which impact on the ability to run services which impacts patient care. |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: This remains a challenge and is also a national problem. |  |  |  |
| Date added to the HB risk register April 2012 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Regular monitoring of recruitment position with reports to Executive Team and Board via Medical Director and Medical Workforce Board. - Specialty based local workforce boards established to monitor and control specific issues. The HB Workforce OD & Digital Committee will seek assurance of medical workforce plans to maintain services. - Engagement of the Deanery about recruitment position. - Weekly workforce delivery meetings with CEO to review progress against critical medical and clinical posts - Working with specialist agency and head hunters to improve chances to fill hard to recruit posts - Working with a marketing agency to develop a branding and attraction campaign for the health board. - Consideration of the RPO (Recruitment Process Outsourcing) model. - Implemented the CESR (Certificate of Eligibility for Specialist Registration) framework to grow your own consultants |  |  | Action |  | Lead | Deadline |
|  |  |  | Medical training initiatives pursued in a number of specialties to ease junior doctor recruitment |  | Director W&OD | 31/03/2025 |
|  |  |  | The Medical Workforce Board continues to monitor recruitment and junior doctor’s rotas. |  | Director W&OD | 31/03/2025 |
|  |  |  | Continue to recruit internationally. |  | Director W&OD | 31/03/2025 |
|  |  |  | Continue to work with head hunters |  | Director W&OD | 31/03/2025 |
| Assurances (How do we know if the things we are doing are having an impact?) - General situation monitored through W&OD Committee - Communication with Deanery - Recruitment campaigns - Monitoring by Executive Teams and specialty based local workforce boards - Workforce planning and deployment taskforce meetings with service groups - Weekly workforce delivery meetings with CEO as above |  |  | Gaps in assurance (What additional assurances should we seek?) Locum cover Adequate supply of doctors who can work in this country Ability to flexibly deploy doctors in training. Dedicated work between workforce and finance to review and confirm budgeted medical workforce establishment by service group to confirm SIP and vacancy factor. |  |  |  |
| Additional Comments / Progress Notes 25/01/2024: Workforce team reviewing & refreshing risk entry for Feb HBRR. 12/04/2024: Description refreshed to reflect that the focus of this risk is on particular consultant roles, following improvements in recruitment to training grades. |  |  |  |  |  |  |

| Datix ID Number: 739 Health & Care Standard: |  |  | HBR Ref Number: 4 Risk Target Date: 31/03/2025 | Current Risk Rating 4 x 5 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient, and delivers the best possible outcomes for people |  | BAF Ref: 2.1 | Director Lead: Gareth Howells, Executive Director of Nursing Assuring Committee: Quality and Safety Committee |  |  |  |
| Risk: Healthcare Acquired Infection Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 3 =12 |  |  | Rationale for current score: Health Board incidence of key Tier 1 infections per 100,000 population above All Wales rates, indicating Health Board’s population at greater risk of infection. High occupancy rates & frequent ward moves associated with increased risk of infection transmission. Lack of decant facilities compromises environment deep cleaning & decontamination, and planned preventative maintenance programmes. |  |  |  |
| Level of Control = 40% |  |  |  |  |  |  |
| Date added to the HB risk register January 2016 |  |  |  |  |  |  |
|  |  |  | Rationale for target score: Improved governance structures for IPC and antimicrobial stewardship will drive improved local ownership and embed responsibility for these priorities for all levels of staff. Adequately maintained & clean environments facilitate good IPC & minimise infection risks. Reduced occupancy & frequency of patient moves mitigate against infection transmission. Compliant ventilation systems and water safety minimise infection risks. Access to timely data on infections, training, antimicrobial stewardship, cleaning at ward/unit/practice level enables Service Groups to identify areas for focused QI programmes, drive improvement, & effectively measure outcomes. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Policies, procedures, protocols and guidelines supplement the National Infection Control Manual. - Infection Prevention & Control related training provided programmes. - Surveillance of infections, with early identification of increased incidence, and instigation of controls. - Antimicrobial stewardship programmes and systems of monitoring and feedback. - Provision of cleaning service to meet National Standards of Cleanliness. - Engineering controls for water safety, ventilation, and decontamination. - Infection Prevention Improvement Plans for HB and Service Groups for 2024/25 have been submitted for approval by the Health Board's Infection Prevention & Control Strategic Group on 30/04/2024. Progress is reported at SG Infection Control Committees, HB Infection Prevention & Control Group, Quality & Safety Group, Quality & Safety Committee, and Management Board. These include trajectories to meet national targets and report performance against them. - The Health Board has been escalated to Targeted Intervention for its position relating to healthcare associated infection (HCAI). Governance processes for HCAI have been revised to provide strengthened scrutiny and assurance. |  |  | Action |  | Lead | Deadline |
|  |  |  | Review governance and reporting arrangements for IPC. |  | Executive Leads for IPC | Completed |
|  |  |  | Establish Executive Healthcare Associated Infection (HCAI) Scrutiny Group |  | Executive Leads for IPC | Completed |
|  |  |  | Service Group Healthcare Associated Infection (HCAI) Improvement Plans approved by Infection Prevention & Control Strategic Group |  | Co-chairs of IPC Strategic Group | 30/06/2024 |
|  |  |  | Achieve 85% compliance with IPC mandatory training (Levels 1 & 2) |  | Service Group Directors | 31/12/2024 |
|  |  |  | Undertake a programme of decant, deep clean and disinfection with hydrogen peroxide vapour (HPV) in Morriston Hospital. |  | Morriston Service Group Directors | 31/12/2024 |
|  |  |  | Achieve reduction in Tier 1 infections to meet de-escalation criteria for intervention targets |  | Service Group Directors | 31/03/25 |
| Assurances (How do we know if the things we are doing are having an impact?) - Clear Corporate and Service Group IPC Assurance Framework in place. - Infection Prevention Improvement Plans for HB and Service Groups with progress reported at SG Infection Control Committees, HB Infection Prevention & Control Group, Quality & Safety Group and at Management Board. These include trajectories to meet national targets and report performance against them. This is also reported to Quality & Safety Committee. - Ongoing monitoring of infection control rates. - IPC, antimicrobial, decontamination and cleaning audit programmes. - Annual completion of IPC Level 2 mandatory training for all HB staff. - Compliance and validation systems for water safety, ventilation systems and decontamination. - Revised and strengthened governance structure for HCAI, including monthly meetings of Executive HCAI Scrutiny Group. |  |  | Gaps in assurance (What additional assurances should we seek?) - High occupancy rates & frequent ward moves associated with increased risk of infection transmission. - Lack of single room availability, leading to delays in isolating patients with infections and increasing risks to patient contacts. - Increased numbers of clinically optimised patients remaining in hospital leads to increased length of stay, increased risk of over-occupancy and over-crowding, with consequence of increasing risks of acquisition of infection. - General infrastructure of the aging hospital estate compromises ability to clean and decontaminate effectively. - Antimicrobial prescribing, relating particularly to total volume of antibiotics, with the SBUHB having second highest total volume of antibiotics prescribed in primary care in Wales. - Lack of decant facilities compromises environment deep cleaning & decontamination, and planned preventative maintenance programmes. - Varying levels of IPC responsibility embedded across all disciplines and groups, with variable medical engagement at all levels in infection prevention-related Quality Improvements programmes. |  |  |  |
| Additional Comments / Progress Notes 19/06/2024: - Governance and reporting arrangements have been revised and strengthened to ensure improved accountability and focus for reducing HCAI. - Executive HCAI Scrutiny Group established. - Service Groups HCAI Improvement Plans reviewed and to be approved by Co-chairs of Infection Prevention & Scrutiny Group by 30/06/24. - Level 2 IPC training compliance improved to 76.60%; Level 1 training compliance 90.94%. - Tier 1 infection progress to Targeted intervention de-escalation criteria in May 2024: - C. difficile – 4 hospital onset cases (target 6); overall health board cumulative cases (hospital onset and community onset) – 39 cases. - Staph. aureus bacteraemia – 3 hospital onset cases (target 3); overall health board cumulative cases (hospital onset and community onset) – 19 cases. - E. coli bacteraemia - 1 hospital onset case (target 4); overall health board cumulative cases (hospital onset and community onset) – 35 cases. - Klebsiella spp. bacteraemia – 3 hospital onset cases (target 4); overall health board cumulative cases (hospital onset and community onset) – 21 cases. |  |  |  |  |  |  |

| Datix ID Number: 840 Health & Care Standard: |  |  | HBR Ref Number: 16 Risk Target Date: 30/09/2024 | Current Risk Rating 5 x 4 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Planned Care |  | BAF Ref: 2.5 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance and Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 5 x 4 = 20 Target: 4 x 2 = 8 |  |  | Rationale for current score: Whilst the HB has eradicated very long waits for surgery, patients are still waiting in excess of 104 weeks for surgical intervention, which is outside of national policy on RTT. The HB is currently under escalating performance monitoring from WG (Targeted Intervention or TI) for delivery of Planned Care services. The improvement plan developed as a response to TI mirrors that already included in the HB |  |  |  |
| Level of Control = 90% |  |  |  |  |  |  |
|  |  |  | Rationale for target score: There is scope to reduce the likelihood score to reduce the overall risk to an acceptable level. The Risk target date indicates when we expect to see some reduction in waiting lists – albeit the overall risk level may remain as work continues. |  |  |  |
| Date added to the HB risk register January 2013 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - There is a bi-weekly Targeted Intervention (TI) meeting specifically for assurance on the recovery of our elective programme. - Specialty level capacity and demand models set out the baseline capacity and identify solutions to bridge the gap this financial year. - A focused intervention is in train to support to the 10 specialties with the longest waits. - Long waiting patients are being outsourced to the Independent Sector, where appropriate - Additional internal activity is being delivered on weekends (via insourcing), although this is currently at risk due to changes in policy pertaining to the payment of enhanced rates to A4C staff. - Planned care trajectories are being developed and submitted to WG as part of the annual plan by the end of May 2024. - Governance process put in place to monitor performance against trajectories internally, and with Welsh Government as part of Targeted Intervention. - External & internal validation continues. - All long waiting patients are receiving clinical reviews to ascertain continued need for surgery. |  |  | Action |  | Lead | Deadline |
|  |  |  | Develop comprehensive demand & capacity plans for 2024/25. |  | Deputy COO | Complete |
|  |  |  | Work ongoing with Finance colleagues to establish the funding allocation for elective recovery for 2024/25. |  | Deputy COO | Complete |
| Assurances (How do we know if the things we are doing are having an impact?) - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the COO - Bi-weekly planned care meetings chaired by the COO - Monthly TI monitoring meetings with WG |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 08/05/2024: All patients breaching the 104 week target are at treatment stage. Therefore all have a treatment plan in place. 14/06/2024: Actions completed: Development of comprehensive demand & capacity plans for 2024/25; Work with Finance colleagues to establish the funding allocation for elective recovery for 2024/25. |  |  |  |  |  |  |

| Datix ID Number: 1035 Health & Care Standard: |  |  | HBR Ref Number: 27 Risk Target Date: TBC |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The delivery of care is supported by innovative digital solutions |  | BAF Ref: 4 | Director Lead: Matt John, Director of Digital Assuring Committee: Workforce OD & Digital Committee |  |  |  |
| Risk: Digital Transformation Inability to deliver sustainable clinical services due to lack of resources to deliver sustainable Digital Transformation and services. There are insufficient resources to: - Invest in the delivery of the SBU Digital strategy - Support the growth in utilisation of existing and new digital solutions - Replace existing technology infrastructure or software at the end of its useful life. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 4 = 16 Target: 5 x 2 = 10 |  |  | Rationale for current score: C – Reliance on digital ways of working has increased. Loss of IT service has a greater impact on ability to provide clinical care. Lack of investment in new digital solutions to make services more effective will mean clinical service provision will become unsustainable. L- Reduction in capital funding in 2022/23/24 has increased the likelihood of HB not being able to replace aging infrastructure such as the network equipment. There is a £15m capital requirement over the next 3 years. Acceleration of the CTM SLA disaggregation has been proposed and there are further pressures on revenue funding. The shift to cloud and software as a service contracting models will increase the requirement for revenue funding to deliver digital transformation and ongoing services. |  |  |  |
|  |  |  | Rationale for target score: C – Of failure will increase as the reliance and proliferation of the use of digital solutions increases. L – Investment will mean the support mechanisms, rate of failure and ability to deliver solutions that meet the needs of users will improve sustainable digital services. There will however always be an inherent risk of failure of IT solutions. |  |  |  |
| Level of Control = 50% |  |  |  |  |  |  |
| Date added to the HB risk register 2012 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Digital Strategy has been approved by the Health Board and outlines requirements - HB Capital priority group considers digital risks for replacement technology which is fed into the annual discretionary capital plan - Digital Services prioritisation process is in place Digital Leadership Group provides the overarching governance to the delivery of the Digital Strategic Plan including financial considerations. - Digital Services Management Group assesses current service provision and flags risks and issues - Digital Services revenue requirements are included in 2023/24 annual plan |  |  | Action | Lead |  | Deadline |
|  |  |  | Refresh the Digital Strategy including a high level investment plan to set out vision for the Health Board | Assistant Director of Digital: Business Management and Information Governance |  | 31/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - Internal Audit Program assesses Digital in 4 areas annually |  |  | Gaps in assurance (What additional assurances should we seek?) - Lack of certainty over future capital and revenue funding streams makes planning and implementation difficult/less effective. |  |  |  |
| Additional Comments / Progress Notes 15/03/2024 – Digital Strategy redevelopment process has completed. The strategy will go to Board for approval in May 2024 11/04/2024 – The 10-year investment plan has been drafted. A 3-year plan has been submitted to WG via DHCW. The draft Digital strategy includes the 10-year investment plan. The Strategy will be finalised and taken through the Health Board’s governance processes for approval over the coming months. 10/05/2024 – The Digital Strategy will be presented and approved by the Health Board in July 2024. 10/06/2024 – Action 1 target date extended to 30/09/2024. |  |  |  |  |  |  |

| Datix ID Number: 1043 Health & Care Standard: |  |  | HBR Ref Number: 36 Risk Target Date: TBC |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The delivery of care is supported by innovative digital solutions |  | BAF Ref: 4 | Director Lead: Matt John, Director of Digital Assuring Committee: Workforce OD & Digital Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 3 x 3 =9 |  |  | Rationale for current score: C - Inability to find records for patients could delay care/increase length of stay over 15 days. Could also mean patients receive incorrect treatment. Increased risk of fire where records are stored outside of the medical record libraries. L - we know this happens from incidents raised |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: C - The increased development and adoption of the digital record will reduce the need for the paper health record being available at the point of care. L - The increased development and adoption of the digital record, the introduction of RFID and the approach to management of the paper record identified in the Business case process should reduce the amount of paper required to be stored and managed. |  |  |  |
| Date added to the HB risk register June 2016 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - There is a plan in place to increase the functionality of the electronic record to document patient care. The delivery of the plan is overseen by the Digital Leadership Group and progress provided to Management Board. (Supported by individual project boards as appropriate). - Records managed by the Medical Records libraries are RFID tagged and location tracked. - Medical Record libraries are regularly risk assessed for fire by health and safety. - Alternative offsite storage arrangements have been identified. - All records must be documented on the Information Asset Register (IAR). |  |  | Action | Lead |  | Deadline |
|  |  |  | Awaiting WG approval for Health Records Business Case | Head of Health Records & Clinical Coding |  | 30/06/2024 |
|  |  |  | Requirement for legal agreement with landlord once approval from WG received | Head of Health Records & Clinical Coding |  | 30/06/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - RFID has been implemented for the acute record improving the management and storage of records - Health Records performance reports developed in line with RFID technology - Attainment of the Tier 1 Health Board target for clinical coding completeness which relies on the timely availability and quality of the Paper record and electronic sources - Monitoring complaints and incident reporting. - Electronic record is being implemented in accordance with the plan eg implementation of WNCR, ETR, HEPMA etc. |  |  | Gaps in assurance (What additional assurances should we seek?) Investment required supporting the delivery and operational costs of the Digital strategy. Reliance on DHCW for delivery of the solution for a fully electronic patient record. Impact of the Infected Blood Enquiry on the Health Boards ability to destroy notes. Process for ensuring clinical adoption of electronic ways of working and cessation of adding information to the paper record that is already available electronically needs to be agreed and enforced by the Health Board. Impact of the infected Blood Inquiry on the health boards ability to destroy notes and the change in the records code of practice is being reviewed by the Director of Digital. |  |  |  |
| Additional Notes 09/04/2024 - Business Case for Centralisation project approvals to date: Business Case Assurance Group 30th Jan 24, Management Board 13th March 24 & Health Board 28th March 24. 07/05/2024 - Chairs Action received by Director of Digital, Executive Medical Director and Director of Corporate Governance which endorsed the removal of the non-adherence of patients with long term conditions as a recommendation within the revised NHS Records Management Code of Practice for Health & Social Care 2023 05/06/2024 - Update on Actions 1 & 2 -Submission has already been made to WG. Update discussions with NHS finance, awaiting approval 05/06/2024. Necessary legal discussions almost complete for all parties. Can only complete once WG approval received. |  |  |  |  |  |  |

| Datix ID Number: 1217 Health & Care Standard: |  |  | HBR Ref Number: 37 Risk Target Date: 30th June 2024 |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The delivery of care is supported by innovative digital solutions |  | BAF Ref: 4 | Director Lead: Matt John, Director of Digital Assuring Committee: Workforce OD & Digital Committee |  |  |  |
| Risk: Operational and strategic decisions are not data informed: - Business intelligence and information already available is not utilised - Users are unable to access the information they require to make decisions at the right time - Gaps in information collection including patient outcome measures |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 3 = 12 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  | Rationale for current score: C – Opportunity cost of not acting on data could mean opportunities for improvement are missed, failures are not identified in a timely manner resulting in adverse national publicity and/or delays in care/increased length of stay. L - Dashboard utilisation is lower than would be anticipated. Management Board have approved the investment for 4 BI partners to work with the SDGs to become more data driven. |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: C- Will remain the same or increase due to increased reliance in information L- Investment in BI will lead to more information be available and used. The higher the use of information at operational level will lead to better quality data. |  |  |  |
| Date added to the HB risk register: June 2016 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - BI partner roles have been funded and will be introduced to support the SDGs to become more data driven. - COVID19 Dashboards Developed and utilised to inform the decision making process at Gold - The Health Board has invested in interactive dashboards with the addition of the Power BI Business Intelligence software and infrastructure to support it. - 33 dashboards in place including Cancer, Patient Flow, Outpatients, Mortality, Clinical Variation, Primary & Community Care Delivery Unit Dashboard and Ward Dashboard - Safety Huddle implemented in Morriston has improved data quality and improved operational working - Information Dept. working with Planning and Finance leads to develop meaningful indicators, utilising dashboards to present information in a user friendly way - New technologies being reviewed for advanced analytics and integration into a new Health Board analytics platform. - Health Board has representation on national groups such as the Advanced Analytics Group (AAG), all Wales Business Intelligence and Data Warehousing Group and Welsh Modelling Collaborative. |  |  | Action | Lead |  | Deadline |
|  |  |  | Start of 2nd tranche of Data Literacy Module Manager’s Pathway program | Assistant Director of Digital Intelligence |  | Completed |
|  |  |  | Certified Analytical Programme with access to self- service datasets | Assistant Director of Digital Intelligence |  | 30th June 2024 |
|  |  |  | Three additional Data Literacy and Power BI Modules to be created and offered on ad-hoc basis. | Assistant Director of Digital Intelligence |  | 31st July 2024 |
| Assurances (How do we know if the things we are doing are having an impact?) More evidence based and proactive decisions being made. Dashboard technology; assist in developing indicators / triangulating information to identify issues |  |  | Gaps in assurance (What additional assurances should we seek?) Culture of the organisation needs to change to focus on information and Business intelligence for operational rather than reporting purposes. Capability of operational staff to utilise the tools and capacity to act on the intelligence provided. |  |  |  |
| Additional Comments / Progress Notes 01/05/2024 - Successful recruitment of BI Partner with start date end of May - action marked as completed. Monthly meeting invites sent to HCSE, VBHC and other reps to share learning. Have added another action around certified analytics programme - to give advanced users access to self-service data sets. 11/06/2024: Action completed: Start of 2nd tranche of Data Literacy Module Manager’s Pathway programme. |  |  |  |  |  |  |

| Datix ID Number: 1514 Health & Care Standard: |  |  | HBR Ref Number: 43 Risk Target Date: TBC |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Mental Health & Learning Disability Services |  | BAF Ref: 2.3 | Director Lead: Gareth Howells, Executive Director of Nursing Assuring Committee: Quality and Safety Committee For Information: Mental Health Legislation Committee |  |  |  |
| Risk: Deprivation of Liberty Safeguards Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 4 = 16 Target: 3 x 2 = 6 |  |  | Rationale for current score: Although processes have been planned in order to reduce the breach position they have yet to be fully implemented. The impact is yet to be realised. Risk was increased to 20 in Feb 2023 following discussion at Mental Health Legislation Committee. Breaches in DOLS assessments have reduced as a result of increased capacity within the team and additional external Best Interest Assessors. This will continue to be monitored |  |  |  |
| Level of Control = 40% |  |  | Rationale for target score: Consequences of DoLS breaches for the Health Board will not change. With controls in place, over time likelihood should decrease. |  |  |  |
| Date added to the HB risk register July 2017 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| Additional supervisory body signatories in place – this is being undertaken as overtime using additional WG funds. Additional funding received from WG to manage the backlog of DoLS assessments. DoLS assessments are being undertaken via a number of difference sources to address the backlog; - External BIA’s payment to be increased from £120 to £250 (utilising substantive recurring funding) to encourage a large cohort of BIA’s to undertake role. - 2 band 6 WTE BIA’s have been appointed (using WG money). This will reduce the need for agency BIA’s. - Overtime/additional hours agreed utilising WG money for sign off completion. - DoLS database updated and DoLS dashboard in place, monitoring applications and breaches via dedicated BIAs and Admin. - Delivery of DOLS Action plan reviewed monthly. - Regular reporting to Mental Health Legislation Committee (MHLC). - Monthly reporting to Unit Nurse Director and Finance on DoLS breaches. - Health Board presence at National and regional meetings relating to DoLS / LPS. - Increased IMCA services to support increased BIA resource. - Current Mental Capacity Act practice reviewed to support MCA DoLS issues in practice. |  |  | Action | Lead |  | Deadline |
|  |  |  | Overtime/additional hours agreed to fund sign off from nurse assessor team to process the backlog assessments | GND Primary and Community |  | Completed |
|  |  |  | Weekly data monitoring meetings and monthly reporting to Group Nurse Director and Deputy Group Nurse Director. Updates sent through Q&S Groups. | Interim Head of Long Term Care |  | Ongoing |
|  |  |  | Quarterly reporting to Mental Health and Legislative Committee | Interim Head of Long Term Care |  | Ongoing |
| Assurances (How do we know if the things we are doing are having an impact?) Regular scrutiny at Service Group and Safeguarding Committee and by DoLS Internal Audit; monitoring via DoLS Dashboard this will provide real-time accurate data. Update report to MHLC, impact of backlog of DoLS breaches and new LPS implementation. Monthly updates with Unit Nurse Director and Finance. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 19/04/2024: MCA has now transferred from Corporate to the DoLS team in PCTSG to provide a HB wide MCA/DoLS service 01/04/2024 which is hosted in PCTSG. Risk remains unchanged and to be reviewed in next Risk Meeting with PCTSG Governance. New MCA/DoLS Lead commenced 11/03/2024 and is in induction phase. Service remains to rely heavily on external BIA's to support the service. Substantive BIA's are running at 33.3% deficit due to long term sickness. 15/05/2024 (replaces previous holding update): Breaches in DOLS assessments have reduced as a result of increased capacity in the team and additional use of external BIA assessors. Therefore, risk level reviewed and likelihood of breaches reduced. Current sickness (not work related) is impacting on performance (66% {2xBIA} down in capacity). Performance should improve further on return to work – 1 BIA due to return to work the end of this month |  |  |  |  |  |  |

| Datix ID Number: 1761 Health & Care Standard: |  |  | HBR Ref Number: 50 Risk Target Date: 30/09/2024 |  | Current Risk Rating 5 x 5 = 25 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Cancer Care |  | BAF Ref: 2.6 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance and Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. The HB remains unable to deliver on the target of 75% of patients being treated within 62 days and is currently under targeted intervention by WG to improve performance. The HB has been given an initial target of 60% to be delivered by the end of Dec-24, increasing to 70% by the end of March 2025. The most recent performance reported in for March 24, where the HB attained 56%. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 5 x 5 = 25 Target: 4 x 3 = 12 |  |  | Rationale for current score: Risk score based on being off trajectory for SCP. |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: Target score reflects the challenge this area of work present the Board and where small numbers of patients impact on the potential to breach target. |  |  |  |
| Date added to the HB risk register: April 2014 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Tight management processes to manage each individual case on the Single Cancer Pathway (SCP). Enhanced monitoring & weekly monitoring of action plans for top 6 tumour sites. - Initiatives to protect surgical capacity to support SCPs have been put in place - Tumour sites have been given additional targets to achieve by the end of Qtr1: - Achieve the 10-day 1st Outpatient target - Deliver a decision to treat (DTT) by day 31 - A specific plan is being delivered to support Pathology services and ensure SCP tests are turned around within 5 days. |  |  | Action | Lead |  | Deadline |
|  |  |  | Cancer Performance Group to monitor improvement trajectories for both cancer backlog and SCP performance on a monthly basis | Deputy COO |  | 30/06/2024 |
|  |  |  | Full review of gynaecology / gynae-oncology pathway given service constraints to be done. Additional theatre capacity for gynaecological cancer to be agreed to reduce current backlog | Deputy COO |  | 30/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the COO - Bi-weekly Cancer meetings chaired by the Dep COO - Monthly TI monitoring meetings with WG |  |  | Gaps in assurance (What additional assurances should we seek?) Performance and activity data monitored, but delays to treatment continue while sustainable solutions found. |  |  |  |
| Additional Comments / Progress Notes 29/01/2024: Slight in improvement in SCP performance during November and December, 52% and 53% respectively. Improvement in Upper GI performance (73%) but further work required in other tumour site area e.g. gynaecology, urology and breast. 08/05/2024: Further improvement seen in March 2024 with 56% delivered against the target. 18/05/2024: Sustained improvement for April (56%) and improvement in two-week first outpatient appointment target and decision to treat within 31 days evident |  |  |  |  |  |  |

| Datix ID Number: 1759 Health & Care Standard: |  |  | HBR Ref Number: 51 Risk Target Date: TBC | Current Risk Rating 4 x 3 = 12 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient, and delivers the best possible outcomes for people |  | BAF Ref: 2.1 | Director Lead: Gareth Howells, Executive Director of Nursing Assuring Committee: Workforce OD & Digital Committee |  |  |  |
| Risk: Non Compliance with Nurse Staffing Levels Act (2016) – Section 25B Wards The Nurse Staffing Levels (Wales) Act 2016 (NSLWA) legally requires the health board to make provision for appropriate nurse staffing levels within their nursing services. In accordance with section 25B, there is a duty to calculate nurse staffing levels in adult and paediatric acute medical and surgical inpatient wards. There is a risk we may not meet these requirements fully due to increased acuity, unplanned staff absence and vacancies. The potential impact of this maybe non-compliance with the ‘Act’, poor patient outcomes and experience, and suspension of services. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 3 = 12 Target 3 x 2 = 9 |  |  | Rationale for current score: - The scope of the risk has been reviewed to disaggregate the 25B reportable wards as part of the NSLWA to enable clearer identification of risk of non-compliance with the’ Act’ from the aggregated risk across all nurse staffing areas of inadequate staffing levels previously scored 20. - There has been a steady decline in the number of vacancies across the 25B wards as a result of successful international recruitment and student streamlining - The Service Group risk assessments for 25B wards reported at the NMSSAIG 24.03.2024 are as follows: - Morriston Service Group – 9 (unchanged) - NPTSSG – 9 (unchanged) - Paediatrics: In-patient wards – 16 (unchanged) |  |  |  |
| Level of Control = |  |  | Rationale for target score: - The health board has the required structures and processes in place to provide reassurance to the Board that SBUHB is compliant under the Act and as such are allocating resources accordingly. - Health boards are duty bound to take all reasonable steps to maintain nurse staffing levels. - Ward skill mix, recruitment and induction plans impacting on ward - Projected continued decrease in vacancies by end of 2024. |  |  |  |
| Date added to the HB risk register November 2018 Scope Refreshed: January 2024 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| The Health board has put the following controls in place: - The designated person as part of the requirements of the ‘Act’ is the Executive Director of Nursing & Patient Experience - The responsibility for decisions relating to the maintenance of the nurse staffing level rests with the health board is based on evidence provided by, and the professional opinions of the Executive Directors with the portfolios of Nursing, Finance, Workforce, and Operations - Bi-annual calculations undertaken across all Section 25B wards using the triangulated methodology which Service Groups formally present at Executive led scrutiny panels with representation from Nursing, Workforce and Digital and Finance Colleagues. - The Ward Sister / Charge Nurse, Senior Nurses and Group Nurse Director continuously assess the situation and keep the designated person formally apprised - The health board has representation at the All-Wales Nurse Staffing Group and its sub groups to ensure the organisation is aware of national updates - The Board receive a bi-annual report - May (agreed Once for Wales) and November (mandatory). The 3 yearly mandatory paper to Welsh Government is due May 2024. - Workforce planning & redesign, training and development. Recruitment and retention continues. HB Workforce Group has been set up and links to HEIW Retention Work stream, HB representatives on HEIW Group are Associate Head of HR, Recruitment and Retention Manager and Matron, Corporate Recruitment. Workforce plans have been developed by Service Group Nurse Directors and each Service Group agrees staffing, with consideration of all reasonable steps to maintain the nurse staffing level - Work assessing the impact of the 'Team around the Person' continues on a HB and All Wales basis. - Rostering Policy - the Service Groups have a robust roster scrutiny process that is undertaken to ensure roster efficiency and appropriate utilisation of temporary staff. - The health board has a nursing retention plan and actively supports the Retire and Return policy. - SafeCare has been implemented, the All Wales SOP remains a working document as understanding evolves. - Service Groups continue daily staffing huddles and daily staffing tool and escalate as appropriate. |  |  | Action |  | Lead | Deadline |
|  |  |  | Student Streamlining and Overseas recruitment |  | Executive Director of Nursing | 31/12/2024 Monthly ongoing |
|  |  |  | Review of workforce, consider more diverse skill mix, including development of Band 3 and Band 4 roles. Bi-annual re-calculations of inpatient wards have resulted in the addition of Band 3 and 4 roles within the NSA templates. These posts are being recruited into, there is a need for training and supervision for these new posts. Development of Service Group workforce plans to support an overall Corporate Workforce Plan. |  | Executive Director of Nursing | 31/12/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - Ongoing robust recruitment and retention plans in place to reduce vacancies in key clinical areas. - Accurate reporting of acuity data and governance around sign off. - Agreed establishments are funded. - E-Rostering implemented and roster scrutiny undertaken, ensuring effective staff allocation. - All Wales Templates are visible informing patients/visitors of planned roster on all Section 25B wards. Patient Information available on all Section 25B wards, Service Groups have access to all HEIW documents via a SharePoint - Bi-annual Board reports, provide assurance and outline compliance and any key risks, submitted in November and May each year, with three yearly report to Welsh Government due May 2024. - The Health Board Nursing and Midwifery Safe Staffing Assurance and Improvement Group (formally the Nurse Staffing Act Steering Group, amended July 2023) meets on a bi-monthly basis, ensuring risks from all Service Groups are presented, discussed and escalated as appropriate at each meeting. This group is chaired by an Associate Director of Nursing and reports to Nursing and Midwifery Board and the Workforce, Organisational Development and Digital Committee - Service Group risk assessments have been updated and disaggregated into 25B and 25A areas to enable clear risk assessment and escalation of specific risks to ensure robust governance and risk assurance - There is a clear process for scrutiny during bi-annual re-calculations and at any other time when wards require a re-calculation, for example: change to ward purpose, increased bed numbers or increase patient acuity - SafeCare system has been implemented. Support given to help embed the system into everyday use. Use of SafeCare linked to daily staffing huddles. - Historical information and all reporting templates available on a share drive |  |  | Gaps in assurance (What additional assurances should we seek?) - Issue remains regarding Information Technology barriers around the capture of data required for the Act on an All- Wales and Health Board basis. All Wales work with Allocate (Safecare) to improve reporting capabilities of Safecare, via a dashboard continued to progress, SBU is pilot site for testing. Update to Allocate system received, working with rostering team and BCU NSA Lead to check accuracy of reporting. - Ongoing work across Wales to ensure IT systems are compatible with each other for operational and reporting purposes. |  |  |  |
| Additional Comments / Progress Notes Section 25B wards covered by this risk:. NPTSSG; Morriston Service Group. Ward 2 Ward 4 Ward 12 Ward A Ward E Paediatric: Ward M and Oakwood Ward; Ward A, B, W and Clydach Ward Ward C, Cyril Evans Ward, Dan Danino Ward Powys Ward, Tempest Ward Cardigan Ward Ward K, L, R, T and Pembroke Ward Ward D, E, F, G, H, J, S and Gower Ward. For information – 25A areas not covered by this risk include (These are managed within Service Groups and would be escalate for Executive consideration as appropriate).. Morriston Service Group; NPTSG; Mental Health & Learning Disabilities; Community Areas. Critical care areas – GITU & CITU Short stay and assessment areas AMU,SDMU Emergency Department; Neonates Theatres Ward B, C, D NPTH; Mental Health and Learning Disabilities; District Nursing Health Visiting Gorseinon Hospital Ty Olwen. Midwifery is not covered as part of the NSLWA – Refer to Midwifery Staffing Risk ID 2788 (HBR 81) 24/01/2024: Discussed and agreed in Nurse and Midwifery Safe Staffing Assurance and Improvement Group (NMSSAIG) on 24th January 2024. The scope of this risk has changed. The description has been refreshed to clarify that only those services covered under Section 25B of the Act are within its scope. Work is being undertaken to review risks in services outside this section of the Act (including Neonates and MH&LD where staffing level risks have been highlighted previously) in order to reflect separately on HBRR as appropriate. This also includes ensuring the relevant clinical services achieve the required standards set out in the all Wales district nursing and mental health principles as well and the BAPM standards for Neonatal Units and Birth rate plus, 27/03/2024: Risk reviewed and confirmed no change. 19/06/2024: Risk reviewed at Nursing Assurance Meeting 20.5.24 and remains the same as an aggregated score. To note the risk score for Paediatric Wards was increased by the Service Group to 16 as a result of skill mix challenges. The Service Group have a mitigation plan and trajectory to deescalate. |

| Datix ID Number: 1763 Health & Care Standard: |  |  | HBR Ref Number: 52 Risk Target Date: TBC |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, equitable and more equal and prosperous lives |  | BAF Ref: 1 | Director Lead: Richard Thomas, Director of Communications and Engagement Assuring Committee: Performance and Finance Committee |  |  |  |
| Risk: Impact Assessment Requirements The Health Board does not have sufficient skills & resource in place to undertake impact assessments in line with strategic service change and policy development. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  | Rationale for current score: - Current lack of required skills / staff to deliver requirements. |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: - All of these areas need to have adequate resourcing and robust processes / policies in place for the organisation to make robust plans, engage public confidence and meet our statutory and public duties. |  |  |  |
| Date added to the HB risk register November 2018 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Head of EDI to be appointed to support equality impact assessment – funding previously agreed, paper going to Management Board and then Board on 25th January 2024. Funding to be agreed to allow appointment to be made. - Creation of DICE has led to some additional capacity within Engagement Team but alongside a significant increase in demand for activity. - Robust policies and processes to be in place for Impact Assessment going forward. - EIA responsibilities incorporated into wider Impact Assessments. - Development of Strategic Equality Group across organisation to support processes. |  |  | Action | Lead |  | Deadline |
|  |  |  | Appoint Head of EDI Delayed due to need to confirm budget | Assistant Director of Insight, Engagement & Fundraising - DICE |  | 31/03/2024 |
|  |  |  | Review of the current process for developing Equality Impact Assessments around service change, engagement and consultation. | Assistant Director of Insight, Engagement & Fundraising - DICE |  | 31/03/2024 In progress |
|  |  |  | Robust policies and processes to be in place for Impact Assessment going forward. | Assistant Director of Insight, Engagement & Fundraising - DICE |  | 30/06/2024 In progress |
|  |  |  | Roll out Impact Assessment process across organisation. | Assistant Director of Insight, Engagement & Fundraising - DICE |  | 30/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) Advice on Equality Impact Assessment and then wider Impact Assessments available across organisation supported by robust policies and procedures, overseen by Strategic Equality Group. |  |  | Gaps in assurance (What additional assurances should we seek?) Participation from across organisation in Strategic Equality Group. |  |  |  |
| Additional Comments / Progress Notes 19/01/2024: Reviewed – no change currently |  |  |  |  |  |  |

| Datix ID Number: 1762 Health & Care Standard: |  |  | HBR Ref Number: 53 Risk Target Date: 30/09/2024 |  | Current Risk Rating 5 x 3 = 15 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient, and delivers the best possible outcomes for people |  | BAF Ref: 2.1 | Director Lead: Hazel Lloyd, Director of Corporate Governance Assuring Committee: Health Board (Welsh Language Group) |  |  |  |
| Risk: Welsh Language Standards Failure to fully comply with all the requirements of the Welsh Language Standards, as they apply to the University Health Board. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 3 = 15 Current: 5 x 3 = 15 Target: 3 x 3 = 9 |  |  | Rationale for current score: As a consequence of an internal assessment of the Standards and their impact on the UHB, it is recognised that the Health Board will not be fully compliant with all applicable Standards. This position has been confirmed/verified via an independent baseline assessment. |  |  |  |
| Level of Control = 60% |  |  | Rationale for target score: Working through its related improvement plan the likelihood of noncompliance will reduce as awareness and staff training in response to the Standards, is raised. |  |  |  |
| Date added to the HB risk register November 2018 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - An independent baseline assessment of the Health Board’s position against the Standards has been undertaken. This is in addition to the Health Board’s own self-assessment. - Work to implement the recommendations contained within the above baseline assessment has commenced. - An online staff Welsh Language Skills Survey has been launched. - Close constructive working relationships are in place with the Welsh Language Commissioner’s Office - Strong networks are in place amongst WLO across NHS Wales to inform learning and development of responses to the Standards. - Proactive communication and marketing activity is being undertaken across the Health Board to raise awareness of Welsh language compliance, customer service standards and training opportunities. - Meetings of the Welsh Language Standards Delivery Group have recommenced (March 2022) |  |  | Action | Lead |  | Deadline |
|  |  |  | Recruit to current vacancy within the Welsh language Translation Team. | Welsh Language Officer |  | 30/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - Compliance with Statutory requirements outlined in Welsh Language Act and related Standards. - Meetings with the Welsh Language Commissioner. - Self-Assessment against the requirements of More Than Just Words. - Production of an Annual Report. |  |  | Gaps in assurance (What additional assurances should we seek?) Formal and regular reporting to the Board will recommence with the production of the next annual report. |  |  |  |
| Additional Comments / Progress Notes Dec 2023: The long-standing vacancy within the Translation Team has now been filled, with a substantive appointment being made with effect from 01/12/2023. However a further translator has now handed in their notice and will leave the Team on 02/01/2024. A recruitment exercise to fill this post is now underway. March 2024: A recruitment exercise to fill the vacant Translator position was unsuccessful. The JD, Spec and advert will now be reviewed, and a second exercise undertaken later in the year. May 2024: No further Update at this time June 2024: No further update at this time |  |  |  |  |  |  |

| Datix ID Number: 1587 Health & Care Standard: |  |  | HBR Ref Number: 61 Risk Target Date: TBC |  | Current Risk Rating 4 X 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Planned Care |  | BAF Ref: 2.5 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Quality and Safety Committee |  |  |  |
| Risk: Paediatric dental GA (General Anaesthetics)/Sedation services provided under contract from Parkway Clinic, Swansea. Medical Safety risk as GA are performed on children outside of an acute hospital setting. Repatriation of service to acute site delayed due to theatre capacity which means the health board continues to commission services for delivery outside of national guidance (WHC 2018-09). There is also an associated risk in that the diagnosing clinician does not deliver the care to the patient. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 3 = 15 Current: 4 x 4 = 16 Target: 4 x 2 = 8 |  |  | Rationale for current score: There is no immediate access to crash team/ICU facilities in in Parkway Clinic – the client group are undergoing G/A/sedation. Paediatric GA/Sedation services provided under contract from Parkway Clinic, Swansea continue due to lack of capacity for these patients to be accommodated in Secondary Care. |  |  |  |
| Level of Control = 60% |  |  | Rationale for target score: Relocation of the paediatric GA service [provided by Parkway Clinic] to a hospital site being treated as a priority. |  |  |  |
| Date added to the HB risk register 4th July 2018 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| Consultant Anaesthetist present for every General Anaesthetic clinic. Assurance Documentation supplied by Parkway Clinic including confirmation of arrangements in place with WAST and Morriston Hospital for transfer and treatment of patients New care pathway implemented - no direct referrals to provider for GA. Multi-drug sedation ceased from Sep 2018 in line with WHC 2018 009 Revised SLA/Service Specification HIW Inspection Visit Documentation provided to HB All extended GA cases require approval from paediatric specialist prior to treatment |  |  | Action | Lead |  | Deadline |
|  |  |  | Include transfer of services from Parkway on new theatre programme. | Associate Service Group Director (Surgery) |  | TBC |
| Assurances (How do we know if the things we are doing are having an impact?) RMC collate referral and treatment outcome data for review by Paediatric Specialist Regular clinical meeting arranged with Parkway to discuss individual cases/concerns Regular clinical/ management meeting for CDS/primary care management team to discuss service pathway /concerns/issues arising Roll out of new pathway to encompass urgent referrals |  |  | Gaps in assurance (What additional assurances should we seek?) Deputy COO led Task & Finish Group is no longer in place – it will need to be re-established to progress transfer when theatre capacity is agreed. Pressures on the POW special care dental GA list and this service is considered alongside any plans for the Parkway contract. |  |  |  |
| Additional Comments / Progress Notes 18/06/2024: Risk action refreshed. |  |  |  |  |  |  |

| Datix ID Number: 1605 Health & Care Standard: |  |  | HBR Ref Number: 63 Risk Target Date: 31/12/2024 | Current Risk Rating 4 X 5 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Maternity Services |  | BAF Ref: 2.8 | Director Lead: Gareth Howells, Executive Director of Nursing and Christine Morrell, Director of Therapies & Health Sciences Assuring Committee: Quality and Safety Committee |  |  |  |
| Risk: Screening for Fetal Growth Assessment in line with Gap-Grow (G&G). There is not enough Ultrasound scanning & clinic capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme, which states serial ultrasound growth scans should be performed at three weekly intervals. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy) HIE, where a fetus is growth restricted (Intrauterine Growth Restriction - IUGR) and/or small for gestational age fetus (SGA). |  |  | Date last reviewed: June 2024 |  |  |  |
|  |  |  | Rationale for current score: Current score of 20 is 4 (consequence) x 5 (likelihood). Consequence score of 4 calculated due to the governance and assurance – non-compliance with national standards with significant risk if unresolved and likelihood of 5 as expected to happen daily/>50%. The service is unable to provide third trimester scans at three weekly intervals in line with the Perinatal Institute recommendations. |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 3 = 12 Current: 4 x 5 = 20 Target: 3 x 4 = 12 |  |  |  |  |  |  |
| Level of Control = 60% |  |  |  |  |  |  |
| Date added to the HB risk register 1st August 2019 |  |  | Rationale for target score: When the service is able to provide third trimester ultrasound scan in line with GAP recommendations we will be providing care in line with evidence based best national practice as mandated by Welsh Government. Risk Target Date indicates when outcome of potential scanning/review capacity solutions anticipated. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| All staff are required to complete the GAP GROW eLearning on an annual basis. Compliance is monitored via the Training & Education forum. A local policy to scan women 4 weekly is in place. Four qualified midwifery sonographers and a midwifery sonography lead who provides training are in place. Lead sonographers created a governance process for the review of scan images of babies born with a birth weight centile under 10th centile to identify themes and trends within the department and areas for quality improvement. |  |  | Action |  | Lead | Deadline |
|  |  |  | Achieved 85% Gap Grow training compliance at end March 2024. Target of 95% revised for achievement by end August 2024. |  | CPD Midwives & Deputy Head of Midwifery | 31/08/2024 |
|  |  |  | Business case written, including administrative support for midwife sonographer clinics to be secured to ensure streamlined service - currently in circulation for comment with aim of discussion at Senior Management Team by revised date of end of August 2024. |  | Maternity service business manager | 30/08/2024 |
|  |  |  | Follow up meeting to discuss scanning & review capacity |  | HOM, Divisional Manager, Midwifery Sonographer lead & Lead for Sonography Department | 04/07/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) Target 95% Gap Grow training compliance by End November 2023 originally – was 85% at June 2024. Aim is the provision of serial ultrasound scans on a three weekly schedule in accordance with the recommendations from the Perinatal Institute. (Currently the provision of serial ultrasound scans is provided on a four weekly schedule.) The detection rate of IUGR/SGA will increase leading to improved antenatal management plans and intrapartum planning. We will report a reduced rate of stillbirth and/or neonatal mortality/morbidity with improved management of IUGR/SGA babies. The administration support for the service will be fully functional. Lead Sonographers for Singleton and Neath and Lead Midwife sonographer have developed a governance review group to meet monthly to review all ultrasound scan images where there was a baby born under the 10th centile to identify themes and learning for quality improvement. |  |  | Gaps in assurance (What additional assurances should we seek?) Assurance of maintaining a sustainable third trimester ultrasound service. The provision of serial ultrasound scans on a three weekly schedule in accordance with the recommendations from the Perinatal Institute. (Currently the provision of serial ultrasound scans is provided on a four weekly schedule.) |  |  |  |
| Additional Comments / Progress Notes 24/01/2023: Meeting held 10th January 2024 between Head of Midwifery, Divisional Manager, Midwifery Sonographer lead & Lead for Sonography Department (within Radiology) to discuss feasibility of more frequent clinics to review scans in addition to scanning capacity. Further discussion required, engaging with consultant colleagues and Radiology, regarding clinic capacity & provision. Follow up meeting after this on 6th March 2024. Re Gap-Grow 2: Meeting on 26/1/2024 to discuss whether business case required. 19/04/2024: Radiology Service Manager unable to attend scanning capacity meeting – to be rescheduled by end of May 2024. Implementation of Gap Grow 2.0 in place from w/c 15/04/2024. Gap Grow training Compliance 85% March 2024. Action to complete updated. 01/07/2024: Meeting with Radiology moved to 4th July 2024 to accommodate staff leave. New appointment to Professional Development Midwife post – she will focus on drive to improve compliance with Gap Grow training uptake by end of August 2024. |  |  |  |  |  |  |

| Datix ID Number: 2159 Health & Care Standard: |  |  | HBR Ref Number: 64 Risk Target Date: TBC | Current Risk Rating 4 X 4 = 16 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in safe and appropriate settings |  | BAF Ref: 3 | Director Lead: Darren Griffiths, Director of Finance & Performance Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Health & Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function within SBUHB to maintain legal and regulatory compliance for the workforce and for the sites across SBUHB. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 4 x 4 = 16 Target: 4 x 3 = 12 |  |  | Rationale for current score: The Health Board received 12 Health & Safety Executive (HSE) improvement notices during 2019-20 covering various Health & Safety legal breaches covering a range of areas. There is the potential for future multiple notices for not meeting legal requirements. Score reduced to 16. |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: Compliance with the notices and to have sufficient resources to implement a sustainable health and safety provision to support the legal requirements of the Health Board and demonstrate that suitable resources are in place to undertake the roles and responsibilities of the department, also to undertake suitable and sufficient training, provide corporate overview/audit to ensure practices are being employed in the workplace. |  |  |  |
| Date added to the HB risk register September 2019 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Assistant Director of Health and Safety in post to support strengthening and develop the H&S function to support the organisation. Business case submitted for additional resources. - Health and Safety Operational Group and the Health and Safety Committee monitor compliance. Refreshed the Fire Safety Group with additional controls in place. - Fire risk assessments are being prioritised with temporary additional resources put in place in March 2021 to reduce the number of FRA overdue. - Fire training in place and fire wardens in place - Fire risk assessment schedule in place for the next 12 months to maintain 100% compliance of completion and is regularly reviewed |  |  | Action |  | Lead | Deadline |
|  |  |  | It has been agreed to identify posts to progress recruitment on a phased approach over the next 12/24 months. This will be dependent upon availability of funding. |  | Assistant Director of H&S | Closed |
|  |  |  | Review the staffing structure within the Health & Safety function |  | Assistant Director of H&S | 30/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - Monitoring through the appropriate group/committees (H&S committee) to receive assurance and or identify gaps for key compliance and adherence to applicable legislation. - Site visits/tours to identify compliance and gaps in compliances. |  |  | Gaps in assurance (What additional assurances should we seek?) Agreement of funding for resources identified in business case to implement structure in business case by Q2/3 2022/23 financial year. |  |  |  |
| Additional Comments / Progress Notes 02/07/2024: Further increases in staff numbers are unlikely currently, so we are reviewing the way the function is delivered. |  |  |  |  |  |  |

| Datix ID Number: 1834 Health & Care Standard: |  |  |  | HBR Ref Number: 66 Risk Target Date: TBC |  | Current Risk Rating 5 X 3 = 15 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Cancer Care |  |  | BAF Ref: 2.6 | Director Lead: Raj Krishnan, Acting Executive Medical Director Assuring Committee: Quality and Safety Committee |  |  |  |  |  |
| Risk: Access to SACT (Cancer Services) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. |  |  |  | Date last reviewed: June 2024 |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 5 = 25 Current: 5 x 3 = 15 Target: 2 x 2 = 4 |  |  |  | Rationale for current score: Risk was reduced to 12 in June 2023. Further feedback showed that this was not sustained and that there were still significant workforce challenges in CDU and PTS so the risk was returned to 15. |  |  |  |  |  |
| Level of Control = |  |  |  |  |  |  |  |  |  |
| Date added to the HB risk register 30/11/2019 |  |  |  | Rationale for target score: Reduced delays in treatment will reduce risk of harm. |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  | Mitigating actions (What more should we do?) |  |  |  |  |  |
| Review of CDU by improvement science practitioner was completed in 2020. Resulted in change to booking processes to streamline booking process and deferral. Review of scheduling by staff to ensure all chairs used appropriately. Business case endorsed by CEO for shift of capacity to home care to be considered by the Management Board A Daily scrutinizing process in progress to micro manage individual cases, deferrals etc. Changes made to prescribing & authorising processes to improve workflow for PTS reducing potential delays to supply and administration of treatment. Responsibility for checking bisphosphonate prescriptions in CDU moved to nursing staff to free up Pharmacy capacity allowing them to focus on key clinical tasks within Pharmacy. Joint project with Nuclear Medicine to streamline pathways and prioritise SACT patients appropriately halved the average time waiting for MUGA/EDTA tests required before starting SACT. Increased homecare capacity Adopted principles from UK SACT board publication: General Principles to Support Systemic anti-Cancer Therapy Aseptic Pressures September 2023 |  |  |  | Action |  | Lead |  |  | Deadline |
|  |  |  |  | A demand and capacity options paper is being prepared within the service and will be presented to Senior Management Team. Draft completed, further evidence required for SMT presentation July 2024. |  | Interim Divisional Manager (Cancer) |  |  | 30/07/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) Additional funding agreed to support increase in nurse establishment to appropriately staff the unit during its main opening hours. Additional scheduling staff also agreed. This funding has been utilised but with further increase demand further funding for Pharmacy and Nursing would be required Pre-Assessment process has been separated from start date in an attempt to fill deferral slots at short notice where possible. Improved communication between MDT to streamline booking and deferral process. Continue to monitor patient experience via friends and family in conjunction with the Welsh Cancer Patient Experience Survey results under our PTR procedures. Monitoring our waiting times against new SACT metrics, which is a measure based on treatment intent and is no longer reported as average waiting time so is more linked to expected outcomes etc. This performance metric is included in our Cancer Performance report we send to WG and Management Board and internally via governance arrangements with NPTSSG where Oncology services sit. SBU Capacity Task and Finish group meeting monthly to analysis demand and capacity gap. Common themes for delays will continue to be identified and analysed each month. A quarterly report will be provided to the SACT, Consultant meeting and Division Business meeting to inform of the outcome Main breach causes are due to CDU capacity and SACT booking delays. Quarterly reports demonstrate this trend. Further work being done on new ways of working and possible increase in workforce. Breaches by priority for last 2 months. April: 64% patients breached P2 (average number of days over is 4) 56% patients breached P3 (average number of days over is 3) May: 67% patients breached P2 (average number of days over is 9) 82% patients breached P3 (average number of days over is 4) Previous months:; Oct23; Nov23; Dec23; Jan24; Feb24; Mar24. Overall average wait beyond breach date (days); 8; 7; 6; 10; 7; 6. P2 average wait beyond breach date (days); 7; 7; 7; 11; 7; 6. P3 average wait beyond breach date (days); 7; 7; 5; 9; n/a; 5. | Gaps in assurance (What additional assurances should we seek?) Capital & Revenue assumptions & resources for second business case for increasing chair capacity in 2022/23 to meet increased demand. No change to this area which is why the risk remains at 15. A demand and capacity options paper is being prepared within the service and will be presented to Senior Management Team March 2024. Workforce within Pharmacy remains an issue to continue with current capacity and increase in demand. |  |  |  |  |  |
| Additional Comments / Progress Notes 10.04.2024: A visit is planned in July/August 2024 to Christie Cancer Centre in Manchester where stakeholders will share best practice 19/06/2024: Ongoing work by ChemoCare team to update the critical expiry on each individual regimen before extended critical test expiries can be utilised. When the updated blood test expiries are introduced, this data collection will take place again to ensure no increase in re-bleed rate on day of treatment in CDU, or any other negative impacts. Continuation of focus group discussions to create an elective admission pathway for patients treated electively on Ward 12. Data collected by SACT QIP in accordance with Ward 12 booking clerk show all patients not prepared correctly for admission were from Haematology.) Work underway to move to fully paperless drug administration; the ChemoCare team will work with senior nurses to develop an SOP, give training and provide support as staff adapt to new way of working. Although it may reduce efficiency initially once staff are familiar with the system it will release some capacity in both CDU and Pharmacy. For example, no more filing or looking for paper copies to answer queries and the percentage of regimens marked as given should be 100%, reducing the need for Pharmacy to query if previous cycles were given when clinically checking. This will also help to improve the quality of record keeping and meet the requirements of Infection Control to reduce the paper burden on the unit. Training started early February but due to staff shortages, limited opportunity to train nurses. Explore removing the booking form from Hywel Dda UHB. |  |  |  |  |  |  |  |  |  |
| Datix ID Number: 1418 Health & Care Standard: |  |  |  | HBR Ref Number: 69 Risk Target Date: See Target Rationale |  |  | Current Risk Rating 5 X 4 = 20 |  |  |
| Objective: Children & Young People Services |  |  | BAF Ref: 2.7 | Director Lead: Deb Lewis, Chief Operating Officer Supporting Director: Gareth Howells, Executive Director of Nursing Assuring Committee: Quality & Safety Committee |  |  |  |  |  |
| Risk: Risk of issues related to adolescent patients being admitted to Adult MH inpatient wards- Inappropriate settings resulting in 'Safeguarding Issues' The WG has requested that HBs identify Secondary Care in -patient facilities for the care of adolescents- in Swansea Bay University Health Board Ward F NPT hospital is the dedicated receiving facility with one bed identified. |  |  |  | Date last reviewed: June 2024 |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 2 x 3 = 6 Current:5 x 4 = 20 Target: 2 x 3 = 6 |  |  |  | Rationale for current score: Every health board is required to have an admission facility for adolescent Mental Health patients. Whilst ward F has been identified as the single point of access in SBU and a dedicated bed is ring-fenced for adolescent admissions it is a mixed sex adult ward. Therefore the facilities are less than ideal for young patients in crisis. |  |  |  |  |  |
| Level of Control = |  |  |  |  |  |  |  |  |  |
| Date added to the HB risk register 27/02/2020 |  |  |  | Rationale for target score: The longer term aim for the Health Board remains to create an admission facility for adolescent Mental Health patients but this will not be possible until the new Adult Inpatient Unit is built. |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  | Mitigating actions (What more should we do?) |  |  |  |  |  |
| Safeguarding Training for Staff, Joint protocol with Cwm Taf LHB [CAMHS] currently subject to review, Local SBUHB policy on providing care to young people in this environment. This includes the requirement for all such patients on admission to be subject to Level 3 Safe and Supportive observations. Only Adolescents within 16-18 age range are admitted to the adult ward. The health board works with CAMHS to make sure that the length of stay is as short as possible. |  |  |  | Action | Lead |  |  | Deadline |  |
|  |  |  |  | Next service group review of effectiveness of current controls. | MH&LD Head of Operations & Clinical Directors |  |  | 30/09/2024 |  |
| Assurances (How do we know if the things we are doing are having an impact?) Individual Rooms with en Suite Facilities, Joint working with CAMHS, monitoring of staff training, Monitoring of admissions by the MH&LD SG Legislation Committee of the Health Board. The ongoing issues with the risks presented by the use of this has recently been raised at an all Wales level with Welsh Government and a formal review is anticipated. The Service Group continues to flag the risk particularly in light of Ward F being identified as the SPOA for AMH in the Health Board which has resulted in an increase in acuity and a greater concentration of individuals who are experiencing the early crisis of admission - this has served to increase the already identified risks for young people in the environment. |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |  |  |
| Additional Comments / Progress Notes 12/02/2024: Recent out of hours CAMHS admission to ward F and was then transferred a few days later to the CAMHS regional inpatient unit in CTMUHB. After reviewing the ongoing issues and increased acuity on ward F for the previous 12 months it is agreed that this risk is scored correctly, but will continue to be closely monitored. 08/05/2024: Reviewed by COO and no change currently. 13/06/2024: After reviewing the ongoing issues and increased acuity on ward F for the previous 18 months it is agreed that this risk is scored correctly, but will continue to be closely monitored. |  |  |  |  |  |  |  |  |  |

| Datix ID Number: 2522 Health & Care Standard: |  |  | HBR Ref Number: 75 Risk Target Date: TBC |  | Current Risk Rating 5 x 2 = 10 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient, and delivers the best possible outcomes for people |  | BAF Ref: 2 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance and Finance Committee |  |  |  |
| Risk: Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 2 = 10 Target: 5 x 1 = 5 |  |  | Rationale for current score: Risk reflects transition to business as usual as part of living with Covid strategy. BCP plans in place. There is still fluctuation in patient numbers and new variants continue to emerge so score maintained as watching brief. |  |  |  |
| Level of Control = 25% |  |  | Rationale for target score: The strategy of moving towards living with Covid will eventually lower the risk level to target. |  |  |  |
| Date added to the HB risk register May 2021 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Sites have business continuity plans and the impact of one site being overwhelmed by COVID demand has been reviewed. - Monitoring of associated risks has been being transferred to appropriate forums such as UEC Board, Elective Care Board and Nosocomial Group with overall oversight by Management Board. - Ongoing surveillance of epidemiology data for early warning and further change to risk level via live Covid dashboard. |  |  | Action | Lead |  | Deadline |
|  |  |  | Periodic review of risk | COO |  | See Notes Below |
| Assurances (How do we know if the things we are doing are having an impact?) Monitored via Management Board for early warning signs. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 03/11/2023: Consideration currently being given to replacement of this risk with fresh entry on wider organisational business continuity arrangements |  |  |  |  |  |  |

| Datix ID Number: 1832 Health & Care Standard: |  |  | HBR Ref Number: 80 Risk Target Date: 30/09/2024 |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Urgent & Emergency Care |  | BAF Ref: 2.4 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Quality & Safety Committee |  |  |  |
| Risk: Transfer of Clinical Optimised Patients A deficit in the availability of appropriate community / domiciliary care results in unacceptable delays in discharging patients from acute hospital beds. As a result, patients can decompensate and never gain the independence that could have been available from an early discharge. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 2 = 8 |  |  | Rationale for current score: - Sustained levels of clinically optimised patients (COPs) leading to overcrowding within ED, use of inappropriate or overuse of decant capacity in ED and delays in accessing medical bed capacity, clearly emerged as themes. - Constraints in relation to all patient flows out of Morriston to a more appropriate clinical setting, identified and included in an expanded risk. - Delay in discharge for clinically optimised patients can result in deterioration of their condition. |  |  |  |
| Level of Control = 25% |  |  |  |  |  |  |
|  |  |  | Rationale for target score: Targeted reduction of Clinically Optimised patients remains a priority for the HB in order to minimise risk of avoidable harm to patients within the HB and in the wider community. |  |  |  |
| Date added to the risk register May 2021 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - One of the measures under targeted intervention is to see a reduction in pathway of care delays, which specifically supports the reduction in the number of clinically optimised patients. - Review is undertaken on a patient by patient basis – with explicit action agreed in order to progress transfer to appropriate clinical setting. - Critical constricts in relation to access/time delays for social workers and assessment for package of care and social placement - The health board continues to procure 63 additional care home and hospital beds to provide additional discharge capacity. - Clinically optimised patients (COP) have been cohorted into the available capacity at Singleton Hospital to ensure that their needs can be met more appropriately. This has reduced the number of COPs at Morriston Hospital. Weekly escalation meetings are held with health and social service colleagues to ensure the requirements of the patients are reviewed and patients are pulled through the system where possible. |  |  | Action | Lead |  | Deadline |
|  |  |  | Paper highlighting outputs and lessons learned from the implementation of the Patient Assessment Team to be considered by UEC Board to inform further actions / next steps. | Medical Director / HON (Transformation) |  | 31/07/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) - Patient level dashboard allows breakdown by delay type - Close management of utilization of additional care home beds. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments 09/10/2023: IDH pilot completed, data being analysed, initial review shows a positive impact on turning patients around at the front door. Roll out to be completed in Q3. 13/02/2024: Action completed: Patient Assignment Team (PAT) element of an Integrated Discharge Hub is in place. There are further potential elements that have not be implemented, but are to be considered next – a Ward-based facilitation team and a Complex Discharge Team. A paper will submitted for consideration by the UEC Board (currently planned for 6th March). It will highlight the outputs and lessons learned from the implementation of a PAT in order to support discussion of next steps including consideration of the additional teams not currently in place. 08/05/2024: This is integral component of the HB TI recovery plan |  |  |  |  |  |  |

| Datix ID Number: 2788 Health Care Standards: |  |  | HBR Ref Number: 81 Risk Target Date: 30/10/2024 |  | Current Risk Rating 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Maternity Services |  | BAF Ref: 2.8 | Director Lead: Gareth Howells, Executive Director of Nursing Assuring Committee: Quality & Safety Committee For Information: Workforce OD & Digital Committee |  |  |  |
| Risk: Critical staffing levels – Midwifery Unplanned absences resulting from long and short-term sickness, alongside maternity leave, have resulted in critical staffing levels, which undermine the ability to maintain the full range of expected services safely, increasing the potential for harm, poor patient outcomes and/or choice of birthplace. Poor service quality or reduction in services could impact on organisational reputation. |  |  | Date last reviewed: June 2024 |  |  |  |
|  |  |  | Rationale for current score: The vacancy position has improved further and for Band 5 & 6 registered staff there are no vacancies. Some aspects of service provision continue to be suspended and this is subject to review currently. In view of this the risk was reduced from 25 to 20 initially. Whilst the service is now over-established with registered midwives, the score remains as high risk (20) due to unregistered vacancies (which we are recruiting to) and unavailability (due to parenting leave and sickness). There are improved numbers of registered midwives per shift with most shifts achieving the required 14 midwives. Additional staff required in AAU to ensure two on duty at all times. |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 5 x 4 = 20 Target: 4 x 4 = 16 |  |  |  |  |  |  |
| Level of Control = % |  |  | Rationale for target score: It is intended that through actions currently identified to address vacancies we can reinstate services fully and reduce the likelihood of the need to suspend elements further. |  |  |  |
| Date added to the risk register 12/10/2021 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Service Group Nurse Director chairs fortnightly roster scrutiny meetings to ensure effective deployment of staff. - All midwives are working at the hours they require up to full time. - Specialist midwives and management redeployed to support clinical care as required - Birth rate plus Intrapartum acuity tool completed 4 hourly to guide safe service provision and escalation - Escalation meeting held daily during the week to review rotas and reallocate staff as required chaired by Head of Midwifery - Morning safety huddle for community midwifery teams - Morning safety huddle for obstetric unit generates RAG-rated daily acuity and shares this with the Service Group for its daily meeting. - Additional shifts offered via Bank, additional hours and overtime at enhanced rates - Utilisation of off-contract midwifery agency authorised by Executive Director of Nursing - Open advert for recruitment on TRAC (recruitment system) - On-Call Manager Rota in place. - Continue to suspend services in the FMU (Freestanding Midwifery Unit) at Neath Port Talbot Hospital. - International recruitment campaign initiated with MEDACS. - Offer of additional support worker shifts particularly in the postnatal area for additional support for women - Maternity Care Assistance (MCA) role in place to support Midwives in providing care in women and their families. - Regular communication with stakeholders includes: Early warnings to Welsh Government; Verbal and formal communication with Llais; Internal communications on home births, RCM updates; weekly staff briefings and bulletins. - Maternity Services Improvement & Assurance Board has been instated, meeting fortnightly, chaired by NPTS Nurse Director. This will report into the Midwifery & Neonatal Service Performance Board in place chaired by EDON |  |  | Action | Lead |  | Deadline |
|  |  |  | Advertising for Community Team Leaders (Band 7) to support plans to re-open services in Neath Port Talbot. Three in post, but further interviews taking place in April with expected start end June. | Community Matron / Consultant Midwife |  | Complete |
|  |  |  | Recruitment of 5 WTE (whole time equivalent) Band 2 HCA (health care assistant) positions at Singleton: Some staff in post – start dates expected for others in May. | Obstetric Matron |  | Complete |
|  |  |  | Gateway review in place in relation to reinstatement of community services, first point is recruitment of band 7 community team leaders. Paper to go to Management Board. | HOM |  | Complete |
|  |  |  | Seventeen newly qualified midwives through streamlining to commence employment form October 2024 onwards. Expect to be in post by December 2024. | HOM |  | 31/12/2024 |
|  |  |  | Business case to support implementation of BSOTS (Birmingham Symptom Specific Obstetric Triage System) in the Ante Natal Assessment Unit to be developed. The service plans to implement a new AAU pathway and documentation process. | DHOM |  | 30/09/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) The following assurance mechanisms in place currently: Birth-rate Plus Intrapartum acuity tool completed 4 hourly Daily staff escalation meetings chaired by Head of Midwifery which considers sickness & other absences and daily review of safety and quality outcomes. The Group Head of Quality Safety & Risk is supporting daily oversight of Datix incidents. The following red flag events are monitored: • Delayed or cancelled elective caesarean sections; • Missed or delayed care incidents; • Delayed or cancelled induction of labour; • Delay of 2 hours or more between admission for induction of labour and beginning of process; • Delay of 30 minute or more between presentation and triage. Birthrate Plus assessment outcome (last internal assessment Oct 2023 – now compliant) |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 01/07/2024: Action completed: Gateway review in place in relation to reinstatement of community services, first point is recruitment of band 7 community team leaders. Paper has been to Management Board. Following discussion there issues have been raised by staff side requiring further consideration. This is subject to review currently by the service and Executive Team. Action completed: Recruitment of 5 WTE (whole time equivalent) Band 2 HCA (health care assistant) positions at Singleton: All five now in post. Action Completed: Community Team Leaders (Band 7) to support plans to re-open services in Neath Port Talbot. All in post. |  |  |  |  |  |  |

| Datix ID Number: 2561 Health & Care Standard: |  |  | HBR Ref Number: 85 Risk Target Date: 31/03/2025 | Current Risk Rating 4 x 5 = 20 |
| --- | --- | --- | --- | --- |
| Objective: Children & Young People Services |  | BAF Ref: 2.7 | Director Lead: Christine Morrell, Director of Therapies & Health Sciences Assuring Committee: Quality & Safety Committee |  |
| Risk: Non-Compliance with ALNET Act There are risks to the Health Board’s ability to meet its statutory duties and establish the effective collaborative arrangements required by the ALN Act, which is being implemented through a phased approach. This risk is caused by: - Lack of staff resource needed to carry out the additional work needed to comply with the ALN Act for operational services, especially those in the PCST Service Group. - Implementation of the Act for those of above compulsory school age (post-16) commenced in September 2023. This presents risks because of gaps in service provision. - Multiple pressures for operational services are impacting on capacity / engagement of leads within impacted services to progress tasks that need to be undertaken to mitigate the risks and current vacancy in ALN Project Manager post. - Issues with Data Quality due to pressure on ALN and Service administration teams, process issues and absence of a robust system to enable data capture and analysis. This means that accurate and up-to-date data regarding the Health Board’s compliance is not available. Potential consequences of this risk are: non-compliance with statutory duties, parent / carer and young peoples' dissatisfaction leading to complaints. Educational Tribunals and Judicial Reviews (this is new legislation with many points of ambiguity and is highly likely to be legally ‘tested’); reputational impact; and children failing to access the multi-agency support that they need with their learning needs, leading to poor outcomes. |  |  | Date last reviewed: June 2024 |  |
|  |  |  | Rationale for current score: Risk score reflects that while controls are in place, there are multiple areas of risks (relating to compliance with legislation; governance and assurance; workforce and OD; and sustainable services); and high probability (especially given multiple risk areas) of at least one of these areas of risk being realised. Caused by implementation timetable for the ALN Act, slippage against plan and need for strengthened governance (as described in ‘Risk’ section). |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 5 = 25 Current: 4 x 5 = 20 Target: 2 x 3 = 6 |  |  | Rationale for target score: As the ALN Act is new legislation, there remains some ongoing likelihood of risk events during the initial phases of implementation, though with lessened consequences as a result of mitigating actions. |  |
| Level of Control = |  |  |  |  |
| Date added to the HB risk register 14/05/2022 |  |  |  |  |

| Controls (What are we currently doing about the risk?) | Mitigating actions (What more should we do?) |  |  |
| --- | --- | --- | --- |
| - Progressing the necessary work within an appropriate structure (see under ‘ACTIONS’) are constrained by financial and/or service delivery pressures. - DECLO (Designated Educational Clinical Lead Officer) is in post - this is a statutory requirement. - Health Board ALN Steering Group has been established, with governance structure in place involving the ALN Operational Group working under the governance of this - Operational processes through which the Health Board fulfils its statutory duties under the ALN Act are in place. - Ongoing collaboration between the DECLOs at a national level ensures a broadly consistent approach across Wales to how Health Boards fulfil their requirements under the ALN Act. Some ongoing differences remain because of different Local Authority approaches, through Welsh Government have formed a national group to support improved consistency around Health-Education collaboration through the ALN Act. - Regarding demand / capacity and staffing resource challenges, WG has a phased implementation timetable that has recently been extended from summer 2024 to summer 2025. From summer 2025, the Act will be fully in ‘delivery as usual’. The phased implementation offers partial short-term mitigation of the risks. - Awareness has been raised at Board level through Development session and bi-monthly updates are provided to the Patient Safety & Compliance Group. - Welsh Government have been engaging with the Designated Education Clinical Lead Officers on a national basis regarding ALN key performance indicators and compliance. A Welsh Health Circular requiring regular reporting against statutory key performance indicators is anticipated in the coming months. - Audit and Assurance Services have conducted an audit of the Health Board in relation to the ALN Act, which provided an overall ‘limited assurance’ rating. Management responses have been developed and a work plan is in place, monitored through the ALN Steering Group, to address issues identified in the audit. | Action | Lead | Deadline |
|  | Requirement to establish data infrastructure to provide assurance regarding HB compliance with statutory duties | DECLO & Director of Digital | 30/09/2024 |
|  | Develop and implement administrative operational model to support accurate data capture | DECLO | 30/09/2024 |
|  | Effective, realistic operational processes - Activity to ensure operational processes through which statutory duties are fulfilled balance statutory duties and the ethos of the ALN Act with the need to deliver requirements without additional resource. | DECLO | 20/12/2024 |
|  | Securing longer-term administrative and project management support needed to mitigate risks | DoTHS | 30/09/2024 |
|  | Progress action plan in relation to ALN audit | DECLO | 31/03/2025 |
| Assurances (How do we know if the things we are doing are having an impact?) - There is regular reporting in respect of the ALN Act through the Patient Safety and Compliance Group. - ALN Steering Board has been established, ensuring oversight at a senior level within all impacted operational and corporate areas. - DECLO meets regularly with ADOTHS / DoTHS of the 3 health boards of South-West and Mid Wales for update and assurance. - National ALN Reform Steering Group has been formed and will include Health representation (SBU Deputy DOTHS). This will provide a national forum for consideration of risks. | Gaps in assurance (What additional assurances should we seek? - Extent of gap in staffing resource (gap between work required and capacity available) has been provisionally quantified, but data is imperfect and there remains some uncertainty. This is in a context where demands will increase significantly over the next year. |  |  |
| Additional Comments / Progress Notes 12/06/2024: Deadlines have been added to the actions, ‘Requirement to establish data infrastructure to provide assurance regarding HB compliance with statutory duties’ and ‘Develop and implement administrative operational model to support accurate data capture’. The deadline for both actions is 30/09/2024. Support of digital services to develop a data infrastructure has been secured, and it is anticipated that these deadlines are achievable. Once a data structure is in place, a period of data will need to be analysed in order to recalibrate the Health Board’s risk regarding non-statutory compliance. For the action, ‘Securing longer-term administrative and project management support needed to mitigate risks’, deadline has been moved to September 2024. Resource has been secured for Therapies and Health Sciences to enable this action to be progressed and recruitment activity is underway, but is unlikely to have been completed before September 2024. For the action ‘Progress action plan in relation to ALN audit’, deadline has been moved to March 2025. The current gap in project management support is impacting the timeliness with which actions relating to the audit are being progressed and slippage against the completion of a number of management actions is anticipated. This issue is being brought to the attention of Audit Committee separately for oversight. |  |  |  |

| Datix ID Number: 3071 Health Care Standards: |  |  | HBR Ref Number: 89 Target Risk Date: 31/07/2024 | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- |
| Objective: Primary & Community Care |  | BAF Ref: 2.2 | Director Lead: Gareth Howells, Executive Director of Nursing Supporting Director: Deb Lewis, Chief Operating Officer Assuring Committee: Quality & Safety Committee |  |  |
| Risk: Healthcare Nursing Staff Levels at HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the June 2022 HIW governance review. In addition there is no head room built into the Prison nursing establishment so periods of sickness, leave and study renders the roster short. |  |  | Date last reviewed: June 2024 |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 2 x 2 = 4 |  |  | Rationale for current score: Consequence major – unable to fully deliver on the recommendations of HIW due to low healthcare staffing numbers, further impacted during periods of sickness or absence as no headroom. Recommendations also raised in Prison & Probation Ombudsman reports. Likelihood expected – suboptimal care provided on a daily basis. |  |  |
| Level of Control = % |  |  | Rationale for target score: Consequence minor – With sufficient staffing numbers the prison will be able to deliver on HIW recommendations and fully implement the actions in the Health Delivery Plan. Likelihood unlikely – With full establishment and headroom, suboptimal care is less likely. |  |  |
| Date added to the risk register 30/11/2022 |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |
| Daily communication with the Governor about the availability and priority of healthcare nursing staff. Pharmacy technician role established – can administer drugs to support nursing establishment. Agreed that Health Care Support Workers to be 2nd checkers for CD drugs and to support substance withdrawal monitoring (awaiting accreditation). Bank and agency staff are used in a limited way, when skillset allows. E-roster implemented and scrutinised with regular reporting to Service Group Patient Safety & Compliance Group. Escalation for overtime and additional hours to fill shortfalls. |  |  | Action | Lead | Deadline |
|  |  |  | Further baseline assessment commencing in July 2024, led by MH Substance Misuse & Vulnerable Groups Division of WG. | Healthcare Lead | 30/09/2024 |
|  |  |  | Service Group are considering how it might reduce the risk and source additional resource | Service Group Director | 20/07/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) Prison feedback and complaint process Progress reporting on action plans through Service Group PS&C Group, and Health Board Q&S structures (via Patient Safety & Compliance Group). |  |  | Gaps in assurance (What additional assurances should we seek?) Implementation and reporting of clinical audits. Audit framework for HMP Swansea in development - Clinical Pathways/Audits and Health Promotion groups taking forward. |  |  |
| Additional Comments 19/06/2024: Awaiting a start date for the mental health and clinical substance misuse service review. Public Health Wales have provided support to undertake the Prison Health Needs Assessment this work commenced June 2024 and will conclude September 2024. The assessment will contain data in relation to prison population health need and services delivered. Actions completed: HCSW second checkers of CDs to be accredited externally; Fresh gap analysis to be undertaken to identify staffing shortfall and set out further proposals to address. The service group are reviewing all services within PCT. Prison Healthcare lead will meet with Finance for review of health services baseline and nursing headroom cost. Most recent cost is £298.037 for 26.9% Nursing Headroom of which approx. £36,544 has been invested from the service group. |  |  |  |  |  |

| Datix ID Number: 2796 Health Care Standards: |  |  | HBR Ref Number: 90 Target Risk Date: 30th April 2024 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The delivery of care is supported by innovative digital solutions |  | BAF Ref: 4 | Director Lead: Matt John, Director of Digital Assuring Committee: Workforce OD & Digital Committee |  |  |  |
| Risk: Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs), along with other health records requests for disclosure of personal data The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of subject access /access to health records requests received from requestors. The ICO have previously been involved with a number of breaches and complaints in this area and there is the potential for future enforcement action if significant improvements are not made. Misfiling and redaction are major issues for Health Records, IG and Health Professionals. SAR breaches have led to successful compensation claims and media interest. |  |  | Date last reviewed: June 2024 |  |  |  |
|  |  |  | Rationale for current score: C – The Health Board has a statutory requirement to comply with UK GDPR and Data Protection Act 2018. This includes compliance with an individual’s Right to Access their personal data. The Information Commissioner has the power to take enforcement action, including substantial monetary penalties, for non-compliance. A number of complaints regarding the handling of SARs within SBUHB have been highlighted previously in both the mainstream media and on social media, leading to a loss of trust in the Health Board with damage to staff and Health Board reputation. L- The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of SARs received from both patients and staff. There are inconsistent processes across the Health Board, with varying levels of robustness regarding legal compliance. The increased use of various digital applications has impacted the volume and complexity of content and the ability to retrieve the personal data required to comply with SARs. The process for ensuring information is appropriately reviewed and redacted by health professional within services has become far more complex and resource intensive increasing the likelihood of personal data breaches and/or non-compliance with legal timescales for disclosure. The ICO have previously been involved with a number of complaints in this area and there is an increased potential for future enforcement action if significant improvements are not made. There continues to be an increase in both the number and complexity of SARs received as data subjects become more aware of their rights and the mediums in which data are recorded expands. |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 4 = 16 Target: 4 x 2 = 8 |  |  |  |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: C – As above L – Additional resources would allow the organisation to make significant improvements to the process by which SARs are managed. Being able to adequately comply with legal requirements reduces the likelihood of enforcement action and fines from the ICO, as well as minimising the risk of reputational damage. |  |  |  |
| Date added to the risk register Jan 2023 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - New SAR (Subject Access Request) Working Group established in February 2024 - Prioritisation of workload - Revised SAR policy in place (to be reviewed & updated in line with Working Group actions) - Advice sought from Legal and Risk on complex cases - Escalating areas of concern to IGCAG (Information Governance & Cyber Assurance Group) |  |  | Action | Lead |  | Deadline |
|  |  |  | Undertake GAP analysis and develop action plan | Data Protection Officer |  | 31st July 2024 |
|  |  |  | Implement priority tasks outlined within the action plan within agreed timescales | Data Protection Officer |  | 31st March 2025 |
| Assurances (How do we know if the things we are doing are having an impact?) - Bi-monthly IGCAG chaired by SIRO (Senior Information Risk Owner) and attended by Deputy Caldicott Guardian and Data Protection Officer - Escalation reports from IGCAG to Management Board & Workforce OD & Digital Committee as required - IG governance structures in place with key roles and responsibilities established e.g. SIRO, Caldicott Guardian, DPO (Data Protection Officer) |  |  | Gaps in assurance (What additional assurances should we seek?) Recent internal audit identified the requirement to invest in resources to address gap in assurance. |  |  |  |
| Additional Comments / Progress Notes 09/10/2023 – SAR Lead starting date confirmed as the 30th October 2023. 16/11/2023 – SAR Policy approved by WODDC in October 2023. Previous action to review all SAR documentation amended to indicate re-establishment of SAR working Group to perform gap analysis. 08/02/2024 - First meeting of new SAR Working Group to take place on 8 February 2024. Terms of Reference have been agreed and an action plan is to be developed, approved and implemented with priority tasks to be given attention in the coming months. 10/05/2024 – Updated progress 2 to include entry: 08/05/24 - GAP analysis has been circulated for completion by membership of SAR Working Group to inform action plan. Comment added to reflect the above. |  |  |  |  |  |  |

| Datix ID Number: 3432 Health & Care Standard: |  |  | HBR Ref Number: 91 Risk Target Date: TBC |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Mental Health & Learning Disability Services |  | BAF Ref: 2.3 | Director Lead: Gareth Howells, Executive Director of Nursing Supporting Director: Hazel Lloyd, Director of Corporate Governance Assuring Committee: Quality and Safety Committee For Information: Mental Health Legislation Committee |  |  |  |
| Risk: Mental Capacity Act Assessments There is a risk that assessments under the Mental Capacity Act (MCA) are not undertaken and recorded as required. This is caused by: - There is no identified MCA structure or designated resource to support the implementation and compliance with MCA across the organisation - Recent DoLS (Deprivation of Liberty Safeguards) audits show that there are significant deficits in knowledge and awareness of the MCA in some areas, which could result in the Health Board failing to meet its statutory responsibilities. - Lack of funded budget for Health Board Level 2 and 3 training and a lack of coordination in the review and development of training content - No agreed structure for oversight and management of HB IMCA (Independent Mental Capacity Advocate) contract Where the UHB fails in its statutory duty to enact the MCA appropriately this could result in harm to vulnerable individuals, and/or unlawful deprivations of liberty, leading to litigation. Such cases could incur significant financial penalties, cause distress to staff members and patients, and risk damage to the organisations reputation. |  |  | Date last reviewed: June 2024 |  |  |  |
|  |  |  | Rationale for current score: - The implementation of the MCA is accountable to the Court of Protection, which is a higher-level court equivalent to the High Court. This means that decisions carry precedence and fines are considerably higher and often high profile. - There is a mixed approach to referral to the Court of Protection, and as such a need to improve the Governance structures around this. There is no current central system up to date with current court of Protection cases - There is no local agreed MCA Policy in place, although the MCA has associated guidance which provides advice on implementation - Standard operating procedures have been identified as necessary relating to elements required under the act, but there is a need for these to be centrally identified developed and managed. - It is difficult to access percentage compliance data with MCA training due to the ongoing challenges with ESR - This risk is linked to HBRR 43: Deprivation of Liberty and the work ongoing in this area overseen by a Task & Finish Group. |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 4 = 16 Target: 4 x 2 = 8 |  |  | Rationale for target score: Consequences noncompliance for the Health Board will not change. Addressing the oversight and Governance will reduce the likelihood of non-compliance. The Risk Target Date reflects timescale for the MCA lead to take up position and the establishment of governance structures & processes. |  |  |  |
| Level of Control = |  |  |  |  |  |  |
| Date added to the HB risk register June 2023 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Director level responsibility confirmed in principle with the agreement to host the MCA / DoLS structure from April 2024. Head of Nursing MCA to continue to coordinate the various elements in the interim. - Appointed a band 5 business manager and a band 6 professional development nurse 0.6 to support the coordination of the elements relating to MCA and support the service groups with application in practice. - Agreement by the PCTSG Board in principle for PCT to host a combined MCA / DoLS team but not to include IMCA or Court of Protection at this point in time. - Urgent support in practice is provided by the DoLS team lead and there are now three Best Interest Assessors in post to support increased monitoring of compliance and access to advice. - Escalated and the Director of Nursing and Patient Experience has established a task and finish group to ensure any gaps in compliance are managed, the service is future proofed, and accountability agreed - Core health board training remains in place. A review has demonstrated low compliance linked to the efficacy of the training to support the practical needs of front line staff. An all Wales benchmarking process showed training delivered in house to be more effective. The development of a training post will support delivery of training more flexibly to meet the needs of clinical staff. - Corporate Head of Nursing is working with Corporate Governance and Service Delivery Group Governance leads to identify concerns, work to address these and ensure that those responsible for the local implementation of the MCA are aware of their responsibilities. |  |  | Action | Lead |  | Deadline |
|  |  |  | A review of training has been placed on the agenda for the MCA / DoLS / Subgroup of the West Glamorgan Safeguarding Board – Agreed to a regional approach to reviewing and planning MCA DoLS training. | Head of Nursing MCA |  | Closed. Risk being re-assessed in PCT. |
| Assurances (How do we know if the things we are doing are having an impact?) - Corporate Head of Nursing will provide regular updates and reports to Mental Health Legislation committee including any highlighted concerns. - The ongoing development work to ensure a robust MCA DoLS process will continue to monitor MCA compliance and provide operational advice and support to the service groups - Reporting processes are via - The Mental Health Legislation Committee - The safeguarding committee - West Glamorgan Safeguarding Board |  |  | Gaps in assurance (What additional assurances should we seek?) Policies, standard operating procedures, accountability and assurance not yet in place. With LPS not being implemented during this parliament and no agreed future date likely, policies, standard operating procedures, accountability and assurance arrangements for the MCA to be confirmed via the task and finish group established. There is a requirement to set up MCA/DoLS assurance audits to provide data. |  |  |  |
| Additional Comments / Progress Notes 22/04/2024: MCA has transferred from corporate to join the DoLS Team in PCTSG 01/04/2024 to form a MCA/DoLS Service which is hosted by PCTSG. The new Lead for MCA/DoLS commenced 11/03/2024 and is currently undergoing induction. Agreement to keep risk score at 16 until induction period completed, following which the risk will be discussed and reviewed in the PCTG Risk Meeting in 2 months. 15/05/2024 (Replaces previous holding comment): A number of causative factors have been / are being addressed: • There is no identified MCA structure or designated resource to support the implementation and compliance with MCA across the organisation – This is concluded: MCA/DOLS lead is in place and reviewing processes. • No agreed structure for oversight and management of HB IMCA (Independent Mental Capacity Advocate) contract – This has been concluded. Tender awarded and contract to start on 1st June – this will sit with Corporate Nursing. • Lack of funded budget for Health Board Level 2 and 3 training and a lack of coordination in the review and development of training content – Level 2 training is now on ESR and level 3 training has commenced. Training is in its infancy currently. Risk as described is being reviewed for re-articulation & re-assessment as most causative factors have been addressed. |  |  |  |  |  |  |

| Datix ID Number: 3444 Health & Care Standard: |  |  | HBR Ref Number: 92 Risk Target Date: 31st March 2025 | Current Risk Rating 5 x 5 = 25 |  |
| --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  | BAF Ref: 6 | Director Lead: Darren Griffiths, Director of Finance and Performance Assuring Committee: Performance and Finance Committee |  |  |
| Risk: Forecast Deficit Forecast deficit is not met due to insufficient progress on run rate reduction and £26.1m saving targets across all areas which is required to ensure the planned in month deficit is achieved. |  |  | Date last reviewed: June 2024 |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 5 = 25 Target: 5 x 1 = 5 |  |  | Rationale for current score: - Delivery of the deficit plan is predicated on a combination of savings and run rate reductions - Consequence is significant as failure to deliver the plan could impact service delivery if cost reduction required later in the year - A deficit plan is a failure to meet a statutory duty |  |  |
| Level of Control = 25% |  |  |  |  |  |
| Date added to the risk register June 2023 |  |  | Rationale for target score: - The consequence will not change given the important of financial delivery and its relationship with the delivery of the Health Board recovery and sustainability plan - Reducing likelihood to 1 supports a confidence that the deficit plan will be delivered. |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |
| The Health Board is doing the following: - Enhanced governance arrangements in place from April 2024, including the submission of Financial Strategies from all Service Groups on 31st May 2024 - Following discussions with Independent Members on 11th June 2024 a series of further actions have been agreed to support the wider financial position. - Clear action requested directly from interim CEO and agreed via Management Boards on the management of Variable Pay at the meeting on 15th May 2024. - Further actions set by interim CEO for Executive Directors above Thematic programmes. - Outlined in the plan submitted 28th March 2024 the Health Board has been focusing on its Thematic Programmes to support the reduction of the £50.1m, which are aligned to the national Value & Sustainability programmes - Transparent exchange of position with NHS Executive & Welsh Government - Clear financial plan in place for 2024/25 - Savings Programme Management Office (PMO) in place to support savings delivery - Enhancement of reporting by exploring options on weekly reporting of drivers of expenditure - Focus on efficiency of core resource to avoid spending premium cost resource |  |  | Action | Lead | Deadline |
|  |  |  | Continuation of financial performance meetings and escalation as necessary | Director of Finance & Performance | Will run until targets met |
|  |  |  | Develop robust cross system service change plans which improve quality of care and reduce system cost | Director of Finance & Performance and Chief Operating Officer | Will run until target is met |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board financial performance is reviewed and monitored through: - Monthly financial recovery meetings - Performance and Finance Committee - Routine reporting to Board of most recent monthly position and financial forecasts - Development of weekly reporting of drivers of expenditure. - Comprehensive mid-year and Q3 review of trajectory to 31st March 2025 will be completed in October and January for discussion with WG and Board. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |
| Additional Comments / Progress Notes 03/05/24 - Letter from WG dated 3rd May outlined that the plan as it stands is unacceptable and unsupportable and resubmission is required by 31st May 2024. 13/05/24 – Interim CEO set out clear action in the financial position 15/05/24 – Discussions with Management Board and setting position regarding agency spend 05/06/24 – Presentation to WG by DOF/Deputy DOF on Financial Plan and the position at Month 1 11/06/24 – Presentation and further actions agreed by Independent Members |  |  |  |  |  |

| Datix ID Number: 3448 Health & Care Standard: |  |  | HBR Ref Number: 93 Risk Target Date: TBC | Current Risk Rating 5 x 4 = 20 |
| --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  | BAF Ref: 6 | Director Lead: Darren Griffiths, Director of Finance and Performance Assuring Committee: Performance and Finance Committee |  |
| Risk: Reduced Capital Funds Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2024/25. |  |  | Date last reviewed: June 2024 |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 4 = 20 Target: 5 x 1 = 5 |  |  | Rationale for current score: - The Health Board has been advised that its discretionary capital allocation for 2024/25 is £11.168m. - The funding available within the Capital Resource Limit (CRL) will not meet the demands for capital investment. Discretionary capital is deployed to replace ageing medical devices & equipment; to address backlog maintenance of premises; and to support small scale, non-National service improvements with capital investments - The current Health Board assessment of the carry forward and previously agreed commitments for inclusion in the 2024/25 capital plan currently suggests a requirement for an additional £8.4m to balance the plan and meet highest risk priorities only. - WG are currently assessing the outputs from the national capital prioritisation exercise, which means some major capital scheme business cases are on hold. - The approved plan assumes additional income of £3.224m. RAG status shows Red £0.892m related to WG business case fees and disposal proceeds. This is a higher-than-normal risk due to the on-going national capital prioritisation exercise. - It is likely that due to slippage on capital schemes, this over-commitment will reduce. - There is potential for further capital requirements arising from service model changes which will need to be managed. - Potential consequences of this risk are the inability to achieve the ambitions set out within health board plans; the potential failure of ageing equipment leading to service disruption; the exposure to potential environmental health & safety risks. |  |
| Level of Control = 25% |  |  |  |  |
| Date added to the risk register June 2023 (refreshed June 2024) |  |  | Rationale for target score: The target score expresses the aspiration of the health board for addressing this risk. The target date indicated above reflects the point which the current actions are anticipated to reduce the risk, though knowledge of the actual funding available is required to reduce it further and this is not available until some months into the financial year. |  |

| Controls (What are we currently doing about the risk?) | Mitigating actions (What more should we do?) |  |  |
| --- | --- | --- | --- |
| The Health Board is doing the following: - - Regular dialogue with Welsh Government regarding capital requirements. - Clear communication and reporting of the capital position, the risks and limitations. - Close management of all schemes to ensure slippage is understood along with the impact on service. - Clear prioritisation of any new requirements recognising the current constraints | Action | Lead | Deadline |
|  | Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk based basis. | Director of Finance & Performance | Monthly through the financial year as plan is dynamic |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board capital position is reviewed and monitored through: - Quarterly capital prioritisation group - Performance and Finance Committee quarterly finance report - Monthly Monitoring Returns to Welsh Government. | Gaps in assurance (What additional assurances should we seek?) Reporting on impact of constraints to the capital programme on service delivery. |  |  |
| Additional Comments Board members will be aware that capital plans are dynamic through the year with mitigating actions taken and opportunities for slippage and further support from WG sought on a consistent basis. This process will continue in 2024/25 in efforts to de-risk the capital plan. 18/06/24: Updated for 2024/25 position. |  |  |  |

| Datix ID Number: 3516 Health Care Standards: |  |  |  |  |  | HBR Ref Number: 94 Risk Target Date: TBC |  |  |  | Current Risk Rating 4 x 3 = 12 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Mental Health & Learning Disability Services |  |  |  | BAF Ref: 2.3 |  | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance and Finance Committee For information: Quality & Safety Committee |  |  |  |  |  |  |
| Risk: CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. Links to other CAMHS risk register entries: (Ref: 3410/3373/3351/3346/3349/3350) |  |  |  |  |  | Date last reviewed: June 2024 |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 3 = 12 Target: 3 x 3 = 9 |  |  |  |  |  | Rationale for current score: Marked improvement in the performance against the Mental health Measure for CAMHS. Data validation for new patients complete. Current risk score reduced to 12 in view of improved performance however this reflects the fragility in the workforce to deliver sustained performance. |  |  |  |  |  |  |
| Level of Control = % |  |  |  |  |  | Rationale for target score: The rationale for the target score is linked to successful recruitment and more timely access to services for children and young persons which will reduce risk. |  |  |  |  |  |  |
| Date added to the risk register October 2023 |  |  |  |  |  |  |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  |  |  | Mitigating actions (What more should we do?) |  |  |  |  |  |  |
| -Ongoing recruitment into all staff groups -Temporary agency workforce in nursing at premium pay rates to sustain current levels of performance -Use of locum medical staff due to high vacancy level on medical workforce. -Recent appointment into psychological therapies lead posts. |  |  |  |  |  | Action |  |  | Lead |  |  | Deadline |
|  |  |  |  |  |  | Continued efforts at recruitment |  |  | Acting Associate Service Director |  |  | Monthly review |
| Assurances (How do we know if the things we are doing are having an impact?) -Monthly CAMHS Directorate meeting in place where performance and workforce are scrutinised -Reporting into Weekly Business Team and MH & LD management board. -Reporting into SBU Performance & Finance Committee and IQPD (Integrated Quality & Performance Delivery) meeting with Welsh Government -Ongoing validation of the waiting list to ensure robust reporting going forward |  |  |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |  |  |  |
| Additional Comments / Progress Notes 13/06/2024: There has been sustained improvement performance against the Mental Health Measure for CAMHS since last review date in line with the predicted trajectories, however there was a deterioration in the first few months of 2024 due to the agency nursing workforce depleting. We are continuing to try and recruit to substantive nursing posts for part 1a of the service (three band six posts being re-advertised again this week) to reduce the need for agency nursing, to make the service provision more clinically and financially sustainable. Current risk score remains at 12 in view of improved performance over a period, however this reflects the fragility in the workforce to deliver sustained performance. |  |  |  |  |  |  |  |  |  |  |  |  |
| Datix ID Number: 3571 Health & Care Standard: |  |  |  |  | HBR Ref Number: 96 Target Date: 31st March 2025 |  |  | Current Risk Rating 4 x 5 = 20 |  |  |  |  |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  |  | BAF Ref: 6 |  | Director Lead: Nerissa Vaughan, Interim Director of Strategy Assuring Committee: Performance and Finance Committee |  |  |  |  |  |  |  |
| Risk: Failure to Develop an Approvable IMTP (statutory compliance) Failure to have an approvable (Integrated Medium Term Plan) IMTP for 2024/5 and for 2025/26 then we will lose public confidence and breach legislation. |  |  |  |  | Date last reviewed: June 2024 |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x5 = 20 Current: 4 x 5 = 20 Target: 4 x 2 = 8 |  |  |  |  | Rationale for current score: The Health Board does not have a WG approved IMTP and has been placed in enhanced monitoring for Finance, Strategy and Planning following the inability of the Health Board to submit a balanced IMTP in March 2023. Given the All Wales financial context the Health Board was not able to submit an IMTP in March 2024 and has instead developed an Annual Plan 24/25 set in a three year context. It is also unlikely that the HB will be able to submit financially balanced IMTP in March 2025 |  |  |  |  |  |  |  |
| Level of Control = 70% |  |  |  |  |  |  |  |  |  |  |  |  |
| Date added to the HB risk register October 2023 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Rationale for target score: The target remains to develop a financially balanced IMTP so that we meet our statutory duties. |  |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  |  | Mitigating actions (What more should we do?) |  |  |  |  |  |  |  |
| - An integrated process is in place to develop the Annual Plan 2025/26. - The existing IMTP Executive Steering Group will provide oversight of the Annual Plan/IMTP, Performance and Finance Plans assured by P&F Committee. W&OD Committee reviews the workforce plan, Q&S Committee the Q&S elements. JET meetings with WG - An Annual Plan was submitted to WG in March 2024 along with an Accountability Officer Letter - As per the Welsh Government de-escalation criteria for Strategy and Planning work has commenced to refresh the HB’s Clinical Services Plan with a view to develop a draft that can be shared with WG in March 2025. - As per the Welsh Government de-escalation criteria for Strategy and Planning work in being undertaken to assess the HB against the Planning maturity Matrix and develop an action plan in response. The baseline assessment should go to Board in September at the latest. |  |  |  |  | Action |  | Lead |  |  |  | Deadline |  |
|  |  |  |  |  | Establish baseline assessment against the Planning Maturity Matrix with an associated action plan |  | Interim Director of Strategy |  |  |  | 30/09/2024 |  |
|  |  |  |  |  | Development of a draft Clinical Services Plan to be shared with WG in March 2025. |  | Interim Director of Strategy |  |  |  | 31/03/2025 |  |
|  |  |  |  |  | Amended: Development of a robust Annual Plan for 2025/26 in a three year context to be submitted to WG in March 2025. |  | Interim Director of Strategy |  |  |  | 31/03/2025 |  |
| Assurances (How do we know if the things we are doing are having an impact?) Robust arrangements are in place to execute the Annual Plan and for 2025/26 these arrangements are being strengthened with updated reporting and monitoring arrangements through the newly established Annual Plan Oversight Group chaired by the COO. |  |  |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |  |  |  |  |
| Additional Comments / Progress Notes 20/06/2024: Risk refreshed |  |  |  |  |  |  |  |  |  |  |  |  |

| Datix ID Number: 3692 Health & Care Standard: |  |  | HBR Ref Number: 98 Target Date: TBC | Current Risk Rating 5 x 4 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in safe and appropriate settings |  | BAF Ref: 3 | Director Lead: Darren Griffiths, Executive Director of Finance & Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. The backlog maintenance costs are in excess of £200 million. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 4 = 20 Target: 3 x 3 = 9 |  |  | Rationale for current score: 6 FACET survey Estates Strategy and Development control plans General compliance with fire regulations and WHTM/WHBN requirements. Backlog maintenance Health Board estates strategy and DCP task and finish group Audit and Assurance limited assurance report Access to funding |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: Through the 6 FACET survey a number of key items have been identified covering the Physical condition, Functional suitability, Space utilisation, Quality audit, Statutory compliance and Environmental management. In addition an equality review was undertake on sites. All of which identified significant issues with the current estate, with very few areas achieving condition ‘B’. The overall backlog maintenance is in excess of £200m. |  |  |  |
| Date added to the HB risk register 07/02/2024 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Planned preventative maintenance, prioritising highest risk depending on funding available (EFAB – Discretionary) – linked to creation of decant space through service changes - Regular reviews of the estate. - Reactive maintenance. - 20% annual review/update of 6 FACET surveys - Undertaken capital schemes where funded - Address issues where practicable through EFAB/Discretionary capital - Estates Strategy and development control plans task and finish group |  |  | Action |  | Lead | Deadline |
|  |  |  | Maintain effective engagement with Welsh Government to provide funding to implement estates strategy and development control plans to address all areas outlined. |  | Assistant Director of Capital Planning | 31 March 2025 |
|  |  |  | Work with Welsh Government to source alternative solutions to funding the HB estates strategy and development control plans |  | Assistant Director of Capital Planning | 31 March 2025 |
| Assurances (How do we know if the things we are doing are having an impact?) - Monitoring through quality & Safety, Audit & Assurance and Performance and Finance committee to receive assurance and or identify gaps for key compliance and adherence to applicable legislation. - NWSSP internal audits - Site visits/tours to identify compliance and gaps in compliances. - Completion of FRA’s within targeted schedule - Estates strategy and development control plans being implemented - Half yearly Board oversight of strategy implementation |  |  | Gaps in assurance (What additional assurances should we seek?) Suitable funding to implement the estates strategy and development control plans, this will be over a 10 – 15 year period. Allocate funds where available to address issues outlined Detailed work to be commissioned to consider primary and community estates strategy along with mental health services |  |  |  |
| Additional Comments Through the 6 FACET survey a number of key items have been identified covering the Physical condition, Functional suitability, Space utilisation, Quality audit, Statutory compliance and Environmental management. In addition an equality review was undertake on sites. All of which identified significant issues with the current estate, with very few areas achieving condition ‘B’. The overall backlog maintenance is in excess of £200m. Key areas include ventilation and cooling with major infection control and other implications. Theatres/Wards/ED and general acute settings including mental health and learning disabilities being old and not compliant with the latest WHBN’s and WHTM’s. The heating, power and medical gas systems have also been identified as issues for concern in the 6 FACET surveys and from independent audits. The health board’s latest NWSSP estates audit received a limited assurance due to limited Welsh Government funding available to undertake backlog maintenance and implementation of estates strategy. |  |  |  |  |  |  |

| Datix ID Number: TBC Health Care Standards: |  |  | HBR Ref Number: 99 Target Risk Date: See Rationale |  | Current Risk Rating 5 x 4 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, equitable and more equal and prosperous lives |  | BAF Ref: 1 | Director Lead: Jennifer Davies, Interim Director of Public Health Assuring Committee: Population Health & Partnerships |  |  |  |
| Risk: Failure to implement the population health strategy approaches at the required scale. This arises from risk of a failure of the organisation to understand and act on the provisions of the strategy for building whole of system actions across the 4 pillars; and the consequent lack of systems and processes to support the delivery of population health improvements. Currently identified contributors to this risk include the absence of the tactical level planning required to design and deliver cross-cutting programmes within a federated operational delivery system; lack of systematic review and capture of population health contributions of existing services; limited behaviour change to adopt a population health focus at service and corporate level; uncertainty about the financial commitment to support Population Health Strategy Implementation as well as a lack of clear processes for accessing available funding; a limited focus on prevention; and a lack of consideration of how to act to influence the wider determinants that affect the population’s health and how the Health Board might contribute to addressing these. The outcome if the risk is not addressed is worsening health in our population with widening health inequities. |  |  | Date last reviewed: June 2024 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 5 = 25 Current: 5 x 4 = 20 Target: 4 x 2 = 8 |  |  | Rationale for current score: Within SBUHB there is a limited focus on prevention; and a lack of consideration of how to act to influence the wider determinants that affect the population’s health. The Population Health Development Board governance mechanism to enact population health is being reviewed and is not currently operational. We are not in a position where marginal investment is available to begin to develop population health activity. The organisation is unable to confirm the financial allocation to support population health strategy implementation. The public health team have been unable to establish budgetary control or governance processes for utilisation of funding held in the population health reserves affecting implementation of priorities agreed through the Population Health and Partnerships Committee. Developing a transformative approach to how we conduct our business is dependent upon the ability of SBUHB to: better understand our population’s needs and address them; focus on actions which foster and maintain health and wellbeing; design services that incorporate prevention and tackle inequities; and develop robust partnerships that tackle the wider determinants of health that ultimately drive demand for healthcare. Currently there is a lack of capacity and capability in the wider organisation to deliver on this agenda. |  |  |  |
| Date added to the risk register 14/03/24 |  |  | Rationale for target score: Given the system wide changes required to mitigate this risk and the requirement to works across organisational boundaries achievement of this target has been be a long term consideration. Target Risk Date will be reviewed as part of gateway checkpoint on risk/actions. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Population Health Strategy adopted by SBUHB Board 30/03/23. - Population Health Strategy aligned to organisational strategic objective 1. Population health integrated into planning infrastructure through R&S plan 24/25 process. - Population Health and Partnerships Committee and Population Health Development Board established as governance mechanisms for Population Health. - Mandate through governance to progress on key strategic workstreams: - Capability & Capacity building - Anchor Institution baselining - Anti-poverty - Strategic Indicators Population Health - Repurposing SBUHB financial resource to support population health - Behavioural change resource identified to develop behavioural change framework for SBUHB to develop capability and capacity in support of required cultural change. - Health Intelligence resource identified to lead organisational work to build health intelligence infrastructure. - Local population health measures in development with SDGs to be reported quarterly through Annual Plan Oversight Group (APOG). |  |  | Action | Lead |  | Deadline |
|  |  |  | Gateway review of progress on governance actions: Population Health Board re-jig; SDG reporting changes; Capability and capacity review and development work. | Executive Director of Public Health / Director of Corporate Governance (support) |  | 31/06/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) An approach to capturing activity through the quarterly performance reviews is being piloted with the aim of identifying at Service Delivery Group level how population health gain is being addressed. In addition these will then be reviewed at the APOG as appropriate. The Population Health Development Board is being reformed to bring in appropriate senior representation from SDGs to enable it to act as a governance forum for population health activity. |  |  | Gaps in assurance (What additional assurances should we seek?) SDG reporting will allow for development of a view of service group level activity and creation of monitoring framework but this is a development journey and there will be a delay of several quarters while this matures. No mechanism to develop approaches which sit across more than one SDG or which are not directly related to SDG responsibilities. Available data are fragmented due to federated operational delivery structures in support of population health. Work is underway to identify ‘strategic indicators’ which will provide a framework to monitor the impact of action on population health. |  |  |  |
| Additional Comments Given the complexity of the requirements to enable system change at scale the implementation of the population health strategy the organisational journey to becoming population health focused and competent has to be viewed as a long term objective. |  |  |  |  |  |  |

| Datix ID Number: TBC Health & Care Standards: |  |  | HBR Ref Number: 100 Target Risk Date: 31/03/2025 | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, equitable and more equal and prosperous lives |  | BAF Ref: 1 | Director Lead: Nerissa Vaughan, Director of Strategy Assuring Committee: Population Health & Partnerships Committee |  |  |
| Risk: A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners at the Public Services Board (PSB) and/or Regional Partnerships Board (RPB), there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. |  |  | Date last reviewed: June 2024 |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 3 = 12 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  | Rationale for current score: Currently the likelihood of non-delivery of partnership priorities that meet expectations is possible. |  |  |
| Level of Control = % |  |  | Rationale for target score: The occurrence of non-delivery of partnership priorities will reduce with an improved partnership approach within the Health Board, although given the complex nature of partnership working it is unlikely to completely eradicate the risk. |  |  |
| Date added to the risk register 29/05/2024 |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |
| - Senior Health Board leadership has been identified across the West Glamorgan Regional Partnerships Board (WGRPB) governance to improve visibility and decision making. - The newly established Strategic Partnerships Group (SPG) provides oversight of partnership discussions, including the WGRPB and the Public Service Boards (PSB) In development: - Organisational Development work is being progressed with the WGRPB Directors - Collaborative Framework to be developed by the SPG to ensure a joined up and co-ordinated approach to partnership working. The Framework will set-out the roles & responsibilities of Health Board staff and the competencies and skills required to support partnership working. - Joint working is in development between the Health Board Strategy Team and the West Glamorgan RPB regional team to identify alignment with priorities at the outset. |  |  | SB) | Lead | Deadline |
|  |  |  | Development of a robust Strategic Partnerships Group and the Collaborative Framework. | Director of Strategy | 31/12/2024 |
|  |  |  | Improve visibility of partnership working across the Health Board | Director of Strategy | Completed |
|  |  |  | Alignment of Partnership priorities with the Health Board IMTP | Director of Strategy | 31/03/2025 |
|  |  |  | Consideration of the OD working progressed with the WGRPB Directors | Director of Strategy | 31/12/2024 |
|  |  |  | Consideration of Health Board position in relation to identified challenge areas incl. children & young people. | Director of Strategy | 31/12/2024 |
| Assurances (How do we know if the things we are doing are having an impact?) Strategic Partnerships Group (SPG) established in October 2023 will provide oversight of partnership discussions, including the WGRPB and the Public Service Boards (PSB). |  |  | Gaps in assurance (What additional assurances should we seek?) There is no framework currently to direct partnership working in a consistent way (Collaborative Framework to be developed to address this) |  |  |
| Additional Comments 20/06/2024: Risk was discussed at Population Health & Partnerships Committee on 6th June 2024. All the actions are within date. There is therefore nothing to add at this stage. |  |  |  |  |  |

Risk Score Calculation

For each risk identified, the LIKELIHOOD & CONSEQUENCE mechanism will be utilised.  Essentially this examines each of the risks and attempts to assess the likelihood of the event occurring (PROBABILITY) and the effect it could have on the Health Board (IMPACT).  This process ensures that the Health Board will be focusing on those risks which require immediate attention rather than spending time on areas which are, relatively, a lower priority.

This indicates whether there has been an increase / decrease in risk score since the previous month’s HBRR.