| Meeting Date | 21 March 2024 |  | Agenda Item |  |  | 2.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Board Effectiveness Action Plan 2024 |  |  |  |  |  |
| Report Authors | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Committee of arrangements in place to regularly review, update and report on progress against the Board Effectiveness Action Plan (BEAP) 2024, and to update the Committee on progress made against those elements of the BEAP 2024 which have been assigned to the Audit Committee for oversight. |  |  |  |  |  |
| Key Issues | - The board is required to assess its effectiveness in terms of governance and internal control. - To that end, an external review was commissioned, to compare the results with those of the previous internal processes, as well as to set some robust recommendations to take the board forward. - A comprehensive Action Plan for 2024 has been developed based on the findings of that review, which has been further strengthened by the inclusion of recommendations made by Audit Wales following their most recent Structured Assessment review. - Elements of the plan have been assigned to individual Committees or retained to the Board for scrutiny and oversight. The following reports on progress with those actions assigned to this Committee. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE progress made as detailed within the Board Effectiveness Action Plan 2024 extract included at Appendix 2, and ongoing actions carried forward from previous action plans as summarised at Appendix 3. - AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead. |  |  |  |  |  |

BOARD EFFECTIVENESS ACTION PLAN 2024

- INTRODUCTION

1.1	The purpose of this report is to inform the Committee of arrangements in place to regularly review, update and report on progress against the Board Effectiveness Action Plan (BEAP) 2024, and to update the Committee on progress made against those elements of the BEAP 2024 which have been assigned to the Audit Committee for oversight.

2.	BACKGROUND AND CONTEXT

2.1	The board is required to undertake an annual assessment of its effectiveness in terms of governance and internal controls.

2.2	It was agreed that for this year, an external review of board effectiveness would be commissioned, to compare the results with those of the previous internal processes, as well as to set some robust recommendations to take the board forward.

2.3	Deloitte were commissioned to undertake the review, with work taking place during May and June 2023. It comprised of a combination of interviews with board members, senior staff, service groups and external stakeholders, a survey, documentation review and meeting observations. The initial feedback was shared with the board in July 2023 and the draft report received for comments in August 2023. Feedback was incorporated and included in the final version.

2.4	A comprehensive Action Plan for 2024 has been developed based on the findings of the report, which has been further strengthened by the inclusion of recommendations made by Audit Wales following their most recent Structured Assessment review.

2.5	The Action Plan contains a total of 31 recommendations and actions, each of which has been assigned to an oversight committee or retained to the Board to monitor implementation. Processes have been put in place to ensure that regular updates are requested from the relevant lead executives, and that all responses received are reported to the appropriate forum for scrutiny and oversight in a timely manner. In addition, the complete BEAP 2024 will be reported periodically to both the Audit Committee and the Board for assurance. The Head of Compliance has produced a draft reporting timetable covering the first half of 2024/25, which is included at Appendix 1. A further timetable covering the remainder of the year will be produced at a later date, taking into account the Committee/Board meeting dates, and the target dates/deadlines for the remaining actions.

3.	STATUS UPDATE – AUDIT COMMITTEE EXTRACT

3.1	Relevant extracts from the action plan have been circulated to all lead officers with a request that they provide updates on the recommendations assigned to them. The updated extracts relating to the five actions assigned to this Committee for oversight have been included at Appendix 2 for information.

3.2	In addition to the above, three ongoing actions have been carried over from previous years’ plans. One of these has now been superseded by the content of the 2024 Action Plan. The status of the remaining two actions have been recorded at Appendix 3 for information. At the time of reporting, an update in respect of progress with Action A remains outstanding.

4.	FINANCIAL IMPLICATIONS

4.1	There are no direct financial implications arising from the recommendations in this report.

5.	RECOMMENDATIONS

5.1	Members are asked to:

- NOTE progress made as detailed within the Board Effectiveness Action Plan 2024 extract included at Appendix 2, and ongoing actions carried forward from previous action plans as summarised at Appendix 3.

- AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead.

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☐ |
|  | Effective Care |  |  | ☐ |
|  | Dignified Care |  |  | ☐ |
|  | Timely Care |  |  | ☐ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Ensuring the board carries out its business appropriately and aligned with standing orders is a key factor in the quality, safety and experience of patients receiving care. |  |  |  |  |
| Financial Implications |  |  |  |  |
| There are no direct financial implications arising from this paper |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| There are no direct legal implications arising from this paper |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no direct staffing implications arising from this paper |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| The development of the board will provide a robust and sustainable organisation to support the communities it services. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix 1: Appendix 2: Appendix 3: | BEAP 2024 Draft Reporting Timetable BEAP 2024 Extract – Audit Committee Previous Years’ Actions Carried Forward |  |