| Meeting Date | 21st March 2024 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Audit Tracker and Status of Agreed Actions |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 22nd February 2024. Audit Wales There are currently 6 actions overdue, which represents a reduction of 3 when compared to the last report. All of the closed actions relate to the review of Discharge Planning. NWSSP A&A There are currently 110 actions overdue, which represents an increase of 2 when compared to the last report. A total of 20 new actions became overdue during the reporting period, however, this figure has been largely offset by the closure of 18 other actions which had previously been reported as overdue. In total, 36 actions were closed during the reporting period. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to recommendations contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for executives and managers to access and update throughout the year. The deadlines for the reporting periods to the Audit Committee are clearly set out within the file set up, and guidance notes have been produced and distributed to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding recommendations remain, regardless of their age. When all recommendations within a given report are marked closed, the report is archived, and will no longer be included as part of this update.

2.5	Where recommendations have been superseded by the content of later reports, then the original recommendation has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports (Original Deadlines)

3.2	No new actions became overdue during the reporting period. A total of three overdue actions were closed, all of which related the review of Discharge Planning. All actions resulting from this review are now reported as closed.

3.3	The Head of Compliance has offered to work with the Head of Nursing (Optimising & Improving Patient Flow) and Chief Operating Officer, in addressing the overdue actions stemming from the NWSSP Audit & Assurance review of this area prior to the next report to the Committee.

3.4	A summary of all overdue Audit Wales actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |
| --- | --- | --- |
|  | High Priority | Other Priority |
| Exec Lead: Director of Corp. Gov. | 0 | 3 |
| Quality Governance Arrangements | - | 1 |
| Structured Assessment 2022 |  | 2 |
| Exec Lead: Director of ICE | 0 | 3 |
| Equality Impact Assessments | - | 3 |
| Total | 0 | 6 |

3.5	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.6	A further table detailing all actions closed since the last report, including any comments made by the lead executive or their teams in doing so, can be found at Appendix B.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports (Original Deadlines)

4.2	A total of 20 new actions became overdue during the reporting period. However, this figure has been partially offset by the closure of 18 other previously overdue actions. The overall number of overdue actions has therefore increased by 2.

4.3	The new overdue actions are spread across a number of reports, as summarised below:

| Report Name | High Priority | Medium Priority | Low Priority |
| --- | --- | --- | --- |
| Continuing Care (COO) | 1 | - | 1 |
| Stroke Action Plan (COO) | - | 1 | 1 |
| Access to GMS (COO) | - | 4 | - |
| Technical Resilience (DoD) | 1 | - | - |
| Continuing Healthcare (DoF) | 1 | - | - |
| Savings Programme (DoF) | - | 3 | - |
| Estates Condition (DoF) | - | 2 | - |
| Sickness Absence Management (DoWOD) | - | 2 | - |
| P/Care Antimicrobial Prescribing (EMD) | - | 3 | - |
| Total | 3 | 15 | 2 |

4.4	A summary table of all overdue actions is set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.5	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide targets/milestone for completion or further update as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.6	A table detailing all actions closed since the last report, including any comments made by the lead executive or their teams in doing so, is included at Appendix E.

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☒ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☒ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Executive Director. Reports addressing quality and safety issues are discussed in more detail in the Quality & Safety Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have financial implications for the health board. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit recommendations relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no staffing implications associated with this paper. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix A Appendix B Appendix C Appendix D Appendix E | Overdue Actions – Audit Wales Closed Actions – Audit Wales Overdue Actions – NWSSP A&A (Summary) Overdue Actions – NWSSP A&A (Detail) Closed Actions – NWSSP A&A |  |