| Meeting Date | 9th November 2023 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Audit Tracker and Status of Agreed Actions |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 20th October 2023. Audit Wales There are currently 9 actions overdue, which represents a decrease of 1 when compared to the last report. A total of 2 new actions became overdue during the reporting period, however this figure has been more than offset by the closure of 3 other actions which had previously been reported as overdue. In total, 10 actions were closed during the reporting period. NWSSP A&A There are currently 100 actions overdue, which represents an increase of 17 when compared to the last report. A total of 35 new actions became overdue during the reporting period, with 2 further actions needing to be reopened as a result of follow-up work undertaken by NWSSP Audit & Assurance colleagues. However, this figure has been partially offset by the closure of 20 other actions which had previously been reported as overdue. A significant proportion of the increase in overdue actions can be attributed to two new audit reports (Access to Cancer Services and Swansea Wellness Centre), and the need to reopen two actions relating to the NICE Guidance review. Three reports (Access to Cancer Services, Swansea Wellness Centre and Quality & Safety Governance Framework) make up 63% of the 35 new overdue actions reported in this period. In total, 63 actions were closed during the reporting period. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receive and consider reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to recommendations contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for executives and managers to access and update throughout the year. The deadlines for the reporting periods to the Audit Committee are clearly set out within the file set up, and guidance notes have been produced and distributed to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding recommendations remain, regardless of their age. When all recommendations within a given report are marked closed, the report is archived, and will no longer be included as part of this update.

2.5	Where recommendations have been superseded by the content of later reports, then the original recommendation has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES (FORMERLY WAO) REPORTS

3.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales (formerly WAO) recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports (Original Deadlines)

3.2	A total of two new actions became overdue during the reporting period, however this figure has been more than offset by the closure of three other previously overdue actions. The overall number of overdue actions has therefore reduced by one.

3.3	The two new overdue actions relate to the following two areas/reports:

- The addition of comparative data to balanced scorecards

Structured Assessment 2022

- The revision of Equality Impact Assessment processes.

Equality Impact Assessments – September 2022

3.4	A summary of all overdue actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |
| --- | --- | --- |
|  | High Priority | Other Priority |
| Exec Lead: Chief Operating Officer | 2 | 1 |
| Discharge Planning | 2 | 1 |
| Exec Lead: Director of Corp. Gov. | 0 | 3 |
| Quality Governance Arrangements | - | 2 |
| Structured Assessment 2022 |  | 1 |
| Exec Lead: Director of ICE | 0 | 3 |
| Equality Impact Assessments | - | 3 |
| Total | 2 | 7 |

3.5	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide milestone targets for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.6	A further table detailing all actions closed since the last report, including any comments made by the lead executive or their teams in doing so, can be found at Appendix B.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports (Original Deadlines)

4.2	A total of 35 new actions became overdue during the reporting period, with two further actions needing to be re-opened as a result of follow-up work undertaken by NWSSP Audit & Assurance colleagues. However, this figure has been partially offset by the closure of 20 other previously overdue actions. The overall number of overdue actions has therefore increased by 17.

4.3	The new overdue actions are spread across a number of reports, as summarised below:

| Report Name | High Priority | Medium Priority | Low Priority |
| --- | --- | --- | --- |
| Transition from CAMHS to AMHS | - | 4 | - |
| Nurse Rostering | - | 1 | - |
| Access to Cancer Services | 3 | 3 | - |
| Q&S Governance Framework | - | 8 | 1 |
| End of Life Care | - | 4 | - |
| System Implementation – Benefits Realisation | - | 1 | 1 |
| C-19 Cost Management - Response | - | 1 | - |
| C-19 Cost Management - Recovery | - | 1 | - |
| Swansea Wellness Centre | 4 | 2 | 1 |
| NICE Guidance*Reopened | - | 2 | - |
| Total | 7 | 27 | 3 |

4.4	As can be seen from the preceding table:

- A significant proportion of the increase in overdue actions can be attributed to two new audit reports (Access to Cancer Services and Swansea Wellness Centre), and the need to reopen two actions relating to the NICE Guidance review.

- Three reports (Access to Cancer Services, Swansea Wellness Centre and Quality & Safety Governance Framework) make up  63% of the 35 new overdue actions reported in this period.

4.5	A summary table of all overdue actions has set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.6	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide milestone targets for completion or further update as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.7	Lead Executives and their teams have reported 63 actions as closed during the reporting period. In the two instances highlighted below, whilst it has not been possible to deliver all elements referred to in the original response, management feel it is reasonable to close the recommendation at this time given the action taken to date and all other circumstances:

| Recommendation | Response | Remark on Closure |
| --- | --- | --- |
| Transition from CAMHS to AMHS |  |  |
| Mandatory and Statutory training reports distributed within the Service Group to managers for information have been enhanced from a ward/service overall total to now include breakdown to individual staff member. However, these reports only indicate training compliance, and not date of expiry. Including the date of expiry could assist managers in prioritising those staff most overdue. To assist in ongoing monitoring training compliance reports should include expiration dates to assist in addressing those areas longest overdue. | The electronic staff record (ESR) system provides an alert to staff when they fall out of compliance with safeguarding e learning modules. Face to face safeguarding training is uploaded onto ESR by the training facilitators. The MHLD SG will need to work with the ESR team to establish if current reporting can include expiry date or whether an alternative system needs to be developed with digital intelligence colleagues. | October 2023: ESR team have indicated that the inclusion of an expiry date is not possible and would require a national response/review of ESR to be achieved. |
| Management of Physical Health Records |  |  |
| Records are transported in ‘blue boxes; however the lids are only sealed with cello tape currently. We understand that staff sometimes cut themselves on the cable ties that were used previously. Whilst contracts contain confidentiality clauses and NHS staff, (HCSW) and the Taxi companies are bound by NHS Policies, the use of removable seals while transporting records may lead to a risk of unauthorised access or loss of records, in particular when using taxis to transport records. Boxes and envelopes containing health records should be securely sealed while being transported, using tamper proof tape, or locked cages for bulk transport. | Undertake an assessment of the options available to us and a paper will be submitted to the Information Governance Group (IGG) for consideration | October 2023: The Health Records Management Team have reviewed the recommendation made by Internal Audit following their review of using tamper proof tape to secure the blue boxes used for transportation of records across the Health Board, and following a detailed internal review by the Senior Records Management Team and benchmarking exercise carried out with colleagues across Wales; feel that the current measures that are in place across SBUHB are secure and maintain confidentiality of records at all times. The Health Board vans and courier services used to transport records are tracked and records are never left unattended at any time, and are picked up and delivered directly from one site to another and dropped off in secure areas. Due to the practical and financial implications of staff having to daily validate/check through hundreds of blue boxes on a daily basis, if tamper proof tape was used there would be no added value of using the tape to secure the boxes due to the confidential way in which records are transported. |

4.7	In line with previous observations by the Committee, the Head of Compliance has asked that both of these issues are considered for inclusion in the relevant Service Group/Directorate risk registers.

4.8	A table detailing all actions closed since the last report, including any comments made by the lead executive or their teams in doing so, is included at Appendix E.

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☒ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☒ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Executive Director. Reports addressing quality and safety issues are discussed in more detail in the Quality & Safety Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have financial implications for the health board. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit recommendations relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no staffing implications associated with this paper. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix A Appendix B Appendix C Appendix D Appendix E | Overdue Actions – Audit Wales Closed Actions – Audit Wales Overdue Actions – NWSSP A&A (Summary) Overdue Actions – NWSSP A&A (Detail) Closed Actions – NWSSP A&A |  |