Appendix 2

Outstanding Actions from Previous Board Effectiveness Assessment

Audit Committee (November 2023)

| Action Number | Criteria Area | Action | Lead | Timescale | Progress |
| --- | --- | --- | --- | --- | --- |
|  | Values and Behaviours | The organisational cultural survey combined with the public sector and staff surveys to be used to establish how the values are embedded in the organisation. | Director of Workforce and OD | October 2021 | May 2023: This work is now being progressed as part of ‘Our Big Conversation’, with progress being reported via the 2022/23 Board Effectiveness Action Plan. As such, this action has been closed. |
|  | Values and Behaviours | Just Culture and other programmes to be incorporated into a single Swansea Bay organisational development programme, with progress measured through the Workforce and OD Committee | Director of Workforce and OD | October 2021 | May 2023: This work is now being progressed as part of ‘Our Big Conversation’, with progress being reported via the 2022/23 Board Effectiveness Action Plan. As such, this action has been closed. |
|  | Quality | A dashboard be developed which sets out the quality impacts of performance for patients. | Director of Finance Director of Nursing & Pat. Experience | August 2021 | December 2022: Quality dashboard to be launched in January 2023. May 2023: Issues regarding the extraction of data from DATIX Cymru and a number of other systems have impeded the development of Phase One of the Dashboard. These are now being resolved, and the revised plan is for Phase One to be released to a limited number of key stakeholders for data validation by the end of May 2023. Work is continuing in parallel on stratifying and refining measures and data sources for Phase Two, which includes further engagement with stakeholders. We continue to work across Wales on the Once For Wales Digital Dashboard project, which is currently in the design phase. June 2023: Dashboard went live as a soft launch for SG and HB review, testing and further feedback. The dififculties with data flow and automatic extraction into and out of the data wharehouse still pose risks and active problems but that initial workarounds are functioning. October 2023 Maternity data is now live undergoing final testing, Mortality data and drill down dashboards in place, EOL live data in place staff training remains outstanding, DALS, Basic Falls activity data, Sepsis data in place, further sepsis metrics under development, stroke data and patient complaints and experience data is next to be brought on line, care after death dashboard linked, work still to bring badgernet, national cleaning scores and rest of quality priorities on line. |
|  | Quality | The quality strategy be developed, taking into account consideration of the impact of the new Quality Bill and key areas of quality. | Director of Nursing & Pat. Experience | October 2021 | October 2022: This work is well underway, with completion expected during January 2023 December 2022: Draft Strategy presented to Management Board in December 2022. To be presented to the Board in January 2023. January 2023: The Quality Strategy was approved at the January 2023 meeting of the Board. COMPLETE |