| Meeting Date | 09 November 2023 |  | Agenda Item |  |  | 2.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Board Effectiveness Action Plan |  |  |  |  |  |
| Report Authors | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan for 2022/23 and the Board Effectiveness Action Plan for 2023/24. |  |  |  |  |  |
| Key Issues | - The board is required to undertake an annual self-assessment of its effectiveness in terms of governance and internal controls. The findings of last year’s self-assessment were presented to the September 2022 meeting of the board. A proposed action plan was also presented to this meeting, which was agreed. - A report on progress against that action plan was last received by the Committee in July 2023. This report provides a further update. - At the time of reporting, a total of 38 actions were identified as complete by the relevant lead executive; these are highlighted green in the Action Plan, and represents an increase of three since the last report. It has not been possible to complete the remaining four actions within the original target dates. - With regard to the four actions outstanding from the previous year’s plan, three of these are now reported as closed. - It is proposed that the remaining actions for 2022/23 are included within the Board Effectiveness Action Plan for 2023/24 together with the actions from the Audit Wales Structured Assessment recommendations. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE progress made as detailed within the updated Board Effectiveness Action Plans included at Appendix 1 and Appendix 2 - AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead. - CONSIDER the Board Effectiveness Action Plan for 2023/24, NOTING that it will be submitted to the November Board, subject to final changes, for approval. |  |  |  |  |  |

BOARD EFFECTIVENESS ACTION PLAN

- INTRODUCTION

1.1	The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan.

2.	BACKGROUND AND CONTEXT

2.1	The board is required to undertake an annual self-assessment of its effectiveness in terms of governance and internal controls.

2.2	The findings of last year’s self-assessment were presented to the September 2022 meeting of the board. A proposed action plan was also presented to this meeting, which was agreed.

2.3	A report on progress against that action plan was last received by the Committee in July 2023. This report provides a further update.

3.	STATUS UPDATE

3.1	Since the last meeting of the Committee, the action plan has again been circulated to all lead executives with a request that they provide updates on the actions assigned to them. A copy of the updated action plan has been included at Appendix 1 for information.

3.2	At the time of reporting, 38 of the 42 actions contained within the current plan were identified as complete by the relevant Lead Executive, and these have been highlighted green in the Appendix. The following three actions has been reported as complete since the last update to the Committee:

| No | Action | Progress |
| --- | --- | --- |
| 6 | Create a vision for what we want the organisation to be, linked to the Big Conversation. | Our Big Conversation Phase 3, engagement on the vision for a high quality organisation was completed with senior leaders attending across a total of 7 engagement workshops during July 2023, starting with the Board and including a Special Partnership Forum. A total of 130 Leaders attended across these sessions. The resulting 10-year Vision for a High Quality Organisation and action plan has been shared across all senior leaders and a summery version shared with the wider organisation as part of recent CEO comms. DICE will oversee the wider cascade of the vision and set up a Project Board for the delivery, monitoring and evaluation of actions from the vision from October 2023. |
| 10 | To progress the next stage of the Health Board Culture and Values work. Stage 3: Written narrative, engage and develop actions. | Re-instated Values & Behaviours to simplify the existing framework in line with staff feedback, have been published along with the 10-year vision for a high quality organisation, ‘Promise to our People’ and Partnership Compact to support improve staff experience, their safety and wellbeing. DICE will oversee the wider cascade of the vision and set up a Project Board for the delivery, monitoring and evaluation of actions from the vision from October 2023. |
| 29 | Baseline review of resources to support quality across the organisation in order to consider our structures against those required to meet our responsibilities under the Duty of Quality. | Internal scoping review complete. Externally facilitated workshop is being arranged to review model across organisation. |

3.3	There are a further four instances where it has not been possible to complete actions within the original target dates. These are highlighted red in the Action Plan.

3.4	In addition to the above, four ongoing actions were carried over from the previous year’s plan. Three of these have now been completed, with positive progress reported in respect of the fourth. An update has been included at Appendix 2 for information.

4.	BOARD EFFECTIVENESS ACTION PLAN 2023/24

The Board Effectiveness Action Plan for 2023/24 is attached as Appendix 3 for consideration.  It is proposed that the actions from Audit Wales Structured Assessment, once considered in November Board and approved are included within the plan, together with the three remaining actions from the 2022/23 action plan.

5. FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from the recommendations in this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE progress made as detailed within the updated Board Effectiveness Action Plans included at Appendix 1 and Appendix 2

- AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead.

- CONSIDER the Board Effectiveness Action Plan for 2023/24, NOTING that it will be submitted to the November Board, subject to final changes, for approval.

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☐ |
|  | Effective Care |  |  | ☐ |
|  | Dignified Care |  |  | ☐ |
|  | Timely Care |  |  | ☐ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Ensuring the board carries out its business appropriately and aligned with standing orders is a key factor in the quality, safety and experience of patients receiving care. |  |  |  |  |
| Financial Implications |  |  |  |  |
| There are no direct financial implications arising from this paper |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| There are no direct legal implications arising from this paper |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no direct staffing implications arising from this paper |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| The development of the board will provide a robust and sustainable organisation to support the communities it services. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix 1: Appendix 2: Appendix 3: | Board Effectiveness Action Pan 2022/23 Board Effectiveness Action Pan 2021/22 Outstanding Actions Board Effectiveness Action Pan 2023/24 |  |