| Meeting Date | 09 November 2023 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | COEG Report on Progress with Actions Resulting from Internal Audit Recommendations |  |  |  |  |  |
| Report Author | Sharon Rağbetli, Clinical Audit & Effectiveness Manager |  |  |  |  |  |
| Report Sponsor | Dr. Raj Krishnan, Acting Executive Medical Director |  |  |  |  |  |
| Presented by | Dr. Raj Krishnan, Acting Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To outline the progress made with actions generated from the recommendations coming out of the recent internal audit report. |  |  |  |  |  |
| Key Issues | Use of the new Audit Management and Tracking (AMaT) system allows the Clinical Outcomes and Effectiveness Group (COEG) to monitor progress. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☐ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to note the report. |  |  |  |  |  |

PROGRESS WITH ACTIONS RESULTING FROM RECOMMENDATIONS FROM THE RECENT INTERNAL AUDIT REPORT

- INTRODUCTION

The review period covered by Internal Audit colleagues was for the 2022/23 Audit Year in addition to the planning round for 2023/24. The audit considered how clinical audit links to strategic risks and objectives and sought to assess the extent to which clinical audit is playing a full role for quality improvement and contributing to Board assurance.

Elements related to the Clinical Audit and Effectiveness Policy and participation in Welsh Government mandated national audits/registries received Reasonable Assurance ratings. However, the overall findings of the report resulted in Limited Assurance and listed several recommendations for consideration.

Management welcomed the recommendations to focus efforts on improvements and a number of early actions were taken on receipt of the draft report, issued in May.  The final report was issued 30th June.

- BACKGROUND

COEG and Service Delivery Groups are now supported by the Audit Management and Tracking (AMaT) system.  Secured at no cost for a two-year period following a successful bid to Health Technology Wales, use of AMaT is integral to the successful monitoring of audit activities, outcomes and actions and now supports the audit tracker for actions resulting from the recent Internal Audit.

- GOVERNANCE AND RISK ISSUES

The tracker outlining the broader actions and progress is attached as Appendix 1.  The detail of individual elements of those actions are described in more detail below;

3.1	In order to evidence the rationale on which clinical audits in the Health Board’s plan have been prioritised, plan documentation should include explanatory narrative and links to the reference materials used

3.1.1	The Health Board’s plan includes Levels 2-4 of the Audit Hierarchy.  Narrative on the rationale for the Health Board Priority Topics (Level 2) is provided by the designated leads and forms part of the introductory pages.  This information is now COMPLETE following presentation of the End of Life Care topic at the August COEG meeting.

3.1.2	To facilitate completion of data fields, Service Delivery Groups (Level 3 and 4) had been reminded at recent COEG meetings of the need to ensure that datasets (inclusive of rationale) need to be completed in full in building the audit plans for 2023/24.  Therefore, this action point is considered as COMPLETE.  For updates on the appropriate action taken within the Service Delivery Groups (see 3.1.5).

    - For completed topics Level 3 and 4 topics in 22/23 that resulted in; the need for re-audit as recorded in AMaT and/or a combined assurance/risk matrix score of 4 and above, lists were issued to Service Delivery Group Medical Directors 7th June to consider for inclusion within their 23/24 plans.  Therefore, for these inclusions the links to risk/assurance scores and/or re-audit requirements are pre-populated by the Clinical Audit team and this element is considered COMPLETE.

3.1.4	During their presentations to COEG in June/July, all areas confirmed inclusion of these topics on their plans and therefore the action for this section is marked as COMPLETE.

3.1.5	Service Delivery Groups to ensure completion of all data fields for all planned audit topics (Level 3 and 4).  This has been actioned in some cases and therefore is noted to be PARTIALLY COMPLETE, OVERDUE.  In the small number of cases where data is missing, COEG agreed at the October meeting to provide one further week prior to removal of topics.  The areas in question are being contacted and advised appropriately.

3.2	The 2023/24 clinical audit plan should be finalised and approved as soon as possible and the annual planning process should be reviewed to ensure that the clinical audit plan can be approved at the outset of the applicable financial year

3.2.1	Formal presentation of the Level 3 and 4 plans for 2023/24 from all Service Delivery Groups have been received and approved at the COEG meetings in June and July, meaning that this part of the process is considered as COMPLETE

3.2.2	Plans to be finalised, with all data fields completed for formal launch no later than 1st September 2023. Due to a very small number of cases where gaps remain related to rationale for inclusion, this action point is considered as PARTIALLY COMPLETE, OVERDUE.  As noted in 3.1.5, the Clinical Audit and Effectiveness team will be contacting the relevant areas to advise that topics will be removed from the plans if data fields are not completed.

3.2.3	Having now overcome access issues with single sign on, the 2024/25 Audit Plans will realign to the financial year, with planning scheduled to commence in December 2024 for launch on 1st April 2024. NEW

3.3	The monitoring of national audit reports by COEG should be enhanced to include information about the Health Board’s in-year participation/ contribution to each of the national audits in order to ensure compliance with requirements and best practice timescales for completion of responses should be adhered to

3.3.1	Management recently received confirmation from Welsh Government that there are no immediate plans to reinstate completion of assurance proformas for Level 1 topics, providing COEG with an opportunity to amend and streamline the forms and process for use locally.  The revised process is now in use.  COMPLETE

COEG have commenced a short period of amnesty for all outstanding assurance and guidance responses, ending at the COEG meeting on 10th November, at which point the Quality Safety Group will be in receipt of all necessary escalations.

3.3.2	The Level 1 process is supported by a flowchart detailing timescales.

3.3.3	In any instances where delays in receiving responses are deemed to be appropriate, this information will be clearly documented within the notes of the relevant meeting.

3.3.4	Compliance will be reported at each COEG meeting and in those instances where it is necessary and entirely appropriate to extend deadlines to support a quality, meaningful response, these will be clearly documented in the meeting notes.

3.3.5	Management have agreed the addition of a quarterly request to Audit Leads, now in use for the Level 1 Welsh Government mandated national audit/registry topics to identify case ascertainment and any associated issues/concerns or good practice to be received at the COEG.  The Acting Executive Medical Director will be summarising the findings at the meeting on 10th November.

3.4	A lessons learned exercise should be undertaken to ‘support’ the low completion rate of the 2022/23 SDG clinical audit plans and an appropriate and achievable SDG clinical audit plan should be approved for 2023/24, with defined escalation plans for reporting of progress within the wider health board governance structure.

3.4.1	To focus areas on learning from the previous report period, the Clinical Audit team met with as many Audit Leads as possible between the January to April period to; update on the 2022/23 plans, outline the Audit Hierarchy approach and run through the AMaT system.  This element is COMPLETE and has been instrumental in ensuring that areas consider their experiences from 2022/23 to inform 2023/24 planning of Level 3 and 4 topics, in addition to supporting users of AMaT.

3.4.2	Lessons learnt has featured as part of the SDG presentations to COEG on formal closure of Level 3 and 4 2022/23 plans and content of 2023/24 plans.  Presentations were received in the June and July meetings and therefore this action point is marked as COMPLETE.  A number of projects (Appendix 4.) have been deferred to later plans.

3.5	The Health Board should utilise the action tracker functionality within AMaT to capture and manage to closure all of the change actions that emerge from all clinical audits undertaken. This should include the escalation of actions not implemented by the due date

3.5.1   As part of their presentations to COEG, Service Delivery Groups were also asked to describe their governance arrangements and to confirm that they would monitor progress of actions resulting from completed 2022/23 projects to their conclusion which they did in all cases and for that reason this part of the action is marked as COMPLETE.  This will be a standing agenda item at COEG meetings from September (see 3.5.2).

3.5.2	The Service Delivery Groups will be asked to act on the information provided related to progress and issues with delivery of action points (see 3.5.1) within the defined timescales.  The approach commenced in the meeting on 8th September 2023.

3.5.3	In any instances where delays in delivering actions are deemed to be appropriate, this information will be clearly documented within the notes of the relevant meeting.  Commenced at the September COEG meeting.

Amendments to and progress with the 2022/23 Level 3 and 4 plans are attached as Appendix 2, with an improved completion rate of 59% overall, the highest recorded completion rate for the Health Board as a whole.  The majority of removed topics were signposted to the Ward/Area and Service Module, under the responsibility of the Nursing Directorate.  Deferred projects will feature on the 2023/24 and later plans as a result of the “lessons learnt” within the Service Delivery Groups.

- FINANCIAL IMPLICATIONS

The successful business case within the Nursing Directorate has included funding of the licence fees for AMaT for an additional year.  Consideration will need to be given to the source/s of continued funding for fees and associated resources past that date if the system is to be retained within the Health Board.

- RECOMMENDATION

The Committee is asked to note the report.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Compliance with national audit and registry topics provides an opportunity to benchmark performance for quality, safety and patient experience, while the appropriate identification and planning of necessary local priorities can support improvements and provide assurance. |  |  |  |
| Financial Implications |  |  |  |
| The benefits and impact of the AMaT system are expected to be wide ranging and a business case will be required to secure additional funding for its continued use, if deemed appropriate. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None. |  |  |  |
| Staffing Implications |  |  |  |
| None. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Long term the aim is to continue to embed a new culture in terms of the prioritisation of audit and improvement activities, while balancing the need to meet requirements placed on doctors and healthcare professionals in training. |  |  |  |
| Report History |  | As required. |  |
| Appendices |  | Appendix 1. AMaT Action Tracker Overview Appendix 2. Current status of 2022/23 Audit Plans |  |

Appendix 1.  AMaT Action Tracker – Progress at 23/10/23

*New = deadline not yet due/ongoing

Appendix 2.  Status with 2022/23 Audit Plans 23/10/23

|  | Completed @ |  | Deferred | Abandoned |
| --- | --- | --- | --- | --- |
|  | Level 3 | Level 4 |  |  |
| Mental Health and Learning Disabilities | 7/8 | 3/3 | 1 | 1 |
| Morriston | 0/2 | 43/61 | 19 | 24 |
| Primary, Community and Therapies | 2/2 | 10/12 | 4 | 21 |
| Singleton and Neath Port Talbot | 0/10 | 8/25 | 12 | 7 |
| Totals | 9/22 | 64/101 | 36 | 53 |
| Percentage | 59% |  |  |  |