## Slide 1
Discharge planning audit – Progress report
9 November 23
Deb Lewis – Chief Operating Officer
Carol Doggett – Head of Nursing: Optimising and Improving Patient Flow

## Slide 2
Presentation structure….reason for the report
Purpose:
This report aims to provide an overview of the current progress set against the action plan created following the Wales Audit Office (2018) and NWSSP Audit & Assurance (2021) reviews.
The report and presentation considers the action plan’s pertinence to the challenges of delivering the expectations of 6 Goals (Notably goals 5 & 6), the Urgent and Emergency care priorities and the adoption of Signal Version 3 as the digital solution for managing and monitoring patient flow.
Report and presentation structure follows:
Background & context (‘where have we been’)
Relevant work underway (‘where are we now’)
Key Risks and Governance
Next steps (‘where are we going’)

## Slide 3
Background and context…..
Previous work re; coordinated holistic discharge planning across the Health board ended in 2018 ahead of the 2019 review of the current Discharge policy, (which resulted in the inclusion of the SAFER principles for discharge planning)
Real time Demand and capacity (RTDC) programme ran during 2022 and narrowly focussed on flow - Admissions, Discharges and Transfers (ADTs) Hour by hour, day to day
2 audits were undertaken in 2018 and 2021 identified actions pertinent to good governance and holism around discharge planning at ward level…….what was not clear is the support, which would have been required to ensure the policy is deliverable, sustainably, across all our inpatient areas
No standardised approach to SAFER – Optimising patient flow - and each service Group’s use of Signal V3 is variable when compared to each other.

## Slide 4
Relevant work underway…..
The launch of the national 6 Goals Programme in January 2022 reintroduced SAFER and demanded closer integration with Local authority partners to deliver D2RA (Discharge to recover and then Assess).
During January 2023, Morriston Service group set up a dedicated Optimising patient flow team to tackle the challenge of rolling out the SAFER programme in conjunction with the launch of the AMSR reconfiguration.
  Involved dedicated presence and focus on each of the 29 wards across the Morriston service group, presenting the methodology of SAFER
Signal was also adapted and relaunched to support the roll out and act as the digital “One version of the truth” platform for patient flow. This required the creation of a rolling programme to train ward clerks and receptionists.
  Live data entry and the ability to rely on the “one version of the Truth” – Signal, will enable those responsible for flow management across sites and the Health board to trust the system and make decisions on Admission, Discharges and transfers (ADTs) based on the information in front of them

## Slide 5
Risks & Governance
During the winter months, alongside the emerging local flow schemes, (Continuous Flow Model etc.) there will be heightened support at ward level to ensure a sustainable SAFER solution is delivered
Work to standardise the approach to discharge planning across the Health Board remains a priority to support the closure of the current action plan
  Actions to improve process can and should be monitored through the newly created SAFER dashboard and can be utilised by Matrons and ward managers to monitor their compliance
Safer Discharge Policy has been extended to December 2023 to reflect the launch time of the national All Wales Discharge Policy – national policy will be adapted to ‘fit’ SBUHB
Reporting via the 6 Goals/ Urgent care Board through the 4 Programmes of work for unscheduled care and shared with the National Executive – Optimal Patient flow work-streams
SAFER performance of each ward can be monitored through SAFER dashboard

## Slide 6
Summary and next steps
National perspective is that Swansea Bay is leading Discharge planning transformation through the embedding of SAFER with Signal and has been identified as an exemplar for how digital solutions for patient flow can help transform ward to board reporting.
To support the delivery of improved patient flow following the success of Phase 1 roll across all service groups
Work will remain with the Optimising patient flow Improvement team reporting to the 6 Goals Urgent and Emergency care Board
The improvement team will review the current action plans and update the entries/comments to reflect changes to discharge planning and practices, and the revised SAFER principles. Team to continue to work with the Head of Compliance to provide full and timely updates to the Audit Tracker

## Slide 7
Thank you for listening…….happy to take any questions.
Questions and answers