| Meeting Date | 21 November 2024 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Board Assurance Report and Risk Register |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update on progress to re set the Board Assurance Framework (BAF) following the Board development session on risk and assurance in July 2024. The report also presents the Health Board Risk Register (HBRR) to the Audit Committee for review and assurance. |  |  |  |  |  |
| Key Issues | - Development of a revised Board Assurance Framework, template of a Strategic Risk & Assurance Register supported by a Risk Management Strategic Implementation plan. - The Health Board Risk Register was last received by the Committee in July 2024. - Since then, entries have been refreshed by Board Directors as part of the monthly review cycle. This report presents the October 2024 HBRR. - The HBRR contains 33 risks, of which 22 have risk scores at, or above, the Health Board’s risk appetite threshold. Three of these have risk scores of 25. - The health board is undergoing a review and reset of its risk management arrangements currently. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the revised Board Assurance Framework, template for a new Strategic & Assurance Register and risk management strategic implementation plan; - SUPPORT these documents, subject to any final changes, to be submitted to the Board for consideration; - RECEIVE the Health Board Risk Register (HBRR) and update on risk matters. - CONSIDER whether further assurance is required on risks and associated actions & controls – In particular on those risks exceeding the Board’s stated appetite levels. |  |  |  |  |  |

BOARD ASSURANCE REPORT

- Introduction

The purpose of this report is to provide the Audit Committee with an update on progress to re set the Board Assurance Framework (BAF) following the Board development session on risk and assurance in July 2024.  The report also presents the Health Board Risk Register (HBRR) to the Audit Committee for review and assurance.

- Review of Board Assurance Arrangements

Following the Board Development Session in July 2024, the corporate governance team are undertaking a ‘review & reset’ of the framework which underpins how the Board gains assurance from the Board Assurance Framework and risk management arrangements.  Discussions have been held in the Risk Management Group, Risk Scrutiny Panel and with management board members.  As a result of these discussions the following documents have been development for consideration by Audit Committee to help inform the documents to be submitted to Board for consideration:

- Board Assurance Framework – Appendix 1

This has been drafted on the basis that it is purely a framework, setting out how the Board gains assurance and the governance to support the functioning of the Board.

- Strategic Risk & Assurance Register Template – Appendix 2

This document has been developed to support the recording and monitoring of the strategic risks the health board faces against the achievement of the health boards objectives.

The template attached contains notes and guidance setting out what is envisaged will be included in the final/actual document.

Each strategic risk entry (found in the ‘Detail’ section of the attached) would be split into three parts:

- The 1st section relates to the risk itself;

- The 2nd section in blue talks about the controls in place, and the assurance Director’s receive and provide to the Board regarding controls; and

- The 3rd section deals with any identified gaps in the controls or assurance, and the actions which have been agreed to manage the gaps.

A ‘Summary’ section will be included on the front of the Register for reporting to the Board.  The Strategic Risk & Assurance Register (and Summary) will be updated by Directors and their Teams in much the same way as our current Board Assurance Framework.

The intention is the Strategic Risk & Assurance Register is reported to Board three times a year and replaces the Health Board Risk Register.  An operational Risk Register and Corporate Risk Register would then be developed and would underpin the Strategic Risk & Assurance Register.

- Risk Management Strategic Implementation Plan – Appendix 3

In support of the reset a strategic implementation plan has been developed setting out key deliverables/milestones with the end date of March 2026.

- Health Board Risk Register (HBRR) Summary Position

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

The Health Board Risk Register was last received by the Audit Committee in July 2024. Since then entries have been refreshed by Board Directors as part of the monthly review cycle. This report presents the October 2024 HBRR. The HBRR contains 33 risks, of which 22 have risk scores at, or above, the Health Board’s risk appetite threshold. Three of these have risk scores of 25.

The HBRR is as attached at Appendix 4, and the most recent updates highlighted in red font. In addition to risks presented there, the following risks are deemed sensitive and are overseen in private session of Board and/or Committees:

- HBR 60	Cyber Security

- HBR 101	Industrial Action

The profile of risk scores within the HBRR is as follows:

| Risk Analysis | Number of Risks |  |
| --- | --- | --- |
|  | Jun 2024 HBRR | Oct 2024 HBRR |
| Risk Score of 25 | 3 | 3 |
| Risk Score of 20 | 15 | 14 |
| Risk Score of 16 | 7 | 9 |
| Risk Score 9-15 | 8 | 7 |
| Risk Score of 5-8 | 0 | 0 |
| Risk Score of 1-4 | 0 | 0 |
| Total | 33 | 33 |

3.1 	Risk Changes

The following movements are noted in the register in the period since the July 2024 meeting:

- Two risks have been added to the register

- Two risks have increased in score:

- One risks have reduced in score:

- Two risks have been closed/de-escalated from the register:

3.1.1 The risk(s) added to the HBRR since the last update is/are:

| Risk Ref | New Risks | Lead Exec Director | Current Risk Score |
| --- | --- | --- | --- |
| 102 | Inability to Maintain Birthrate Plus Compliant Rosters Birthrate Plus® enables health boards to calculate their midwifery staffing requirements based on their specific activity, case mix, demographics and skill mix. There is a risk non-compliance with roster templates due to increased acuity, unplanned staff absence and vacancies. The potential impact of this may be reduced staffing levels against the agreed Birthrate Plus ®, staffing template resulting in poor patient outcomes and experience, and potential suspension of services. | Executive Director of Nursing & Patient Experience | 16 |
| 103 | High Quality Choices in Birth Place The Community Intrapartum services remain suspended. There is a risk of not being able to provide high quality choices in place of birth (via appropriately staffed and resourced community midwifery teams, the freestanding midwifery unit at Neath Port Talbot Hospital, the alongside midwifery unit and obstetric unit at Singleton Hospital). The potential impact of this is poor patient experience and birth outcomes, poor staff morale and increased attrition of community midwives, increased acuity within obstetric services at Singleton Hospital, and the reduction of services could impact on organisational reputation. | Executive Director of Nursing & Patient Experience | 16 |

3.1.2 The risk(s) with increased scores is/are:

| Risk Ref | Increased Risks | Lead Exec Director | Previous Risk Score | Current Risk Score |
| --- | --- | --- | --- | --- |
| 52 | Impact Assessment Requirements The Health Board does not have sufficient skills & resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. | Director of Insight, Communication & Engagement | 12 | 16 |
| 66 | Access to SACT (Cancer Services) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. | Executive Medical Director | 15 | 20 |

3.1.3 The risk(s) with reduced scores is/are:

| Risk Ref | Reduced Risks | Lead Exec Director | Previous Risk Score | Current Risk Score |
| --- | --- | --- | --- | --- |
| 63 | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound scanning & clinic capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme, which states serial ultrasound growth scans should be performed at three weekly intervals. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy) HIE, where a fetus is growth restricted (Intrauterine Growth Restriction - IUGR) and/or small for gestational age fetus (SGA). | Executive Director of Nursing & Patient Experience | 20 | 12 |

3.1.4 The risk(s) closed within the HBRR is/are:

| Risk Ref | Closed Risks | Lead Exec Director | Commentary |
| --- | --- | --- | --- |
| 91 | Mental Health Capacity Act | Executive Director of Nursing & Patient Experience | Noting progress in respect of structures and processes, it was agreed to close this risk entry and consider the risk afresh with focus on its remaining causes – training/competency. The residual risk has been assessed to have a lower risk level and was agreed to be managed within the operational service register in PCT Service Group. |
| 97 | Disruption due to Industrial Action | Executive Medical Director | This was closed following the standing down of industrial action by the BMA. |

3.2	Risks Above the Board Risk Appetite

There are twenty two risks that are assessed as reaching the Board’s risk appetite threshold:

| Risk Ref | Risk Title & Description | Current Score | Executive Lead & Nominated Board Committee |
| --- | --- | --- | --- |
| 1 | Access to Unscheduled Care | 25 | - Chief Operating Officer - Performance & Finance Committee |
| 3 | Workforce Recruitment (Medical & Dental) | 20 | - Director of Workforce & OD - Workforce & OD Committee |
| 4 | Infection Prevention & Control | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 16 | Access to Planned Care | 20 | - Chief Operating Officer - Performance & Finance Committee |
| 43 | Deprivation of Liberty Safeguards | 16 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 50 | Access to Cancer Services | 25 | - Chief Operating Officer - Performance & Finance Committee |
| 52 | Impact Assessment Requirements | 16 | - Director of Insight, Communication & Engagement - Performance & Finance Committee |
| 60 | Cyber Security | 20 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 61 | Paediatric Dental GA Service (Parkway) | 16 | - Chief Operating Officer - Quality & Safety Committee |
| 64 | Health & Safety Infrastructure | 16 | - Director of Finance & Performance - Quality & Safety Committee |
| 66 | Access to SACT (Cancer Services) | 20 | - Executive Medical Director - Quality & Safety Committee |
| 69 | Safeguarding: Adolescents on Adult Mental Health Wards | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 80 | Inability to Transfer Patients | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 85 | Non-Compliance with ALN Act | 20 | - Director of Allied Health Professionals & Health Science - Quality & Safety Committee |
| 89 | Healthcare Nursing Staff Level (HMPS) | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 90 | Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests | 16 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 92 | Finance – Forecast Deficit | 25 | - Director of Finance & Performance - Performance & Finance Committee |
| 93 | Capital Plan | 20 | - Director of Finance & Performance - Performance & Finance Committee |
| 96 | Develop an Approvable IMTP (statutory compliance) | 20 | - Director of Strategy - Performance & Finance Committee |
| 98 | Overall condition/compliance and suitability of Health Board Estate | 20 | - Director of Finance & Performance - Performance & Finance Committee |
| 99 | Failure to implement the population health strategy approaches at the required scale | 20 | - Director of Public Health - Population Health & Partnerships Committee |
| 101 | Industrial Action (HCSW) | 20 | - Director of Workforce & OD - Workforce & OD Committee |

The full HBRR at Appendix 4 details key controls in place to manage these risks and actions being taken to address them further. The Board’s Committees receive regular reports on their allocated risks highlighting key steps taken to manage risk to an acceptable level. Reports also include updates on those risks below appetite, in recognition of the Board’s aspiration to reduce risks further.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries or dedicated board/committee papers for information.

- RECOMMENDATIONS

Members are asked to:

- CONSIDER the revised Board Assurance Framework, template for a new Strategic & Assurance Register and risk strategic implementation plan;

- SUPPORT these documents, subject to any final changes, to be submitted to the Board for consideration;

- RECEIVE the Health Board Risk Register (HBRR) and update on risk matters.

- CONSIDER whether further assurance is required on risks and associated actions & controls – In particular on those risks exceeding the Board’s stated appetite levels.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | This report updates on risk matters received in July 2024. |  |
| Appendices |  | Appendix 1 - Board Assurance Framework. Appendix 2 Template for a new Strategic & Assurance Register Appendix 3 Risk Management Strategic Implementation Plan Appendix 4 – Health Board Risk Register (HBRR) Risks |  |