| Meeting Date | 11 March 2025 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Meeting Name | Digital Data Research and Innovation Committee |  |  |  |  |  |
| Report Title | Clinical Coding Internal Audit Update Paper |  |  |  |  |  |
| Report Author | Lee Morgan, Assistant Director of Digital Intelligence |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Lee Morgan, Assistant Director of Digital Intelligence |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides an update of the 12 management actions identified as part of a limited assurance internal audit on Clinical Coding, published on 16th August 2024 and the Clinical Coding Modernisation report that was approved at Formal Executive Board on 26th February 2025. |  |  |  |  |  |
| Key Issues | The paper identifies that of the 12 recommended actions, 10 are completed, 1 is on hold and 1 is in progress. One action is due for completion in the forthcoming months. The plan to address the key issue of performance against the Tier 1 target requires the implementation of auto-coding and associated remodelling of the Clinical Coding workforce. A report on coding modernisation was taken to the formal executive board on the 26th February 2025. This report outlined 4 main options and recommended reallocating the existing coding budget to implement an auto-coding solution and re-band the department with any remaining budgeted coding vacancies filled. This recommendation was presented to the Formal Executive Board and approved on 26th February 2025. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | The Committee is asked to: - Acknowledge the progress made against the Clinical Coding Internal Audit; - Note the approval of the recommendation within the Clinical Coding Modernisation Report at the Formal Executive Meeting on 26th February 2025. |  |  |  |  |  |

INTRODUCTION

This report provides an update of the 12 management actions identified as part of a limited assurance internal audit on Clinical Coding, published on 16th August 2024 and updates on the Clinical Coding Modernisation report approval by formal executive board on 26th February 2025.

- Update

Since the previous Clinical Coding Internal Audit Update report, presented to the committee on 16th January 2025, a coding intranet page has been created containing information and resources on the Coding Department and the bookmark sheet showing clinician terms to use/not use within the notes has been distributed as outlined in the audit management action plans.

Of the 12 actions identified 10 have now been completed and 1 (3.1a) is on hold due to the recruitment freeze.

3.1a Appointment of a Band 6 Service Improvement lead responsible for creation and enabling of a service improvement plan).

The remaining action of the coding department being centralised at the Ty Samlet Unit is due April 2025.

GOVERNANCE AND RISK ISSUES

The Clinical Coding department currently has 3 whole time equivalent (WTE) vacant trainee posts which, though approved by vacancy panel in October 2024, are still awaiting Welsh translation of the job descriptions. Since the report was produced, the Trainee manager has vacated their post and moved into the national team based at Digital Health and Care Wales (DHCW). The band 6 Service Improvement post is on hold due to the vacancy freeze. In total the department has a 6.5 WTE vacancy factor.

Non recruitment into clinical coding posts and lack of investment into clinical coding continues to result in a failure of the Tier 1 target. It also impacts on the Health Board Welsh Costing Returns (WCRs), completion of freedom of Information Requests (FOIAs) where clinical data is requested, and also population health requests when planning for future services.

A report on Clinical Coding Modernisation was approved by the Formal Executive Board on 26th February 2025. This report outlined 4 main options and recommended re-allocating a proportion of the remaining coding budget derived from the current vacancy factor to implement an auto-coding solution and re-band the department. This included a three-year plan which would result in 98% of episodes being coded by year three meeting Tier 1 Welsh Government coding targets.

- FINANCIAL IMPLICATIONS

The three-year resource plan approved by formal executive board is cost-neutral and is within existing budgets.

- RECOMMENDATION

The Committee is asked to:

- Acknowledge the progress made against the Clinical Coding Internal Audit;

- Note the approval of the recommendation within the Clinical Coding Modernisation Report at the Formal Executive Meeting on 26th February 2025.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Clinical Coding is used from a quality perspective to inform the Health Board Welsh Costing Returns (WCRs), completion of freedom of Information Requests (FOIAs) where clinical data is requested, and also population health requests when planning for future services. These services can also have a direct impact on patient experience. |  |  |  |
| Financial Implications |  |  |  |
| Cost-neutral plan within existing budgets has been approved for the recruitment of additional trainee coders and modernisation of department through the implementation of auto-coding solution and re-banding of the department this will entail. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Staffing Implications |  |  |  |
| Non-recruitment of staff will continue to have a detrimental effect on achieving the Tier 1 Target. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | January 16th |  |
| Appendices |  | Appendix 1 |  |