## Slide 1: The SBUHB Digital Strategy Mobilisation Plan: 2025-26
Setting out the critical next steps to promote the success of the Swansea Bay University Health Board Digital Strategy
February 2024

## Slide 2
Contents
1. | Summary | p. 3
2. | Kotter’s 8 Step Model | p. 4
3. | Ingredients for Successful Delivery | p. 5
4. | Activities for the Year One and the Next 12 Weeks | p. 6
5. | Mobilisation Risks | p. 12

## Slide 3
From Strategy to Reality
In developing the SBUHB Digital Strategy to 2035 we engaged extensively with colleagues across the organisations in both group and 1:1 settings. A consistent theme was a general nervousness about what would happen once the strategy was developed and how quickly staff would start to see action and feel like they were making tangible progress towards the new digital vision.
Research from the Harvard Business Review confirms what many of us already suspect – the majority of strategies fail.*
The reasons for this are varied, but high on the list is that most strategies never fully launch at all. We know that taking prompt action and seeing tangible progress in the first 12 weeks and the first year following strategy development is essential to maximising an organisation’s opportunity to succeed.
Typically, organisations underestimate the work that goes into building momentum and engagement around a strategy – that energy is lost far more quickly than it’s gained and as soon as a strategy is seen to stop or ‘pause’ colleagues tend to disengage. This cannot be allowed to happen for SBUHB.
Delivery of the SBUHB Digital Strategy for 2035 will require significant changes to organisational ways of working, with all teams taking a much more collective responsibility for digital transformation and the realisation of the potential benefits.
This Mobilisation Plan sets out the 3 key areas of work that must now be undertaken over the course of the next 12 weeks and 12 months to evaluate SBU’s current work and maximise the SBUHB Digital Strategy’s success.
The three areas are:
    Aligning – securing sign-off, maintaining momentum and building buy-in
    Mapping – testing and prioritising digital projects against the new vision,
    Structuring – setting up the programme for success
  By making progress quickly and ensuring readiness to deliver, SBUHB can capitalise on the energy, engagement and good will built up through the strategy development work and realise the ambitions of both the 3-year Digital Roadmap and the broader SBUHB Digital Strategy to 2035.
*Source: 4 Common Reasons Strategies Fail, Harvard Business Review (2022)

## Slide 4
Kotter’s 8 Step Model – Successful Transformation in the NHS
The chevrons below show Kotter’s 8 step model for successful transformation in the NHS alongside an initial RAG rating for SBU’s current progress against each step as of February 2024
SBUHB has begun to build a sense of urgency and to build a coalition of the willing around the future vision and this now needs to extend, broadening out to reach more colleagues across more teams so that we can build a cultural commitment to digital transformation.
This will require both Executive support and endorsement as well as a willingness from SDGs and other service teams to partner with Digital Services and take shared responsibility for the realisation of the desired benefits
This Mobilisation plan will support SBUHB to continue to build on steps 1 – 4 whilst making concerted progress against steps 5) and 6)
1) Create Urgency
2) Build a Guiding Coalition
3) Create Vision
4) Communicate Vision
5) Empower action by Removing Barriers
6) Generate short-term wins
7) Build on the change
8) Anchor in Organisational Culture

## Slide 5
Ingredients for Successful Delivery of the SBUHB Digital Strategy
Alignment with the strategic agenda
Executive endorsement and active commitment
Buy-in from all levels and a sense of urgency and importance
Organisational commitment and belief in the value of the financial investment in Digital
Development of an organisational wide Benefits Framework to enable clear articulation of benefits and a shared sense of the scale of the opportunity
Single coherent view mapping all the digital and data work and capabilities being carried out and supported across SBUHB, including those supported by the Digital Services team, but also other organisation-wide activities
Development of a Prioritisation Framework using the agreed set of criteria from the Benefits Framework to test activities (both current and future) against the future vision
Application of the framework, starting to rationalise projects and BAU activities, freeing up capacity for the programme, while acknowledging the dis-benefits to services that may occur in the short-term
Set-up of appropriate Delivery Vehicle for the work across existing portfolios and new programme areas
Align individuals with the most critical skills and experience to specific areas of delivery ensuring ownership and accountability for outcomes
Robust reporting and governance processes with appropriate technical and strategic support available to unblock challenges
Set-up appropriate KPIs and define success criteria to track delivery and celebrate success
Continuing business critical activities and delivering on commitments such as the CTM disaggregation
ALIGNING
MAPPING
STRUCTURING

## Slide 6
Year One SBUHB Digital Strategy Activities
SBUHB Digital Strategy Mobilisation Plan
ALIGNING
MAPPING
STRUCTURING
Socialisation and engagement with executives and SBUHB teams – sustaining and building momentum and excitement
Mapping current digital commitments to understand capacity and work needed to keep the lights on
Development of a prioritisation framework to test work activities against
Rationalisation and streamlining of digital activities
Secure financial commitment and conduct more detailed financial modelling and costings
Development of an organisational wide benefits framework to better understand full potential of transformation and to aid organisational support and motivation
Design the Delivery Vehicle and organising digital portfolios to support the strategic programme
Governance review and set-up of new Technical Design Authority (TDA), Clinical Design Authority (CDA) and central governance Board with membership across SBUHB
Workforce Strategy to understand the skills and experience required to deliver the strategy and kick off recruitment
Continuing business critical activities

## Slide 7
The Next 12 Weeks – Evaluating next steps and ensuring readiness for Success
SBUHB Digital Strategy Mobilisation Plan
Supporting colleagues at all levels to engage with the vision and directly contribute to the strategic direction for digital, advocating for the agenda as a critical SBUHB priority
Aligning
1
Commitment at all levels
Completing a mapping of SBUHB digital systems, services and programmes – rationalising and consolidating directorate activity by testing and prioritising against the strategic vision
Mapping
Every project with purpose
Designing an optimised delivery vehicle to undertake the work required to realise the SBUHB digital strategy, focussing initially on the ambitions of the 3-year Roadmap
Structuring
3
Teams ready to deliver
Preparation Year
Key Activities
Socialisation and Executive Alignment
Develop Benefits Framework
Financial Planning
Immediate Priorities
Key Activities
Mapping Digital Provision
Developing Prioritisation Criteria
Testing Current Directorate Portfolio
Key Activities
Portfolio Alignment
Review Governance and Assurance
Design Programme Structure
2
This work will need to take place alongside BAU and whilst continuing to support and sustain business critical digital activities

## Slide 8
Indicative Mobilisation Plan
SBUHB Digital Strategy Mobilisation Plan
Socialise Strategy with Execs
Sign-off
Benefits Framework Development
Benefit analysis and detailed financial modelling (aligned to annual planning)
Financial sign-off
Engagement & socialisation across SBUHB teams to secure buy-in and maintain momentum
Mapping of digital workload
Develop prioritisation framework
Test and prioritise current workload
Strategy sign-off
Financial sign-off in principle
First Capacity Released
Digital Services Mapping
Digital Services Portfolio Alignment
Design Strategy Programme & Review Governance
Set-up Programme
Set-up new process/groups e.g. TDA with Central Digital Board
Launch Governance
Digital Workforce Strategy
Begin planning and scoping of EPR approach
Digital assessment & early mapping to kick-start work on data standards
Recruitment to fill immediate skills gaps
Implement Strategically aligned solutions agreed in IMTP ie EPR Integrated Teams, Maternity EPR, Ophthalmology EPR
Business Case Submitted
Strategy Sign-off
Regular programme reporting and updates against key metrics and outcomes
Begin rationalisation and consolidation of
digital activity
Develop business case for UEC EPR
Begin planning and scoping of CDR approach
Workstreams | 
ALIGNING | 
MAPPING | 
STRUCTURING | 
SOLUTIONS | 
Socialise Strategy with Execs
Sign-off
Benefits Framework Development
Benefit analysis and detailed financial modelling (aligned to annual planning)
Financial sign-off
Engagement & socialisation across SBUHB teams to secure buy-in and maintain momentum
Mapping of digital workload
Develop prioritisation framework
Test and prioritise current workload
Strategy sign-off
Financial sign-off in principle
First Capacity Released
Digital Services Mapping
Digital Services Portfolio Alignment
Design Strategy Programme & Review Governance
Set-up Programme
Set-up new process/groups e.g. TDA with Central Digital Board
Launch Governance
Digital Workforce Strategy
Begin planning and scoping of EPR approach
Digital assessment & early mapping to kick-start work on data standards
Recruitment to fill immediate skills gaps
Implement Strategically aligned solutions agreed in IMTP i.e. EPR Integrated Teams, Maternity EPR, Ophthalmology EPR
Business Case Submitted
Strategy Sign-off
Regular programme reporting and updates against key metrics and outcomes
Begin rationalisation and consolidation of
digital activity
Develop business case for UEC EPR
Begin planning and scoping of CDR approach
April
May
June
July
Aug
Sept
Oct
Nov
Dec
Jan 25
Feb 25
Mar 25
First 12 Weeks

## Slide 9
Supporting colleagues at all levels to play their role in delivering the future vision for digital, and to advocate for the agenda as a critical SBUHB priority
Aligning
1
Commitment at all levels
It is crucial to empower our colleagues across SBUHB to actively contribute to realising the Digital Strategy future vision as achieving benefits and improved outcomes relies on embedding the strategy throughout the organisation. By securing buy-in now from all levels and departments, we can prepare our colleagues to more readily embrace the digital initiatives in the future. Unless we act promptly, we risk losing the momentum and commitment we have cultivated throughout the Digital Strategy process.
Activity | Description | Process
Strategy Sign-off | Taking the SBUHB Digital strategy to 2035 through the internal governance processes and securing formal sign-off from the SBUHB Executive | Board level sign-off through formal processes
Socialising Strategy with Executives | Supporting each of the executives to understand the impact of the digital strategy to their portfolio and what will be required from them to support the strategy to succeed This includes helping executives understand that in order to focus our capacity and resource on delivering the future digital vision, some projects will need to stop, and some digital asks won’t be able to be fulfilled It will require them to act as Senior Responsible Officers for individual programmes of work whilst also releasing their resources to contribute to specific projects | Director of Digital to hold 1:1s with Executives Group discussions and presentations focussed on the digital strategy Articulated benefits for each executive portfolio area and SDG Support for executives and leaders to engage with their teams directly on the strategy Identification of key influencers and change champions to support the work
Socialising Strategy across SBUHB Teams | Working with individual teams as well as through group forums to share the strategy and discuss the implications for the different areas including their role in delivering the transformational benefits, key outcomes and consequences for current digital projects which might need to stop | 
Financial Planning and Discussion | Securing agreement in principle for increasing the levels of financial investment in digital to deliver the future vision subject to further modelling and benefits analysis | Preparation of materials Discussions with finance and agreement in principle
Benefits Framework and Analysis | Support the development of an Organisational wide Benefits Framework Conducting detailed analysis to understand the alignment of the Strategy to the Benefits Framework, including improved outcomes, efficiencies and cash releasing opportunities As part of this, considering that by standing down some programmes or projects there might be some negative consequences on services in the short to medium term | Benefits identification Benefits modelling Benefits impact assessment
Financial Modelling | Building the benefits assumptions into the broader financial model and investment planning, and iterate the financial modelling as clarity is gained around certain solutions | Financial modelling conducted for both the 3-year and 2035 horizons with benefits analysis built in

## Slide 10
Activity | Description | Process
Map digital workload | Mapping out the full range of digital and data projects, programmes, services and capabilities currently being carried out and supported across SBUHB, including those supported by the Digital Services team, but also other organisation-wide digital activities. Understanding the level of resource attached to each area of work and the intended outcomes and impact | In partnership with digital services leads, complete a mapping of the entire workload Assess the resource allocation of workload components
Develop prioritisation framework | Develop a set of criteria by which to judge whether a piece of work is sufficiently aligned to the future vision, or sufficiently critical to BAU that it justifies continued or new resource being given to it. Judging an area of work against the criteria needs to be straightforward with little room for ambiguity or disagreement about the performance of an area against the framework This will enable consistency of application and is likely to improve adoption, while acknowledging that as technology advances there will be some technology that we inevitably need to support | Development of the criteria, led by the Digital Services team with input from wider SDG and programme stakeholders Iteration of the framework soliciting feedback from across the organisation Sharing of the final framework through formal governance channels to assure the process
Test and prioritise current workload | Start to apply the prioritisation framework developed to assess the appropriateness of each current project in relation to the Digital Strategy future vision. Evaluating each project against the prioritisation framework allows the Digital Services team to begin to identify which projects build towards the future vision, and which should be stood-down. This will help to identify opportunities for SBUHB to release capacity which can then be redirect for other solutions contribute more directly towards the Digital Strategy Vision We need to establish our appetite for risk – halting projects and maintaining legacy solutions both entail a level of risk. Establishing our risk appetite enables consistent decision making and clear communication with the organisation | For each project identified in the initial mapping exercise, assess it against the prioritisation workload Use this to develop a score-card by which to identify projects that should be considered for stand-down
Begin rationalisation and consolidation | Reviewing low scoring projects identified through the framework against available resources - these projects contribute less directly to the delivery of the future vision and SBUHB should consider discontinuing them Any programmes which are stood down require a robust plan to ensure minimal disruption to services and clear communication with colleagues to manage expectations. As part of this, anticipating that stand-down projects will also require resources in the short-term Reallocating resources effectively to maximise the success of priority programmes | Assess the low-scoring projects against the available delivery resource to make a formal decision on the projects that will be stood-down to free up capacity Make a plan for each of the identified projects and communicate expectations Ensure efficient reallocation of resource with support from relevant teams
Completing a mapping of SBUHB digital systems, services and programmes - consolidating directorate activity by testing and prioritising against the strategic vision
Mapping
2
Every project with purpose
Without a comprehensive understanding of the current landscape, we risk duplicating efforts and wasting valuable time and resources. Aligning current digital activities with our strategic vision is imperative to ensure that all our energy is directed towards building the future vision for our organisation. By prioritising and consolidating efforts now, we can streamline operations, minimise time spent on less valuable activities, and focus our resources on initiatives that drive us closer to our strategic goals.

## Slide 11
Designing an optimised delivery vehicle to undertake the work required to realise the SBUHB digital strategy focussing initially on the ambitions of the 3-year Roadmap
Structuring
3
Teams ready to deliver
Setting up our digital governance for success is crucial to achieving the objectives outlined in our Digital Strategy. By acting swiftly to establish an optimised governance and reporting mechanism, we can ensure efficient execution of initiatives, timely achievement of milestones and continued alignment with our strategic goals. This proactive approach will enable us to capitalise on opportunities, mitigate risks as they arise, and stay on course to realise our digital vision.
Activity | Description | Process
Portfolio Alignment | Organisational alignment with the digital strategy and existing priorities Review the Digital Strategy solutions portfolio against the current Digital Services workload, to identify where there is immediate alignment This will help to identify ‘quick wins’ and to maintain momentum for those solutions where existing teams / programmes are able to easily drive these forward | Consolidate the new digital solutions with the mapping of existing work Where there is alignment allocate digital solutions to these programmes/teams Communicate decisions clearly & share workplans
Governance Review and Design of New Processes | Embedding Digital into Operational Governance Framework and reporting (think digital!) Evaluate existing governance frameworks, committees, and decision-making processes to identify strengths, weaknesses and areas for improvement Iterate the governance framework outlining the structures, roles, responsibilities and decision-making processes. Design a new Technical Design Authority (TDA) responsible for ensuring that technical solutions align with the organisational standards, cyber security requirements and strategic objectives Consider establishing a Clinical Design Authority (CDA) responsible for ensuring that clinical requirements are effectively incorporated into the design, development and implementation of digital solutions | Conduct governance review Develop new governance process based on findings including documentation and collateral for any new governance forums Iterate and test with SBUHB leadership team and SBUHB Digital Services team
Establish New Governance | Identify the key individuals / teams required for the new governance processes Develop appropriate governance documentation and a change management plan to communicate governance changes. Establish operating procedures and guidelines, defining meeting schedules and reporting mechanisms | Identify key stakeholders for new governance groups Communicate changes to the organisation Develop governance documentation Implement new governance groups
Set-up the Digital Strategy Programme | Dedicating a team from across SBUHB that is responsible for the delivery and implementation of the Digital Strategy will increase the likelihood of success Ensure this is the right mixture of people is critical – there needs to be organisational buy-in to support the delivery of the Digital Strategy combined with Digital Expertise This group will need to meet regularly to monitor and evaluate the programme performance, with individual projects reporting to the programme board and SRO | Identify key individuals including digital professionals, clinicians, departmental reps and patient representatives to lead the running of the programme and design the optimum structure to support delivery particularly focussing on robust reporting, managing interdependencies, collaborative delivery and avoiding silos
Establish Reporting | Ensuring the appropriate reporting mechanisms are in place is critical to optimising the delivery of the digital strategy, and establishing this early will be key | Define reporting requirements, frequency, templates and recipients

## Slide 12
Current Asessment of the Mobilisation Risks
Theme | Current Risk | Proposed Mitigations
Organisational & National Alignment | There is a risk that there is a perceived misalignment between the priorities of the digital strategy, the wider organisation and national, resulting in difficulty mobilising the Digital Strategy due to limited buy-in from non-digital stakeholders from across SBUHB and DHCW | Achieve formal sign-off from the Execs, rapidly following strategy completion Sustain communication efforts with both Execs, the wider organization and DHCW, communication key priorities and immediate next steps, and continuing to align the Digital Strategy programme with the organisational priorities
Culture, Empowerment & Belief | While the Digital Services team have developed positive relationships with clinical and operational teams, established collaborative processes are currently limited which risks perpetuating siloed ways of working. This could risk reinforcing a culture where digital and non-digital teams work in siloed ways – some view digital initiatives as solely owned by Digital Services while others independently source digital solutions | In the short-term, the Digital Strategy will require universal buy-in. Digital and non-digital leadership need to socialise the strategy and demonstrate the achievability of its plans to staff Ensure there is non-digital representation as part of the governance processes for the Digital Strategy as a whole, as well as for individual projects including establishing Clinical Digital leadership group and Clinical Design Authority
Governance & Reporting Framework | Siloed management of digital initiatives without a comprehensive overarching governance structure and sufficient technical input, increases the risk of fragmented strategic components. Similarly, SBUHB have historically struggled to prioritise robustly and stop work that isn’t serving them which risks not releasing sufficient capacity to deliver | Review and establish refreshed governance and reporting frameworks and processes to support centralised progress sharing and priority setting, allowing for innovation and ‘failing fast’ where appropriate Establish a TDA responsible for solutions aligning with the organisational strategy Develop and apply prioritisation framework consistently – commit to saying “no”
Ownership & Accountability | If there is unclear indication of ownership for individual components of the strategy, there is a risk of ambiguous accountability leading to potential implementation challenges | As part of reviewing and establishing governance processes for the Digital Strategy programme, identify accountable officers for each project in the portfolio Through governance groups, foster a culture of supportive challenge where programmes are not on track or change in approach is needed
Appropriate Benefits | Whilst there have been Benefits proposed for solutions as part of the 3-Year Roadmap, if benefits are not aligned to HB strategic objectives and not used to inform decisions on the Digital Strategy, it poses a risk of inadequate performance measurement and strategic alignment. | Agreeing an organisational method for identifying, tracking and responding to benefits related to the Digital Strategy Strategising how benefits will be adapted and reported on as digital solutions progress over time
Skillsets | The potential presence of skills gaps in areas of required digital expertise, e.g., digital procurement, and modern digital skills, e.g. cloud service platform skills, software defined networking and advanced cyber security skills, combined with the capacity pressures already faced by the digital workforce poses a challenge to the execution of critical Digital Strategy solutions. | Conduct a prompt gap analysis to identify missing staff capabilities and accompanied recruitment drive to fill the identified capability gaps Execute the mapping exercise of current digital projects led by both digital teams and services to consolidate workload and free up capacity for new activities Increased digital team training and development offering to increase productivity, build skills and improve retention
Finance & Resourcing | Failure to secure financial commitment for the Digital Strategy investment required, due to the sstantial increase in budget proposed, risks making successful implementation unviable | Develop comprehensive financial and benefits analysis of the Digital Strategy Promptly mobilise the financial planning discussions required to secure funding in principle for the Digital Strategy