## Sheet1
Milestone Description | Assigned To / groups committees | Progress | Progress | outstanding risk | Mitigation
MCA DoLS Establishment
Appoint MCA Lead |  | Interview 22/12 | post offered and accepted due to commence 3rd March 24 | Will require induction period short timescale to handover prior to end of Corporate HON contract. | Support from Long Term Care manager in the interim
Appoint to all MCA posts | Professional development nurse | complete
| Business admin manager | complete
| 2 x Best Interest Assessors | 1 in post 1 out to advert | due for interview 6th Feb 6 for interview | managing workload until in post and inuction complete | Use of independent asessors
Transfer funded establishment to PCTSG | Finance and HR leads | Meeting set for January | Meeting held, forms to be sent out for completion
MCA
Governance and reporting | MCA Policy | Currently working to relevant codes of practice no MCA policy in place | To progress once MCA lead in post | No SBUHB MCA Policy | Work to relevant codes of practice
| MCA DoLS operational group | To be developed | To progress once MCA lead in post
MCA DoLS regional subgroup
SBUHB Safeguarding Group
Western Bay Safeguarding Board
Mental Health and Legislative committee reporting
Risk management | Review corporate risks and transfer |  | Reviewed with Assistant Head of Risk and Assurance January 2024 | To be reviewed once service established and risks handed over | Oversight by Head of Nursing and Long Term Care manager MCA in the interim
Management structure | PCT Nurse director management structure |  | New lead post will report to Interim Head of Long Term Care, while senior structure is reviewed
Operational | Set up centralised MCA mailbox |  | To be established once MCA lead in post |  | Currently picked up by DoLS Mailbox
| Weekly monitoring and escalation process |  | Currently weekly data review of DoLS progress and MCA issues, held with Long Term Care manager DoLS lead and Corporate Head of Nursing this will continue with new MCA lead
DoLS
Oversight of database and in box
weekly allocation BIA resource
weekly monitoring of referrals waiting list and case progress
| Review Sign off and S12 resource |  | Fragile structure, not allocated within any body's job plan, currently being undertaken as overtime. Needs reviewno leave or absence cover | Increased breaches | Use of overtime for sign off to be included as part of management structure review
Training
Develop L 3 training | Package developed to be trialled with Service groups in new Year |  | Close working with learning and development to ensure HB governance and ESR compliance measures are in place | capacity to deliver due to sickness absence | Use of BIA staff to supportas part of the role
Agree HB training plan | Proposal for L1 and 2 to discuss with Head of Education and learning in January |  | Proposal agreed in principle. Head of Learning and development to take to HB education and leadership forum end of January and will feed back
Set up administrative system for delivering and reporting on MCA DoLS Training | Link with ESR and education and learning |  | Leadership and development team will support with setting up of course structure for monitoring and reporting