| Meeting Date | 03 February 2026 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | The Additional Learning Needs Act: Update on Monitoring and Management Action Plan following Internal Audit |  |  |  |  |  |
| Report Author | Dr Luke Jones, Designated Clinical Lead Officer (DECLO) |  |  |  |  |  |
| Report Sponsor | Alison Clarke, Deputy Director of Allied Health Professions and Health Sciences |  |  |  |  |  |
| Presented by | Dr Luke Jones, DECLO |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides an update regarding progress with actions that were agreed in response to Internal Audit Services’ report on the Health Board’s arrangements to ensure compliance with the Additional Learning Needs and Education Tribunal (Wales) Act 2018 (ALN Act). |  |  |  |  |  |
| Key Issues | Further progress has been made with the completion of management actions agreed from completion of the audit in January 2024. A single action remains outstanding and overdue, with a target completion date of February 2026. The Health Board can now provide assurance regarding meeting its duties under the ALN Act. Data that is now available shows some ongoing compliance risk, but appropriate governance mechanisms are now in place to manage these issues and risks. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Receive this as an update. |  |  |  |  |  |

THE ADDITIONAL LEARNING NEEDS ACT: UPDATE ON MONITORING AND MANAGEMENT ACTION PLAN FOLLOWING INTERNAL AUDIT

- INTRODUCTION

This report follows up on a report that was provided to this Committee in October 2025.  It provides assurance regarding further progress that has been made with completing management actions that were agreed in response to Internal Audit Services’ January 2024 report on the Health Board’s arrangements with regards to the ALN Act.

- BACKGROUND

This Committee received a report on progress against the 23 agreed management actions that were agreed in response to the auditors’ recommendations in 5 thematic areas in May 2025 and a further update in October 2025.  All management actions had been completed by the time of the October report, apart from a single action which remained outstanding.

An update on progress against the one outstanding action follows.

  - Resource implications

Management action required: to formalise and document arrangements between Swansea Bay, Hywel Dda and Powys Health Boards regarding joint funding of the statutory Designated Education Clinical Lead Officer (DECLO) role.

The Deputy Director for Allied Health Professions and Health Sciences has collaborated with neighbouring Health Board colleagues to formalise the financial arrangement whereby the DECLO is hosted by Swansea Bay but also covers Hywel Dda and Powys Health Boards.

This action remains unfinalized, though a draft letter to neighbouring Health Boards has been agreed with Finance and it is anticipated that this action will be completed, with responses received, by the end of February 2026.

Interim assurance can be provided that no issues or concerns have been raised with regard to the above; that working relationships between the three Health Boards with regard to the DECLO post are excellent; and that this is therefore not assessed as being an area of significant risk for the Health Board.

- GOVERNANCE AND RISK ISSUES

Governance matter of need to close down final outstanding action.  Risk associated with this action is assessed as being low given excellent ongoing collaboration between the three Health Boards of South West and Mid Wales regarding the DECLO post.

- FINANCIAL IMPLICATIONS

None linked to matters addressed in this report.

- RECOMMENDATION

It is recommended that the Committee:

- notes progress made in completing the final outstanding management action that were agreed in response to the audit’s recommendations and received assurance that this is expected to be closed by the end of February 2026.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The Health Board’s compliance with its duties under the ALN Act is crucial to the ALN Act’s aims of better outcomes and better experiences for children and young people with ALN being realised. |  |  |  |
| Financial Implications |  |  |  |
| No new financial implications at this stage. Financial implications may become apparent when further demand / capacity analysis is carried out by Operational services. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The ALN Act placed legal duties on Health Boards. This Health Board has an infrastructure and processes that enable it to provide assurance regarding the extent to which it is fulfilling these duties. |  |  |  |
| Staffing Implications |  |  |  |
| Actions have been undertaken with regard to staff training, raised in the initial audit report, to ensure that the workforce has the necessary skills and training required to meet the requirements of the ALN Act. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Well-being of Future Generations Act’s 5 ways of working align closely with the general principles underpinning the ALN Act: - Long Term – facilitating access to education and promoting independence for some of our most vulnerable groups will enhance the long-term life chances of these individuals. - Prevention – early identification of needs and effective early help are key principles underpinning the ALN Act - Integration and Collaboration – collaboration between Health Boards and Local Authorities is a key principle underpinning the Act. - Involvement – Person-centered practice with the voice of the child at the heart of decision-making is another key principle underpinning the ALN Act. |  |  |  |
| Report History |  |  |  |
| Appendices |  | Appendix I: ALN Internal Audit Report January 2024 |  |