| Meeting Date | 06 May 2025 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | The Additional Learning Needs Act: Update on Monitoring and Management Action Plan following Internal Audit |  |  |  |  |  |
| Report Author | Dr Luke Jones, Designated Education Clinical Lead Officer (DECLO) |  |  |  |  |  |
| Report Sponsor | Christine Morrell, Executive Director of Allied Health Professions and Health Sciences |  |  |  |  |  |
| Presented by | Dr Luke Jones, DECLO |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides assurance regarding progress with actions that were agreed in response to Internal Audit Services’ report on the Health Board’s arrangements to ensure compliance with the Additional Learning Needs and Education Tribunal (Wales) Act 2018 (ALN Act). |  |  |  |  |  |
| Key Issues | Continued progress has been made with the completion of management actions, working within timescales that were reset with the agreement and oversight of the ALN Steering Group. Regular updates on progress have been provided to the audit committee via the audit tracker report produced by the Head of Compliance. The majority of agreed management actions have been completed as planned, with a small number of actions remaining open. It should be noted that Audit and Assurance services have requested additional information regarding the basis on which some of these actions have been closed. This is part of an annual follow-up review undertaken by Audit and Assurance where they verify the basis for closing down a sample of management actions across a number of audit reviews, across SBUHB. The information that has been requested is currently being collated. Based on data that is now available, assurance will be provided to the Health Board’s ALN Steering Group on the 20th May 2025 regarding the extent to which the Health Board is meeting new statutory requirements that have been introduced through the ALN Act. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - receive assurance regarding the progress that has been made in addressing the limited assurance rating provided by the audit; - receive progress made in completing management actions that were agreed in response to the audit’s recommendations; - receive assurance that while most audit actions have now been completed, activity overseen by the ALN Steering Group is either ongoing or planned to ensure that there is ongoing improvement in how the Health Board, working collaboratively with its Education delivery partners, delivers on the requirements of the ALN Act and contributes towards better outcomes and experience for children and young people with ALN. |  |  |  |  |  |

The Additional Learning Needs Act: Update on Monitoring and Management Action Plan following Internal Audit

- INTRODUCTION

This report follows up on a report that was provided to this Committee in December 2024 (embedded at ‘Report History).  It provides assurance regarding continued progress that has been made with management actions that were agreed in response to Internal Audit Services’ January 2024 report on the Health Board’s arrangements with regards to the ALN Act.  The audit (which is attached at Appendix I) provided the Health Board an overall ‘limited assurance’ rating, noting the impact of resourcing issues on the Health Board’s implementation of the ALN Act.  There were 23 agreed management issues in response to 20 recommendations in 5 thematic areas / ‘matters arising’ in the audit.

- BACKGROUND

The ALN Act was introduced in September 2021, with implementation phased through to September 2025.  It aims to ensure better outcomes and experience for children and young people with additional learning needs (ALN).  While the Act is Education legislation, it introduced a number of new legal duties for Health Boards in recognition of that fact that many children and young people with ALN have significant healthcare needs that impact their ability to make progress with learning.  A joined-up approach between Health and Education is critical for them to achieve positive outcomes.

An audit carried out by Audit and Assurance Services in autumn 2023 provided an overall ‘limited assurance’ rating on the arrangements in place in the Health Board to ensure compliance with the ALN Act.  Their report, noting the impact of resourcing issues on the Health Board’s implementation of the ALN Act, contained 23 agreed management actions in response to 20 recommendations in 5 thematic areas (‘matters arising’) in the audit.  Initial timescales for completing these management actions were reset in June 2024 and a progress update was provided in December 2024.

The current report provides a further update on progress in the audit’s 5 thematic areas.  For assurance, Appendix II provides an updated ‘Audit Tracker’ that has been used to provide regular updates to the Audit Committee.  Appendix II document shows a number of actions as being ‘overdue’ where the deadlines have been adjusted (see comments in Column L).

In several areas, agreed management actions have closed down but activity is either ongoing or planned to ensure that there is ongoing improvement in how the Health Board, working collaboratively with its Education delivery partners, delivers on the requirements of the ALN Act and contributes towards better outcomes and experience for children and young people with ALN.

The Audit and Assurance services have requested additional information regarding the basis on which some of these actions have been closed.  This is part of a wider piece of work that Audit and Assurance are conducting with the Health Board, to verify the basis for closing down management actions.  The information that has been requested is currently being collated.

2.1	Matter arising 1: Governance arrangements

All actions to address the audit’s findings in relation to governance arrangements have now been completed.

Since the last update report, the ALN Steering Group has reviewed and assessed existing Terms of Reference for the ALN Steering and Operational Groups, the jointly developed strategy, and collaborative governance arrangements around ALN more generally.  Revisions to Terms of Reference and collaborative governance arrangements have been approved.

It has been agreed that there will be activity over summer 2025 to refresh and update the joint ALN strategy.

2.2	Matter arising 2: Policies and Procedures

Since the last update report, key documents including Standard Operating Procedures and guidance documents have been reviewed by the ALN Operational Group and approved by the ALN Steering Group.  These have been saved in a central resource depository that is accessible to all relevant staff.

This action cannot be fully closed down as planned, as it was identified that Equality Impact Assessments (EQIA) of the Standard Operating Procedures has not yet been carried out.  EQIA activity is ongoing and finalised documents will be brought for approval to the ALN Steering Group on the 20th May 2025.

2.3	Matter arising 3: Delivery Priorities

A key factor in the overall ‘limited assurance’ provided by the audit was that only limited data was available to measure the Health Board’s compliance with its legal duties under the ALN Act.  Significant activity has since been undertaken to establish a digital infrastructure and revised operational processes to enable the Health Board to robustly monitor its compliance with its statutory duties.  The new digital infrastructure and revised operational processes were ‘launched’ in January 2025, meaning that from this point onwards, data is available to provide assurance regarding the Health Board’s compliance with key legal duties.

For assurance purposes, a first compliance report based on this data will be brought to the ALN Steering Group on the 20th May 2025.  Once this report has been provided, all management actions in this thematic area can be closed down.

2.4	Matter arising 4: Resource implications

The audit noted resource challenges for both Corporate and Operational services.

Resource has been secured for the corporate infrastructure required to support ALN implementation and Health Board compliance.  Work remains ongoing to bring in the capacity that is required.  Activity also remains ongoing to formally document arrangements between Swansea Bay, Hywel Dda and Powys Health Boards regarding joint funding of the (Corporately-hosted) DECLO role.  Responses from the neighbouring Health Boards required to close down this action remain outstanding.

2.5 	Matter arising 5: Effective mechanisms

A number of issues were identified under matter arising 5, including staff training, capturing the voices of service users, and measuring outcomes and experience.

Since the December update, in order to assess the knowledge and confidence of relevant Health Board staff, a survey was developed and completed by 89 staff.  Results informed the development of a training plan that is now being implemented, to ensure Health Board staff are well-equipped to meet the requirements of the ALN Act moving forward.  Key resources have been made available for new starters and saved on the central resource depository noted at 2.2.

As was noted in the December update, there has been progress with establishing mechanisms to ensure the voices and perspectives of children, young people and their parents / carers informs the Health Board’s approach to meeting the requirements of the ALN Act.  However, it is recognised that this is an area where more work will be required once Project Management capacity is in place.

Next steps towards the measurement of outcomes and experience of children and young people with ALN have been agreed with operational colleagues and approved by the ALN Steering Group.

All management actions in this thematic area have been completed.

- GOVERNANCE AND RISK ISSUES

The Health Board has an ongoing risk with regard to failure to comply with its legal duties under the ALN Act.  This is recorded on the Health Board Risk Register (ref 85), with the absence of robust compliance data a key cause of the risk.  On the basis of the report provided to the ALN Steering Group in May 2025 (see 2.3 above), this risk will be re-assessed.

- FINANCIAL IMPLICATIONS

The ALN Act placed new legal duties on Health Boards without additional resource, with implications for both Corporate and Operational services.  At a corporate level, resource has been secured that enables the corporate infrastructure needed to support the Health Board to meet the requirements of the ALN Act to be put in place.  At an Operational level, an initial demand / capacity assessment has been carried out by Children’s Therapies services.  This does not enable definitive conclusions to be drawn at this point but highlights the need for further demand / capacity assessment to be carried out as the implementation of the Act continues and as reliable data becomes available.

- RECOMMENDATION

It is recommended that the Committee:

- receives assurance regarding the progress that has been made in addressing the limited assurance rating provided by the audit;

- receives progress made in completing management actions that were agreed in response to the audit’s recommendations;

- receives assurance that while most audit actions have now been completed, activity overseen by the ALN Steering Group is either ongoing or planned to ensure that there is ongoing improvement in how the Health Board, working collaboratively with its Education delivery partners, delivers on the requirements of the ALN Act and contributes towards better outcomes and experience for children and young people with ALN.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The Health Board’s compliance with its duties under the ALN Act is crucial to the ALN Act’s aims of better outcomes and better experiences for children and young people with ALN being realised. |  |  |  |
| Financial Implications |  |  |  |
| No new financial implications at this stage. Financial implications may become apparent when further demand / capacity analysis is carried out by Operational services, informed by reliable data that will be available from January 2025. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The ALN Act placed legal duties on Health Boards. This report notes progress that has been made in establishing an infrastructure and processes that will enable the Health Bord to provide assurance regarding the extent to which it is fulfilling these duties. |  |  |  |
| Staffing Implications |  |  |  |
| Actions that are being undertaken with regard to staff training (matter arising 5) will ensure that the workforce has the necessary skills and training required to meet the requirements of the ALN Act. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Well-being of Future Generations Act’s 5 ways of working align closely with the general principles underpinning the ALN Act: - Long Term – facilitating access to education and promoting independence for some of our most vulnerable groups will enhance the long-term life chances of these individuals. - Prevention – early identification of needs and effective early help are key principles underpinning the ALN Act - Integration and Collaboration – collaboration between Health Boards and Local Authorities is a key principle underpinning the Act. - Involvement – Person-centered practice with the voice of the child at the heart of decision-making is another key principle underpinning the ALN Act. |  |  |  |
| Report History |  |  |  |
| Appendices |  | Appendix I: ALN Internal Audit Report January 2024 Appendix II: ALN Audit Tracker Updated March 2025 |  |