| Meeting Date | 04 November 2025 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Mental Health Legislation Committee |  |  |  |  |  |
| Report Title | The Additional Learning Needs (ALN) Act: Update on Monitoring and Management Action Plan following Internal Audit |  |  |  |  |  |
| Report Author | Dr Luke Jones, Designated Clinical Lead Officer (DECLO) |  |  |  |  |  |
| Report Sponsor | Alison Clarke, Deputy Director of Allied Health Professions and Health Sciences and Christine Morrell, Executive Director of Allied Health Professions and Health Sciences |  |  |  |  |  |
| Presented by | Dr Luke Jones, DECLO |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides an update regarding progress with actions that were agreed in response to Internal Audit Services’ report on the Health Board’s arrangements to ensure compliance with the Additional Learning Needs and Education Tribunal (Wales) Act 2018 (ALN Act). |  |  |  |  |  |
| Key Issues | Continued progress has been made with the completion of management actions agreed from completion of the audit in January 2024. A single action remains outstanding and overdue, with a target completion date of December 2025 The Health Board can now provide assurance regarding meeting its duties under the ALN Act. Data that is now available shows some ongoing compliance challenges, but appropriate governance mechanisms are now in place to manage these issues and risks. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Receives assurance regarding the progress that has been made in addressing the limited assurance rating provided by the audit; - Considers the progress made in completing management actions that were agreed in response to the audit’s recommendations, and notes that two actions that remain outstanding are expected to be closed in December 2025. |  |  |  |  |  |

THE ADDITIONAL LEARNING NEEDS ACT: UPDATE ON MONITORING AND MANAGEMENT ACTION PLAN FOLLOWING INTERNAL AUDIT

- INTRODUCTION

This report follows up on a report that was provided to this Committee in May 2025. It provides assurance regarding further progress that has been made with completing management actions that were agreed in response to Internal Audit Services’ January 2024 report on the Health Board’s arrangements with regards to the ALN Act.

- BACKGROUND

Information about the legislative context of the ALN Act, its requirements for Health Boards, and the report provided by Audit and Assurance services regarding the Health Board’s arrangements in place to meet these requirements have been provided in previous reports to this Committee and will not be repeated here.  Committee members are referred to these reports if this contextual information is required.

This Committee received a report on progress against the 23 agreed management actions that were agreed in response to the auditors’ recommendations in 5 thematic areas in May 2025.  All management actions had been completed against two thematic areas entitled governance arrangements and effective mechanisms.  A single management action remained outstanding in each of the remaining three priority areas: policies and procedures, delivery priorities, and resource implications.

In addition, when the May report was provided to this Committee, it was noted that Audit and Assurance services had requested additional information regarding the basis on which some of these actions have been closed.  This was part of a wider piece of work that Audit and Assurance were conducting with the Health Board, to verify the basis for closing down management actions.  Through collaboration between the DECLO and the Head of Compliance (Governance), this additional information was shared and was to the auditors’ satisfaction.

An update on progress against the outstanding actions follows.

  - Policies and procedures

Management action required: for Equality Impact Assessments (EQIAs) to be completed with regard to approved ALN Standard Operational Processes

Integrated Impact Assessments (which have now replaced EQIAs) have been completed for the Health Board’s ALN Standard Operating Procedure through collaboration between the DECLO and the Directorate of Insight, Communication and Engagement.  These have been discussed at the ALN Steering Group where it was agreed that the Impact Assessments could be approved by the Steering Group Chair on behalf of the Steering Group.  This has been undertaken and this action can therefore now be closed down.

  - Delivery priorities

Management action required: for data regarding the Health Board’s compliance with its statutory duties under the ALN Act to be brought to the ALN Steering Group for assurance purposes

Quantitative data about the Health Board’s compliance with the requirements of the ALN Act was brought for approval to the ALN Steering Group in May 2025.  Compliance was also shared with the Patient Safety and Compliance group in July 2025, with follow-up data to be provided in November 2025.

Data shows challenges for the Health Board in fully meeting the statutory requirements of the ALN Act, though robust governance mechanisms are now in place to ensure organisational visibility for these challenges and associated risks.

This action can therefore be closed down.

  - Resource implications

Management action required: to formalise and document arrangements between Swansea Bay, Hywel Dda and Powys Health Boards regarding joint funding of the statutory Designated Education Clinical Lead Officer (DECLO) role.

The Deputy Director for Allied Health Professions and Health Sciences has collaborated with neighbouring Health Board colleagues to formalise the financial arrangement whereby the DECLO is hosted by Swansea Bay but also covers Hywel Dda and Powys Health Boards.  There have been delays in receiving responses leading as a result of which this has not been finalised.  It is anticipated that this will be completed by December 2025.

Interim assurance can be provided that no issues or concerns have been raised with regard to the above and that this is not an area of significant risk for the Health Board.

- GOVERNANCE AND RISK ISSUES

The Health Board has an ongoing risk with regard to failure to comply with its legal duties under the ALN Act.  This is recorded on the Health Board Risk Register (ref 85).  Data shows that this remains an area of significant risk.  Actions have been agreed via the ALN Steering Group to mitigate the risk moving forward.

- FINANCIAL IMPLICATIONS

The ALN Act placed new legal duties on Health Boards without additional resource, with implications for both Corporate and Operational services.  At a Corporate level, resource has been secured that enables the corporate infrastructure needed to support the Health Board to meet the requirements of the ALN Act to be put in place.  At an Operational level, an initial demand / capacity assessment has been carried out by Children’s Therapies services.  This does not enable definitive conclusions to be drawn at this point but highlights the need for further demand / capacity assessment to be carried out as the implementation of the Act continues and as reliable data becomes available.

- RECOMMENDATION

It is recommended that the Committee:

- Receives assurance regarding the progress that has been made in addressing the limited assurance rating provided by the audit;

- Considers the progress made in completing management actions that were agreed in response to the audit’s recommendations, and notes that two actions that remain outstanding are expected to be closed in December 2025.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The Health Board’s compliance with its duties under the ALN Act is crucial to the ALN Act’s aims of better outcomes and better experiences for children and young people with ALN being realised. |  |  |  |
| Financial Implications |  |  |  |
| No new financial implications at this stage. Financial implications may become apparent when further demand / capacity analysis is carried out by Operational services, informed by reliable data that will be available from January 2025. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The ALN Act placed legal duties on Health Boards. This report notes progress that has been made in establishing an infrastructure and processes that will enable the Health Bord to provide assurance regarding the extent to which it is fulfilling these duties. |  |  |  |
| Staffing Implications |  |  |  |
| Actions that are being undertaken with regard to staff training (matter arising 5) will ensure that the workforce has the necessary skills and training required to meet the requirements of the ALN Act. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Well-being of Future Generations Act’s 5 ways of working align closely with the general principles underpinning the ALN Act: - Long Term – facilitating access to education and promoting independence for some of our most vulnerable groups will enhance the long-term life chances of these individuals. - Prevention – early identification of needs and effective early help are key principles underpinning the ALN Act - Integration and Collaboration – collaboration between Health Boards and Local Authorities is a key principle underpinning the Act. - Involvement – Person-centered practice with the voice of the child at the heart of decision-making is another key principle underpinning the ALN Act. |  |  |  |
| Report History |  |  |  |
| Appendices |  | Appendix 1: ALN Internal Audit Report January 2024 |  |