| Meeting Date | 23 April 2024 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Theatre Efficiency and the direction for correcting theatre utilisation statistics successfully |  |  |  |  |  |
| Report Author | Rhodri Davies, Associate Service Group Director - Surgery |  |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Ceri Gimblett, Service Group Director, NPTSSG Rhodri Davies |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To outline the theatre efficiency and utilisation work underway with the national ‘Getting it Right First Time’ (GIRFT) programme. |  |  |  |  |  |
| Key Issues | Theatre utilisation and productivity must be improved within SBUHB and a wider surgical pathway approach is required via the new Theatres Board to be established. The national Getting It Right First Time (GIRFT) programme is being implemented as part of this approach. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | - Note the progress made in redesigning the infrastructure to support implementation of the Theatre optimisation and utilisation programme - Note the establishment of the Theatres Board - Note the approach being taken with data and statistics to support Theatre optimisation and efficiency |  |  |  |  |  |

Theatre Efficiency and the direction for correcting theatre utilisation statistics successfully

- INTRODUCTION

This paper provides an outline of the theatre efficiency and utilisation work underway with the national ‘Getting it Right First Time’ (GIRFT) programme.  It also gives an overview of the critical foundations being put in place to drive the improvement programme forward.

- BACKGROUND

To support elective recovery, Getting it Right First Time (GIRFT) is helping to lead a national theatre programme which aims to draw together all key national workstreams engaged in improving theatre productivity, efficiency and workforce.

The key aims of the programme are to support Health Boards and systems to maximise the effectiveness and throughput of their surgical theatres through improvements across the surgical elective pathway.

GIRFT is a clinically led, data driven programme of healthcare quality improvement. The GIRFT programme uses clinical data to look at variation and where variation exists, this is discussed with two way clinician to clinician conversations with the goal of understanding the reasons for data variation and with emphasis on delivery of improved better quality of care and outcomes for patients. The underlying core principle of the programme is that it is a clinically led, peer-to-peer, data-driven approach to healthcare improvement

GIRFT is working closely with NHS Wales Executive to implement the Theatres Optimisation and Efficiency programme across Health Boards in Wales.  A national Implementation Board has been established with senior representation from each of the HBs.  There are fortnightly checkpoint meetings established per region in Wales and SBU Health Board is part of the South West region with Hywel Dda HB.

- Progress in Swansea Bay Health Board (SBUHB)

SBUHB theatre management infrastructure has been reconfigured to support delivery of the national, regional and local strategic priorities.

SBUHB aims to modernise and transform surgical services by embracing new and more efficient ways of working and to embed these approaches into a sustainable service delivery model.

The approach will be to undertake a comprehensive whole system review across Surgical services to ensure the provision of a sustainable high quality, person-centred, safe, effective and affordable theatre delivered service. In any reconfiguration of hospital services there are four interlinked drivers:

- Quality (including safety),

- Workforce,

- Access

- Cost.

The challenge is to try to arrive at a configuration that optimises all these elements, as far as this is possible given the complex trade-offs that exist between them, and the need to balance resources across unscheduled and elective care to achieve the highest quality of care. Quality considerations include timely access to highly trained professionals in all disciplines, compliance with clinical guidelines, access to diagnostic and interventional technologies, access to other support services and strong clinical governance. For some conditions, the time it takes to access these services will also be an indicator of quality.

Theatres Board

The Planned Care Programme within SBUHB has three pillars to its core work programme – Outpatient redesign, Diagnostics and Theatres.

The aim is to establish a Theatres Board that aligns delivery of theatre services across all SBUHB sites to the SBUHB Strategy, understanding surgical pathway performance and constraints to deliver informed decision making.  It is proposed that the Theatres Board will decide on:

- Resource allocation.

- Resource alignment.

- Governance infrastructure.

- Planned priorities.

The Theatres Board will therefore set, monitor and maintain safety and quality outcomes and surgical pathway performance related to theatre productivity.  Through an inclusive improvement culture deliver continual benefits in theatre productivity.  It will employ communication and learning across the theatre management hierarchy and stakeholders to enable effective contextual updates for system understanding and subsequent decision making.

The Theatres optimisation and efficiency programme is being supported by the HB’s Transformation Team, with the Associate Medical Director for Health Care Systems Engineering (HCSE) taking the clinical lead for the improvement work.  The Transformation team will also support the programme management.

Theatres Board is the last work programme to be established under the planned acre programme, as it was felt critical that key operational roles were recruited into in order to ensure the operational implementation of the work programme takes place in a timely way, these posts are:

- Associate Service Group Director – Surgery (with responsibility for Theatres) – appointed April 2024

- Directorate Manager for Theatres and Anaesthetics – appointed March 2024

- Associate Medical Director – Surgery (with responsibility for Theatres redesign and Chair of the Theatres Board) – recruitment process currently underway

The AMD for Surgery (once appointed into) will Chair the Theatres Board and the terms of reference for the Board and governance structure will be finalised at that point.

- The importance of Data and Theatre Utilisation statistics for success

The optimisation and utilisation programme under the Theatres Board will develop an Improvement Plan based on principles of approach directly tied to how strategy becomes implemented via operational delivery with continuous improvement generated through understanding of the components of our surgical pathways on theatre performance.

Using this data and knowledge to enable the operational team to inform and improve as part of standard theatre management practice, whilst providing the strategic view with appropriate feedback on progress, constraints and risks for delivery.

This change in approach should allow us to integrate improvement into our operational review and delivery across theatre services and their stakeholder dependent services in surgery, anaesthetics, HSDU etc.

The key elements are as follows:

- Establish a clear performance framework that incorporates a set of standards and measures for theatres services

- Deliver services to achieve set performance objectives. Clearly identifying reasons for variance with appropriate system understanding and data validation through constant feedback monitoring.

- Through an inclusive improvement culture deliver continual benefits in theatre productivity

- Employ communication and learning across the theatre management hierarchy and stakeholders to enable effective contextual updates for system understanding and subsequent decision making.

Reviews of theatre productivity will be multidisciplinary and supported by the Patient Access Management and Health Care Systems Engineering. The aim of reviews will be to facilitate understanding and identify components of the surgical pathway for focused redesign through the Theatres Improvement Team. This work will be integrated into to SBUHB component of the National Theatre Optimisation Programme [NHS Executive and GIRFT].

As part of the fortnightly checkpoint meetings with GIRFT, a data pack is shared based on theatre information gathered from SBUHB systems.  A copy of the most recent data pack is included in Appendix 1.

The metrics currently monitored by GIRFT are as follows:

- Volumes – Theatre usage over time, e.g. average number of theatres in use per week and number of cases per day

- Day cases – proportion of elective activity that is provided as day case

- Elective session planning - Average actual session duration vs. planned session duration (hours)

- Touch time utilisation – theatre procedure timings

- Cancellations, e.g. same day cancellations

- Fallow Days - Average number of days per theatre in which no activity takes place

- Late starts and early finishes

- HVLC – Opportunities for High Volume Low Complexity activity

- GOVERNANCE AND RISK ISSUES

Nothing specific to include at this point but he P&F Committee is asked to note the establishment of the Theatres Board and the governance and reporting mechanisms to Planned Care Board.

- FINANCIAL IMPLICATIONS

It is important to point out the resource implications for implementing such a large programme of work with particular input required from the Theatres operational teams, Health Care Systems Engineering and the Transformation team.

There may be financial support required for work undertaken by the Board but this will require the usual business case process within the Health Board and as part of the Annual Planning Framework.

- RECOMMENDATION

- Note the progress made in redesigning the infrastructure to support implementation of the Theatre optimisation and utilisation programme

- Note the establishment of the Theatres Board

- Note the approach being taken with data and statistics to support Theatre optimisation and efficiency

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Inefficient theatre services have a detrimental impact on patient experience, safety and quality. By introducing better and more efficient process into Theatres, patient outcomes will be improved. |  |  |  |
| Financial Implications |  |  |  |
| There are no known additional costs apart from redirection of resources within transformation, HCSE and operational teams in order to implement changes. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| N/A. |  |  |  |
| Staffing Implications |  |  |  |
| There is a significant staffing implication for operational teams due to the competing demands, however it is hoped that implementing theatre optimisation and efficiency actions will lead to more streamlined processes and therefore resource neutral in the longer term |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  |  |  |
| Appendices |  |  |  |