| Meeting Date | 29 April 2025 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Welsh Government Oversight and Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and Senior Responsible Officer (SRO) for Targeted Intervention (TI) Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in February 2025, the Health Board was de-escalated for the following areas previously at TI I level 4 for Performance and Outcomes: - Child and Adolescent Mental Health Services (CAMHS) will be de-escalated to level 3 (enhanced monitoring) and - Planned care will be de-escalated to level 3 (enhanced monitoring). All other areas of escalation remain unchanged and the summary is as follows: - Level 4 for finance, strategy and planning. - Level 4 for performance and outcomes relating to cancer, urgent and emergency care and quality of care related to Healthcare Acquired Infections (HCAIs). - Level 3 for maternity and neonatal services. - Level 3 for performance and outcomes relating to planned care and CAMHS. - Level 2 for Mental Health and Learning Disabilities (MH&LD). This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |
| Appendices | No Appendices |  |  |  |  |

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Maternity and Neonatal Services

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the SRO for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- CAMHS de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group, and are outlined below.

- The Service Group continues to work with the NHS Executive Mental Health leads as part of the Level 2 support. The work is ongoing and is now at the stage of updating the review following the various site visits and reviewing the shared data and documentation provided.

- The Health Board has commenced work in advance of the receipt of the report and is setting up a Transformation Programme. This has been informed by a review of the service by an external advisor. Her findings were presented to an in committee meeting of the Board in February and her recommendations were approved. There were some recommendations which were considered urgent by the Board and these have been completed or are in progress. The Transformation Programme will be led by a Programme Board with supporting reporting structures including workforce, IT/digital, service redesign, Quality and Safety and estates. The recommendations of the review by NHS Executive MH and LD leads will form part of the work programme. The Board will receive an update at its next meeting.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (March 25) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - 80% of open pathways to be waiting less than 52 weeks and maintained for 3 months. | - 86.18% - meets de-escalation criteria |
| - 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline.) | - 4.59% reduction |
| - 65% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 74.38% - meets de-escalation criteria |
| - 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 82.08% |
| - 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 40.78% |
| - 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 99.96% |
| - 85% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 100% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at Neath Port Talbot Hospital to reduce demand for Morriston Hospital services.

4.2 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the Health Inspectorate Wales (HIW) unannounced inspection at Singleton as set out in the report published on the 15th December 2023.

In order to appropriately scrutinise and seek assurance of the work being undertaken in Maternity and Neonatal services, a Gold command structure was established. The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning.

Detailed progress against these areas have been outlined in the Gold command for maternity and Neonatal services progress report.

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of local primary mental health support services mental health assessments undertaken within 28 days from the date of receipt of referral. | - January – 42% - February – 74% - March – 75% |
| - 65% of therapeutic interventions started within 28 days following an assessment. | - January - 100% - February – 100% - March – 100% |
| - 80% of Health Board residents in receipt of secondary mental health services who have a valid care and treatment plan. | - January – 98% - February – 98% - March – 98% |

Actions being taken to improve include:

- Substantive recruitment is ongoing for three permanent band six post to improve the workforce for this part of the service

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - December – 63% - January – 52% - February – 56% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Continued focus on cellular pathology, Health Care Systems Engineering (HCSE) team working with the service and workforce gaps going through vacancy control process.

- Weekly performance reviews with all tumour site leads, chaired by the Deputy Chief Operating Officer and/or Cancer Performance and Information Manager.

- Identify additional surgical (Upper Gastrointestinal in particular), robotic (urology) and chemotherapy capacity; business case for an additional 2 chairs agreed.

- Further actions/improvement in Skin, particularly to mitigate increased seasonal demand; Lower Gastrointestinal, to decision to treat and Pre-Assessment; Urology diagnostics and increasing robotic capacity; and Lung.  Progress against actions to be monitored through Cancer Performance Improvement Group (CPIG).

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - January – 593 - February – 554 - March - 555 |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - January – 9.9% - February – 12.4% - March – 11.3% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - January – 82.3% - February -84.6% - March – 82.21% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - January – 280 - February – 273 - March - 219 |
| - Assessment of declared Business Continuity Incidents (BCI), including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 |

Of most concern is the increase in pathway of care delays since August.  It should be noted that Welsh Government has recently issued new guidance on the reporting of pathway of care delays and this may change the figures formally reported.  The current criteria includes patients that are delayed in transferring from their “current” bed, even if that is to a Community Hospital.  The new criteria is understood to only be patients delayed to discharge out of a hospital bed to the community.

Actions being taken to improve include:

- Full implementation of D2RA model – Executive agreement between Health & Social Care CEO’S to deliver a D2RA model with an externally facilitated workshop planned for 18th March 2025.  A 7-day test of change Multi Agency Discharge Event took place based at the Morriston Hospital site between the 11th and 17th April. The purpose of the 7 days is to identify changes in practices and redesign resources required to speed up flow from the front door to discharge and improve the quality of patient care and experience. We aim to maximise our Home First approach, reduce our reliance on P3 as a destination without rehabilitation being considered, and achieve our Shared Purpose for D2RA.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital

- UEC Care co-ordination Hub - Vision to expand the hours of service across seven days. Acute Clinical Team (ACT) and Virtual Wards linked in and a Improvement project linked to St John Ambulance response unit to test the impact of Community outreach

- Review of community capacity and operating models: ACT & Virtual Wards (VW), Business case in draft form

- Senior decision makers at front door services

- Rota proposals shared with Acute Physicians

- Recruitment to Acute Clinical Physician/Care of the Elderly posts ongoing, one recent appointment made.

- Plan to introduce an interim rota 1st June 2025.

- Pathway of Care Delays (PoCD) – Focus on the delivery of actions to reduce pathway of care delays, Clinical Optimised Patients (COP) deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. Escalation to COO / Directors of Social Services on a weekly basis. This is continuing and links to the D2RA test of change week mentioned above

- Revised flow operating model: with consistent tactical command at Level 4 and introduction of revised internal escalation processes. External facilitated workshop held in march and Centralised flow proposal for discussion with the COO 23rd April

- Falls Pathway – Plan to commence February 2025 – enhanced opportunity via the Care Co-ordination Hub PDSA above linked to Hub

- UEC capital redesign – expansion of the Urgent and Emergency Care (UEC) footprint with the addition of a demountable co-located with the Emergency Department (ED) will enable and integrated front door model for acute medicine, enhanced by the Care Co-ordination Hub. Sign off of the plan has been obtained with Clinical Leadership. Scope of works with architect currently expecting draft plans 24th April 2025

5.3 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&s Committee Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - January – 19 - February – 11 - March - 15 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - January – 4 - February -5 - March - 3 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - January – 9 - February -8 - March - 4 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - January – 8 - February -3 - March - 5 |

During March 2025, there were 14 infection related incidents/outbreaks (including 6 outbreaks that continued from preceding month.

- 8 in Morriston: 1 Influenza; 3 COVID-19; 4 Norovirus (153 bed days lost).

- 3 in Neath Port Talbot: x2 COVID-19 and 1 concurrent COVID-19 & Norovirus (76 bed days lost).

- 1 in Singleton: COVID -19 (4 bed days lost)

- 2 in Mental Health: 1 Norovirus and 1 Group A Strep (40 bed days lost).

During March, there were 2 separate gnomically-linked outbreaks of C. difficile identified: 2 wards in Morriston (involving 2 patients in one and 3 patients in the other).  In both cases, there was concurrent infection with Norovirus.

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group continues, with Silver Groups reporting into Gold.

- The Digital App for HCAI incident case reviews: data is being entered into the live-staging stage of the App to test. This will then extend to wider user testing.

- The C. difficile risk stratification project work continues.

- Continued focus on improving antimicrobial stewardship, in particular the outcomes of antimicrobial review.

- Collaboration with Domestic Services and Infection Prevention & Control on improving processes and governance for enhanced cleaning during Periods of Increased Incidence.

- Collaboration with Digital intelligence to standardise and centralise recording of scrutiny panel outcomes and learning.

5.4 Finance

At the point of drafting the Finance section for the report the financial position for 2024/25 remains interim pending (1) final Welsh Government Allocations for 2024/25 and (2) the completion draft Annual Accounts and full audit process during May and June 2025, with the final 2024/25 Annual Accounts submitted to Welsh Government on 30th June 2025. In the meantime, this report provides a summary of the information available at the 17th April 2025.

Revenue Resource Limit (RRL) 2024/25

The Health Board was not forecasting a balanced plan for 2024/25 and through various plan submissions during 2024/25 had a line of sight to £50.1m. In early December 2024 WG issued an additional £6.4m of recurrent funding to the Health Board, which reduced the deficit plan to £43.7m.  The draft interim position against the Revenue Resource Limit at 17th April 2025 was £42.4m over spent, which is £1.3m under the deficit plan of £43.7m.

Capital Resource Limit (CRL) 2024/25

The approved Capital Resource Limit (CRL) value, at 31st March 2025, was £0.061m under. The approved CRL value includes Discretionary Capital and the schemes under the All Wales Capital Programme.

Public Sector Payment Policy (PSPP) @ 31st March 2025

The Health Board is expected to deliver a target of 95% against the total number of Non NHS Invoices Paid Within 30 Days. At the 31st March 2025 the interim performance for the year was 95.04% against the 95% target.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated April 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan (CSP). | Current CSP rolled over as the agreed road map. Refreshed CSP agreed for development in 25/26 Detailed timelines in development, with DPP/COO/EMD to as tripartite lead. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Planning Maturity Matrix update to Board Development in July 2025, and will be reported to Board in July. |
| Progress made with regional planning | Next RJC meeting taking place 7th May 2025. Key outputs are to agree programme of work, including Clinical Services and Capital Planning, Data & Digital, Workforce and OD |

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | No Appendices |