| Meeting Date | 29th August 2023 |  | Agenda Item |  |  | 6.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Performance Report Endoscopy |  |  |  |  |  |
| Report Author | Fiona Hughes Associate Service Group Director, Morriston Service Group |  |  |  |  |  |
| Report Sponsor | Craige Wilson, Deputy Chief Operating officer, Swansea Bay University Health Board (SBUHB) |  |  |  |  |  |
| Presented by | Fiona Hughes, Associate Service Group Director Neath Port Talbot and Singleton, Medicine |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | In April 2022 the “Transforming and modernising planned care and reducing NHS waiting lists” was published. This plan outlined recovery and transformation objectives for planned care in Wales to reduce waiting times and move towards sustainable elective and diagnostic services by 2026. From an Endoscopy service perspective a recovery trajectory was developed against the following priority area: - National target of zero patients waiting over 8 weeks for a diagnostic endoscopy by March 2024. Within SBHUHB an allocation of £3.4m was identified in the annual financial plan to reduce the demand and capacity gap, through increasing the current workforce (medical and nursing) and insourcing. This left a gap of 3291 patients waiting over 8 weeks by the end of March 2024. In August 2023 to enable the Health Board to achieve the 8-week waiting time target by the end of March 2024 a further £1.5m has been allocated from Welsh Government. The purpose of this paper is to provide an overview of the Endoscopy performance against the current agreed trajectory (3291 patients) as well as an update of the development of further improvement plans to deliver the zero patients waiting over 8 weeks by the end of March 2023. The paper will also detail the improvements in the waits for an urgent suspected cancer referral for a diagnostic Endoscopy as well as provide an overview of current waits for Surveillance and Bowel Screening Endoscopy. |  |  |  |  |  |
| Key Issues | The key issues set out within this report are: - An improvement trajectory has been set to reduce the 8-week cohort of patients by the end of March 2024 to 3291 patients and there is confidence that this will be achieved. - To meet the National Target of zero patients by the end of March 2024 there is a requirement to secure additional capacity through internal efficiencies and outsourcing. There will be considerable challenge to this. - There has been a 72% reduction in the number of patients on the colorectal cancer pathway waiting for an urgent suspected cancer diagnostic endoscopy. - The NHS Executive Team were invited to provide an assessment of the current Endoscopy Service and an initial report shared with the SHUHB on the 7th July 2023 demonstrates the need to implement process improvements. An improvement plan has been drafted and a weekly monitoring meeting scheduled to oversee progress. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE: The Improvement in the Endoscopy wait for the colorectal cancer pathway - NOTE: The improvement in the over 8-week diagnostic waits since April 2023 and performance against trajectory. - NOTE: The new trajectory will be developed in line with the additional funding of £1.5m and submitted early September 2023. - ACTION: Agree to receive a response in the September 2023, to the NHS Executive Report. This response will include the detailed action plans to maximise the productivity and efficiency of existing Endoscopy capacity. |  |  |  |  |  |

ENDOSCOPY PERFORMANCE UPDATE

- INTRODUCTION

The purpose of this report is to provide the Performance and Finance Committee with an update on Endoscopy performance against the Welsh Government Diagnostic recovery target and a review of future capacity and demand requirements to support recovery and sustainability within the service.

There is currently insufficient core capacity available to meet local demand for upper and lower gastrointestinal endoscopy. This demand and capacity mismatch has led to delays in our patients’ diagnostic pathways and subsequent treatment and our ability to meet the national 8-week diagnostic waiting time standard.

In April 2022 the “Transforming and modernising planned care and reducing NHS waiting lists” was published. This plan outlined recovery and transformation objectives for planned care in Wales to reduce waiting times and move towards sustainable elective and diagnostic services by 2026.

From an Endoscopy service perspective a recovery trajectory was developed against the following priority area:

- National target of zero patients waiting over 8 weeks for a diagnostic endoscopy by March 2024.

Within SBHUHB an allocation of £3.4m was identified in the annual financial plan to reduce the demand and capacity gap, through increasing the current workforce (medical and nursing) and insourcing. This left a gap of 3291 patients waiting over 8 weeks by the end of March 2024.

In August 2023 to enable the Health Board to achieve the 8-week waiting time target by the end of March 2024 a further £1.5m has been allocated from Welsh Government.

The purpose of this paper is to provide an overview of the Endoscopy performance against the current agreed trajectory (3291 patients) as well as an update of the development of further improvement plans to deliver the zero patients waiting over 8 weeks by the end of March 2023.

The paper will also detail the improvements in the waits for an urgent suspected cancer (USC) referral for a diagnostic Endoscopy as well as provide an overview of current waits for Surveillance and Bowel Screening Endoscopy.

- BACKGROUND

Endoscopy plays a vital role in the diagnosis of, and on-going surveillance for gastrointestinal cancers, including bowel and oesophageal cancer and performed for the diagnosis, surveillance and treatment of a wide range of conditions and diseases that are not cancer-related.

Demand for Endoscopy is currently significantly out of balance with the available core capacity and health boards across Wales and the UK have struggled to develop sustainable solutions.

In March 2020, the British Society of Gastroenterology due to the Covid-19 pandemic advised a pause in endoscopic services for all but emergency and essential procedures, to protect patients and the workforce and permit time to plan service reconfiguration. Within SBUHB following eight months of low levels of activity, this resulted in a considerable backlog of patients awaiting a diagnostic, therapeutic and surveillance endoscopy.

Endoscopy Service Profile

The current service profile for Endoscopy is as follows:

- There are six procedure rooms across the Health Board - Morriston, Singleton and Neath Port Talbot Hospital all have Endoscopy Units comprising of two procedure rooms.

- The service funded to provide 38 sessions per week.

- There is capacity for 60 sessions within the working week with 22 sessions currently unfunded.

- The sessions are delivered Monday – Friday. The morning session starts at 9am-12:30 and afternoon session 13:30-17:00.

- Upper and Lower Gastrointestinal (GI) endoscopy sessions are delivered through a combination of Consultant Gastroenterologists, Upper GI and Colorectal Surgeons, Upper GI middle grade doctors, GP with specialist interest and Clinical Endoscopists.

- The types of Procedures Performed within the procedure rooms include:

  - Upper GI Endoscopy (Gastroscopy/OGD) –

  - Lower GI Endoscopy (Colonoscopy)

  - Flexible sigmoidoscopy

  - -Bronchoscopy and End bronchial ultrasound (EBUS) for the diagnosis of disorders of the Upper Respiratory Tract.

  - Endoscopic Retrograde Cholangiopancreatography (ERCP)

- There is also activity performed within the department but outside of procedure rooms for example carbon and hydrogen breath tests and small bowel capsules.

- There is a 24/7 GI bleed on call rota for emergency endoscopies staffed by the Gastroenterology Consultant Team.

- Endoscopy uses a points system for time allocation: an OGD or flexible sigmoidoscopy is allocated one point, a colonoscopy is allocated two points and therapeutic procedure is allocated as required.

- CURRENT ENDOSCOPY PERFORMANCE

- Cancer Referrals

Patients referred for a USC diagnostic Endoscopy on the Lower GI pathway has reduced from 531 patients waiting in September 2022 to 150 on the 19th July 2023.

Graph 1 below demonstrates this reduction.

This is a 72% reduction in the number of patients waiting for a USC Endoscopy and patients referred in for an Endoscopy prioritised as an urgent suspected cancer (USC) are currently being booked within 10-14 days.

- Diagnostic and Surveillance waits

The waiting list for endoscopy as at 20th August 2023 consists of the following:

- Total Diagnostic waiting List of 5066 patients and 4435 waiting over 8 weeks. This equates to a backlog of 6104 points and would require in total 1017 Endoscopy sessions to clear.

- Length of wait in weeks has reduced from 181 weeks to 110 weeks (reduced the waits by over 14 months):

- In November 2022, the longest wait for an Endoscopy was 181 weeks.

- By the 31st July 2023 the longest wait for an Endoscopy was 126 weeks

- As at the 20th August 2023 the longest wait is 110 weeks.

- Total waiting list of 3045 surveillance patient and 1874 are over due to date.

- Total Bowel Screening Wales (BSW) waiting List of 6 patients. These are within the standards set.

- ENDOSCOPY DEMAND, CAPACITY AND CAPACITY GAP.

The service has been developing a capacity and demand plan essential for the planning and delivery of a quality and timely Endoscopy service. The following provides an overview of the total capacity and demand for the service since 2019.

Key messages:

- Average weekly demand in Quarter1 23/24 has increased on previous years.

- Average weekly funded capacity has remained static through 2019-2021.

- One additional bowel screening session was funded in 2022.

- Average weekly capacity gap in Quarter1 2023/24 is 135 points and this equates to a capacity gap of 14 sessions a week if scheduled to 10 points and 11 sessions a week if scheduled to 12 points.

- Funding has been agreed in the recovery plan to support an additional 8 sessions per week in 2023/24. The gap for 2024/25 will then be in the region of 3-6 sessions to match the demand.

To manage the backlog within the service the additional capacity required in 2023/24 will be as follows:

- The capacity required to manage the current RTT backlog is 1017 sessions.

- The capacity required to manage the current surveillance backlog is a total of 531 sessions.

- Currently the service is insourcing 14 sessions a week.

- TRAJECTORY FOR IMPROVEMENT

The Endoscopy Team have developed a capacity and demand plan to improve the performance against the 8-week target. The Table below sets the trajectory of improvement and reduction of 1459 patients during 2023/24. By the end of July 2023 the trajectory 4461 was exceeded and actual waits fell to 4388. An improvement of 73 patients over and above projected performance.

Current improvement plan

The plan to reduce the over 8 week waits to 3291 by March 2024 includes the following key initiatives:

- Recruiting Endoscopy Nurses to support an additional 8 sessions to increase funded sessions from 38 to 46 sessions during 23/24.

- Clinical and administrative validation.

- Clinical Endoscopist workforce increasing from one (currently within establishment and competent) to three whole time equivalent in 2023/24.

- Appointed two new Gastroenterology Consultant posts. One whole time equivalent commenced and 0.8 whole time equivalent to commence in September 2023.

- Additional weekend lists

- Insourcing capacity through of 14 lists per week (196 points per week)

- Fixed term booking clerks to support additional activity and validation.

- Internal Waiting list imitative. Uptake is poor.

- There is a need deliver consistently 10 points per session initially. Introduced a weekly scheduling meeting to review capacity two weeks ahead to ensure 10 points delivered with the objective of increasing to 12 points per session +/- 10% as per the Joint Advisory Group (JAG) of the Royal College of Physician’s recommendation.

Plan for further Improvements during 2023/24

The NHS Executive Team were invited to provide an assessment of the current Endoscopy Service and an initial report shared with the SHUHB on the 7th July 2023. The report demonstrated the need to implement process improvements. An improvement plan has been drafted and a weekly monitoring meeting scheduled to oversee progress. Key areas of focus are as follows:

Improving efficiency measures

- Improving the management of the new referrals process

- Use of Faecal Immunological Test (FIT) introduced in primary care to stratify referrals within SBUHB has increased (see Table 9)  however the effective use of FIT to manage demand needs improvement (NHS Welsh Executive

- Development of a standard endoscopy referral form. Action by 10/09/23

- Implementation of a clinically led process to reduce the variation in the vetting.  Action by 10/09/23

- Managing the Surveillance Waiting List

- Good progress has been made in clinical validation against the 2019 British Society Gastroenterologist Guidelines but there is opportunity to reduce the number on the waiting list with the completion of this validation in the region of 10%. Action 16/09/23

- The use/roll out of Cytosponge should be accelerated, in accordance with the opportunity set out in the National Institute Clinical Excellence briefing.

- Good waiting list Management

- Administrative validation and clinical validation of total waiting list underway.  Over 100 week’s cohort targeted.  Of the 189 clinically validated over the last 4 weeks 85 removed/suspended (either completely or redirected for telephone assessment). Action continue with validation process throughout Q2 2023/24

- Review of booking processes to reduce the patients that do not attend.

- Scheduling (NHS Executive noted following areas):

- Positive that patients are now being booked a few weeks prior to the procedure and an adequate pre-assessment process in place

- Positive that text messaging is in place to remind patients of their appointment. Further use of technology to be utilised to support efficient use of resource.

- Update the Endoscopy Management System with Endoscopist specific templates to understand fully capacity. Action 30/08/23

- Need to develop a short notice cohort of patients, who have indicated they are able to take a short notice cancellation. Action taken.

- Need to implement a robust scheduling process.  Action by 01/09/23

- FURTHER RECOVERY FUDNING

In August 2023 to enable the Health Board to achieve the 8-week waiting time target by the end of March 2024 a further £1.5m has been allocated from Welsh Government. The Team are currently developing an improvement plan and revised trajectory in line with the need to work towards a zero over 8 week position by the end of March 2024.

The solutions being reviewed are to further increase internal sessions and to outsource capacity. A plan will be finalised and shared by the 10th September 2023.

- GOVERNANCE AND RISK ISSUES

Whilst the Health Board will achieve the current trajectory that has been set of 3291 patients over 8 weeks by the end of March 2024 there is a considerable challenge to meeting the zero position by March 2024.  There are significant risks associated with this and are:

- Nursing capacity – this has improved in terms of recruitment and less vacancies however the long lead time of at least 6 months to train an Endoscopy nurse is challenging.

- HSDU capacity – the refurbishment of the HSDU at Morrison and subsequent temporary centralisation of services on the Singleton site has the potential to cause difficulties in the responsiveness to Endoscopy demand.

There is an established Endoscopy Recovery group to oversee the improvements/initiative made to ensure that robust governance with the appropriate clinical and service management support is in place. The Endoscopy Recovery Group escalates risks and issues through to the Division of Medicine and Morriston Service Group.

- FINANCIAL IMPLICATIONS

The financial plan below has been agreed for 2023/24 and includes a combination of non-recurrent and recurrent implications as described.

.

The financial plan is monitored on a weekly basis to ensure governance and control.

- RECOMMENDATIONS

It is requested that the Management Board consider the following recommendations:

- NOTE: The Improvement in the Endoscopy wait for  the colorectal cancer pathway

- NOTE: The improvement in the over 8-week diagnostic waits since April 2023 and performance against trajectory.

- NOTE: The new trajectory will be developed in line with the additional funding of £1.5m and submitted early September 2023.

- ACTION: Agree to receive a response in the September 2023, to the NHS Executive Report. This response will include the detailed action plans to maximise the productivity and efficiency of existing Endoscopy capacity.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☐ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic, therapeutic and surveillance endoscopy who are unable to access the service.

Financial Implications

Funding agreed for 2023/24

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.

Staffing Implications

Increase in Endoscopists and Nursing workforce to reduce capacity gap.

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | Endoscopy update Report shared with Management Board in November 2022. |