| Meeting Date | 27 August 2024 |  | Agenda Item |  |  | 4.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Performance Update for Neurodevelopmental Service |  |  |  |  |  |
| Report Author | Sue Kotrzuba, Directorate Manager, Children & Young People Directorate |  |  |  |  |  |
| Report Sponsor | Ceri Gimblett, Service Group Director, NPTSSG Deb Lewis, Chief Operating Officer / Executive Director of Primary Care & Mental Health |  |  |  |  |  |
| Presented by | Sue Kotrzuba, Directorate Manager, Children & Young People Pramodh Vallabhaneni, Clinical Director, Children & Young People |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this paper is to provide a position statement for the Swansea Bay UHB Neurodevelopmental Service, including an update around collaboration with partners within the local authority and education sector. The paper will also outline initiatives and mechanisms in place to support Children, Young People and their parents/carers whilst they await a formal assessment. |  |  |  |  |  |
| Key Issues | The key points of this paper are: - Current demand and waiting times - Reduced capacity due to staffing deficits - Focus on needs-led approach shifting away from a diagnosis-led culture |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to ACKNOWLEDGE the: - current demand, capacity and staffing challenges faced by the Neurodevelopmental team. - levels of support, advice and training provided by the Neurodevelopment Team to stakeholders. - collaborative working in place with key partners - update provided and - SUPPORT the next step actions proposed |  |  |  |  |  |

PERFORMANCE UPDATE FOR NEURODEVELOPMENTAL SERVICE

- INTRODUCTION

The purpose of this paper is to provide a position statement for the Swansea Bay UHB Neurodevelopmental Service, including an update around collaboration with partners within the local authority and education sector.  The paper will also outline initiatives and mechanisms in place to support Children, Young People and their parents/carers whilst they wait for a formal assessment.

- BACKGROUND

The management of Neurodevelopmental Disorders (ND) Services (5 – 18 years) was transferred from Child and Adolescent Mental Health Services (CAMHS) to the Children and Young People Directorate (previously named Children & Young People Division) in April 2017, following provision of ring-fenced funding by Welsh Government to all Health Boards across Wales.

Detailed papers have been presented to the Service Group and Performance and Finance Committee over the last 3 years, outlining the background to the Neurodevelopmental Disorders (ND) Service, the ongoing increase in demand versus insufficient capacity, waiting times, along with how the team have developed best practice within the service with limited resources. The last update was delivered in July 2024, together with an update to Management Board in March 2024.

- Performance Update - Neurodevelopmental Service (ND)

Within SBUHB, there are 1351 children and young people, waiting for 35 months for assessment and diagnosis of Autism Spectrum Disorder (ASD) and Attention Deficit Hyperactivity Disorder (ADHD) or both. Of the 1351 waiting, there are 684 children and young people waiting over 52 weeks. The increased demand on service, together with impact from the pandemic, has resulted in continued long waiting times for this service.

Waiting times are also affected by the need to offer a person centred assessment as this can mean additional appointments to ensure the quality and safety of the diagnostic outcome, e.g. a further observation of the child at school, specialist advice or tests before ADHD medication can be initiated, e.g. Cardiology, ECG.  Where the original assessment identifies further need for investigation, this is done concurrently to prevent any further avoidable wait or delay for the family, for example - the ASD assessment identifies possible ADHD which was not identified in the original referral.

The below table demonstrates the waiting list position as of 31st July 2024:

| weeks wait | ADHD | ASD | Dual | Total |
| --- | --- | --- | --- | --- |
| <=11 weeks | 86 | 126 | 76 | 288 |
| 12-17 weeks | 18 | 41 | 12 | 71 |
| 18-25 weeks | 22 | 43 | 24 | 89 |
| 26-35 weeks | 33 | 31 | 20 | 84 |
| 36-51 weeks | 29 | 81 | 15 | 125 |
| >51 weeks | 136 | 433 | 125 | 694 |
| Grand Total | 324 | 755 | 272 | 1351 |

Demand

The referral variance profile reflects the level of public awareness of ND; 55% of referrals are for autism spectrum disorder (ASD) only, 25% attention deficit / hyperactivity disorder (ADHD) only, 20% DUAL assessment of ASD and ADHD simultaneously. Every case has an initial assessment (IAX) with the family, which takes 1.5 hours for ASD, 2 hours for ADHD and 2.5 hours for dual cases. At this point, they are removed from the waiting list, which makes up the RTT performance data. Subsequent follow-up appointments are also carried out. For each case, the clinician needs 4-5 hours of documentation review and report writing time.

Overall, the total clinician hours required for each case to reach diagnosis are approximately:

- ASD assessment – 15 hours

- ADHD assessment and treatment – up to 20 hours

- ASD and ADHD (dual) assessment and treatment – up to 30 hours.

It should be noted that where there is a requirement to monitor medication effectiveness, this can take up to four months to stabilise and as a consequence, needs frequent review and monitoring.

The hours per pathway calculation is detailed within the below table:

|  | ASD | ADHD | DUAL |
| --- | --- | --- | --- |
| Initial appointment | 4 hours x Band 7 | 4 hours Doctor or 8a AP nurse | 4 hours x Doctor |
| Parent interview 3di | 2 hours x Band 6 | 2 hours x Band 6 | 2 hours x Band 6 |
| Specialist SLT tests | 2 hours x Band 6 | 2 hours B6 or B7 | 2 hours Band 6 or Band 7 |
| Observation ADOS | 3 hours x 2 staff Band 7 + 8a AP SLT |  | 3 hours x 2 Band 6 or 7 or Band 8B or Doctor |
| MDT discussion | 30 mins | 30 mins | 30 mins |
| Feedback | 2 hours | 2 hours | 2 hours |
| Medication observations |  | 30 mins weekly Band 6 - appointments until medication stable | 30 mins weekly Band 6 - appointments until medication stable |
| Medication titration |  | 45 mins weekly appointments until medication stable - Doctor or 8a AP Nurse | 45 mins weekly appointments until medication stable - Doctor or 8a AP Nurse |
| Total hours | 15h | Up to 20h | Up to 30h |

Demand vs Capacity Gap

The service has funded capacity to see up to 42 new patients (initial assessments) and 200 follow-up assessments/feedback appointments for open cases per month.  Clinical capacity is calculated at 42 working weeks available each year (80%) to allow for annual leave, study leave and professional leave. This equates to overall annual capacity of 504 first initial assessments slots and 2016 follow-up assessments. Taking an average of the referrals received in 2022 – 2023, minus removals other than treatment at a rate of 23%, this equates to an estimated revised demand of 880 referrals (average 73 per month). This demonstrates a demand and capacity gap of 376 new appointments and 1504 follow up assessment/feedback appointments per year (4 follow ups per new case). It is important to note that even when all current establishment posts are filled (no vacancies or sickness) the demand and capacity gap of 376 remains, together with a backlog of 694 children waiting over 52 weeks.

During 2023 referral rates show greater identification of ADHD for solo and dual referrals: 53% ASD only, 24% ADHD only, 24% dual referrals. This is evidence of the awareness raising and training to the wider education and third sector workforce increasing the identification of ADHD which has always been under-identified.

There is a continued need to increase the staffing establishment in order to close this gap, which in turn, will have a positive impact on reducing the waiting times.

Workforce

Both the ND (5 – 18 years) and Early Years ND (0 – 5 years) have experienced significant workforce challenges in recent months due to high levels of sickness absence and vacancies within the team(s), which has had a significant impact on capacity.

Service capacity for the ND team is currently 15 initial assessments per month (capacity is usually 42 initial assessments per month when full funded established in place). Current assessment capacity equals 60 hrs of clinical time including administrative time to write up the lengthy necessary reports. This time is only for initial assessments. The capacity will increase by 8 initial assessments within 2 months due to a staff member returning to work and a further member of staff completing ADOS training.

The recruitment process is ongoing.  The ND team has previously experienced challenges when trying to recruit to Band 7 specialist SaLT posts and has taken the opportunity to further review the workforce model required to diversify and maximise capacity available to provide support, advice and undertake assessments.

Team members are also meeting with colleagues from neighbouring Health Boards to explore alternative ways of working and share best practice.

Recovery Plan

The waiting list position has been outlined on page 3. There is a clear requirement to balance the demand and capacity within this service, in line with the review of ND services undertaken across Wales and working collaboratively with Regional Partners to strengthen support for families, children and young people and where possible reduce the demand on the ND service. It is well recognised that families are keen to seek a diagnosis in order to understand their child in a better way and in turn to support more effectively.

A paper was presented to Management Board in March 2024 which outlined options to secure resources to start to reduce the number of children waiting and their waiting times, and inform an improvement trajectory, with the ultimate aim to improve access to support as soon as possible. Given the significant recruitment challenges facing ND services nationally, the SBUHB ND service proposed a stepped approach to addressing the backlog, which included:

- Reduce the number of children waiting over 52 weeks by 300, through insourcing provision by December 2027 which is costly at £1,500 - £2,500 per assessment.

- Recruit to substantive posts using a phased approach by December 2027 in order to deliver a sustainable service with demand and capacity in balance

- Continue to contribute to Welsh government neurodevelopment improvement programme developing an All Wales Model, together with working collaboratively with regional partnership board to develop pre and post diagnosis support for Children, young people and their families.

- Undertake further demand and capacity review to understand insourcing requirements and associated costs post September 2025 with aim to reduce reliance on requirement to insource as the substantive team are appointed and demand and capacity becomes balanced.

The proposals within the Management Board paper in March 2024 are currently unaffordable.

Stakeholder Engagement

Advice and signposting

The school age service signposts parent / carers to advice and support and have established an advice and consultation line for families and referrers seeking advice. The advice line has been received positively by users. Whilst the service has a duty to assess those already on the waiting list, it also has a universal duty to support health and wellbeing through advice and information for the population of 55,000 children and young people of school age living in SBUHB.

A factsheet has been developed for school-age children.  In June 2024, the factsheet was distributed (please see appendices), making it available to every stakeholder, child, young person, parent / carer and education colleagues.  The resource provides answers to some frequently asked questions, advice around the ND pathway as well as signposting stakeholders to universal resources to support the needs of the child/young person while they are awaiting an assessment. To compliment the factsheet, the ND team are updating and extending the information available via the Swansea Bay UHB Internet site.

The ND team provides advice to children and young people, and / or their parents /carers who have not already been referred to the service or on the ND waiting list to support and signpost.  Each call takes anything between 30 to 60 minutes, dependent on complexity of query, and is followed up by a letter detailing the discussion and advice provided.

Advice and Training

The team continues to deliver training to health colleagues and partner agencies to improve outcomes for Children and Young People through interagency collaboration and partnership, including third sector parent carer support groups. These include:

- ALN Coordinator (ALNCo) Training

Over fifty ALNCo’s attended two one-hour sessions in June 2024 to share, discuss and learn more about the content of the ND factsheet and how this can support children & young people with suspected Neurodivergence.

- ND Forums

ND forums were held across six days during May, June and July 2024.  Eighty slots were available to be booked by school, colleges or home-schooling parents/carers for a 45-minute appointment to discuss and problem solve possible ND referrals. The forums form part of the statutory ALNet ACT responsibility to identify and meet need delivered in partnership with Local Authority Specialist Teachers and ND service.

There is a multi-disciplinary approach to assessment process for ASD and across age groups and presentations. There is post diagnostic advice and signposting available for children and young people who are diagnosed with ASD and/or ADHD. This is provided during feedback and follow up appointments. Additionally, a rolling 6-week programme of advice and guidance is available for the families of children under five diagnosed with ASD, and a psychoeducation session is offered following diagnosis of ADHD. Psychoeducation is mandatory prior to initiation of medication.

Partnership working

Needs-led approach

The ND Clinical Lead, Service Manager and Designated Educational Clinical Lead Officer (DECLO) attended two sessions with headteachers for primary and secondary schools in Swansea.  During the session’s representatives from the Swansea Headteacher Association raised concerns around the demand placed on schools in relation to ND referrals.  The Local Authority Additional Learning Needs (ALN) senior manager was also in attendance.  The impact of the surge in demand on whole system capacity to support Children & Young People through statutory additional learning and emotional Health and Wellbeing frameworks was discussed.  It was agreed to continue collaborative working through further meetings to focus on a needs-led approach, shifting focus away from diagnosis-led culture.

Referral Pathway Redesign Project

The ND service is working in partnership with Swansea Parent Carer Forum to co-produce a revised referral pathway.  This is in response to wider stakeholder feedback around barriers to referral which cause delay and distress to children, young people and their parents / carers.

A draft pathway has been produced with a meeting planned for the autumn to link in with Local Authorities. A digital referral form will also be developed, with a training package, to simplify the referral process and make support readily available.

- RISKS

Despite the recent success of recruitment, the team has considerably reduced staffing levels due to sickness absence and vacancies.  The sickness level is currently 19.92%, which is being managed through wellbeing support and Health Board policies.  The recruitment process is ongoing.

The significant demand and capacity gap outlined on page 4 must be noted as a significant risk.

The fragility of such a small, specialist team has been on the risk register since 2018, with a risk rating of 16.  The risk is reviewed and updated regularly, however, it is likely this will increase due to the increased demand and decreased capacity particularly due to the reduced staffing levels.  Commencing in the Autumn, we will be liaising with NHS England colleagues, as well as other neighbouring Health Boards, to benchmark and understand innovative approaches adopted to improve the experience for patients and their workforce models in particular any diverse workforce models that can be a pivotal support mechanism for both families and education colleagues whilst children and young people wait.

It is important to note that the support, advice and education provided to Children, Young People, parents/carers and local authority has continued during the periods of sustained staffing deficits.

- Next Steps

Given the significant recruitment challenges facing ND services nationally, the SBUHB ND service propose a stepped approach to addressing the backlog and service pressures which includes:

- Recruit to substantive posts using a phased approach.  This will enable robust training and support for new members to the team while balancing capacity with demand, thus building a sustainable service that is able to ensure the needs are met for children & young people waiting.

- Continue to develop support, advice and education provided to stakeholders increasing awareness, promoting a needs-led culture and waiting-well approach by meeting the needs of the children & young people while they wait assessment.

- Continue to contribute to Welsh government neurodevelopment improvement programme developing an All-Wales Model, together with working collaboratively with regional partnership board to develop pre and post diagnosis support for Children, young people and their families.

- Recommendations

Members of the Performance and Finance Committee are asked to ACKNOWLEDGE:

- The current demand, capacity and staffing challenges faced by the Neurodevelopmental team.

- The levels of support, advice and training provided by the Neurodevelopment Team to stakeholders.

- The collaborative working in place with key partners

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The team are currently making every effort to recruit to current vacancies. This has been challenging but they are starting to make progress. The lack of service sustainability has been included on the risk register since 2018, with a risk score of 16 for demand on the service and the limited capacity available. The risk will continue to increase, together with the number of children waiting for assessment and their waiting times if no resource can be secured in order to invest into this service. |  |  |  |
| Financial Implications |  |  |  |
| Currently the priority will be to stabilise the workforce by recruiting to vacant posts within the budgeted establishment, using a staggered approach whilst exploring, developing and implementing innovative ways of working. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Nil to note |  |  |  |
| Staffing Implications |  |  |  |
| The size of the team is small, highly specialist, and currently has a significant staffing deficit, which is having a direct impact on performance. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Service is developing a preventative approach and working with local authority colleagues to reduce health inequalities, and encourage a needs-based approach irrespective of diagnosis. The service recognises the importance of timely advice and assistance, and that information is easy to access and available to all. |  |  |  |
| Report History |  | Regular reports have been presented at Performance and Finance Committee |  |
| Appendices |  |  |  |