| Meeting Date | 26 August 2025 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance & Finance Committee |  |  |  |  |
| Report Title | Welsh Government Oversight and Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Committee with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. |  |  |  |  |
| Key Issues | This report provides updates on all areas of delivery currently in escalation against WG’s Performance Framework, namely: Level 4 - Maternity and Neonates (escalated in July 2025). - Finance, strategy and planning. - Performance and outcomes relating to cancer, Urgent and Emergency Care and quality of care related to HCAIs. Level 3 - Performance and outcomes relating to planned care and CAMHS. Level 2 - Mental Health and Learning Disabilities This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |
| Appendices | No Appendices |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Maternity and Neonatal Services

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

Following the publication of the Independent Maternity and Neonatal Review published on 15th July 2025, the decision was made to escalate Maternity and Neonates to Level 4 (Targeted Intervention) from Level 3 Enhanced Monitoring.

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group and are outlined below.

- The Service Group continues to work with the NHS Executive Mental Health leads as part of the Level 2 support. The work is now complete, and feedback report provided back to the Health Board Executive team and the Service Group. This is receiving its final amendments following feedback from the CEO office.

- The MH and LD Service leads formally presented the report findings at the Mental Health Divisional Board meeting on 2nd July 2025 and also attended the MH&LD Senior Management Team on 10th July.

- The Health Board had already commenced work in advance of the receipt of the report and had established a Transformation Program. This has been informed by a review of the service by an external advisor. The findings were presented to an in-committee meeting of the Board in February and the recommendations were approved. There were some recommendations which were considered urgent by the Board and these have been completed or are in progress. The Transformation Programme will be led by a Programme Board with supporting reporting structures including Workforce, IT/digital, Service Redesign, Quality and Safety and Estates. The recommendations of the review by NHS Executive MH and LD leads will form part of the work programme. Elements of the programme (such as estates) commenced early with a complex programme to improve the estates in development. The other workstreams commenced in June.  A Programme Initiation Document has been developed which describes the overall Programme in more detail with the deliverables from each of the workstreams and the expected benefits of the Programme.

- The Health Board will receive an update in the June Board and further planned updates in July and Sept already scheduled.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (July 25) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. | - 72.43% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. | - 73.60% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 9.7% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 78.07% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 82.50% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 35.09% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 100% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 100% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at NPTH to reduce demand for Morriston Hospital services.

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - May – 70.5% - June – 81% - July – 81% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - May – 25% - June – 30% - July – 53% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - May – 99% - June – 99% - July - 93% |

Actions being taken to improve include:

- CAMHS Part 1B – Performance against Part 1B will remain a challenge until the backlog of >28-day waits is cleared. However, the recovery plan below will support this, and the planned demand and capacity review will help to identify the gap;

- Staff from other areas of CAMHS workforce to contribute to Primary Mental Health assessments

- Review the delivery methods of the CAMHS first intervention (Part 1B) offer

- Development of a multi-disciplinary case-discussion approach following Primary Mental Health assessment

- CAPA job planning for all staff who directly contribute to Part 1 activity

- Increase the number of group-based intervention by 1/3 across the year

- CAMHS part 1B now shows a slight increase from previously reported performance to 30% for the last reporting period (June) from a previous position of 25%.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - April – 60% (63%) - May – 57% (61%) - June – 52% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Identify additional surgical capacity, increase preassessment capacity to support theatres scheduling.  Additional chemotherapy capacity (business case agreed).

- Further actions/improvement in Skin as seasonal demand increases

- Dermatology Locum commenced in post this month

- Additional outpatient activity planned for September 2025

- Lone skin cancer consultant within ENT.  Urgent plan required from service to manage clinical activity during periods of absence.

- Urology – focussed review of prostate pathway, including discussion to develop a true Straight to Test pathway, reduce number of contacts.

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - May – 599 (4.8% reduction) - June – 249 (58.4% reduction) - July – 144 (42.2% reduction) |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - May – 11.71% - June – 10.88% - July – 10.04% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - May – 86.33% - June – 88.1% - July – 85.96% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - May – 191 - June – 192 - July - 186 |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 |

Actions being taken to improve include:

- Full implementation of D2RA model – Executive agreement between Health & Social Care CEO’S to deliver a D2RA model. Test of change delivered pre-Easter with overwhelming evidence of success. Test of change has continued, a work programme structure has been developed and a formal OCP is required to substantively reorganise workforce. The workshop was delivered on the 21st July 2025, demonstrating both operational and strategic work to drive the model forward. Recent paper presented to community and older persons board, requesting support for joint commitment to OCP in respect of Health and Social care staff required to deliver the D2RA hub.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital. As part of the UEC test of change programme, new initiatives regarding patient placement and pull into specialty wards have been implemented. Requirement to rewrite Health Board escalation framework pre-winter in light of the learning from test of change.

- UEC Care co-ordination Hub – Formally referred to as single point of access. Task and Finish group established to deliver Swansea Bay single point of access as from September 2025. Initial focus will be working in partnership with WAST on the national call before convey initiative for care home residents. National bid being submitted week commencing the 18th August 2025 and draft Standard Operating Procedure in place.

- Pathway of Care Delays (PoCD) – Focus on the delivery of actions to reduce PoCDs, COP deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. Escalation to COO / Directors of Social Services on a weekly basis. Planned adjustments to recording of D2RA pathways on SIGNAL in progress with the D2RA hub taking responsibility for allocation of the D2RA pathway as opposed to ward staff.

- Revised flow operating model/Anglesey Ward: Anglesey ward remains operational until end of March 2026. Initial UEC tests of change have proven successful in decompressing the Emergency department and improving ambulance handover. Phase 2 UEC test of change will commence September 2025, and will focus on the acute medical unit (AMU) downstream wards and the single point of access.

- Falls Pathway – New opportunity exists to further improve management of patient falls in the community. Linking community based teams and WAST with the single point of access provides potential benefits in terms of reduced conveyance to hospital. Further work is required to define these pathways which will enhance the Falls level 2 provision.

- UEC capital redesign – Building on the success of recent UEC tests of change and taking into consideration the learning, there is still ambition to co-locate the assessment function for acute medicine, frailty and same day emergency care (SDEC) services. The UEC capital redesign group will reconvene in September to work up a potential design opportunity within the wards A&B footprint.

5.3 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15th December 2023. Subsequently, in July 2025 the decision was made to escalate Maternity and Neonatal Services to Level 4 – Targeted Intervention.

The updated de-escalation criteria aligned with the new escalation status is still in draft format awaiting Welsh Government final sign off. Following agreement of the updated de-escalation criteria, detailed progress against these areas will be provided as part of the Perinatal Committee, chaired by the Executive Director of Nursing.

5.4 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - May - 5 - June – 11 - July – 13 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - May – 5 - June – 4 - July - 8 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - May – 5 - June – 7 - July - 9 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - May – 9 - June – 7 - July - 5 |

During July 2025, there were 5 new infection-related incidents/outbreaks, and 4 outbreaks which started and were reported in June, but concluded in July.

- 6 in Morriston: 5 COVID-19; 1 Norovirus (overall: 3 bed days lost).

- 1 in Neath Port Talbot Hospital: COVID-19 (overall: 0 bed days lost).

- 2 in Cefn Coed Hospital: both COVID-19 (overall: 54 bed days lost).

- During July, there were 2 genomically-linked outbreaks of C. difficile identified retrospectively in Morriston, the first involved 2 patients (both toxin positive, i.e. infection), the second involved 3 patients (all toxin negative, i.e. colonisation).

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group.

- New C. difficile Standards: Risk Assessment & Governance Framework agreed by Management Board. Multi-channel approach for dissemination and promotion at local level to support adoption.

- Scoping small scale project on antibiotic 72-hour review.

- Initial financial impact assessment of new National Cleaning Standards 2025 for SBUHB - £5m.  Further scoping work to assess the operational and clinical impact and risks.

5.5 Finance

On 6th June 2025 the Health Board received the NHS Wales Chief Executive’s letter which clearly set out the next steps and expectations of Welsh Government with regards to the Annual Plan and Financial Position. Key to this is the expectation that as a minimum the Health Board submits a forecast position that maintains the 2024/25 Outturn position of no greater than £42.5m.

The scale of challenge to address delivery of £42.5m is very significant and the Health Board  fully understands this, however at this point the forecast remains unchanged and is as per the Plan submitted on 31 March 2025 and summarised in the table below:

Table 1: Plan

The Health Board’s actual performance against the three components of the Plan (Operational Pressure, Savings Target, and Planned Deficit) for 2025/26 is provided in the table below. This table shows that in Month 4 the reported deficit was £7.6m, which is £2.7m above the £58.7m planned deficit. The YTD position reports a £31.776m deficit, which is £12.2m above £58.7m plan. The deterioration from the Month 3 position, primarily relates to 1/9th of the £3.1m shortfall in Employer’s NI funding being reflected in the position for the first time from Month 4. As per the Health Board letter to WG on 31 July 2025 it is recognised that the organisation will need to have clear mitigating actions to address this and other risks by 11 September 2025.

Table 2: Delivery of Plan

As you will note from the table above the key driver of the YTD £12.2m deficit over the current plan is the non-delivery of savings. This shortfall was partly mitigated in Month 4 by non-recurrent in-month benefits for the Primary Care, MH/LD and Morriston Service Groups, a further underspend in the Corporate Directorates and the increase in the application of non-recurrent opportunities. However, to counter this the Health Board brought in £0.340m of the £3.1m shortfall in Employer’s NI funding.

The Health Board acknowledged in the letter to WG dated 31 July 2025 that the scale of the savings will be challenging but was clear that it needs to ensure the following stages are addressed both in year and recurrently, and continues its focus on the immediacy of the financial requirements for 2025/26 supported by our external partner, Deloitte:

- Health Board is able to reach a sustainable position and achieve the in-year £58.7m deficit as set out in the March 2025 Plan submission

- Identification and delivery of £16.1m mitigations to off-set risks identified at Month 3, including Band 2/3 and the National Insurance impact for employers.

- Identification and delivery of further £16.2m of savings to allow the forecast to move from the £58.7m deficit plan to the required WG target of £42.5m

For each of the stages above, the level of savings has a stepped requirement. As noted in the Health Board letter of 31 July 2025, the total requirement of £87.7m (£55.4m+£16.1m+£16.2m) reflects 8% of the Health Board’s opening core allocation for 2025/26 and builds in the risks as noted at the end of July. The assessment of all known Risks and attributed value at the end of August will be built into the ‘Savings Gap Plan’ due for submission on 11 September 2025. The 11 September 2025 submission will also provide details on the savings to support the £87.7m requirement, alongside details on the actions and milestones to support this, aligned to the ongoing work of our external partner, Deloitte.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated July 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Management Board June 2025 agreed the process, timeline and approach to the Annual Plan 2026/27. Development of Planning and Performance Framework which sets out all national/local expectations is underway to drive priorities and deliverables for 26/27. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | Management Board approved paper on governance and approach in July. First CSP Exec Steering Group meeting took place 12th August. ToR and scope agreed. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Planning Maturity Matrix update will be shared with WG in September. Awaiting update from WG with regards to amends to Matrix, now expected November 2025. |
| Progress made with regional planning | Previous RJC meeting 7 May Next RJC meeting 18 August Regional working groups being established and governance arrangements finalise Regional work programmes and updates being prepared for 18 August for Regional Health Economy, Clinical Services, Workforce and OD, Data and Digital, Finance and Commissioning, Research and Innovation, Capital Planning. |

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | No Appendices |