| Meeting Date | 17 December 2024 |  | Agenda Item |  |  | 4.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Performance Update for Neurodevelopmental Service |  |  |  |  |  |
| Report Author | Sue Kotrzuba, Directorate Manager, Children & Young People |  |  |  |  |  |
| Report Sponsor | Ceri Gimblett, Service Group Director, NPTSSG |  |  |  |  |  |
| Presented by | Sue Kotrzuba, Directorate Manager, Children & Young People |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this paper is to provide a position statement for the Swansea Bay UHB Neurodevelopmental Service, including an update around Neurodivergence Wales Accelerated Design Event, Welsh Government funding allocation to address longest waits. The paper will also include the processes in place to support Children, Young People and their parents/carers whilst they await a formal assessment. |  |  |  |  |  |
| Key Issues | The key points of this paper are: - Current demand and waiting times - Allocation of Welsh Government Funding - Reduced capacity due to staffing deficits - Focus on needs-led approach shifting away from a diagnosis-led culture |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the funding allocation and plans to reduce long waiting times - ACKNOWLEDGE the current demand, capacity and staffing challenges faced by the Neurodevelopmental team. - BE ASSURED by the levels of support, advice and training provided by the Neurodevelopment Team to stakeholders. - BE ASSURED by the collaborative working in place with key partners |  |  |  |  |  |

PERFORMANCE UPDATE FOR NEURODEVELOPMENTAL SERVICE

- INTRODUCTION

The purpose of this paper is to provide a position statement for the Swansea Bay UHB Neurodevelopmental (ND) Service, including an update around Neurodivergence Wales Accelerated Design Event, Welsh Government funding allocation to address longest waits. The paper will also include the processes in place to support Children, young people and their parents/carers whilst they await a formal assessment.

- BACKGROUND

The management of ND Services (5 – 18 years old) was transferred from CAMHS to the Children and Young People Directorate (previously named Children & Young People Division) in April 2017, following provision of ring-fenced funding by Welsh Government to all Health Boards across Wales.

The service receives referrals for diagnostic assessment of the following:

- Autism Spectrum Disorder (ASD)

- Attention Deficit Hyperactivity Disorder (ADHD)

- Both of above (dual diagnosis)

Detailed papers have been presented to the Service Group and Performance and Finance Committee over the last 3 years, outlining the background to the ND Service, the ongoing increase in demand versus insufficient capacity, increasing waiting times, along with how the team have developed best practice within the service with limited resources. The last update to the Performance and Finance Committee was delivered in August 2024, together with an update to Management Board in March 2024.

- PERFORMANCE UPDATE - NEURODEVELOPMENTAL SERVICE (ND)

Demand

The increased demand on service, and gap within capacity, has resulted in continued long waiting times for this service. The number of children and young people on the ND waiting list as of 30th November 2024 is 1410, of which, 763 have been waiting >51 weeks.

The referral variance profile reflects the level of public awareness of ND, of the 861 referrals received since January 2024 (to end of Month November 2024) the number of referrals for ASD is steadily decreasing: 43% for YTD, with an increase of referrals for ADHD at 29% and Dual Diagnosis at 28%. Mid-year figures produced for the August 2024 Performance and Finance Committee (PFC) showed at that time ASD was 55% of all referrals, with ADHD as 25% and Dual assessments reported as 20%.

It has been noted in previous papers that overall, the total clinician hours required for each case to reach diagnosis is currently:

- ASD assessment – 15 hours

- ADHD assessment and treatment – 20 hours

- ASD and ADHD (dual) assessment and treatment – 30 hours.

The graph overleaf details the number of referrals received per month between January – November 2024. The demand for this service is in line with national statistics.

Workforce

Both the ND (5 – 18 years) and Early Years ND (0 – 5 years) have experienced significant workforce challenges over the past year due to high levels of sickness absence and vacancies within the team(s), which has had a significant impact on available capacity.

Service capacity for the ND team to undertake initial assessments per month has been 15 per calendar month (average year to date), despite recent resignations and then recruitment, this has remained fairly static due to the completion of induction training for the Band 7 CNS who joined the team earlier this year.

The ND team has previously experienced challenges when trying to recruit to Band 7 posts and has taken the opportunity to further review the workforce model required to diversify and maximise capacity available to provide support, advice and undertake assessments. Interviews are being held this month, for a Band 6 nurse role within the team.  The Service has plans to advertise a Band 6 SaLT role and are exploring the opportunity to recruit to a broader Band 6 role which could attract applicants with qualifications, skills and knowledge from a number of professions including Occupational Therapy and Clinical Psychology as examples.

Current Establishment

| Staff Group | Budget WTE | Actual WTE | Additional Information |
| --- | --- | --- | --- |
| G.P. Sessions | 0.44 | 0.00 | Vacant - reviewed as part of Workforce Plan, exploring opportunities for B6 SaLT/Practitioner and/or Clinical Psychologist |
| Consultant | 0.50 | 0.00 | Cross-charged to CAMHS (CAMHS Consultant works 0.5 wte for ND) |
| Band 7 | 0.90 | 0.80 | Band 7 Practitioner |
| Locum Consultant | 1.20 | 1.40 | In post |
| SaLT Band 8A | 2.00 | 2.00 | 1.0 wte substantive & *1.0 wte uplifted via successful RPB bid (fixed term) |
| Registered Nurse Band 7 | 4.40 | 1.30 | Due to recruitment challenges pursuing Band 6 role - interviews 12/12 |
| *AHP posts sit within SaLT budgeted establishment (P&C SG). Currently 1.0 wte Band 7 SaLT vacancy (due to uplift of B8a outlined above). Unable to recruit to backfill B7 SaLT fixed term. |  |  |  |

Horizon Scanning

A business case was presented to Management Board in March 2024 recommending the staffing model below to reduce backlog and ensure a sustainable future service; at the time of submission the business case identified the workforce as having an annual capacity of 504 initial assessment slots and 2016 follow-up assessment slots.  In addition, the business case identified a demand and capacity gap of 376 initial assessments and 1504 follow-up assessment appointments annually and it was noted that even when all current establishment posts are filled (no vacancies or sickness) the demand and capacity gap remain.

The Service acknowledges the business case was developed over nine months ago, therefore, whilst the Service awaits the outcome of the Welsh Government Accelerated Design Event and recruits to current vacant posts, a revised demand and capacity planning exercise will be undertaken alongside workforce planning to look at further opportunities to diversify the workforce to improve waiting times and stakeholder experience.  Due to difficulties experienced when recruiting to posts, the Service will explore other opportunities alongside those outlined below with Occupational Therapy, Clinical Psychology, Primary Care (Shared Care) and CAMHS.

| Staff group | Band | WTE |
| --- | --- | --- |
| Consultant Child & Adolescent Psychiatrist |  | 0.50 |
| Speciality Doctor |  | 1.00 |
| Consultant Practitioner (AHP) | 8b | 1.00 |
| Advanced Practitioners (SALT) | 8a | 1.00 |
| Advanced Practitioners (nurse prescriber) | 8a | 1.00 |
| SaLT, Nurse specialists, Specialist Practitioner | 6 | 4.00 |

Advice and signposting

The school age service signposts parent/carers to advice and support and have established an advice and consultation line for families and referrers.  The advice line has been received positively by users. Whilst the service has a duty to assess those already on the waiting list, it also has a universal duty to support health and wellbeing through advice and information for the population of children and young people of school age living in SBUHB locality.

The ND team provides advice to children and young people, and/or their parents/carers who have not already been referred to the service or on the ND waiting list to support and signpost.  Each call takes anything between 30 to 60 minutes, dependent on complexity of query, and is followed up by a letter detailing the discussion and advice provided. To compliment this, a factsheet has been developed for school-age children (please see appendices).

Universal Duty - Waiting Well

Please find below an excerpt of advice provided to colleagues in education to support a young person, Mia (not her real name) as part of the Universal Duty of Care. The team spent a considerable amount of time talking to Mia, her family and education colleagues.  Mia was not on the waiting list for a formal assessment during that time, education colleagues had identified Mia required additional support however, the details within their referral were insufficient to accept the referral.  Following the advice and support, Mia is now managing much better within the educational setting and is subsequently on our waiting list for a formal ADHD assessment.

“In the classroom, as part of universal learning provision Mia will need adaptive strategies to reduce the impact of her variable attention and focus – these would be small changes that make it easier for her to understand what she needs to do and get her work done. I have attached some general information sheets, including a self-assessment, which staff or parents could use to support Mia to identify areas she would like help with.”

Please see appendices for a blank copy of the self-assessment referred to in the excerpt above.  The document provides tips designed to help education colleagues and the individual develop strategies focussing on strengths enabling Mia to be the absolute best that she can be.

Site Visit by Performance & Finance Committee Independent Members

The EYND and ND team were delighted to spend time talking through our services in more detail with Independent Members, during a site visit that took place in Neath Port Talbot Hospital in August 2024.

The Service is very grateful to the independent members for the generous amount of time spent with us and for their commitment and understanding.  The Service was incredibly appreciative for the opportunity to listen to and learn from the experiences shared by the independent members whilst also discussing strengths, challenges the Service face alongside how we can improve the Service and experience for all of our stakeholders.

Senedd Research Briefing

In June 2024 the Senedd published research briefing around Neurodevelopmental Services in Wales (please see appendices).  The briefing provided helpful insights into ND services, specifically what services are available, the diagnostic pathways used and signposting to sources of help and support.  The briefing also acknowledged the long waiting times and high demand for ND services within Wales.

Minister for Mental Health and Wellbeing Visit

In early November, the ND team were invited to attend a visit to Tonna Hospital by Member of the Senedd, Sarah Murphy.  The visit, hosted by AMHS colleagues included colleagues from the Integrated Autism Service (IAS) for adults, our Chief Executive and COO.  The MS expressed an interest in amplifying the voices of those with lived experience to improve services and was keen to listen to ideas and challenges faced by both the ND Service and IAS.

Neurodivergence Improvement Programme - Accelerated Design Event (ADE)

Colleagues from across all sectors attended a two-day event at the end of November 2024.  The ADE was an opportunity to work collaboratively, share experiences, areas of best practice to learn from one another to manage challenging issues.  The event was well-attended by individuals from Health, Local Authority alongside Neurodiverse individuals who shared their lived experiences.  Whilst we await circulation of the post-event report, the anticipated outcomes, as circulated prior to the event, were:

- to have a clearer understanding of the current situation within ND Services across Wales

- encourage greater collaboration across the entire system

- identify potential solutions to long waiting times for neurodivergence in children and young people

- develop an ambitious plan to redesign neurodivergence pathways and new models of delivery

Digitalisation

The ND Service is working with digital colleagues to develop an electronic referral form.  The current referral form is a 26-page document (please see appendices), with sections that require completion by education as well as parents/carers.  When all sections are completed, the ALNCo will email the referral form to the ND Service’s generic email address.  In many instances there are sections that have vital information missing, delaying the referral triage process for the child /young person.  It is anticipated that the electronic referral form will streamline and improve this process, with optional and compulsory fields that require completion before submission.

Welsh Government Funding Allocation

In October 2024, correspondence was received from NHS Executive recognising the demand and capacity gaps of the ND service within SBUHB and acknowledging the associated length of wait for an assessment within ND & EYND across Wales continues to increase (please see Appendices).  Health Boards were asked to submit data to demonstrate the number of assessments required to reduce >104 week and >156 week waiting list backlog by the end of March 2025, together with the actions required to achieve this.  Plans duly submitted outlined proposed necessary actions if resources could be secured. This submission also outlined the risks and probability of delivery. The greatest risk to delivery was securing adequate skilled, trained workforce to carry out this work.

Following submission, additional information was requested.  NHS Executive colleagues requested the Service provides waiting list information for patients waiting >52 weeks. The additional information was submitted for both EYND and ND teams.  However, at this stage, the service was not required to submit a revised action plan/bid for the additional patient numbers provided (>52 weeks).

On the 11th November, SBUHB received confirmation from Welsh Government that non-recurrent funding had been allocated to reduce the numbers of longest waiting patients (please see Appendices).  This non-recurrent funding has to be utilised by end of March 2025. The Service is grateful for the funding allocation but recognises the significant challenge and is currently working through a realistic deliverable action plan which will have the maximum positive impact on those waiting the longest.

Table1 provides the total cohort for end of March 2025 per waiting times. It is important to note that the data displayed is the number of patients waiting and not the number of assessments required per patient to reach an outcome as outlined above.

Table 1

It is important to note also that the core and additional capacity has been based on an average of 4 assessments per child / young person, however, some individuals will require more than 4 assessments.

The service is scoping a number of options for reducing the waiting list, this includes internal capacity for additional hours (with funding), external providers (outsourcing) as well as agency locums via Medacs agency.  Due to the fragility of the service, there was no appetite to undertake additional sessions within the ND Service. However, there is a small number of sessions offered by consultants within the EYND team.  The service is still exploring opportunities with CAMHS & Primary Care colleagues with the necessary skills and experience to undertake additional sessions for ND and/or EYND patients.

The Service has compiled service specification(s) required by procurement with contracting and commissioning colleagues for the eTender exercise outlining the KPIs, level of assessments required from referral, including all assessments along the pathway, to post-diagnostic support for children and young people.  They will be completed stipulating in more detail the requirements such as professional registration requirements, DBS, governance, reporting/monitoring arrangements and so forth.  The Service is very grateful for the support received by contracting and commissioning colleagues whose contribution was fundamental to ensuring the Tender process commenced before Christmas.

Procurement processes will ensure value for money and robust governance/payment-related performance management processes with providers it is unlikely assessments will commence until January 2025.  This will enable the Service to undertake waiting list validation, stakeholder engagement/patient opt-in and appoint/induct any agency/bank locums to support initiative.

The ASD, ADHD & Dual Assessment Tenders will close on the 11th December 2024, with a Tender evaluation panel scheduled for 17th December 2024 to evaluate bids tendered.  Following procurement guidelines there will be a necessary 10-day standstill period with successful contracts awarded in January 2025, to commence the same month.  At the time of writing this report, there has already been interest shown in the Tender exercise, as such the Service remains optimistic.

- RISKS

Funding

Until the eTender exercise has concluded in early December, the Service is unable to provide an accurate waiting list reduction forecast. However, to maximise potential of reducing waiting times as much as possible, will award to multiple external providers on a part-award basis in the case of external providers and go out to agency as early as possible.

Bids submitted were for a higher value than the funding allocation received.  Based on costings received from one external provider the number of ASD assessments required could cost approximately £851,136.  One provider has advised they estimate they could deliver approximately 300 patients within the timeframe, which is approximately 50% of the assessments the UHB require by the target date of end of March 2025 to clear the >104 week and >156 week waiting list backlog.  However, the ask from Welsh Government is to make a reduction to the number of children and young people waiting, and their waiting times, and this number of children seen would achieve this ask. This provider has also confirmed they do not assess children below the age of 5 years so would only be appropriate for ND and not EYND.  The eTender process will reach out to multiple providers and the Service is committed to ensuring the funding received is invested to maximise the impact on the longest waiting patients across both ND and EYND.

Patient information for External Providers

Some providers have advised they would request a spreadsheet with patient details and a scanned copy of the referral form is uploaded onto their database/portal.  As already noted, each referral is 26 pages and for the volume of patients waiting additional admin & clerical resources will be required to undertake this task.

Patient Choice

Additional administrative support would be required to contact patients and/or their parents/carers to advise them of the proposal to outsource in order to avoid the lengthy waiting times.  This will enable patients to choose to remain on the UHB waiting list should they choose.

Due to the limited time to get this in place, this additional support would need to be sourced through agency following corporate approval.

- Next Steps

Given the significant recruitment challenges facing ND services nationally, the SBUHB ND service proposes a stepped approach to addressing the backlog and service pressures which includes:

- Conclude eTender exercise and commence outsourcing of longest waiting patients

- Develop electronic referral form with speed

- Recruit to substantive posts using a phased approach.  This will enable robust training and support for new members to the team while balancing capacity with demand, thus building a sustainable service that is able to ensure the needs are met for children & young people waiting.

- Continue to develop support, advice and education provided to stakeholders increasing awareness, promoting a needs-led culture and waiting-well approach by meeting the needs of the children & young people while they wait assessment.

- Continue to contribute to Welsh government neurodevelopment improvement programme developing an All-Wales Model, together with working collaboratively with regional partnership board to develop pre and post diagnosis support for Children, young people and their families.

- Recommendations

Members of the Performance and Finance Committee are asked to:

- ACKNOWLEDGE the funding allocation and plans to reduce long waiting times

- ACKNOWLEDGE the current demand, capacity and staffing challenges faced by the Neurodevelopmental team.

- BE ASSURED by the levels of support, advice and training provided by the Neurodevelopment Team to stakeholders.

- BE ASSURED by the collaborative working in place with key partners

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The teams are currently making every effort to recruit to current vacancies. This has been challenging but they are starting to make progress. The lack of service sustainability has been included on the risk register since 2018, with a risk score of 16 for demand on the service and the limited capacity available. The risk will continue to increase, together with the number of children waiting for assessment and their waiting times if no resource can be secured in order to invest into this service. |  |  |  |
| Financial Implications |  |  |  |
| Currently the priority will be to stabilise the workforce by recruiting to vacant posts within the budgeted establishment, using a staggered approach whilst exploring, developing and implementing innovative ways of working. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Nil to note |  |  |  |
| Staffing Implications |  |  |  |
| The size of the team is small, highly specialist, and currently has a significant staffing deficit, which is having a direct impact on performance. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Service is developing a preventative approach and working with local authority colleagues to reduce health inequalities, and encourage a needs-based approach irrespective of diagnosis. The service recognises the importance of timely advice and assistance, and that information is easy to access and available to all. |  |  |  |
| Report History |  | Regular reports have been presented at Performance and Finance Committee |  |
| Appendices |  |  |  |