| Date | 27th February 2024 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Annual Plan 23/24 Delivery: Quarter 3 Progress Report |  |  |  |  |  |
| Report Author | Kirstie Lambert, Strategic Planning Manager Ruth Tovey, Head of Strategic Planning Ffion Ansari, Head of IMTP Development & Implementation |  |  |  |  |  |
| Report Sponsor | Nerissa Vaughan, Executive Director of Strategy Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Ruth Tovey, Head of Strategic Planning – on behalf of Nerissa Vaughan, Interim Executive Director of Strategy |  |  |  |  |  |
| FOI | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides the reported Quarter 3 status of the priorities for delivery, as set out in the Health Board Annual Plan 23/24 as Goals Methods Outcomes (GMOs). |  |  |  |  |  |
| Key Issues | - High-level summary provided of the position at the end of Q3 (1st October 2023 – 31st December 2023) in respect of delivery against Annual Plan priorities (Goals and Methods). Where Methods are reported as off-track, mitigating actions and revised delivery timescales are highlighted as recommended by the Annual Plan Oversight Group on 6th February 2024 - Performance against Annual Plan outcome measures are reported at the end of Q3 are reported where metrics, data sources and trajectories are confirmed. - The Minimum Data Set (MDS) has been updated for Q3 with actual data against the required metrics, as requested by Welsh Government as part of the NHS Wales planning process. |  |  |  |  |  |
| Specific Action Required | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | The Committee is asked to: - NOTE the areas of achievements to deliver the Annual Plan in Q3. - NOTE mitigating actions against GMOs which are off-track. - APPROVE the revised timescales and changes to the plan where delivery is off track/ delayed into 24/25. - APPROVE updated MDS for Quarter 3 for submission to WG. |  |  |  |  |  |

ANNUAL PLAN 23/24 DELIVERY QUARTER 3 PROGRESS REPORT

1. INTRODUCTION

This paper provides the reported status against the priorities for delivery in Quarter 3 23/24, as set out in the Annual Plan as Goals Methods Outcomes (GMOs), together with an assessment of year-end position. Any changes from the plan submitted to WG are presented for the approval of Management Board. In addition, the updated Minimum Data Set (MDS) for Q3 23/24 is provided.

2. BACKGROUND

The Health Board has a statutory duty to submit a financially balanced Integrated Medium Term Plan (IMTP) annually. The Health Board approved and submitted to WG its Annual Plan for 23/24 in March 2023. Following scrutiny from WG, the Health Board submitted Supplementary Information on 31st May 2023, to address concerns on delivery of the Ministerial Priorities, targets and the Financial Plan 23/24.

Responsibility for delivery of the Annual Plan via these ‘Programmes’ or Systems is with a named Lead (Executive Director or Service Group Director), acting as Senior Responsible Officer (SRO), as set out in Table 1 below:

Table 1: SROs for each Annual Plan Programme/ System:

| Programme/ System | Executive Lead |
| --- | --- |
| Primary, Community & Therapies | Group Service Director for Primary, Community & Therapies |
| Urgent & Emergency Care | Chief Operating Officer |
| Planned Care | Chief Operating Officer |
| Cancer | Executive Medical Director |
| Mental Health and Learning Disabilities | Group Service Director for Mental Health & Learning Disabilities |
| Children and Young People | Executive Director of Nursing & Patient Experience |
| Maternity | Executive Director of Nursing & Patient Experience |
| Workforce | Executive Director of Workforce & Organisational Development |
| Digital | Director of Digital |
| Quality and Safety | Executive Director of Nursing & Patient Experience This will not be reported in detail in this report due to separate governance routes and assurance being provided to the Board |
| Population Health | Executive Director of Public Health |

The Annual Plan Oversight Group (APOG) chaired by the Chief Operating Officer received an update on Q3 position from all areas on 6th February 2024.

Minimum Data Set

The Minimum Data Set (MDS) is a part of the IMTP and forms part of the formal submission to WG. The MDS provides a data triangulation between workforce, planned service activity and finance. The MDS is considered by WG as a tool to aid planning, providing quantification of the ambition in plans at organisational level, and not as a performance monitoring tool.

3. ANNUAL PLAN 23/24 DELIVERY UPDATE

3.1 PROGRESS AGAINST PLAN – SUMMARY

System areas were required to update on the Q3 status of Methods, assessed against delivery of Q3 milestone (where these have been detailed), using the following definitions:

| METHODS STATUS | Definitions |
| --- | --- |
| Green | ON TRACK - Progressing as planned /to agreed timelines |
| Amber | OFF TRACK – Not progressing as planned/ to original timelines, however this is manageable & mitigating actions are in place |
| Red | OFF TRACK – Not progressing as planned/ to original timelines, there are significant issues which require escalating |

Table 2 summarises the reported position for each area, see Appendix 1 for the full detail of reporting in Q3 on all Methods.

|  | Q3 status METHODS |
| --- | --- |
| Primary Care, Community & Therapies |  |
| Urgent & Emergency Care |  |
| Planned Care |  |
| Cancer |  |
| Mental Health & Learning Disabilities |  |
| Children & Young People |  |
| Maternity |  |
| Workforce |  |
| Digital |  |
| Population Health |  |
| Quality and Safety | Quality & Safety GMOs have a rigorous governance arrangement and are reported separately via Quality & Safety Committee and Management Board and therefore, rather than duplicating information, we are no longer reporting against Q&S GMOs. |
| OVERALL |  |

3.2 Q3 ACHIEVEMENTS

Q3 achievements are highlighted in Appendix 2.

3.3 OFF TRACK METHODS AND CHANGES TO THE PLAN

The Annual Plan Oversight Group (APOG) on 6th February 2024 chaired by the COO made recommendations on proposed changes to the Plan, in respect of GMOs with methods off track/  delayed into 24/25. Table 3:

| System/ Area | GMO | Recommendations from APOG – Proposed Changes to Plan |
| --- | --- | --- |
| Population Health | Several GMOs from the Population Health area have been reported as Off Track and will not to be delivered by end Q4. | - Agreed that this was not necessarily a true reflection of the positive steps and work undertaken within the Population Health domain during the 23/24 Annual Plan year. - Agreed that moving into Q4, the Population Health GMOs will be cleansed to enable us to illustrate the good work already undertaken during the 23/24 Year and to drive forward the work that has gone into the framing of the 24/25 Annual Plan within the Population Health context. - The reprofiling and narrative for the Population Health GMOs will allow us to illustrate that implementation of the Population Health Strategy is an organisational priority. - The adoption of the strategy, at scale, requires coordinated action across the strategic, tactical and organisational perspectives of the organisation to support a move from transactional to transformational way of doing business. The adoption of population health thinking, actions and behaviours requires a cultural shift within and across the entire health board. |
| Children & Young People | Deliver a permanent 24-hour neonatal transport model through the new Operational Delivery Network | Due to the nature of the funding from WHSSC for this GMO it is unlikely that it will be delivered with the ODN aspect included. This GMO will be reprofiled for Q4 reporting to include what will be delivered by Q4 23/24, and what will be carried forward into the 24/25 Annual Plan. |
|  | Provide CAHMS 24/7 crisis service support in line with adult services | Amended Q4 Milestone: Following OCP embed 24/7 Crisis Team within CAMHS Service |
| Cancer | Transfer PMB service (Bridgend activity) to CTM. | Due to the complexity of needed to complete the disaggregation and transfer of service from CTMUHB, this GMO is unlikely to be delivered by Q4. Timelines are currently being reviewed and the GMO will be reprofiled for Q4 to include what will be delivered by Q4 23/24, and what will be carried forward into the 24/25 Annual Plan |
| MHLD | Develop Adult Mental Inpatient provision business case | Amended Q4 Milestone: Change in WG process. Submit revised detailed information for scheme to WG by 14th February 2024. |
|  | Work with the APB Commissioning team in relation to substance misuse accommodation strategy for all providers across region including CDAT. | Amended Q4 Milestone: Continue to work with HB Capital planning to investigate opportunities for relocation to appropriate premises. |
|  | Evaluate Acute In-Reach Rehabilitation (AIRR) service with a view to expand the service for male patients and roll it out to our Female population | Amended Q4 Milestone: Running a revised pilot based on adult female ward only with baseline measurements agreed. Outcome to be reviewed in Adult Inpatient Provision meeting and will form part of Acute Adult Inpatient Modernisation (Rehab) project included in 24.25 plan |
|  | Improve patients access to routine Dental treatment in Forensic Services | Amended Q4 Milestone: Action plan to be developed based on outcome of SLA discussions and funding secured for refurbishment. |
| Primary Care & Community | Delivery of the Health Delivery Plan and HIW recommendations within HMP Swansea | Work is ongoing within this GMO but is dependent on the availability of additional resources and funding. To complete all works associated with this GMO, funding is required. This GMO will be reprofiled for Q4 reporting to include what will be delivered by Q4 23/24, and what will be carried forward into the 24/25 Annual Plan. |
| Digital | Virtual wards MDT "wards" to support high risk frailty patients in the community. Implemented across 8 Clusters. | Remove from Plan: This has been paused due to ongoing discussions with the Virtual Ward team around development in an alternative system and connecting to Signal. |
|  | Implementation of All Wales PROMS system from the National Framework | Revised Q4 Milestone: Procurement standstill due to finish Jan 24. Contract award completed by end of January Kick off meetings with supplier Feb 24 |

3.4 Off-Track Methods

The below Table 4 details the red ‘off track’ methods reporting, including reasons for delay and the mitigating actions being undertaken.

| PRIMARY CARE, COMMUNITY & THERAPIES Service Group Lead: Brian Owens 1 |  |  |  |
| --- | --- | --- | --- |
| GMO (Reference number and Method) | Off Track Milestone for Q3 | Reason for delay and what is being done to bring activity back ‘on track’ (Mitigating actions) | Change to Plan: Proposed Revised Milestones |
| PCT_034: Delivery of the Health Delivery Plan and HIW recommendations within HMP Swansea to deliver health and wellbeing in an equitable and safe manner. | 7 actions remain open and work to close these is ongoing but dependent on additional resources. Full implementation of plan remains unfunded Delayed into 24/25 | Dependency on additional resources / funding | No revised milestones – will be reprofiled for Q4 |
| URGENT AND EMERGENCY CARE Exec Lead: Deb Lewis 3 |  |  |  |
| UEC_001: Focussed management of at risk UEC patients, to avoid admission to acute settings - Expand the VW model - phase 4 (FDS expansion) and 5 (a Inreach b 7/7) | Virtual wards in all clusters and performance over target. Virtual wards require funding to expand - no additional funding has been accessed so therefore project changed to 'red' as per the GMO definition | Earliest anticipated delivery in 24/ 25 - no available funding identified with 23/ 24 | To be reviewed for Q4 |
| UEC_004 (see VBHC DIAB_001-004): Set up Community Diabetes Clinic within Primary and Community Care | Q3; will not be delivered in 23/24. |  |  |
| UEC_004 (see VBHC DIAB_001-004): Achieve 80% sign-up to the Primary Care Diabetes NES by Q1 2023/24 to increase the numbers of GLP-1 initiations completed within Primary Care; | Off track Q2 and Q3; Currently on hold due to GLP-1 shortage | Diabetes project continuing into 24/ 25 in line with VBHC plans - likely merge of some activity into One Bay Way Programme | To be reviewed for Q4 |
| PLANNED CARE Exec Lead: Deb Lewis 2 |  |  |  |
| PC_013: Expand DXA capacity across the SW Region. | Off-track in Q3 Off Track (manageable) in Q1, Q2 There is no milestone for this activity | Expanding DXA capacity is not being progressed currently. The service have split the waiting lists, with one list for SBUHB patients and one for HDUHB patients. This has been flagged by the COO for SBUHB as creating inequality for patients in the region and a request has been made to the service to produce one list. Current Breaches (end of Dec 2023): SBUHB: 861; Recovery funded activity: - Extended weekday sessions projected an additional 80 patients per month; - Weekend sessions implemented in August 2023 and projected additional 60 patients per month; The WLI activity typically results in higher volumes of patients being seen than projected. HDUHB: 2812 (scanning); No meaningful actions have been implemented to reduce the impact of the COVID pandemic on waiting lists for DXA in Hywel Dda. NB: there is a separate waiting list for reporting. Separate to the HDUHB and SBUHB position, SBUHB provides technical and scientific support to CTMUHB three days a week for DXA scanning; CTMUHB provides the equipment, facilities, reporting etc. and arranges the waiting list. | To be reviewed for Q4 |
| PC_014: Increase cardiac, respiratory and neurophysiology diagnostic, capacity including direct access for primary care. | Cardiac, Respiratory: Off-track in Q3 Off Track (manageable) in Q1, Q2 | There has been no increase in core capacity - enhancements have been delivered through temporary measures (e.g., WLI, insourcing, outsourcing). Risks to achieving the targets have been raised in diagnostics board and escalated to Planned Care Board for consideration of additional funding. See Table 5 for details on mitigation against off track performance for Cardiac CT and MRI | To be reviewed for Q4 |
| CANCER Exec Lead: Raj Krishnan 1 |  |  |  |
| CAN_020: Transfer PMB service (Bridgend activity) to CTM. | Off track in Q2. Delayed into 24/25 | Complexities with SLA disaggregation has led to the delay. Focussed work ongoing and will be included in 24/25 GMOs | To be reviewed for Q4 |
| MENTAL HEALTH AND LEARNING DISABILITIES Service Group Lead: Janet Williams 3 |  |  |  |
| MHLD_024: Continue to work jointly with WHSCC on their 3-5 year plan for Specialist Mental Health Provision in Wales. | Off Track (Significant issues) in Q2 & Q3 | Awaiting Capital Funding – Delayed into 24/25 - To be included in 24.25 plan and further ongoing discussions with WHSCC | Amended Q4 Milestone: Awaiting decision on end of year Capital monies |
| MHLD_027: Implementation of WCCIS into Service Group | Off Track (Significant issues) in Q2 & Q3 | Awaiting confirmation from WG on options and alternatives Will not be delivered – awaiting HB decision | To be reviewed for Q4 |
| MHLD_031: Improve patients access to routine Dental treatment in Forensic Services | Off Track (Significant issues) in Q3; Off Track (manageable in Q2) | With Cwm Taf need capital monies investment case to develop the suite Delayed into 24/25 - Unsure of timescales as currently with CTM for decision making and identification of capital funding from CTM | Amended Q4 Milestone: Action plan to be developed based on outcome of SLA discussions and funding secured for refurbishment |
| CHILDREN AND YOUNG PEOPLE Exec Lead: Gareth Howells 5 |  |  |  |
| CYP_002: Deliver a permanent 24-hour neonatal transport model through the new Operational Delivery Network | Off track in Q2 and Q3; This has been escalated to Nurse Director and CEO who have met with WHSSC. Funding for implementation of ODN frozen by WHSSC due to current financial position – this will be revisited in March 2024 so not deliverable during 23/24 | Funding for implementation of ODN frozen by WHSSC due to current financial position – | No revised Milestone – will be reprofiled for Q4 |
| CYP_012: Work with RPB colleagues within Mental Health services to undertake a review of psychological and multi-disciplinary services required for children with learning disabilities, | Off track Q3; Further work required to capture Health Board wide gap (not just psychology services) |  | To be reviewed for Q4 |
| CYP_027: Design and plan for General and Surgical Paediatric services to be located in a designated Childrens unit | Off track in Q2 and Q3 | Unlikely that business case will be submitted without the availability of an architect | To be reviewed for Q4 |
| CYP_028:design and plan age appropriate accommodation for Adolescents (linked to above) | Off track in Q2 and Q3; Unlikely that business case will be submitted without the availability of an architect - linked to CYP_017 | Unlikely that business case will be submitted without the availability of an architect | To be reviewed for Q4 |
| CYP_036: Colloborative scoping to explore use of Advanced Practitioner posts to demonstrate prudent use of skill set, and release consultant capacity | Off track in Q2 and Q3; Roll over into 24/25 due to funding – linked to above GMOs |  | To be reviewed for Q4 |
| MATERNITY Exec Lead: Gareth Howells 2 |  |  |  |
| MAT_010: For women who need obstetric care, we will undertake a full review of our ante-natal clinics to ensure care pathways and specialist services are available with a view to ensuring that most women see no more than 2 different obstetricians through their pregnancy | Off track in Q3; Off Track (manageable) in Q2 | Departmental focus has been on transforming workforce models in community and the OU - ANC is the next phase and potentially more complex as Obstetricians and Radiology will be involved and job plans likely to be affected. ANC work to commence Q4. | Q4 Milestone Remains extant: Revised Model in Place |
| MAT_012: Develop a robust workforce plan across all services, ensuring we meet RCOG, Birthrate+ and GPAS standards. | Off track in Q3; Off Track (manageable) in Q2 | OCPs complete and recruitment and implementation underway. . Review of non-registered workforce commenced in Q3 and included in IMTP 24-25. Delayed into 24/25 | Q4 Milestone Remains extant: Implementation (ongoing monitoring) |
| DIGITAL Exec Lead: Matt John 4 |  |  |  |
| DIG_003: Virtual Consultations and Reviews - Maintain and increase the use of remote and virtual ways of working introduced for outpatient, primary care and therapy services including utilisation of Attend Anywhere, SOS, PIFU and PROMs functionality | Off Track (significant issues) – Off track (manageable) in Q2 | Usage of the Attend Anywhere platform continues to drop, which is consistent with the national reduction in usage. TEC Cymru (who has funded roll out of the system) will be replacing it with a more cost-effective solution in September 2024, in light of the low usage across Wales. The Digital team will work with the OPD Transformation Group to include the new platform as part of a coherent strategy. | To be reviewed for Q4 |
| DIG_007: Eye Care - eReferrals and EPR for Ophthalmology. | Off Track (significant issues) – Off track (manageable) in Q2 | DHCW are working on the future options for the national programme of work. An initial go live in the glaucoma service will not be feasible in this financial year Delayed into 24/25 | To be reviewed for Q4 |
| DIG_016: Virtual wards - MDT "wards" | Requirements assessed, however the Virtual Ward team have been exploring potential of procuring a 3rd party solution to function as their VW system. The process of migrating from sharepoint to V3 Signal is therefore on hold, pending a decision from the VW team |  | Remove from Plan: paused due to ongoing discussions with the Virtual Wards team around development in an alternative system and connecting to Signal |
| DIG_018: Welsh Intensive Care Information System (WICIS) - | Off Track (significant issues) | Although readiness activity is well underway, including testing, milestone is reported as red due to significant issues discovered with the system resulting in uncertainty around the way forward for the project. Discussions underway with DHCW and the rest of Wales pertaining to the suitability of the solution as a national intensive care system. | To be reviewed for Q4 |
| WORKFORCE Exec Lead: Debbie Eyitayo 2 |  |  |  |
| WF_010: Attract and recruit our workforce | Off track (significant issues) – Off Track (manageable) in Q2 | Unable to deliver review by end of year due to staff absence. Staff sickness will require this to be rolled over into 24/25 GMOs with expected delivery date of end of Q4 (24/25) | To be reviewed for Q4 |
| POPULATION HEALTH Exec Lead: Keith Reid 4 |  |  |  |
| POPHEALTH_002: An action plan is developed for implementing year 1 priority actions aligned to the organisational strategic priorities emerging from the PHS | Off Track (Significant Issues) in Q2/Q3 | There continues to be no mechanism currently identified to allocate and agree ownership / leadership and management of the whole of organisation / whole of system actions required, across all 4 pillars in 23/24. Population Health aligned with strategic objective 1: people of Swansea Bay live healthier more equal prosperous lives. Population health priorities required for all 24/25 R&S plan submissions will enable a better undertstanding of the 24/25 actions for SDGs agreeed through R&S plan process. There continues to be no mechanism, system or processes for strategy implementation ownership & leadership for of whole system/organisation change across 4 pillars | Population Health GMOs are to be reviewed and reprofiled with additional narrative around achievements and positive works completed and underway to support Population Health agenda in future planning arrangements |
| POPHEALTH_003: Supporting programme/project support infrastructure & capacity is established to help drive forward implementation of PHS goals/priorities and cross organisation delivery/response | Off Track (Significant Issues) in Q2/Q3 | Organisational infrastructure does not support strategy execution through organisational development; Active engagement of independent members at Population Health and Partnerships Committee; Development of behavioural change capability and resource to support organisational development; Identification of health intelligence capability requirements to facilitate organisational development; Population Health workshops to support 24/25 planning process; Scoping of external partnerships to support delivery of agreed priority areas. This GMO will be a continuous developmental programme of activity across the health board and partners in support of our population health ambition. |  |
| POPHEALTH_005: Operational delivery mechanisms are established that take account of system wide responsibility and accountability for delivery of population health outcomes | Off Track (Significant Issues) in Q3; Off Track (manageable) in Q2 | Operational delivery remains federated through SDGs; Progress on developing internal structures at system level, impact of these and capability development not being realised at operational level in Q3; Proactive engagement and progress on embedding population health into SBUHB Strategic Objectives along with the development of strategic indicators; Local population health measures process agreed and to be reported quarterly through APOG from Q4; Leads developed to operationalise PHS in some SDGs. Work continuing to engage with SDGs that as of yet have not been responsive. This GMO will be a continuous developmental programme of activity across the health board and partners in support of our population health ambition. |  |
| POPHEALTH_007: Develop a population health intelligence function and products that ensure data & intelligence led decision making | Off Track (Significant Issues) in Q2 & Q3 | Identification of health intelligence capability requirements to build capacity to facilitate organisational development. Scoped additional support requirements to facilitate organisational development around health intelligence. Organisational processes not currently supporting requirements to build organisational capability. Unlikely to be able to secure additional capability within 23/24 due to constrains and timescales associated with procurement of external services |  |
| POPHEALTH_008: Planning, service development & commissioning approaches are informed by population health intelligence & evidence based practice, with a focus on addressing drivers of health inequities. | Off Track (Significant Issues) in Q2 & Q3 | Planning: Integration of PHS into Strategic Objective 1: People of Swansea Bay lead healthier more equal prosperous lives including development of strategic indicators; Population health influence at One Bay Way limited due to continued focus on service delivery, limited health intelligence capability and pathway data; Management Board Paper - resource allocation to achieve population health gains agreed. Ongoing development around operationalising this proposal through population health governance; Population Health supporting development of VBHC strategy; Development of Population Health Indicators for organisation This GMO will be a continuous developmental programme of activity across the health board and partners in support of our population health ambition. Foundational work underway in 23/24 to better develop capability & capacity around planning and service development in 24/25. |  |
| POPHEALTH_009: Public health technical expertise & function is used to embed a focus on addressing health inequities at a population level, including addressing their root causes, through programmes, strategies and partnerships internally & externally (within capacity and prioritised based on need). | Off Track (Significant Issues) in Q2 & Q3 | Resource constraints within public health team Q3; Recruitment processes successful in key areas effect not felt till Q4 23/24 Q4 Increased capacity within public health team to support development of priority areas |  |

3.6 PROGRESS AGAINST PLAN – OUTCOMES

Table 5 below details the key outcomes for Q3 where programmes have approved outcome measures. Performance in Q3 against outcome measures are correct as at February 2024, and are rated accordingly:

- Green, if the outcome measure has met or exceeded the original target,

- Amber, if the measure is moving away from the baseline position in the desired direction, has not yet reached the target but the trajectory indicated that it is likely to do so,

- Red, if the measure is not moving in the desired direction, or the trajectory indicates that it will not meet the target. Mitigating actions being undertaken for off track outcomes are routinely reported to P&F Committee and the Board, and are therefore not duplicated in this report.

TABLE 5: OUTCOMES 23/24 and Q3 performance against trajectories

| Goal |  | Outcome | Target | Baseline Position (March 2023) | Oct Q3 FORECAST | Oct Q3 ACTUAL | Nov Q3 FORECAST | Nov Q3 ACTUAL | Dec Q3 FORECAST | Dec Q3 ACTUAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| URGENT AND EMERGENCY CARE |  |  |  |  |  |  |  |  |  |  |
| Improve ED waits and ambulance handover times |  | Reduced % patients spending more than 4 hours in ED | *Ministerial Target* 95% seen under 4 hours | 73.7% | 77% | 76.63% | 77% | 75.32% | 78% | 74.74% |
|  |  | Reduced number patients spending more than 12 hours in ED | *Ministerial Target* 0 waiting more than 12 hours | 1,385 | 845 | 1,207 | 760 | 969 | 675 | 994 |
|  |  | Reduction in the number of ambulance patient handovers over 1 hour | *Ministerial Target* Improvement trajectory towards a national target of zero by March 2024 | 729 | 444 | 696 | 431 | 724 | 418 | 762 |
|  |  | Reduction in ambulance conveyancing rates | Reduce by 20% or 10 a day | 1,309 | - | 1181 | - | 1183 | - | 1294 |
| Goal |  | Outcome | Target | Baseline Position (March 2023) | Oct Q3 FORECAST | Oct Q3 ACTUAL | Nov Q3 FORECAST | Nov Q3 ACTUAL | Dec Q3 FORECAST | Dec Q3 ACTUAL |
| PLANNED CARE |  |  |  |  |  |  |  |  |  |  |
| Improve access to outpatients (new and follow-up) |  | Number of patients waiting more than 52 weeks for a new outpatient appointment | *Ministerial Target* Improvement trajectory towards a national target of zero | 3,895 | 0 | 0 | 0 | 0 | 0 | 0 |
|  |  | Number of patients waiting more than 36 weeks for a new outpatient appointment | *Ministerial Target* Improvement trajectory towards a national target of zero | 9,163 | 6,153 | 4,508 | 5,746 | 4,282 | 5,602 | 4,546 |
|  |  | Number of patients waiting for a follow-up outpatient appointment who are delayed by over 100% | *Ministerial Target* Improvement trajectory towards a national target of zero | 41,710 | 34,801 | 41,188 | 33,666 | 41,727 | 32,531 | 43,784 |
| Improve treatment wait times |  | Number of patients waiting more than 104 weeks for referral to treatment | *Ministerial Target* Improvement trajectory towards a national target of zero | 6,015 |  | 4,097 |  | 3,460 |  | 2,969 |
|  |  | Number of patients waiting more than 52 weeks for referral to treatment | *Ministerial Target* Improvement trajectory towards a national target of zero | 18,181 | 15,791 | 13,942 | 15,514 | 13,453 | 15,389 | 13,386 |
| Improve access to Therapies |  | Number of patients waiting over 14 weeks for a specified therapy | *Ministerial Target* Improvement trajectory towards a national target of zero by March 2024 | 193 | 105 | 195 | 75 | 84 | 75 | 73 |
| Improve access to Diagnostic services |  | Number of patients waiting over 8 weeks for an Endoscopy | Improvement trajectory towards a national target of zero by March 2024 | 4,554 | 4,136 | 3,737 | 3,988 | 3,427 | 3,824 | 3,553 |
|  |  | Number of patients waiting over 8 weeks for a specified diagnostic | *Ministerial Target* Improvement trajectory towards a national target of zero by March 2024 | 6,514 | 5,389 | 5,939 | 5,089 | 5,429 | 4,750 | 5,616 |
| Goal |  | Outcome | Target | Baseline Position (March 2023) | Oct Q3 FORECAST | Oct Q3 ACTUAL | Nov Q3 FORECAST | Nov Q3 ACTUAL | Dec Q3 FORECAST | Dec Q3 ACTUAL |
| CANCER |  |  |  |  |  |  |  |  |  |  |
| Improve cancer waiting times |  | Number of patients waiting > 62 days for their first definitive cancer treatment from point of suspicion | *Ministerial Target* Improvement trajectory towards al target of zero | 391 | 278 | 316 | 232 | 263 | 272 | 302 |
|  |  | Improvement in % of patients starting their first definitive treatment within 62 days from point of suspicion (regardless of the referral route) | *Ministerial Target* Improvement trajectory towards a national target of 80% by 31st March 2026 | 53.2% | 68% | 52% | 72% | 53% | 74% | 51% |
|  |  | Scheduled Radiotherapy patients | *Ministerial Target* 80% of patients to start RT within 14 days |  | Not available | 10% | Not available | 12% | Not available | 17% |
| CHILDREN AND YOUNG PEOPLE |  |  |  |  |  |  |  |  |  |  |
| Goal |  | Outcome | Target | Baseline Position (March 2023) | Oct Q3 FORECAST | Oct Q3 ACTUAL | Nov Q3 FORECAST | Nov Q3 ACTUAL | Dec Q3 FORECAST | Dec Q3 ACTUAL |
| Community Paediatrics & General Paediatrics |  | Increased % of NDD assessment and intervention received within 26 weeks | *Ministerial Target* 85% (National Target) | 29% | 35% | 30% | 35% | 30% | 40% | 29% |
| MENTAL HEALTH & CAMHS |  |  |  |  |  |  |  |  |  |  |
| Goal |  | Outcome | Target | Baseline Position (March 2023) | Oct Q3 FORECAST | Oct Q3 ACTUAL | Nov Q3 FORECAST | Nov Q3 ACTUAL | Dec Q3 FORECAST | Dec Q3 ACTUAL |
| Improve Adult Mental Health assessment and treatment waits | Part 1a - % of mental health assessments undertaken within (up to and including) 28 days from the date of receipt of referral |  | *Ministerial Target* 80% | 96% | 85% | 100% | 85% | 97% | 85% | 98% |
|  | Part 1b - % of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS |  | *Ministerial Target* 80% | 100% | 95% | 100% | 95% | 100% | 95% | 100% |
|  | Part 2 - % of health board residents in receipt of secondary mental health services who have a valid care and treatment plan |  | *Ministerial Target* 90% | 87% | 90% | 89% | 90% | 90% | 90% | 88% |
| Improve CAMHS assessment and treatment waits | Part 1a - % of mental health assessments undertaken within (up to and including) 28 days from the date of receipt of referral |  | *Ministerial Target* 80% | 74% | 35% | 77% | 35% | 86% | 35% | 70% |
|  | Part 1b - % of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS |  | *Ministerial Target* 80% | 50% | 35% | 100% | 38% | 100% | 40% | 86% |
|  | Part 2 - % of health board residents in receipt of secondary mental health services |  | *Ministerial Target* 90% | 100% | 90% | 92% | 90% | 98% | 90% | 92% |

3.7 MDS UPDATE FOR Q3

Welsh Government have requested formal submission of the MDS updated for Q3 23/24. A copy of the Q3 actual data as provided to date is included as Appendix 4 and will be submitted to WG following approval by Management Board.

3.8 WELLBEING OBJECTIVES ALIGNMENT AND REPORTING

In meeting our duty to deliver the Wellbeing of Future Generations Act (2015), the Health Board is required to publish its Wellbeing Objectives (WBO) and report on their delivery. In 2021, the CEO led a WBO refresh and these are published in the Annual Plan 2021-22. These Wellbeing Objectives are:

- WBO1: Give every child the best start in life

- WBO2: Nurture and use the environment to improve health and wellbeing

- WBO3: Apply ethical recruitment practices and support health and care workers to be healthy, skilled, diverse and resilient

- WBO4: Plan, commission, deliver and promote equitable, inclusive and accessible health and wellbeing services

- WBO5: Provide opportunities to support every adult to be healthier and to age well

- WBO6: Seek to allocate our resources to meeting the needs of, and improving, the population’s health

To delivery of the WBO, the WBOs have been mapped to the Goals of the Annual Plan 23/24. The Q3 updates against delivery of methods were reviewed and the overall position of Goal delivery is reported below. This enables the Health Board to demonstrate how the Annual Plan is contributing to delivering our WBOs.

5. FINANCIAL IMPLICATIONS

The Health Board developed and submitted a  revised 3 Year plan on 31st May 2023 which reported a deficit of £86.6m. Following the hard work undertaken within Welsh Government NHS Wales had received £460m of additional funding of which Swansea Bay received £60.8m for 2023/24, of which £43.3m is recurrent. For 2023/24 there is then a requirement for the HB to deliver a 10% reduction based on the original deficit plan value of £86.6m, to achieve a control total of £17m. There are multiple actions required to achieve the Control total set by WG and this is being overseen by what is referred to as the ‘Landing Plan’, with updates on delivery against the plan provided to Performance & Finance Committee each month. At the end of Mth 9 the YTD position reported to WG in the MMR was £41.5m overspent, and there is considerable work to finalise in the latter quarter of 2023/24 to ensure the £17m Control total is achieved.

6. WORKFORCE IMPLICATIONS

In comparison to previous quarters, very few workforce risks have been raised in quarter 3. Where issues have been raised, these have predominantly been due to workforce funding issues, resulting in uncertainty and delay in the delivery of some GMOs. In contrast, some areas have reported successful recruitment to key posts and/or ongoing recruitment with no concerns. One specific risk worth noting however, is the potential for further industrial action involving Junior Doctors, which will require early engagement and planning to mitigate the potential impact on the delivery timelines for some GMOs.

7. RECOMMENDATION

The Committee is asked to:

- NOTE the areas of achievements to deliver the Annual Plan in Q3.

- NOTE mitigating actions against GMOs which are off-track.

- APPROVE the revised timescales and changes to the plan where delivery is off track/ delayed into 24/25.

- APPROVE updated MDS for Quarter 3 for submission to WG

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| No direct implications of this report, however the Plan is predicated on improving quality, safety and patient experience. |  |  |  |
| Financial Implications |  |  |  |
| No direct financial implications of this report, see financial implication section for detail on the Finance Plan. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| A Quality Impact Assessment and Equality Impact Assessment process will be part of the broader planning arrangements to ensure that service models detailed in the Plan are quality and equality/ diversity impact assessed. |  |  |  |
| Staffing Implications |  |  |  |
| No direct impact outlined in this report however there will be significant staffing implications as a result of new service models outlined in the Annual Plan – risks and implications to workforce form an integral part to planning arrangements. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Annual Plan aims to deliver our Strategic Objectives which were aligned to our Wellbeing Objectives through the development of the Organisational Strategy. This paper sets out the alignment of the approved Health Board Wellbeing Objectives directly to the Annual Plan Deliverables. |  |  |  |
| Report History |  | First version of this report. This report is also to be received by the Management Board on 6th March 2024 and Health Board on 29th March 2024 |  |
| Appendices |  | Appendix 1 – GMO Q3 update master Appendix 2 - Q3 Key Achievements Appendix 3 – MDS Q3 Final |  |