| Meeting Date | 27 February 2024 |  | Agenda Item |  |  | 6.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Performance & Finance Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee (PFC) for scrutiny. |  |  |  |  |  |
| Key Issues | - The Health Board Risk Register was last received by the Board in November 2023. - Since then, Health Board risk register entries have been circulated to lead Executive Directors monthly for review and update. This report presents an extract of risks from the January 2024 HBRR. - Ten risks are assigned to the Performance & Finance Committee for oversight. Six risks are assessed to meet or exceed the Board risk appetite threshold. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Performance & Finance Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in January 2024.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in January 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	MANAGEMENT OF PERFORMANCE & FINANCE RISKS

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to Executive Team for agreement and final version issued. The register was received by the full Board in November 2023. This report presents the risks allocated to this Committee as recorded in the January 2024 HBRR – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent monthly update are highlighted in red font.

3.2 HBRR Performance & Finance Risks

Ten risks are assigned to this Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 4 | 0 | 0 | 4 | 2 |

Movements since last meeting:

- New risks

  - HBR94 CAMHS failure to meet required standards of performance

  - HBR96 Failure to Develop an Approvable IMTP (statutory compliance)

  - HBR97 Disruption due to Industrial Action

- Risks increased in score

  - Nil

- Risks reduced in score

  - Nil

- Risks closed/de-escalated

  - HBR48 Failure to sustain Child and Adolescent Mental Health Services

  - HBR88 Non Delivery of AMSR Programme Benefits

  - HBR82 Closure of Burns service if Consultant Cover not Sustained (Reduced in score and de-escalated for service level management)

There are six risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the Performance & Finance Committee

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 25 | Lead: Chief Operating Officer The risk score currently remains unchanged. Actions Completed: (1) Surgical SDEC opened. (2) Continuous Flow Model implemented (from 9th October 2023) but will be monitored over 12 months (3) Zero tolerance on ambulance waits has been implemented. Further actions ongoing: - Increased hours in SDEC (01/03/2024). - OPAS exploring internal & external funding options (31/03/2024). - Work ongoing in ED/SDEC to pilot additional initiatives (30/03/2024). Additional Update 12/02/2024: Criteria led discharge has been rolled out in Medicine and is continuing to embed. Further work will be required across other specialities over the course of the year. |
| 16 (840) | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Lead: Chief Operating Officer The risk score currently remains unchanged. Action ongoing: - Implement demand management initiatives (target 31/03/2024) - Work ongoing with Finance colleagues to establish the funding allocation for elective recovery for 2023/24 (29/02/2024) Additional Update 29/01/2024: All but three of the longest waiting patients (5 years) will be treated by end January 2024. Plans are in place to treat all patients waiting over 4 years by end of March 2024. Regional working is in place for orthopaedics with SBUHB patients treated in Prince Philip Hospital and Hywel Dda UHB patients treated in NPT Hospital. |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Lead: Chief Operating Officer The risk score currently remains unchanged. Action ongoing: - Cancer Performance Group to monitor improvement trajectories for both cancer backlog and SCP performance on a monthly basis (31/03/2024) - Full review of gynaecology / gynae-oncology pathway given service constraints to be done. Additional theatre capacity for gynaecological cancer to be agreed to reduce current backlog (29/03/2024) Additional update 29/01/2024: There was a slight in improvement in SCP performance during November and December, of 52% and 53% respectively. Improvement in Upper Gastro-Intestinal cancer performance (73%) but further work required in other tumour site area e.g. gynaecology, urology and breast. |
| 92 (3444) | Financial Deficit Achievement Forecast deficit is not met due to insufficient progress on COVID cost reduction, savings identification, run rate reduction and the potential for new in-year pressures. | 20 | Lead: Director of Finance & Performance The risk score currently remains unchanged. Ongoing Actions: - Continuation of weekly escalation meetings and escalation of other areas as necessary - Develop robust cross system service change plans which improve quality of care and reduce system cost |
| 93 (3448) | Capital Plan Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2023/24 | 20 | Lead: Director of Finance & Performance The risk score currently remains unchanged. Board members will be aware that capital plans are dynamic through the year with mitigating actions taken and opportunities for slippage and further support from WG sought on a consistent basis. This process will continue in 2023/24 in efforts to de-risk the capital plan. Ongoing Action: Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk based basis. |
| 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) Failure to have an approvable (Integrated Medium Term Plan) IMTP for 2024/5 then we will lose public confidence and breach legislation. | 20 New Risk | Lead: Director of Strategy Action: Development of a robust Annual Plan for 2024/25 and continued work to set out a timeline for financial recovery (31/03/2025). |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 52 (1763) | Strategic Impact Assessments The Health Board does not have sufficient skills & resource in place to undertake impact assessments in line with strategic service change and policy development. | 12 | Lead: Director of Insight Communications & Engagement The risk score currently remains unchanged. Further Actions: - Appoint Head of EDI – Delayed due to need to confirm budget (30/09/2023) - Review of the current process for developing Equality Impact Assessments around service change, engagement and consultation (31/10/2023) - Robust policies and processes to be in place for Impact Assessment going forward (31/10/2023 – in progress) - Roll out Impact Assessment process across organisation (30/09/2023). |
| 75 (2522) | Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 10 | Lead: Chief Operating Officer Risks in relation to major incidents and business continuity are being reviewed with a view to refreshing/replacing this HBRR entry. (A new register entry HBR67 has been made to reflect the risk to business continuity arising from industrial action – this is reported within closed session). |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 New Risk | Lead: Chief Operating Officer This register entry, reflecting the risk to service provision from a provider perspective, replaces the previous entry (HBR 48) which described the risk when the Health Board commissioned the service from Cwm Taf Morgannwg. Update 13/12/2023: Following its addition to the HBRR in October 2023 with a score of 20, a marked improvement in the performance against the Mental Health Measure for CAMHS has been noted. Data validation for new patients has been completed. Data validation for follow-up patients including ADHD is in progress. Over-recruitment into agency nursing has supported delivery of improved performance outputs however the service continues to struggle to recruit into substantive posts. Current risk score was reduced to 12 in view of improved performance however the risk entry reflects the fragility in the workforce to deliver sustained performance. |

Risk HBR 97 Disruption due to Industrial Action is reported within closed session of this Committee.

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 25 | Quality & Safety |
| 16 (840) | Access and Planned Care. There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Quality & Safety |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Quality & Safety |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Quality & Safety |

Risk HBR 97 Disruption due to Industrial Action is reported to the Quality & Safety Committee for information.

- GOVERNANCE AND RISK

This report and appendix present information on each of the risks assigned to the Committee for oversight. Within the report, particular attention is drawn to those risks exceeding the Board’s appetite, together with updates on action being taken to treat them by lead Directors and management.

- FINANCIAL IMPLICATIONS

There are financial implications to minimising the risks entered on the HBRR in relation to significant revenue implication around strengthening resources in the Health Board, Service Groups and Departments.  Capital monies may also be required in relation to supporting the improvements required to improve and where this is the case further detail is provided in the individual entries on the HBRR.

- RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements in place that ensure organisational risks are captured, assessed and mitigating actions are taken, is a key requisite to ensuring the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| The risks outlined within this report have resource implications which are being addressed by the respective Executive Director leads and taken into consideration as part of the Board’s IMTP processes. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Unit Directors are requested to review their existing operational risks on Datix Risk Module to ensure SBUHB has an accurate and up to date risk profile. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR and the Covid 19 risk register sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PFC which were last reported to the Board in July 2023. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Performance & Finance Committee |  |

This risk is reported in closed session of the Committee.