## Slide 1
Annual Plan 2024/25
Mid-Year Review of Delivery Priorities
(GMOs)
Supporting Slides
Appendix 1

## Slide 2
Purpose
As part of standard Annual Plan Reporting processes, a mid-year review is undertaken in December to establish potential end-of-year position and approve necessary changes to plan.
The Annual Plan 24/25 lists a number of organisational priorities, in the form of Goals, Methods and Outcomes (GMOs), to be delivered by Programme Boards and Service Delivery Groups. The Annual Plan 24/25 was submitted to Welsh Government in March 2024.
The following slides present a mid-year review projection of all GMOs at year-end (24/25). The slides outline the following: Slides 3-11: GMOs reported as ‘off-track – red’ at the mid-year point. Despite the current ‘red’ status of these GMOs, some are still expected to be delivered by year-end. Rationale for the position of each is noted, as well as proposed revised delivery timescales, where relevant. Slides 12-16: GMOs reported as ‘off-track - amber’ (manageable) for consecutive quarters are highlighted. It is expected, however, that these will be delivered by Q4 23/24. Feasibility will be reviewed, in detail, in the Annual Plan Oversight Group (APOG) in February 2025. Slides 16-26: GMOs which are reported to be on-track or to have been ‘off-track – amber’ for only one quarter, but which it is known will not be delivered in 2024/25 due to foreseen barriers. These are described in every instance.

## Slide 3
GMOs Rated Red at the Mid-Year Point
Being
Well-led
Sustainably Resourced
Efficient & Effective
Person Centred
Safe
Timely Services
Leadership culture behaviour
A focus on the patient or customer
Engaged staff who can act
Reliable, designed systems and processes
Alliances and Partnerships
The following GMOs have been reported as ‘Off-track Red’
Despite their ‘red’ status at the mid-year point, some are still expected to be delivered by year-end.
They are flagged here for information.
The detail of these GMOs will be reviewed in the Annual Plan Oversight Group (APOG) in February 25.

## Slide 4
Planned Care Priorities
Executive Lead | Chief Operating Officer
Goal | Delivery against Ministerial outpatient targets |  |  | 
GMO Lead | Ceri Gimblett, Outpatients Group Chair |  |  | 
Method | OP_002: Reduce the number of patients on a follow-up waiting list by 30% (on the March 2019 baseline) |  | Mid Year Status: | 
 |  |  | Off Track | 
Rationale for delay |  | Proposed Q3/Q4 Activity |  | 
Work not started due to issues with the stored procedure in WPAS. This has now been identified as a local issue and the Digital Team are working toward resolving this. Workshop held on 19.09.2024 to consider remaining milestones for 24/25. |  | Anyone waiting up to two years to be transferred to PIFU pathway informed of decision and rights of appeal Development of SOPs Staff training Dashboard to be developed and tested, position monitored and refinements made to dashboard in response to end-user feedback |  | 
Method | OP_003: Reduce the number of patients who are more than 100% delayed on their Follow Up appointment by 30% (March 2019 baseline) and achieve Targeted Intervention target 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline) |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
Digital validation with downtrend in number of patients more than 100% delayed due to the issue with the stored procedure in WPAS. Digital have been working with DHCW to resolve the issue. |  | Development of SOP Staff training | 
Method | OP_004: SOS and PIFU Activity to demonstrate an annual increase as agreed within the Outpatient Steering Group |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
On reporting, the first workshop of the Clinical Pathway Group was awaited, which would inform the direction of the Clinical Group. The workshop would also identify the SOS and PIFU pathways. GiRFT guidelines have been collected and circulated to Clinical leads. |  | - Ongoing validation of list and modify approach according to outcomes as appropriate. - Staff training. | 
Method | OP_005: Show an annual increase in the number of pathways where virtual appointments and reviews are carried out virtually |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
Digital colleagues have been scoping alternatives to Attend Anywhere. A SBAR has been circulated to senior digital colleagues outlining options. |  | Delivery and development Staff training | 

## Slide 5
Planned Care Priorities (Outpatients continued)
Method | OP_009: Develop fit for purpose Referral Management System |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
INNUs shared with Clinical Editors on HealthPathways. Review to be undertaken. |  | Under development | 
Method | OP_010: Deliver Integrated E-Referral and E-Advice |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
PID has been written including benefits map for recommended plans. There is no Clinical Lead allocated to the project. Operational plan has been developed and group being set up with operational service leads end of Q2/start of Q3. Digital recommendations have been internally validated and shared with DHCW The submission routes are being identified. Delivery group being established end of Q2/start of Q3 to submit RFCs and track outcomes Effective Referral dashboard not yet developed which prevents accurate measurement of deliverables. Q3 and Q4 milestones to be updated once groups have allocated timelines to delivery plans. |  | Development dependent on national changes. | 
Method | OP_012: Provide Advice, guidance, and support to empower patients to better self-manage their condition and prepare for treatment and recovery (3Ps) |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
SPOC Team not recruited; escalated to Welsh Government by NHS Exec. |  | Planning | 
Method | OP_013: Ensure Efficient Use of Resources |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
Issues: Allocate - Data Hub: Inability to automatically extract required data to the Data Warehouse prevents progress of dashboard development. Project pause has been agreed at Medical Workforce Group and Outpatient Redesign and Recovery Group. Work ongoing through meetings with RLDatix (supplier) to progress solution for the issue. |  | - Monitor through performance scrutiny meetings and measure against service demand - Roll out across further specialities - Performance Team to continue to assist services to create plans to deliver zero breaches against 52 week target by 31 March 2025 | 
Method | OP_019: Modernised Outpatient Dataset |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
Limited progress made in verification testing and roll out of new FUNBs vital dashboard across all specialities |  | - Monitor position using dashboard and refine in response to end-user feedback | 

## Slide 6
Women’s Health, Maternity and Children’s Health Priorities
Executive Lead (CYP) | Executive Nursing Director
Goal | Sustain, expand Neurodevelopmental services ( 0 - 17.9 years) in order to improve access and quality of services in line with national targets. |  |  | 
Method | NPTS_060: Revise business case in line with recommendations from Welsh Government ND Improvement Programme in readiness to bid for future recurrent funding (RPB funding) |  | Mid Year Status: | 
 |  |  | Off Track | 
Rationale for delay |  | Proposed Revised Q3/Q4 Activity |  | 
Off track due to considerable staffing issues related to staff leavers and sickness, paper was presented to Management Board in March 2024 and position is unchanged Workforce plan to retain current level of staffing, provide adequate capacity to meet demand and start to address the backlog of children and young people awaiting assessments, including finalising a proposal for insourcing support to start to reduce the backlog of patients waiting for an assessment is in development. Off track due to considerable staffing issues related to staff leavers and sickness, paper was presented to Management Board in March 2024 and position is unchanged |  | Q3: Implement short and medium term actions identified from deep dive service review carried out Sept - Dec 2024. Q4: - Utilise the non-recurrent funding from WG in best way to support families, children and service |  | 
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director NPTSSG |  |  | 

## Slide 7
Urgent and Emergency Care Priorities
Executive Lead | Chief Operating Officer
Goal | Programme 1: Co-ordination, signposting and alternatives to admission Tackles 6 Goals UEC priorities, namely: - Goal 1: Co-ordinated planning and support for populations at greater risk of needing UEC - Goal 2: Signposting people with UEC needs to the right place, first time - Goal 3: Clinically safe alternatives to hospital |  |  | 
Method | UEC_001: Predictive identification of future high users of UEC - Data analysis & interpretation (demand forecasting of longer and shorter term trends to drive future portfolio activity) |  | Mid Year Status: | 
 |  |  | Off Track | 
Rationale for delay |  | Proposed Revised Q3/Q4 Activity |  | 
Data collection and review being undertaken; confirmation required of way forward and whether utilising existing internal resource is possible (Population Health, Digital) |  | Update October 2024: Initial planning discussions taken place; recognised that due to current resource constraints unable to take forward meaningful project in year. Request to defer project into 25/26. |  | 
GMO Lead | Neil Cooper, Assistant Director of Operations; Lee Elwell, UEC Programme Manager |  |  | 
Goal | Programme 1: Co-ordination, signposting and alternatives to admission Tackles 6 Goals UEC priorities, namely: - Goal 1: Co-ordinated planning and support for populations at greater risk of needing UEC - Goal 2: Signposting people with UEC needs to the right place, first time - Goal 3: Clinically safe alternatives to hospital |  |  | 
Method | UEC_007: Expansion of District Nursing OOH/ SPOA: Enhance the Community Nursing Service over 24hrs to support End of Life care |  | Mid Year Status: | 
 |  |  | Off Track | 
Rationale for delay |  | Proposed Revised Q3/Q4 Activity |  | 
Noted that no funding available during 24/ 25 for activity – proposed to close the GMO |  | None –GMO closed |  | 
GMO Lead | Neil Cooper, Assistant Director of Operations, Lee Elwell, UEC Programme Manager/ Service Group Lead: PCTG |  |  | 

## Slide 8
Mental Health & Learning Disabilities (MH&LD) Priorities
Executive Lead | Chief Operating Officer
Goal | Centralised inpatient model of service within a purpose-built environment, meeting the needs of the patient population for the Health Board area |  | 
Method | MHLD_016: Adult MH Inpatient Facilities (Cefn Coed): Following approval of the SOC by WG, develop and submit the outline business case for the scheme. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
TBC: Awaiting WG decision on capital. |  | TBC: Awaiting WG decision on capital. | 
Goal | Continue with the redesign of Older People’s Mental Health Inpatient Services across the Service Group and input into the wider West Glamorgan regional work |  | 
Method | MHLD_026: Renovation of Suite 4, Tonna. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
No further update received regarding funding from Welsh Government. |  | TBC: Awaiting confirmation of funding from Welsh Government. | 
Goal | Development of a co-located Older Adult Mental Health Team for Area 1&2 in central Swansea, for Swansea residents (Westfa/Phillips Parade) |  | 
Method | MHLD_028: New build extension at Westfa to support co-located Older Persons’ Community Mental Health Team’s 1 & 2 in central Swansea facilities. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
No further progress made. The scheme continues to require investment. The Capital Team is supporting the Directorate in sourcing alternative accommodation with nothing suitable at present. |  | Q3: As revised in Q1, to submit design plans and secure funding. Q4:As revised in Q1, begin the tender process to identify contractor to undertake the project. | 
GMO Lead | Dermot Nolan, Service Group Director MHLD

## Slide 9
Workforce and Organisational Development Priorities
Executive Lead | Director of Workforce
Goal | Attract and Recruit: We want to be recognised as an employer of choice |  |  | 
Method | W_009: Develop a Swansea Bay ‘Widening Access to Careers in Healthcare’ (WATCH) Programme. |  | Mid Year Status: | 
 |  |  | Off Track | 
Rationale for delay |  | Proposed Revised Q3/Q4 Activity |  | 
Overall programme likely to roll over due to increased partners involved in programme. |  | Q3:As revised in Q2, continue to design the programme due to additional partners who can contribute to the programme Q4: As revised in Q2, launch programme. Roll over evaluation. |  | 
GMO Lead | Simone Houlbrooke, Head of Strategic Workforce Planning |  |  | 

## Slide 10
Digital Priorities
Executive Lead | Matt John, Director of Digital
Goal | Planned Care, Recovery, Diagnosis, Pathways of Care​, Outpatients and follow ups and repurposing of activity, treatment recovery, RTT, capacity gaps in specialties, delivery of targets, regional diagnostic hubs, pathway redesign, straight to test, and onward referral​ |  | 
Method | D_012: TOMS redevelopment. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
Theatre management solution will form part of the initial Digital Strategy implementation. Theatres Board is looking at the wider theatre management processes, which will further inform the approach. |  | As proposed in Q2, remove from 24/25 GMOs. | 
Goal | Planned Care, Recovery, Diagnosis, Pathways of Care​ - Outpatients and follow ups and repurposing of activity, treatment recovery, RTT, capacity gaps in specialties, delivery of targets, regional diagnostic hubs, pathway redesign, straight to test, and onward referral​ |  | 
Method | D_021: Align the local ePMA solution to the National ePMA Framework and the recently published National Standards relating to interoperability. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
The procurement activities for a new ePMA system were paused due to contractual limitations with the current supplier and organisation pressures in unscheduled care. This will be aligned to the new digital strategy. |  | As previously approved by APOG, action to be removed from 24/25 GMOs. | 
Goal | Primary and Community Care​: Access to GP, Community, Dental, Optometry, and Pharmacy Services​, MHLD |  | 
Method | D_022: WCCIS: Scope and identify alternative solutions for existing users of WCCIS that are currently on the Swansea Council contract. Engage with the national and regional WCCIS programme to identify potential solutions post December 2025 to make a decision on the future direction of the health board. Explore the short term digitisation programme for therapies in the absence of WCCIS. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Revised Q3/Q4 Activity | 
Although this is not funded, work has continued locally to inform the national set of requirements. There is still a lack of clarity and understanding nationally as to how the proposed solution will meet the requirements of the integrated teams currently using WCCIS. In mitigation, work continues with the regional and national teams to inform the national requirements and procurement activities. DHCW to visit integrated teams in Swansea to understand their requirements. |  | Q3: As revised in Q2, play back from supplier to demonstrate how the solutions can allow teams to continue working in an integrated way across the region. Completion of National procurement pack and publication of ITT.Q4: As revised in Q2, national evaluation/supplier demonstrations with a view to contract award in Q1 2025. | 

## Slide 11
One Bay Way (OBW) Priorities
Executive Lead | Director of Strategy
Goal | OBW: The five specialty areas agreed MSK, Frailty, Respiratory, Cardiology and Diabetes will address whole system pathway that potentially cover a patient’s lifetime. The OBW aims to standardised the approach to pathway redesign focussing on the elements of the pathways at the preventative, early intervention and admission avoidance stages, providing opportunity to address key issues which will contribute to the overall betterment of the pathway as a whole via streamlining and VBHC principles. |  | 
Method | P_003: Cardiology: Eradication of patients over follow-up target date. PIFU model implemented. Creation of hot clinics. Improved patient management pathway. PCT_001: Deliver Physio First Contact Practitioners for all Clusters based on re-modelled resources which are currently available and roll-out digital booking system. |  | Mid Year Status:
 |  |  | Off Track
Rationale for delay |  | Proposed Q3/Q4 Activity | 
Awaiting Executive confirmation to progress on all OBW pathways work. |  | Q3/Q4 Review of phase 1 progress to be undertaken and plans drawn up for rollout. | 

## Slide 12
GMOs Rated Amber for 2 Consecutive Quarters
Being
Well-led
Sustainably Resourced
Efficient & Effective
Person Centred
Safe
Timely Services
Leadership culture behaviour
A focus on the patient or customer
Engaged staff who can act
Reliable, designed systems and processes
Alliances and Partnerships
The following GMOs have been reported as ‘Off-track Amber’ (manageable) for two consecutive quarters, however, it is expected that these will be delivered by Q4 24/25.
They are flagged here for information.
The detail of these GMOs will be reviewed in the Annual Plan Oversight Group (APOG) in February 2025.

## Slide 13
Planned Care Priorities
Executive Lead | Chief Operating Officer
GMOs reporting as AMBER in Q1 and Q2, consecutively, as they are ‘off track’ against original timelines, however are expected to be delivered by Q4 24/25 | 
Method | OP_020: Embed 6 monthly check-ins with those waiting over 52 weeks linked to local 3Ps services. Attendance records at each training programme: Prompt roll-out is ongoing and will be utilised for 3Ps in Q3
Method | OP_023: Develop digital options as part of modernisation (Included in Service Wide GMO for Develop Digital Priorities for Service Group). Engage in wider corporate discussions regarding the support from the health board wide booking functions.

## Slide 14
Women’s Health, Maternity & Children’s Health Priorities
GMOs reporting as AMBER in Q1 and Q2, consecutively, as they are ‘off track’ against original timelines, however are expected to be delivered by Q4 24/25 | 
Method | NPTS_045: Development of a capital development programme for maternity services, particularly focused on resolving concerns about the 2nd Obstetric Theatre, location of bereavement room on labour ward, and the expansion and relocation of the Bay Birthing Unit. Y1 Planning - HiW Report specifics.
Executive Lead | Executive Nursing Director
Method | NPTS_068: Refurbishment of the current ward footprint, whilst developing a business justification case for a new build. (Tto include appropriate indoor and outdoor play facilities)
Method | ALN_001: Ensuring Project Management capacity is in place for the 2024/25 period to direct and support the continued monitoring, review and improvement of operational processes, meeting the requirements of The Act.
GMO Lead | Luke Jones, Designated Education Clinical Lead Officer (DECLO)
GMO Lead | Michelle Mason Gawne, ASDG NPTSSG

## Slide 15
Mental Health & Learning Disabilities (MH&LD) Priorities
GMOs reporting as AMBER in Q1 and Q2, consecutively, as they are ‘off track’ against original timelines, however are expected to be delivered by Q4 24/25 | 
Method | MHLD_004: Role development for LD Primary Care and Secondary Care.
Executive Lead | Chief Operating Officer
Method | MHLD_015: Development of an Assessment Hub to provide a single point of contact for Mental Health Services to support the 111 press 2 referral pathway to allow all category c assessments to be undertake by the hub.
Method | MHLD_018: CMHT Modernisation and SPOA.
Method | MHLD_024: Develop digital options as part of modernisation (Included in Service Wide GMO for Develop Digital Priorities for Service Group). Engage in wider corporate discussions regarding the support from the health board wide booking functions.
GMO Lead | Dermot Nolan, Service Group Director, MHLD

## Slide 16
Digital Priorities
GMOs reporting as AMBER in Q1 and Q2, consecutively, as they are ‘off track’ against original timelines, however are expected to be delivered by Q4 24/25 | 
Method | D_002: Implementation of RISP
Executive Lead | Matt John, Director of Digital
Method | D_005: WCP - Implementation of the Phlebotomy Module
Method | D_008: Swansea Bay Patient Portal: Implement and embed Swansea Bay Patient Portal to expedite the digitisation and transformation of Outpatients and to support the 3Ps programme
Method | D_011: NHS Wales App: Implement and embed SBPP and the NHS Wales App to expedite the digitisation and transformation of Outpatients and to support the 3Ps programme
Method | D_023: Maximising use of WPAS ED to facilitate a digital first approach, including supporting any required changes to WPAS A&E

## Slide 17
GMOs unlikely to be delivered by Year End
Being
Well-led
Sustainably Resourced
Efficient & Effective
Person Centred
Safe
Timely Services
Leadership culture behaviour
A focus on the patient or customer
Engaged staff who can act
Reliable, designed systems and processes
Alliances and Partnerships
The following GMOs have either been reported as being on-track or ‘off-track amber’ in only one quarter of the first half of the year. Despite this, they are unlikely to be delivered by 2024/25 year-end. The rationale for this is included in relation to each GMO.
They are flagged here for information.
The detail of these GMOs will be reviewed in the Annual Plan Oversight Group (APOG) in February 25.

## Slide 18
Cancer Priorities
Executive Lead | Raj Krishnan, Deputy Executive Medical Director
GMO cannot be delivered due to a lack of identified funding. | 
Method | NPTS_010: Develop a ring-fenced Haematology Elective Bay on Ward 11 to increase elective capacity, reduce treatment wait times and improve patient flow across Singleton and Morriston sites.
GMO Lead | Ceri Gimblett, NPTSSG Service Group Director

## Slide 19
Planned Care Priorities
Executive Lead | Chief Operating Officer
GMO delivery delayed as further development on demand and capacity work within the General Gynae space is required. A demand and capacity plan which will support in the allocation of theatre lists is being conducted by an external company. | 
Method | NPTS_017: Deliver Ministerial targets in specialities; Gynae.
GMO Lead | Ceri Gimblett, Service Group Director – NPTSSG
GMO cannot be delivered due to a lack of identified funding. | 
Method | M_017: Mobilising the Surgery Robot: Implement Robotic Theatres to improve patient outcomes and to be competitive in the recruitment of high calibre staff and trainees to SBUHB.
GMO Lead | Sue Moore, Morriston Service Group Director
GMO cannot be delivered as OBC will only recommence if funding confirmed for SCP and internal costs from WG. | 
Method | M_038: Deliver capital investment in Pathology estate in South West Wales via Welsh Government Capital Business Case Route.
GMO Lead | Neil Miles, Pathology Programme Director

## Slide 20
Women’s Health, Maternity & Children’s Health Priorities
Executive Lead | Executive Nursing Director (CYP and Mat); Director of Therapies and Health Science (Womens’ Health)
GMO delivery delayed as update awaited from national programme. | 
Method | NPTS_032: Engagement with Digital Maternity Cymru and support for the implementation of a national maternity record and development of local/national performance dashboards.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director
GMO delivery delayed as further guidance awaited following investigation of change of approach in other Health Boards. | 
Method | NPTS_034: Implementation of Dilapan for induction of labour.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director
GMO delivery delayed following revised approach agreed in Q1. Delivery will roll into 2025/26. | 
Method | NPTS_051: Refresh the current Children and Young People Strategic Plan with aim to put in place a 5-year strategic framework and direction for all specialities who deliver services for Children and Young People within Swansea Bay UHB.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director

## Slide 21
Women’s Health, Maternity & Children’s Health Priorities
Executive Lead | Ceri Gimblett, Service Group Director – NPTSSG-led
GMO delivery on hold following decision by JCC not to fund. | 
Method | NPTS_065: Develop business case for JCC to permanently fund 24-hour neonatal transport model.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director
GMO cannot be delivered due to a lack of identified funding. | 
Method | NPTS_070: Collaborative scoping to explore use of Advanced Practitioner posts to demonstrate prudent use of skill set, and release consultant capacity. Linked with SPOA work for Y2; there is a need to work around SPOA/Medical Workforce.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director
GMO delivery delayed following revised approach agreed in Q1. Delivery will roll into 2025/26. | 
Method | NPTS_059: Work with RPB and colleagues within Mental Health services to undertake a review of services required for children with learning disabilities, to identify gaps in service provision, unmet need and priorities for development. Implementing the multi-agency CYP Emotional Wellbeing & Mental Health Delivery Plan.
GMO Lead | Michelle Mason-Gawne, Associate Service Group Director

## Slide 22
Urgent & Emergency Care Priorities
Executive Lead | Chief Operating Officer
GMO delivery delayed dependent on funding being sourced. | 
Method | UEC_004: Virtual ward expansion (Enhanced Community Care) - from 5-7 day service (to avoid admission and / or pull from acute sites for care in the community)
GMO delivery delayed dependent on funding being sourced. | 
Method | UEC_005: High Intensity Users (UEC) review and engagement/ service
GMO delivery delayed pending Executive decision on funding. | 
Method | UEC_002: Improved management of Long Term Conditions as admission avoidance - driven by data/ One Bay Way priorities.
GMO delivery to roll into 2025/26 as agreed in line with Q2 milestone amendment. | 
Method | UEC_008: Productive ward(s) to reduce length of stay: Roll-out of key initiatives across the Health Board so as to encourage productive Board Rounds/ Wards and to encourage timely flow and discharge. Key initiatives to include: SAFER, Red2Green, D2RA, Criteria Led Discharge (CLD), Avoiding deconditioning, COP escalation & management, Other (TBC)
GMO delivery to roll into 2025/26 as agreed in line with Q2 milestone amendment. | 
Method | UEC_010: Pathways of Care Delays (POCD) action plan implementation.
GMO cannot be delivered due to a lack of identified funding. | 
Method | UEC_012: Evaluation of current Home First discharge support and subsequent agreement / development of future intermediate bed provision (RPB & SBUHB in partnership) including Bonymaen beds.

## Slide 23
Mental Health & Learning Disabilities (MH&LD) Priorities
Executive Lead | Chief Operating Officer
GMO delivery delayed due to slippage in funding / capital planning timelines. Capital Finance has been secured from WG to commence this work, however. | 
Method | MHLD_013: Caswell Clinic: Secure capital investment to build two seclusion suites and de-escalation areas.
GMO delivery delayed due to timelines of commissioners (JCC) having slipped. Clinical workstreams have commenced and are under review by JCC. | 
Method | MHLD_012: Engage with service modernisation work, led by JCC, to define future role and function of Caswell clinic (specialist MH) inpatient wards and set out associated workforce requirements.
GMO delivery delayed following further work having been undertaken on bed capacity and presented to the Joint Commissioning and Performance Strategic Group. The recommendations for bed capacity reduction were not endorsed pending development of an overarching business case to outline this plan in greater detail. The timescale for this was felt to be longer with action for engagement with Llais also required. | 
Method | MHLD_003: Review of Complex Care Unit inpatient beds to consider the bed requirements for Learning disability services.
GMO delivery delayed as driven by SLA disaggregation with CTMUHB. | 
Method | MHLD_014: Forensic dental services: Disaggregation of SLA with CMTHB and refurb of suite.

## Slide 24
Workforce & Organisational Development Priorities
Executive Lead | Director of Workforce
GMO delivery delayed due to change in education funding. | 
Method | W_010: Introduce 2 Gateway Academy programmes to pilot career pathways for specified hard to fill roles.
GMO delivery delayed due to demand of competing priorities and limited capacity. | 
Method | W_02: In collaboration with our partners, deliver and embed the national Speaking Up Safely Framework Action Plan.

## Slide 25
Digital Priorities
Executive Lead | Matt John, Director of Digital
GMO delivery delayed due to lack of clarity in national approach. | 
Method | D_014: Implement Open Eyes (Open ERS/Open EPR), including the optometry solution.
GMO delivery delayed until Q1 2025 due to system not having been built nationally for testing. | 
Method | D_01: Implementation of LIMS 2 on a regional basis alongside identity access management supporting a regional pathology hub.
GMO delivery delayed pending Executive decision. | 
Method | D_016: Virtual Ward Digital Development.

## Slide 26
Population Health Priorities
Executive Lead | Director of Public Health
GMO delivery delayed pending Health Board commitment to fund recurrently as a Ministerial Priority. | 
Method | P_002: Development of quarterly highlight report and evaluation papers to ensure ongoing sustainability of the Maternal service and HMQ in Hospital service is prioritised. Integrate into existing OBW work programme.
GMO Lead | Alice Puchades, Consultant in Public Health
GMO delivery delayed as no long-term funding has been identified for establishment of substantive L3 adult service beyond 24/25 PEY funding. Work continues to develop an integrated weight management pathway, however. | 
Method | P_001: Development of integrated weight management pathway and service specification for level 1-3 services. Pathway development will integrate across existing One Bay Way work.
GMO Lead | Alice Puchades, Consultant in Public Health