## Current Implementation Plan 25
Action | KPIs | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
1 | Admitted to Stroke Unit within 4 hours of arrival to hospital | Access to a Stroke Bed within 4 hours to be raised at site meetings with as high profile as other targets and plans to be created for getting ring fenced capacity back | Site Team/ Service Managers | 2022-10-01 | Ongoing / Daily | Raised profile of Ring-fenced stroke capacity in line with specialties such as ITU, A&E, and Cardiac. Service Director has previously instructed that capacity is to be ring-fenced. | Improved compliance against 4 hour target |  | n/a | 53% | 8.6% | 27% | 40% | 95%
|  | Ringfencing of 18 Stroke beds on the ASU - To breach a ring fenced stroke bed a proforma should be completed and signed off by gold. | Site Team/ Service Managers | 2023-07-01 | Ongoing / Daily | Maintain 4 ring-fenced beds per 24 hours – do not go into the night without a ring-fenced bed without exec approval. Last bed not to be used for non-stroke admissions unless exec approval. The attached pro-forma is to be populated (by Bed Manager or On-call Manager) each time the ring-fenced bed on the Acute Stroke Unit has been breached (by a non-stroke). This process is being adopted to ensure that the bed management SOP for stroke is applied consistently and that appropriate escalation takes place prior to occupation of the ring fenced bed. Escalated to Site management due to increasing numbers of medical outliers on the ASU (13-14 patients). Under ringfencing agreements there should be a maximum of 6 medical patients. Policy in place but not adhered to due to site pressures. New directroate manager not convinced this is happening - Next Steps - Arrange site meeting to discuss | Improved compliance against 4 hour target Reduced LoS from not using the therapies room |  | N/A
|  | Transfer Delays - Transfer issues to be raised at 10:30 internal site call and work with other sites to move longest waiters and ensure compliance | Site team(s)/ ECHO manager | 2022-10-01 | Ongoing / Daily | Use the ASU delayed transfer list to highlight transfer delays, monitor them and work to reduce them. Email is sent daily to proactively raise the profile long waiters at Morriston in order for other sites to pull. In place yet other rehab sites – NPTH are reliant on being able to discharge to the community which is no longer straight forward. Highly problematic given lack of social care. Reduced transfer delays at present a benefit of AMSR - Next Steps - Arrange meeting with Louise Driscoll | Reduced LoS on ASU |  | N/A
|  | Immediate action 1: All site matrons reminded that breach of a Stroke bed needs authorisation from Silver & Gold. | Rebecca Davies | 2024-05-01 | 2024-05-01 | All staff reinformed of this 8/5/2024. Breach proforma reintroduceded. New directroate manager not convinced this is happening - Next Steps - Arrange site meeting to discuss | Expected improvement in 4 hours compliance |  | N/A
|  | Develop joint MDT board rounds between Morriston and NPT to support the flow of patients between Morrisotn and NPT identifying any bottle knecks in the process. | Abi Landeg | 2025-07-01 | TBC | PDSA cycle developed. Twice weekly joint board rounds bewteen Morriston and NPT have been developed and commenced W/C 7th July 2025. | Improve flow between Morriston and NPTH freeing up acute beds in Morriston |  | N/A
|  | Streamline the process of accepting and transfering patients from Morriston to NPTH | Abi Landeg | 2025-07-01 | TBC | PDSA cycle developed- TOCALS nurse now attends board round. Referals to NPT wil be discussed and listed at board round - removing the process of a TOCALS review for every patient. | Reduce the number of steps in the pathway. |  | N/A
2 | CT within 1 hour compliance (now changed to 20 minutes) | Direct to CT to be explored with radiology | Mark Ramsey/ Toby Wells /Tal Anjum | 2022-10-01 | Implemented July 2023 | Pilot took place and was succesful however we are unable to progress this action any further and it is now on hold due to the inability of ring-fencing stroke beds on Ward F. | Reduced time to CT Head |  | N/A | 51.2% | 38.6% | 50% | 66% | 95%
3 | Stroke consultant review within 24hrs ** target now changed to 14 hours** | Recruitment plan for Consultants in place - 2 WTE planned for 24/25 | Abi Landeg | 2023-09-01 | 2025-06-01 | June 2025 update: 1 Stroke Consultant was succesfully recruited to in 2023. Unable to progress 2 additional consultant posts following the withdrawal of funding. These 2 posts will join hybrid Neuro/Stroke rota to be revived to ensure all future recruits in Neuro go on the Stroke on-call rota. | To sustain stroke consultant review within 24 hours |  | Funded from agreed recruitment plan | 95% | 94.4% | 94% | 95% | 100%
4 | Discharged Home Directly from ASU <= 72 hours | Develop an Integrated Community Stroke Service (ICSS) to enable more stroke survivors to receive their on-going rehabilitation in a community based setting. | Susan Wilson | 2024-04-01 | 2025-03-01 | The ESD service deals with those patients who have mild-moderate strokes however we are missing a cohort of patients who are suffer with more moderate to severe strokes but could be discharged home with ongoing access to specialist therapy for a period of time - this would avoid them having to stay in our rehab beds reducing LOS by Half. Next steps - develop a SBU business case which identifies a number of costed options. | Stroke evidence base demonstrates significant improvements in outcomes for all stroke patients when they receive community based rehab. |  | £1.2 million. Without investment, GMO won't be delivered | N/A | 20% | 21% | 24% | N/A
5 | Immediate actions to maximise use of Thrombectomy treatment | Expansion of CT perfusion service from Monday-Friday 9-5pm to 24/7 | Hannah Khirwadkah | 2024-05-01 | 2024-07-01 | All 17 radiographers have been trained and the service is taking place in hours. The service is unable to take place OOH until the stroke constaultant on -call rota is put in place. Next Steps - await funding for stroke rota. | Greater compliance with CT<1hour as well as increased thrombectomy rate from increased ability to identify salvageable brain following Stroke.
6 | New Addition: Therpay KPI to be included | Reduce the surge capacity within the therapy space from +3 to +1/0 on Ward F | Abi Landeg/Sue Wilson | 2025-04-01 | 2025-07-01 | Issue - We are currently surging +3 within our dedicated therapies space on Ward F. As a result we are having to undertake vital stroke therapeutic rehab at the bedside without the use of appropriate equipment. Next Steps - Arrange site team meeting. | Maximising therapeutic input and best patient outcomes . |  | N/A
7 |  | Develop a plan to stop surging into the therapy space on B2 in NPT Rehab Ward. | Abi Landeg/Sue Wilson | 2025-04-01 | 2025-07-01 |  | Maximising therapeutic input and best patient outcomes |  | N/A
National Work
On Hold | Hyper Acute Stroke Unit (HASU) / Comprehensive Regional Stroke Unit (CRSC) | Access to beds | ARCH | TBC | TBC | SOP and Ring-fencing policy to be adopted following New. March 2025 update -ARCH meetings have now been re-established so hopefully this work will progress.
|  | Dedicated CT facility to improve scan times. | ARCH | TBC | TBC | £400k in stroke legacy fund to be put towards developing dedicated CT facilities, which will provide an additional benefit of working with RAD. HDUHB were asked to contribute as per charitable funds committee and HD declined. | Improve scan times |  | n/a
|  | Improved door to needle times from increased ANP workforce | ARCH | TBC | TBC | ANP posts are now in place. | Improve door to needle times |  | n/a
|  | Recruitment of 3 x Hybrid Stroke/Neuro consultants | ARCH | TBC | TBC | Picked up as part of action 4 - awaiting funding and cannot progress until received. |  |  | £450,000 (funded as part of Business case approved in 2024)

## Completed Actions
| KPIs | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
1 | Admitted to Stroke Unit within 4 hours of arrival to hospital | Access to a Stroke Bed within 4 hours to be raised at site meetings with as high profile as other targets and plans to be created for getting ring fenced capacity back | Site Team/ Service Managers | 2022-10-01 | Ongoing / Daily | Raised profile of Ring-fenced stroke capacity in line with specialties such as ITU, A&E, and Cardiac. Service Director has previously instructed that capacity is to be ring-fenced. | Improved compliance against 4 hour target |  | n/a | 53% | 8.6% | 27% | 40% | 95%
2 | CT Scanned within 1 hour | Direct to CT to be explored with radiology | Mark Ramsey/ Toby Wells /Tal Anjum | 2022-10-01 | Implemented July 2023 | July 2023 Direct to CT pilot live from 17/7/23 November 2023 Brainomix Artificial Intelligence now live. December 2023 Pilot in place and due to continue. April 2024 CT Perfusion operating Mon-Fri 9-5pm, with plans to expand to all CT radiographers covering on call to ensure a 24/7 service. | Reduced time to CT Head |  | n/a | 51.2% | 38.6% | 50% | 66% | 95%
3 | Door to needle Thrombolysis - 45 mins | ANP recruitment | Rebecca Bowers | 2023-07-01 | Implemented July 2023 | 6 Stroke ANP (trainees) recruited to date due to be fully qualified in 2026 | Improve door to needle times |  | Funded from agreed recruitment plan | 17.5% | 8% | 25% | 50% | 95%
4 | Stroke consultant review within 24hrs | Recruitment plan for Consultants in place, 1 WTE out to advert in 23/24 and 2 WTE planned for 24/25 | David West/ Claire Thomas | 2023-09-01 | 2024-06-01 | Ongoing recruitment Interviews 10th June 2024 for 1 Stroke Consultant - Succesfully recruited to post. 2 posts be be progressed in 2024 /25 and join hybrid Neuro/Stroke rota to be revived to ensure all future recruits in Neuro go on the Stroke on-call rota. | To sustain stroke consultant review within 24 hours |  | Funded from agreed recruitment plan | 95% | 94.4% | 94% | 95% | 100%
5 | Swallow screen assessment within 4 hrs | Increased education of ED staff | Rebecca Davies/ Karen Ward | 2023-07-01 | 2024-06-01 | Ongoing training and weekly monitoring of preformance | To sustain swallow screen assessment within 4 hours |  | n/a | 79.3% | 75.8% | 82% | 90% | 95%
6 | Formal Swallow screen assessment <=72 hrs | Increased education of ED staff | Rebecca Davies/ Karen Ward | 2023-07-01 | 2024-06-01 | Ongoing training and weekly monitoring of preformance | To sustain formal swallow screen assessment within 72 hours |  | n/a | 95% | 90.3% | 92.5% | 95% | 100%
8 | Compliance with patients receiving the required minutes for Occupational Therapy | Recruitment underway for additional B6 OT post to support Rehab site. B4 Rehab practitioners x2 appointed and commencing 18th Dec Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | OT interviews Monday 18th Dec Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per the stroke SBAR | 51% | 74.1% | 80% | 95% | 95%
9 | Compliance with patients receiving the required minutes for Physiotherapy | B4 Rehab practitioners x2 appointed and commencing 18th Dec. Out to advert for x1 more B4 post Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per stroke SBAR | 58.8% | 66.9% | 74% | 88% | 95%
10 | Compliance with patients receiving the required minutes for Speech and Language Therapy | B4 Rehab practitioners x2 appointed and commencing 18th Dec Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per stroke SBAR | 31.6% | 64.3% | 52% | 83% | 95%
11 | Percentage of applicable patients screened for nutrition and seen by a dietitian by discharge | Recruited to 0.85 WTE B7 dietitian | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Start Date January 2nd 2024 | Improvement of compliance and data analysis |  | As per stroke SBAR | 95.3% | 62.5% | 67% | 90% | 95%
12 | Percentage of patients discharged with ESD | Mutiple posts have been recruited too | Site Team | 2022-10-01 | Completed Jan 2024 | Delayed Transfers of Care discussed every Tuesday via the Clinically optimised meeting. Ward F patients’ profile to be raised as well as other key areas. July 2023 ESD expansion in SBUHB investment plan for 23/24 Dec 2023 Multiple posts recruited to in ESD | Increased patient flow, reduce LOS |  | Part of the Stroke Expediture plan, £280k recurrent ear marked for ESD | 22% | 43% | 44% | 45% | 45%
13 | Six Month patient follow up assessment | Life after stroke clinics | Ceri Eady | 2023-06-01 | Ongoing - weekly | Life after stroke clinics have been running since June 2023. Clinic appointment are being offered at closer three/four months instead of six as patients are requesting input sooner. Face to face / TEAMS/ telephone calls are also still offered at 6 months | Patient experience |  | n/a | 53.5% | 8.6% | 45% | 95% | 95%
14 | SSNAP data | Weekly scrutiny of data in conjunction with consultants, site teams, managers to identify themes | David West | 2022-10-01 | Ongoing -weekly | Completed – Occurs Weekly | Improved Scrutiny of recorded data |  | n/a
15 | TIA Clinics to run 5 days a week where possible. | Clinics to run Mon - Thurs and Friday when required | Dave West | 2021-08-01 | Ongoing - weekly | Implemented. Dedicated Doppler scans. 2 clinics per week back up and running at NPTH | In place – admission avoidance |  | n/a
0 | Review of Actions from Thrombolysis Action plan 2019/20 to ensure lessons learnt remain embedded. |  | David West/ Tal Anjum | 2021-09-01 | In Place | 2019/2020 Action Plan: | Lessons learnt and kept on for information |  | n/a
19 | Review of Actions from Therapies Action plan 2020 to ensure lessons learnt remain embedded. |  | David West/ Tal Anjum/ Sue Wilson | 2021-09-01 | In Place | 2020 therapies action plan: Therapies room ring-fenced going forward | Lessons learnt and kept on for information |  | n/a
20 | Porter cover – pool porters & A&E porters to be involved in pathway to ensure we minimise delays. |  | Alan Thorne | 2022-02-01 | In Place | Reduce delays in CT/Ward transfers. | Reduced time to CT |  | n/a
21 | Pre-Alert ED – Site to be alerted ahead of time to pull the patient through to a bed. |  | WAST / SWITCHBOARD |  | In Place | Already in place | Reduced time to first assessment / CT/ Swallow assessment |  | n/a
26 | AMSR | Decompression of ED / AMSR redesign - COMPLETE | Morriston Site team | 2022-12-01 | 2023-10-01 | Decompression of ED and Stroke patients going to a dedicated medical area will mean assessments are more focussed and will better tailor for Stroke patients whose symptoms are not immediately obvious of stroke. Anticipated Benefit includes: • Improved CT Head time • Improved door to needle time for Thrombolysis AMSR implementation took place in December 2022. Full audit results and measures awaited at the time of writing but ED and the new AMU remain congested due to a lack of patient flow back into the community. February 2023 Double running phase to complete. No major benefit yet realised from AMSR to date in terms of its impact on Stroke performance. July 2023 ED still 100+ patients most days post AMSR. CT pilot commenced 17/7/23 to avoid delays and release crews. AMSR Closed down October 2023 |  |  | n/a
27 | Third Sector Colloboration |  | David West | 2023-01-01 | 2024-03-01 | Tender being submitted January 2024 | No impact to SSNAP but will allow more support to patients |  | £65k funded and awarded
|  | All site matrons reminded that breach of a Stroke bed needs authorisation from Silver & Gold. | Rebecca Davies | 2024-05-01 | 2024-05-01 | All staff reinformed of this 8/5/2024 Breach proforma reintroduceded | Expected improvement in 4 hours compliance |  | n/a
30 | Immediate actions to address Thrombolysis compliance | Thombolysis pathways to be reissued to all medical and ED staff | Tal Anjum /Mark Poulden | 2024-05-01 | 2024-05-01 | Dr Polden and Dr Anjum to send out guidance to capture all eligible patients for thrombolysis. | Expected improvement in thrombolysis compliance by ensuring all eligible patients are given this treatment. |  | n/a
|  | Recruit to develop 7 day a week 8am-10pm cover | Tal Anjum/ David West | 2024-05-01 | 2024-06-01 | 2 substantive PA’s to be recruited in place of locum ED team. | Expected improvement in thrombolysis compliance by ensuring specialist teams are available all throughout the week. |  | Funded from agreed recruitment plan
These 2 PA’s will join with 2 already in post substantive PA’s as well as 6 ANP’s and 3 CNS’s to form 7 day a week cover
|  | Continued education to On-call staff about thrombectomy options | Tal Anjum | 2024-05-01 | 2024-05-01 | Extended opening hours of this service has been cascaded to senior and junior staff | Increased utilisation of thrombectomy service in North Bristol. |  | n/a
|  | Continued education to On-call staff about thrombectomy options and NBNHST operating policy to be cascaded | Tal Anjum | 2024-05-01 | 2024-05-01 | Extended opening hours of this service has been cascaded to senior and junior staff | Increased utilisation of thrombectomy service in North Bristol. |  | n/a
|  | Extended ANP cover due to 2 now been signed off to independently see Stroke patients. Another 4 to come on line over the next 12-24 months | Tal Anjum | 2024-05-01 | 2024-05-01 | 2 trained as of May 2024, 4 more ANP colleagues to qualify over the next 24 months | Greater use of thrombectomy services due to quicker identification and referral to Bristol in conjunction with reduced CT and Thrombolysis times. |  | n/a
|  | Training of ED/AMU reception Staff to highlight suspected strokes or expedited triage | Tal Anjum | 2024-05-01 | 2024-07-01 | Reception staff being trained in BEFAST tool to identify suspected Stroke patients to expedite triage by nursing staff | Quicker identification of walk in stroked to reduce time to CT, Thrombolysis and thrombectomy. |  | N/A
|  | Continued education to On-call staff about thrombectomy options | Tal Anjum | 2024-05-01 | 2024-07-01 | Extended opening hours of this service has been cascaded to senior and junior staff | Increased utilisation of thrombectomy service in North Bristol. |  | N/A
5 | SALT input | National shortage of SLT staff which is resulting in several internal vacancies hindering compliance. | Jade Farrell | 2024-05-01 | 2024-11-01 | Ideas included: exploring overtime, longer-term locum, overseas recruitment, pulling staff from general ward areas? Following a meeting on 07/4/2025 this can be closed as recruitment has taken place and vacancies filled. | Increased compliance of therapy time by having more staff to delivery the therapy. |  | TBC
| Immediate action 2: Medical outliers should be capped at 6 on Ward F. Morriston to link in with NPTH around maximising use of rehabilitation facilities to improve flow | Rebecca Davies / David West | 2023-04-01 | 2024-09-01 | David West & Rebecca Davies to meet with Melanie Collins | Expected improvement in patient flow resulting in improvement in 4 hour compliance. |  | N/A