APPENDIX 2

| Meeting Date | 29th July 2025 |  | Agenda Item |  |  |
| --- | --- | --- | --- | --- | --- |
| Report Title | Welsh Government Oversight and Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in February 2025, the Health Board was de-escalated for the following areas previously at TI level 4 for Performance and Outcomes: - Child and Adolescent Mental Health Services will be de-escalated to level 3 (enhanced monitoring) and - Planned care will be de-escalated to level 3 (enhanced monitoring). All other areas of escalation remain unchanged and the summary is as follows: - Level 4 for finance, strategy and planning. - Level 4 for performance and outcomes relating to cancer, urgent and emergency care and quality of care related to HCAIs. - Level 3 for maternity and neonatal services. - Level 3 for performance and outcomes relating to planned care and CAMHS. - Level 2 for Mental Health and Learning Disabilities This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Maternity and Neonatal Services (since escalated to targeted intervention)

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows: -

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group and are outlined below: -

- The Service Group continues to work with the NHS Executive Mental Health leads as part of the Level 2 support. The work is now complete, and feedback report provided back to the Health Board Executive team and the Service Group. This is receiving its final amendments following feedback from the CEO office.

- The MH and LD Service leads formally presented the report findings at the Mental Health Divisional Board meeting on 2nd July 2025 and also attended the MH&LD Senior Management Team on 10th July.

- The Health Board had already commenced work in advance of the receipt of the report and had established a Transformation Program. This has been informed by a review of the service by an external advisor. The findings were presented to an in-committee meeting of the Board in February and the recommendations were approved. There were some recommendations which were considered urgent by the Board and these have been completed or are in progress. The Transformation Programme will be led by a Programme Board with supporting reporting structures including Workforce, IT/digital, Service Redesign, Quality and Safety and Estates. The recommendations of the review by NHS Executive MH and LD leads will form part of the work programme. Elements of the programme (such as estates) commenced early with a complex programme to improve the estates in development. The other workstreams commenced in June.  A Programme Initiation Document has been developed which describes the overall Programme in more detail with the deliverables from each of the workstreams and the expected benefits of the Programme.

- The Health Board will receive an update in the June Board and further planned updates in July and Sept already scheduled.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (June 25) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. | - 71.18% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. | - 73.65% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 7.39% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 76.53% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 82.58% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 32.70% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 100% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 99.94% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at NPTH to reduce demand for Morriston Hospital services.

4.2 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15th December 2023.

In order to appropriately scrutinise and seek assurance of the work being undertaken in Maternity and Neonatal services, a Gold command structure was established and has now subsequently been stood down in June 2025. A Perinatal Committee has now been established in its place and will continue to support the governance and assurance of the improvements of maternity and neonatal services.

Detailed progress against these areas will continue to be provided as part of the Perinatal Committee, chaired by the Executive Director of Nursing.

As of 15 July 2025 Maternity and Neonatal Services have been escalated to Targeted Intervention and arrangements for this will be taken forward in due course.

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - March – 75% - April – 87.2% - May – 70.5% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - March – 100% - April – 22% - May – 25% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - March – 98% - April – 98% - May – 99% |

Actions being taken to improve include:

- CAMHS Part 1B – Data Recording Error -The coding and logic that  had been applied to data being pulled was erroneous and this was rectified from 1st April 2025.  It was only including assessment and treatments booked together in the same month, not those that were assessed in a previous month with treatment in month so that was pulling through in reported figures.

- Further work is underway to manage capacity issues within the Part 1B team, utilising agency staff where required, this will be reviewed on a rolling monthly basis.

- CAMHS Part 1B now shows a slight increase from previously reported performance to 25% for the last reporting period (May 2025) from a previous position of 22%. 1A showed a fall in May 2025 due to moving of staff to support 1B and address capacity there.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - March – 62% - April – 60% - May – 57% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Continued focus on cellular pathology, further discussions to address backlogs that impact performance.  Exploring use of planned care funding more proactively to improve performance, e.g. targeting in the most pressured areas such as urology.

- Identify additional surgical capacity, increase preassessment capacity to support theatres scheduling.

- Additional chemotherapy capacity – now in recruitment and training phase, improvements in performance expected towards the end of the year.

- Further actions/improvement in Skin as seasonal demand increases, LGI, Urology – meetings with services arranged for July 2025

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - April – 629 (13.3% Increase) - May – 599 (4.8% reduction) - June – 249 (58.4% reduction) |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - April – 12.87% - May – 11.71% - June – 10.88% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - April – 83.26% - May – 86.33% - June – 100% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - April – 211 - May – 191 - June - 192 |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 - None since |

Actions being taken to improve include:

- Full implementation of D2RA model – Executive agreement between Health & Social Care CEO’S to deliver a D2RA model. Test of change delivered pre-Easter with overwhelming evidence of success. Test of change has continued, a work programme structure has been developed and a formal OCP is required to substantively reorganise workforce. A workshop is planned for the 21st July 2025.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital but with reduced measures in place. Health Board launch of ‘your next patient’ commenced on Monday 16th June 2025 and it has shown significant improvements across patient flow.

- UEC Care co-ordination Hub – Funding application submitted to Six Goals to extend the role and function of the UEC care coordination hub over the seven-day period. Initial priority to deliver five day single point of access and to implement the national ticket to ride framework.

- Pathway of Care Delays (PoCD) – Focus on the delivery of actions to reduce PoCDs, COP deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. Escalation to COO / Directors of Social Services on a weekly basis.

- Revised flow operating model/Anglesey Ward: Anglesey ward test of change commenced 2nd June. 25 bedded general medical ward has been opened as a key enabler to test changes in the operating model across the UEC pathway. Significant improvements already realised, particularly in respect of ambulance handover, lost hours, ED patient turnaround time. 8 PDSA’s in total scheduled during the next 6-week period. Executive approval to sustain the test of change model at Morriston Hospital has been provided.

- Falls Pathway – Commenced in February 2025 – The opportunity to further improve access to the service has been achieved in line with the revised flow operating model outcomes as above.

- UEC capital redesign – Following executive discussion, letters sent from CEO to Judith Paget (NHS Wales CEO) to outline the current tests of change in progress that will influence the capital request. There is also an expression of interest to pursue a digital platform to underpin the UEC pathway and has been supported by a demonstration to clinical operational staff on 8th July 2025.

5.3 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - April – 11 - May - 5 - June - 11 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - April – 4 - May – 5 - June - 4 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - April – 6 - May – 5 - June – 7 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - April – 4 - May – 9 - June - 7 |

During June 2025, there were 8 infection-related incidents/outbreaks, 2 of which reported in May, but concluded in June.

- 5 in Morriston: 4 COVID-19; 1 Norovirus (68 bed days lost).

- 2 in Neath Port Talbot Hospital: both COVID-19 (7 bed days lost).

- 1 in Singleton Hospital: COVID-19 (2 bed days lost).

During June, there was one genomically-linked outbreak of C. difficile identified retrospectively on a ward in Morriston, involving 2 patients. Both patients had been discharged by the time Whole Genome Sequencing identified the likely transmission.

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group continues, with Silver Groups reporting into Gold.

- The Digital App for HCAI incident case reviews user acceptability testing continues.

- New C. difficile Standards: Risk Assessment & Governance Framework agreed by Management Board. Multi-channel approach for dissemination and promotion at local level to support adoption.

- Continued focus on improving antimicrobial stewardship, reducing Primary Care and Secondary Care total antibiotics by documented daily doses, and reducing high risk 4C antibiotic use.

- Review and undertake financial impact assessment of new National Cleaning Standards 2025.

5.4 Finance

On 6th June 2025, the Health Board received the NHS Wales Chief Executive’s letter which clearly set out the next steps and expectations of Welsh Government with regards to the Annual Plan and Financial Position. Key to this is the expectation that as a minimum the Health Board submits a forecast position that maintains the 2024/25 Outturn position of no greater than £42.5m.

The scale of challenge to address delivery of £42.5m is very significant and the Health Board is fully committed to this, however after full consideration by the Board, at this point the forecast remains unchanged and is as per the Plan submitted on 31 March 2025 and summarised in the table below:

The Health Board’s actual performance against the three components of the Plan (Operational Pressure, Savings Target, and Planned Deficit) for 2025/26 is provided in the table below. This table shows that in Month 3 the reported deficit was £7.123m, which is £2.23m above the £58.7m planned deficit. The YTD position reports a £24.167m deficit, which is £9.48m above £58.7m plan.

As you will note from the table above the key driver of the YTD £9.48m deficit over the current plan is the non-delivery of savings. This shortfall was partly mitigated in Month 3 by non-recurrent in-month benefits for the Primary Care Service Group, a further underspend in the Corporate Directorates and the application of 10/12th of £2.7m non-recurrent opportunities.

The submission on the 30th June 2025, following the letter from the NHS Waels Chief Executive, contained the construct of the work completed in assessing delivery of the £42.5m, and the planned contribution of each element of the approach to close the gap from the current financial performance of the Health Board to the £42.5m (which was provided in Table 11).

The latest assessment of that work, following receipt of the Month 3 data, and also the confirmation of the National Insurance Funding, is provided below. Of note is: -

- Opening Gap – at 30 June 2025 the opening gap was £50m. This has reduced to £48.2m for 2 reasons: (1) £0.7m improvement in savings and (2) Operational underspend which has been helped by the release of 10/12ths of £2.7m N/R Opportunities and delivery of an enhanced corporate underspend.

- Risks – overall these have reduced due to value of the Red savings schemes reducing. However a proportion of this benefit has been offset by the recognition of the National Insurance funding from WG, which is £3.1m below the assessed costs incurred by the Health Board.

- Recovery Actions:

  - Variable Pay (VP) – the £32.3m was based on (VP) reducing to capped level of £1.8m per month. This was not achieved in Month 3 and so the cap will need to reduce to £1.4m from Month 9 onwards.

  - Corporate Directorates Underspend – this was achieved in Month 3 and is incorporated in the Delegated Budget Line on the second table provided above. The £3.6m is the remaining value left to be achieved on this line.

  - Central N/R Opportunities – £2.7m of Non Recurrent opportunities was identified and £0.270m was transacted in Month 3 and is part of Delegated Budget Line in above table. The £2.4m is the remaining value of the funding opportunity identified.

- Sustainability Options – this is the additional savings value the organisation needs to identify from the opportunities available and the total value has reduced since the submission on 30th June, linked to many of the changes noted in the points above.

The external support commences Monday 14 July 2025 and the initial programme will start with scrutiny and challenge on Variable Pay and the wider Health Board pay bill, before supporting the identification and delivery of the required Sustainability Options to deliver the £42.5m.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated June 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Management Board June 2025 agreed the process, timeline and approach to the Annual Plan 2026/27. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | Management Board to receive paper on governance and approach in July. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Planning Maturity Matrix update will be shared with WG in September. |
| Progress made with regional planning | Previous RJC meeting 7 May Next RJC meeting 18 August Regional working groups being established and governance arrangements finalise Regional work programmes and updates being prepared for 18 August for Regional Health Economy, Clinical Services, Workforce and OD, Data and Digital, Finance and Commissioning, Research and Innovation, Capital Planning. |

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | No Appendices |