| Meeting Date | 29 July 2025 |  | Agenda Item |  | 3.6 |
| --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance & Finance Committee |  |  |  |  |
| Report Title | Risk Management Report – Performance & Finance Risks |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee (PFC) for scrutiny. |  |  |  |  |
| Key Issues | - The Health Board Risk Register was last received by the Committee in April 2025. - Since then, Health Board risk register entries have been circulated to lead Executive Directors monthly for review and update. This report presents an extract of risks from the June 2025 HBRR. - Ten risks are assigned to the Performance & Finance Committee for oversight. Five risks are assessed to meet or exceed the Board risk appetite threshold. |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☐ | ☒ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - REVIEW the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified and consider whether further action / assurance is required in respect of any. |  |  |  |  |

RISK MANAGEMENT REPORT – Performance & Finance Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular risk update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

As part of the resetting of health board risk management arrangements a new Risk Management Group had its inaugural meeting in April 2025. The Group is chaired by the Deputy Chief Executive and reports to the Management Board. It meets monthly and its role includes oversight of the risks within risk registers, and of the escalation and de-escalation of risks between them. The last meeting of the group was in July 2025.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high-quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating a lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. This report presents the position as recorded within the June 2025 HBRR.

3.2 HBRR Performance & Finance Risks

Ten risks are assigned to this Committee for oversight (see extract attached at Appendix 1 for detail). The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 4 | 0 | 1 | 3 | 2 |

Key movements are:

| New Risks | Nil |
| --- | --- |
| Scores Increased | HBR52 Statutory Impact Assessments 1216 HBR93 Reduced Capital Funds 1220 |
| Scores Reduced | HBR1 Access to Unscheduled Care 2516 HBR16 Access to Planned Care 1612 |
| Risks De-escalated | Nil |

The changes in current risk scores noted above have the net effect of a reduction to the number of risks meeting or exceeding the Health Board’s risk appetite thresholds from seven to five. Table 1 below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the Performance & Finance Committee

| Risk Ref | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 50 (1761) | Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. The HB remains unable to deliver on the target of 75% of patients being treated within 62 days and is currently under targeted intervention by Welsh Government to improve performance. The Health Board has been given an initial target of 60% to be delivered by the end of Dec-24, increasing to 70% by the end of March 2025 | 25 | Lead: Chief Operating Officer The score remains unchanged currently. Update: The Health Board missed the target of 70% for the end of March 2025 – it delivered 62%. This will increase at the three-month refresh point. Current control actions will continue during 2025/26 to deliver sustained improvements. Additionally, the below adjustment is noted: Action: - Following a review of governance processes for our Annual Plan, cancer monitoring will now be included in the Planned Care Board (30/09/2025). |
| 92 (3444) | Forecast Deficit Forecast deficit is not met due to (1) insufficient progress on run rate reduction, (2) the extended saving targets required across all areas to meet the financial assessment submitted to WG on 26th September are not achieved, and (3) 30 other risks within the financial assessment are not mitigated. | 25 | Lead: Executive Director of Finance & Performance The score remains unchanged currently. Update: The controls and assurances sections have been refreshed for 2025/6. Controls: - Accountability Letters and Budgetary Management Framework were issued to all Directors in April 2025, which set the expectation and budget for 2025/26. - From Q3 2024/25 the Health Board has put in place oversight via the Recovery & Sustainability (R&S) Board, which reported directly to the Performance & Finance Committee (PFC) and is chaired by the Chief Executive. This Board is held bi-weekly. - Supporting the R&S Board is the R&S Team, which for 2025/26 has dedicated resource to lead the programmes of work agreed for 2025/26, of which the Board has agreed on 5 key areas. - Budgetary management approach 2025/26 requires all service groups to produce a financial strategy by end May 2025. - There is the continued transparent exchange of position with NHS Executive & Welsh Government, and weekly and monthly meetings with the NHS Executive. - Standard Day 5 Finance Reports on Variable Pay, Savings Performance and Flash report published via SharePoint site. - Variable Pay Cap agreed by the organisation to deliver £32m of savings as set out in the Financial Framework dated 30/06/2025. Additional actions: - The Financial Framework submitted to Welsh Government on 30/06/2025 clearly outlines recovery actions required by the Health Board to meet Welsh Government expectations. - The Health Board is commissioning external support, in collaboration with Welsh Government, which will commence from 14/07/2025. |
| 93 (3448) | Capital Plan Reduced National NHS funds available for major capital schemes requiring a restricted Capital Plan for 2025/26. | 20 (was 12) | Lead: Executive Director of Finance & Performance Risk score has increased from 12 from the beginning of the new financial year. Update: There is some uncertainty around the future approval of capital funding following the Welsh Government (WG) letter of 06/06/2025 on the unapproved revenue financial plan for the Health Board. Actions ongoing through the year: - Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk-based basis. - Examine the specific prioritisation and phasing of capital investment to meet health board objectives through the Capital & Estates Taskforce. - Maintenance of risks through the Capitalisation Prioritisation Group should additional WG funding become available later in the year. |
| 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) If we fail to have an approvable Integrated Medium-Term Plan (IMTP) for 2026/27 then we will not meet our statutory duty to break even and may lose public confidence. | 20 | Lead: Director of Strategy The score remains unchanged currently. Update: The following actions have been completed: - Review of the planning process followed to produce the 2025/26 Annual Plan, to make recommendations for the 2026/27 Plan process. Paper went to Management Board in June 2025. - Review and update of the Health Board Organisational Strategy. It will go to the Health Board Annual General meeting in September 2025. - Strengthened governance and scrutiny of delivery of the plan through development of new performance management and accountability framework – now in place. Actions ongoing: - Refresh Clinical Services Plan (31/03/2026) - Recovery and Sustainability Board to continue to focus on savings delivery and now shift to a more sustainable approaches in the longer term. A new monthly performance review regime and Executive Team members to oversee thematic savings workstreams and support Service Groups to meet targets (31/03/2026). |
| 98 (3692) | Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. The backlog maintenance costs are in excess of £200 million. The overall level of controllable risk is affected – compounded – by the resilience of the Health Board’s Health & Safety infrastructure (HBR64 Health & Safety Infrastructure risk) and the level of resourcing of Operational Estates, which influences the adequacy of capacity and capability for responding to priority risk mitigation (HBR92 Reduced Capital Funds risk) | 20 | Lead: Executive Director of Finance & Performance The score remains unchanged currently. Update: - TEF (Targeted Estates Funding) bids were successful, with £16.3m funding agreed for 2025/26 & 2026/27. - WG approved 3 schemes to progress with business cases in Q4 2024/25: Emergency Department, OR1 Theatre NPTH, and Hybrid Theatre, Morriston Hospital. AHU (Air Handling Unit) works commenced April 2025 at Singleton Hospital. - TEF works continue to be rolled out over 2025/26 & 2026/27 covering, Infrastructure, Fire, Infection Prevention & Control, Decarbonisation, Decontamination and Mental Health & Learning Disabilities. This is in parallel with priority works identified by Estates based on risk to coordinate works overall programme. Additional actions: - Review capacity and capability of Operational Estates and make recommendations on cost neutral investment in a longer-term plan to improve effectiveness (30/09/2025) - Update Asset Register, review Planned Preventative Maintenance tasks, and implement SFG20 (industry standard compliance management) to enhance approach to ensuring viability of core infrastructure and provide assurance on business continuity (30/09/2025). (Deadline dates to be reviewed 01/09/2025 as progress varies by objective). |

Table 2 below lists additional risks assigned to the Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes the Emergency Department, Acute Medical Unit and impact in community from ability to release ambulances at both front doors.) | 16 (was 25) | Lead: Chief Operating Officer The score has been reduced from 25. Update: The Urgent & Emergency Care (UEC) system continues to see high demand, with ambulance attendances higher than seen previously. However, this demand has been mitigated (beginning June 25) by improvement activity across the hospital resulting in improved flow away from the Emergency Department (ED). This improvement activity has been married with additional capacity at the front door (Ward) to decongest ED and resulted in the resultant reduced risk score. Discharge to Re-Assess principles across the Health Board have been reinforced. Significant progress made regarding key front door (e.g. ambulance handover, time in ED department etc) metrics coupled with reduced numbers bedding/ overcrowding front door services. During June improvement work was undertaken at Morriston Hospital including: - Anglesey Ward to temporarily operate as a General Medical ward to help decompress the ED. - Streamlining ED assessment and direct referrals to Medicine - Redesigning the medical assessment model in the Acute Medical Unit (AMU). - Enhancing specialty assessment and patient allocation. - Implementing a 7-day Same Day Emergency Care (SDEC) model. - Reviewing and applying consistent criteria to reside. - Roll-out of a new patient flow model: ‘Your Next Patient’. Community services review has not been undertaken by the PCT Group Nurse Director as anticipated. It has been agreed with the Executive Director of Nursing & Patient Experience and Director of Finance that additional support will be commissioned to undertake this crucial review. Anticipated start date of 01/08/2025, with review to run for 3 months. Actions ongoing (refreshed timescales): - Implementation of revised senior decision-making capacity within SDEC and AMU (31/10/2025) - Review of community services being undertaken by Service Group Nurse Directors for Primary Community & Therapies / Morriston to ensure return of investment ahead of expansion (31/10/2025) - Implementation of UEC Navigation Hub to decrease demand and implement right patient right place process (31/09/2025 pending Welsh Government funding) - Focus on reducing pathway of care delays (PoCDs) as per the Care Action Committee 50-day Challenge (Reduce to 100 clinically optimised patients by 31/09/2025) - Further develop admission avoidance pathways with WAST (Welsh Ambulance Services University NHS Trust), focussing on falls prevention and respiratory conditions (31/9/2025 linked to six-goals reporting & funding) |
| 16 (840) | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 12 (was 20) | Lead: Chief Operating Officer The score has been reduced from 20 (score previously reported at last meeting). Update: Patients are still waiting more than 104 weeks for surgical intervention, which is outside of national policy on Referral To Treatment. However, the position is improving: targets set for 2024/25 were met and the Health Board was de-escalated by Welsh Government from Targeted Intervention (TI) for delivery of Planned Care services, to Enhanced Monitoring. Current risk score reflects that improved position. |
| 52 (1763) | Impact Assessment Requirements The Health Board does not have sufficient skills and resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. | 12 (was 16) | Lead: Director of Insight Communications & Engagement The score has reduced from 16. Update: There has been no increase in the capacity in the engagement team, but the impact assessment process has progressed, so the risk entry has been amended. Actions previously completed: - Review of the current process for developing equality impact assessments around service change, engagement and consultation. - Robust policies and processes in place for impact assessment going forward. Actions & targets refreshed: - Revised structure within Engagement team to ensure equity, diversity & belonging (EBD) issues are coordinated across the Health Board (01/08/2025) - Revised structure to be agreed and posts appointed to (01/10/2025) - Roll out of Impact Assessment process across the organisation (Training and integration with planning processes across the organisations will be required) (30/09/2025) |
| 75 (2522) | Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 10 | Lead: Chief Operating Officer Risks in relation to major incidents and business continuity are being reviewed and will be reflected afresh as part of the resetting of Board-level risk reporting arrangements. |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. | 12 | Lead: Chief Operating Officer The score remains unchanged currently. Update: Review of all vacant posts across CAMHS has been completed and vacant funds moved to Part 1 of the service to improve the potential capacity to meet the demand and maintain the performance against target. There was a reporting error in Part 1b which has now been rectified and additional control measure put in place to monitor the data and the activity on a weekly basis. |

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 16 | Quality & Safety |
| 16 (840) | Access and Planned Care. There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 12 | Quality & Safety |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Quality & Safety |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. | 12 | Quality & Safety |

4. FINANCIAL IMPLICATIONS

There are financial implications to minimising the risks entered on the HBRR in relation to significant revenue implication around strengthening resources in the Health Board, Service Groups and Departments.  Capital monies may also be required in relation to supporting the improvements required to improve and where this is the case further detail is provided in the individual entries on the HBRR.

5. RECOMMENDATIONS

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- REVIEW the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PFC which were last reported to the Committee in April 2025. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Performance & Finance Committee |  |