| Meeting Date | 24th June 2025 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Welsh Government Oversight and Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Performance and Finance Committee with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in February 2025, the Health Board was de-escalated for the following areas previously at TI level 4 for Performance and Outcomes: - - Child and Adolescent Mental Health Services will be de-escalated to level 3 (enhanced monitoring) and - Planned care will be de-escalated to level 3 (enhanced monitoring). All other areas of escalation remain unchanged and the summary is as follows: - - Level 4 for finance, strategy and planning. - Level 4 for performance and outcomes relating to cancer, urgent and emergency care and quality of care related to HCAIs. - Level 3 for maternity and neonatal services. - Level 3 for performance and outcomes relating to planned care and CAMHS. - Level 2 for Mental Health and Learning Disabilities This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER and DISCUSS the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |
| Appendices | No Appendices |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Maternity and Neonatal Services

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group and are outlined below.

- The Service Group continues to work with the NHS Executive Mental Health leads as part of the Level 2 support. The work is now complete, and feedback report provided back to the Health Board Executive team and the Service Group. This is receiving its final amendments following feedback from the CEO office.

- The MH and LD Service will then liaise with NHS Executive MH Leads for formal presentation of the reporting finding to relevant parts of its service. The findings and recommendations of the report will form part of the Transformation Program workstreams to ensure all aspects are addressed.

- The Health Board had already commenced work in advance of the receipt of the report and had established a Transformation Program. This has been informed by a review of the service by an external advisor. The findings were presented to an in-committee meeting of the Board in February and the recommendations were approved. There were some recommendations which were considered urgent by the Board and these have been completed or are in progress. The Transformation Programme will be led by a Programme Board with supporting reporting structures including Workforce, IT/digital, Service Redesign, Quality and Safety and Estates. The recommendations of the review by NHS Executive MH and LD leads will form part of the work programme. Elements of the programme (such as estates) commenced early with a complex programme to improve the estates in development. The other workstreams commenced in June.  A Programme Initiation Document has been developed which describes the overall Programme in more detail with the deliverables from each of the workstreams and the expected benefits of the Programme.

- The Health Board will receive an update in the July Board and further planned updates in September already scheduled.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (May 25) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. | - 69.45% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. | - 73.44% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 7.39% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 75.64% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 80.67% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 32.06% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 99.84% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 99.91% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at NPTH to reduce demand for Morriston Hospital services.

4.2 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15th December 2023.

In order to appropriately scrutinise and seek assurance of the work being undertaken in Maternity and Neonatal services, a Gold command structure was established. The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning.

Detailed progress against these areas have been outlined in the Gold command for maternity and Neonatal services progress report.

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - February – 74% - March – 75% - April – 87.2% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - February – 100% - March – 100% - April – 22% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - February – 98% - March – 98% - April – 98% |

Actions being taken to improve include:

- Inaccurate reporting of Part 1B data has been corrected, revealing poor compliance with national performance metrics for first intervention timescales due to capacity constraints. The necessary notifications to the NHS Performance and Improvement team ahead of the next Level 3 Enhanced Monitoring Meeting.

- Further work is underway to manage capacity issues within the Part 1B team, utilising agency staff where required, this will be reviewed on a rolling monthly basis.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - February – 56% - March – 62% - April – 60% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Continued focus on cellular pathology, workforce review - several posts going through vacancy control process; ongoing discussions to address backlogs that impact performance.  Identify opportunities to improve turnaround times for urological USC’s.

- Identify additional surgical capacity, increase preassessment capacity to support theatres scheduling.  Additional chemotherapy capacity (business case agreed).

- Further actions/improvement in Skin as seasonal demand increases, LGI, Urology and Lung.

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - March – 555 (0.18% Increase) - April – 629 (13.3% Increase) - May – 599 (4.8% reduction) |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - March – 11.3% - April – 12.87% - May – 11.71% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - March – 82.21% - April – 83.26% - May – 86.33% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - March – 219 - April – 211 - May - 191 |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 |

Actions being taken to improve include:

- Full implementation of D2RA model – Executive agreement between Health & Social Care CEO’S to deliver a D2RA model. Test of change delivered pre-Easter with overwhelming evidence of success. Test of change has continued, a work programme structure has been developed and a formal OCP is required to substantively reorganise workforce.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital. Health Board launch of ‘your next patient’ commences Monday 16th June 2025.

- UEC Care co-ordination Hub – Funding application submitted to Six Goals to extend the role and function of the UEC care coordination hub over the seven-day period. Initial priority to deliver five day single point of access and to implement the national ticket to ride framework.

- Pathway of Care Delays (PoCD) – Focus on the delivery of actions to reduce PoCDs, COP deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. Escalation to COO / Directors of Social Services on a weekly basis.

- Revised flow operating model/Anglesey Ward: Anglesey ward test of change commenced 2nd June. 25 bedded general medical ward has been opened as a key enabler to test changes in the operating model across the UEC pathway. Significant improvements already realised, particularly in respect of ambulance handover, lost hours, ED patient turnaround time. 8 PDSA’s in total scheduled during the next 6-week period.

- Falls Pathway – Plan to commence February 2025 – enhanced opportunity via the Care Co-ordination Hub PDSA above linked to Hub.

- UEC capital redesign – Following executive discussion, letters sent from CEO to Judith Paget (NHS Wales CEO) to outline the current tests of change in progress that will influence the capital request. There is also an expression of interest to pursue a digital platform to underpin the UEC pathway.

5.3 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - March – 15 - April – 11 - May - 4 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - March – 3 - April – 4 - May - 5 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - March – 4 - April – 6 - May - 5 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - March – 5 - April – 4 - May - 9 |

During April and May 2025, there were 8 infection related incidents/outbreaks.

- 6 in Morriston: 3 COVID-19; 3 Norovirus (144 bed days lost).

- 2 in Neath Port Talbot Hospital: both Norovirus (32 bed days lost).

- 1 in Cefn Coed Hospital: Group A Streptococcus (a continuation from an outbreak in March 2025, with re-colonisation/re-infection). Ten patients and five staff involved over the period (71 bed days lost 28 March to 10 April; 130 bed days lost 14 May to 7 May.).

- During April, there was a genomically-linked outbreak of C. difficile identified on a ward in Morriston, involving 2 patients. There were 9 bed days lost.

- During May, there was a genomically-linked outbreak of C. difficile identified in a different ward in Morriston, involving 2 patients. There were no bed days lost.

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group continues, with Silver Groups reporting into Gold.

- The Digital App for HCAI incident case reviews moves into user acceptability testing.

- New C. difficile Standards: Risk Assessment & Governance Framework agreed by Management Board.  Formalise launch of Standards.

- Continued focus on improving antimicrobial stewardship, in particular the outcomes of antimicrobial review.

- Collaborative work with ED team, Domestic Services Team and IPC on cleaning schedules and requirements in ED.

5.4 Finance

The Annual Plan submitted to Welsh Government on 31st March 2025 for assessment and scrutiny included a financial assessment, as summarised in the table below:

The Health Board’s actual performance against the three components (Operational Pressure, Savings Target, and Planned Deficit) for 2025/26 YTD are provided in the table below. This table shows that in Month 2 the reported deficit was £8.043m, which is £3.15m above the planned deficit. The YTD position reports a £17.04m deficit, which is £7.26m above plan.

As you will note from the table above the key driver of the YTD £7.26m deficit over plan is the non-delivery of savings. This shortfall was partly mitigated in Month 2 by non-recurrent in month benefits for the NPTS and Morriston Service Groups and a further underspend in the Corporate Directorates. To achieve the original £58.7m plan the Health Board needs to recover the £7.26m during 2025/26 by delivering more savings and/or reducing expenditure below plan in future months.

Following the closedown of the Month 2 financial position, the Health Board received a letter from Judith Paget (dated 6th June 2025) which clearly set out the next steps and expectations of Welsh Government with regard to the Annual Plan and Financial Position. Key is the expectation that as a minimum the Health Board submits a forecast position that maintains the 2024/25 Outturn position of £42.5m. Since receipt of the letter the Health Board has been working through actions and developing plans to meet the savings requirement and delivery of expectation of £42.5m for 2025/26,  via a detailed action plan for submission to Welsh Government on 30th June.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated May 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | Management Board to receive paper on governance and approach in July. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Planning Maturity Matrix update ill be reported to Board in July via DPP |
| Progress made with regional planning | Previous RJC meeting 7 May Next RJC meeting 18 August Regional working groups being established and governance arrangements finalise Regional work programmes and updates being prepared for 18 August for Regional Health Economy, Clinical Services, Workforce and OD, Data and Digital, Finance and Commissioning, Research and Innovation, Capital Planning. |

- GOVERNANCE AND RISK ISSUES

The key risks associated with the escalation report are included in the Health Board risk register.

- FINANCIAL IMPLICATIONS

The financial position of the Health Board is set out in this report. There are no direct financial implications arising from this report itself.

This report is followed by a detailed presentation on the overall financial position as summarised above.

- RECOMMENDATION

Members are asked to:

- CONSIDER and DISCUSS the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | No Appendices |