| Meeting Date | 26 March 2024 |  | Agenda Item |  |  | 4.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Planned Care Performance Update |  |  |  |  |  |
| Report Author | Craige Wilson, Deputy COO |  |  |  |  |  |
| Report Sponsor | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Presented by | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | In May 2022, Welsh Government set out its ambitious intention for planned care recovery with two specific priority areas: - No patient will wait more than 52 weeks for a first outpatient appointment by end of 2022. - Patients will wait less than 104 weeks for treatment within most specialties by the end of 2022/23 These targets were subsequently revised to October 2023 for 52 weeks outpatient waiting times and March 2024 for 99% of 104 week waiting times at all stages. This paper provides an update on improvement plans to deliver against the trajectories submitted to Welsh Government and progress against the revised target dates. |  |  |  |  |  |
| Key Issues | - The Health Board achieved the 52-week target by the end of October 2023 and has maintained. - 96.7% of patients waited less than 104 weeks at the end of December 2023 (Target 97%) - There is a considerable challenge to achieve the 99% of patients waiting less than 104-weeks by the end of March 2024. - There is a concerted focus is on achieving zero 156 week waits. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: To note the progress made to date to achieve the Ministerial Targets, support the additional actions being undertaken to deliver the March 2024 target and acknowledge the associated risks. |  |  |  |  |  |

Planned Care Performance Update

- INTRODUCTION

In May 2022, Welsh Government set out its ambitious intention for planned care recovery. The output of that ambition was a requirement for Health Boards to submit recovery trajectories against two specific priority areas:

- No patient will wait more than 52 weeks for a first outpatient appointment by end of 2022.

- No patients will wait less than 104 weeks for treatment within most specialties by the end of 2022/23

These targets were subsequently revised to October 2023 for 52 weeks outpatient waiting times and March 2024 for 99% of 104 week waiting times at all stages.

This paper provides an update on improvement plans to deliver against the trajectories submitted to Welsh Government and progress against the revised target dates.

- BACKGROUND

The Recovery and Sustainability (R&S) Plan 2022-25 was endorsed by Management Board on March 2022, approved by Board, and subsequently submitted to Welsh Government for consideration.

One of the core components of the R&S Plan was the recovery of planned care, which had been impacted significantly by the pandemic. The WG recovery plan ask assumed that planned care activity levels have resumed to pre-pandemic levels (19/20) and will be exceeded as a result of the additional recovery funded provided.

The Health Board submitted initial trajectories but highlighted that further work would be undertaken to refine the modelling and strengthen the plan in the following areas:

- Strengthening GP led services to prevent referral to secondary care and diagnose and/or treat at source.

- Developing demand management solutions across our systems of care.

- Considering the application of referral management criteria to be applied to existing lists and new referrals.

- Increasing core capacity for open pathways by diverting capacity previously assigned to follow up pathways as a result of:

  - modernisation of follow up system,

  - better use of clinic slots through partial bookings,

  - individual consultant productivity and

  - rigorous enforcement of DNA protocols

- The opening of further planned capacity in our system at Neath and Port Talbot

- CURRENT POSITION

# Stage 1 Position

The zero-breach target for Stage 1 (outpatients) was achieved in October 2023 and have been maintained. There is an expectation that this is a continuous target and as a Health Board we work towards achieving a zero-breach position at 36 weeks.

# All Stages (104 weeks)

The graph below shows the progress that has been made since April 2023 to the end of February 2024, when 2176 breaches were reported.

With regards to the longest waiting patients the table below provides a summary of the reported position at the end of February. Two of the three longest waiting patients were referred for treatment at Kings College Hospital in London.

| Target | February Position |
| --- | --- |
| 260 Weeks | 0 |
| 208 Weeks | 131 |
| 156 Weeks | 508 |

# 104 Week Cohort for March 2024

In order to achieve the 104-week target of 99% the Health Board is required to have approximately 1004 patients waiting over 104 weeks. There are at the time of writing this report (18th March) 2122 patients in the cohort who need to be seen, receive any diagnostics investigations and be treated by the end of March 2024; 158 patients in this cohort currently have dates for treatment in March.

Whilst Orthopaedics has the greatest number of patients in this cohort there are also significant numbers in other specialties, notably, General Surgery ENT, Gynaecology, and Plastic Surgery; as shown in the table below.

| Speciality | Appointed | Waiting | Grand Total |
| --- | --- | --- | --- |
| ENT | 23 | 143 | 166 |
| General Surgery | 11 | 150 | 161 |
| Gynaecology | 24 | 570 | 594 |
| Oral/Maxillo Facial Surgery | 8 | 32 | 40 |
| Plastic Surgery | 16 | 241 | 257 |
| Spinal | 4 | 75 | 79 |
| Trauma & Orthopaedic | 71 | 718 | 789 |
| Urology | 0 | 35 | 40 |
| Grand Total | 158 | 1964 | 2122 |

Insourcing and outsourcing of long waiting patients has continued and additional internal capacity commissioned to achieve the best possible position. Administrative and clinical validation continues.

As an example of the benefit of clinical validation, General Surgery has undertaken an MDT approach to clinical validation, the outcome from which can be seen below:

|  | Clinically Validated | Removed |
| --- | --- | --- |
| Hernias | 966 | 131 (14%) |
| Lumps & Bumps | 161 | 43 (27%) |

Other specialties with large numbers of long waiting patients are in discussion with their clinical teams regarding taking the same approach.

# 156 Week Cohort

Due to the volume of patients and the requirement to remove the longest waiting patients the fortnightly Performance Scrutiny meetings with the Service Groups are focusing particularly on the 156-weeks cohort of patients.

For the services highlighted in green below, there are plans to clear this cohort and the other services are still currently working on treatment plans for the remaining patients. The services that will not deliver the 156 weeks target are Plastics, Spinal and Gynaecology.

| Service | Appointed | Waiting |
| --- | --- | --- |
| ENT | 16 | 0 |
| General Surgery | 3 | 1 |
| Gynaecology | 6 | 216 |
| Oral/Maxillo Facial Surgery | 1 | 0 |
| Plastic Surgery | 15 | 48 |
| Spinal | 2 | 8 |
| Trauma & Orthopaedic | 41 | 18 |
| Urology | 1 | 0 |
| Total | 86 | 291 |

Scrutiny and Assurance Process

Accountability and Monitoring of the Trajectories

The dynamic nature of the recovery necessitates scrutiny and monitoring, both internal and external to the organisation. The following outlines the monitoring and reporting structure that is in place and the mechanism for directorates to be held to account for delivery.

External Monitoring

Biweekly monitoring meetings are scheduled with WG / NHS Executive officials and HB is represented at the monthly meetings by the COO and Deputy COO.

The monthly meetings focus on:

  - Validation

  - Treat in turn

  - Plans for longest waits

  - Detailed speciality discussions / issues / areas of concerns

  - Progress on HB transformation measures

  - Progress on developing patient support and communication

A weekly patient level submission on the plan for all patients waiting over 4 years, a summary of which can be seen below, is also being provided to the NHS Executive.

Internal Monitoring

There are fortnightly meetings with the Service Groups where they are held to account for delivery of the trajectories. Escalation for the non-delivery against the submitted levels will be to the Service Group Directors in the first instance and subsequently to the Planned Care Board and Management Board.

- Operational monitoring - the current performance management meetings:

  - Monitor delivery of the trajectories and the areas of efficiency noted above

  - Ensure core capacity is at or above 2019/20 levels

  - Ensure robust housekeeping is in place for RTT pathways

  - Further develop recovery plans as required for approval via Planned Care Board

- Formal monitoring / assurance

  - Service Group Performance Reviews

  - Planned Care Board

  - Management Board via the Performance Report

  - Performance & Finance Committee

To help support directorates a Planned Care Dashboard has been developed with specialty level performance information.

Risks

Whilst the Health Board has achieved the 52 week target and is expected to maintain this position, there are significant risks associated with meeting the 156 week and 104-week position:

- Reliance on core, insourcing and outsourcing capacity to deliver 156-week target. An increased number of patients will breach 104 weeks by End of March due to changes to outsourcing contract.

- Industrial Action schedule to take place in February will result in activity will be reduced

- Theatre Capacity – the current shortfalls in theatre staff and anaesthetists are currently limiting the delivery of optimum theatre capacity. Recruitment of theatre staff is ongoing and improving but the recruitment of anaesthetic staff is providing more of a challenge.

- FINANCIAL IMPLICATIONS

As a result of the additional funding secured for the NPTH development £38.4m was allocated to Planned Care Recovery for 2023/24. There are a number of assumptions in this figure including the anticipated spend on the NPTH development and full utilisation of the outsourcing capacity.

The Health Board’s end of year financial recovery plans assumes that a saving of approximately £36.4m will be spent and consequently outsourcing was reduced where it did not impact on the 156 cohort of patients with resulting revised trajectories.

- RECOMMENDATION

Members are asked to note the progress made to date to achieve the Ministerial Target, support the additional actions being undertaken to deliver the target by March 2024 and acknowledge the associated risks.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The successful implementation of the plans outlined have the ability to improve the quality and safety of services and in turn patient experience. However, the report has outlined a number of risks, which have the potential to delay benefit realisation. |  |  |  |
| Financial Implications |  |  |  |
| There is a significant risk that the financial allocation in 2023/24 for the Planned Care Recovery Programme will limit the progress that the Health Board is able to make in reducing waiting times further. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications to consider as a direct result of this report. |  |  |  |
| Staffing Implications |  |  |  |
| A number of the improvement plans are facing challenges with recruitment and the availability of re-current funding. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| This paper outlines how service areas within the Planned Care Programme are working in collaboration not only to look at the short term, but also to develop services across Swansea Bay in the long-term including the new theatres and the plans to enhance innovation and new ways of working. |  |  |  |
| Report History |  | Planned Care Update (November 2023) |  |
| Appendices |  | None |  |