| Meeting Date | 24 March 2026 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance and Finance Committee |  |  |  |  |
| Report Title | The Welsh Government Oversight and Escalation Update and Swansea Bay University Health Board (SBUHB) Integrated Performance Report (IPR) |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and Senior Responsible Owner (SRO) for Targeted Intervention Marie Davies, Executive Director of Planning and Partnerships |  |  |  |  |
| Presented by | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated as part of the Welsh Government Oversight and Escalation Framework, along with a general update of the Health Boards Performance against the Key Strategic Objectives. |  |  |  |  |
| Key Issues | This report provides a monthly update on all areas of delivery currently in escalation against the Welsh Government Oversight and Escalation Framework, namely: Level 4 - Maternity and Neonates (escalated in July 2025). - Finance, strategy and planning. - Performance and outcomes relating to cancer, Urgent and Emergency Care and quality of care related to HCAIs. Level 3 - Performance and outcomes relating to planned care and CAMHS. The attached Integrated Performance report (IPR) is a routine report that provides an overview of how the Health Board is performing against the National Delivery measures and key local quality and safety measures. The IPR includes an update against four three priority areas for the Health Board: - The Welsh Government Escalation (RAG Rating status) - Performance against the Health Boards 5 Strategic Objectives - Service Specific Updates The Performance metrics outlined within Section two of the Integrated Performance Report have been aligned to the Health Boards five Strategic Objectives. Key Updates will therefore be provided against the five Strategic Objectives below: - - People of Swansea Bay live healthier, equitable and more equal and prosperous lives - Care is high quality, safe, efficient and delivers the best possible outcomes for people - Care is delivered in safe and appropriate settings supported by innovative digital solutions - The health board is a great place to work where staff feel valued and work together towards a common goal - The health board is a resilient, financially sustainable and responsible organisation An additional section has been included in the report which will provide “Service Specific Updates” as and when requested by the Performance and Finance Committee work programme. In this paper, the following service specific update will be included: - Cancer Care |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☐ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. - ACKNOWLEDGE and DISCUSS the Health Board performance against key measures and targets. |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE AND INTEGRATED PERFORMANCE REPORT

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services escalated to targeted intervention status. The reports provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board (SBUHB) and will include;

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Maternity and Neonatal Services

- Finance

- Strategy and Planning

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Child and Adolescent Mental Health

- BACKGROUND

Following WG tripartite meeting in December 2023, SBUHB was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12 April 2024, SBUHB had its inception meeting with the Welsh Government colleagues and on 24 April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG

The Welsh Government officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted intervention, and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria were provided by the Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

Following the publication of the Independent Maternity and Neonatal Review published on 15 July 2025, the decision was made to escalate Maternity and Neonates to Level 4 (Targeted Intervention) from Level 3 Enhanced Monitoring. Updated de-escalation criteria relating to Maternity & Neonates was published in September 2025 and has been incorporated into this paper.

- PERFORMANCE AGAINST THE AREAS ESCALATED UNDER THE WELSH GOVERNMENT OVERSIGHT & ESCALATION FRAMEWORK

Detailed updates against the escalated areas have been included in Section 1 in the Integrated Performance Report in Appendix 1.

- INTEGRATED PERFORMANCE REPORT

The detailed Integrated Performance Report can be found in Appendix 1 of the attached report. The purpose of this report is to provide an update on current performance of the Health Board at the end of the most recent reporting window in delivering key performance measures outlined in the NHS Wales Delivery Framework, local Quality & Safety measures, updates against the Welsh Government De-escalation targets and routine reporting against measures outlined within the NHS Wales Planning Framework.

In alignment with the revised Swansea Bay University Health Board (SBUHB) Performance and Assurance Framework, the Integrated Performance Report has been reviewed and will now update against three key areas: -

- The Welsh Government Escalation

- Performance against the Health Boards 5 Strategic Objectives

- Service Specific Updates

As and when required, the Integrated Performance Report will provide ‘Action and Intervention’ focus on areas of performance which are off target or an area of concern for the Executives. Additionally, as and when Committee/Board members are concerned with an area of Performance, they can request that an Action and Intervention focus be undertaken within the IPR. An ‘Action and Intervention’ focus will provide a deeper look into the service and will provide detailed action steps which are being taken to recover performance.

The Performance metrics outlined within Section two of the Integrated Performance Report have been aligned to the Health Boards five Strategic Objectives. Key Updates will therefore be provided against the five Strategic Objectives below: -

- People of SBUHB live healthier, equitable and more equal and prosperous lives

- Care is high quality, safe, efficient and delivers the best possible outcomes for people

- Care is delivered in safe and appropriate settings supported by innovative digital solutions

- The health board is a great place to work where staff feel valued and work together towards a common goal

- The health board is a resilient, financially sustainable and responsible organisation

An additional section has been included in the report which will provide “Service Specific Updates” as and when requested by the Performance and Finance Committee work programme.

In this paper, the following service specific updates will be included:

  - Cancer Care

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria.

- ACKNOWLEDGE and DISCUSS the Health Board performance against key measures and targets.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted. |  |  |  |
| Financial Implications |  |  |  |
| Funding not yet agreed for 26/27 |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Delay to diagnosis and treatment potential in service delivery |  |  |  |
| Staffing Implications |  |  |  |
| Additional support staffing required to deliver the programme |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | First comprehensive update presented. |  |
| Appendices |  | Appendix 1: Integrated Performance Report |  |