The following are highlights of the Quarter 4 achievements by area. These achievements were reported as GMOs ‘Green On Track’ as part of the Highlight Reports provided for APOG on 4th April 2024

UEC / Six Goals

Programme 1: Co-ordination, signposting, and alternatives to admission

- Virtual wards in all clusters, fracture discharge service (FDS) in place and operating.

- Heart Failure redesign (VBHC project): 3631 patients coded as having heart failure on the 36 GP Practices registers (which agreed access) – of those cleansed to date 15% have no evidence of diagnosis of heart failure, 16% require further review by a Cardiologist, 13% have been seen in the ‘core’ service within last 9 months and not require a review this year – total number invited to attend annual review at 2371 patients with a 7% DNA rate (up from 1565 patients at end of Q3) – total patients where new AF has been identified = 1.5%

- Core Community Heart Failure Service (VBHC project):  Secured clinical spaces across region to expand service which has increased weekly clinic provision from 18 to 35 clinics per week.

- Atrial Fibrillation redesign: (VBHC project) Increased no. of patients diagnosed – on Feb 24, 10042 patients with AF in SBUHB (increase of 48 since last report) prevalence = 2.54% compared to all Wales national average which is 2.43%. Improved access to one stop clinics for AF by clinical professionals with specialist interest in AF, e.g. PAF clinics underway with GJ Estuary Practice. Staff recruitment completed to provide new community-based echo service for newly diagnosed AF patients.

- Diabetes redesign:  Pre diabetes programme delivered in 7 clusters since Sept 2023. Activity data / patient contacts = 630 (up from 444 in last report). 31 practices are engaged with the programme.

- Increased psychology presence in Primary Care clusters: Funding sourced to take community psychology forward initially for Cwm Tawe, Bay and Upper Valleys (review performance and further develop model).  Cwm Tawe Community Psychologist in post (Full Time - Band 7/8a). Recruitment underway for Bay and Upper Valleys Clusters (Both Full Time – Band 8a posts) – interviews planned for W/C 18/03/24.

Programme 2: Integrated front door

- Care home rapid response & optimisation of care/ trialling chest pain & falls pathways: Pharmacy reviews for all residents at the agreed care homes continue to be rolled out. Rapid response element of project operational (for the 5 care homes receiving wrap-around support). Additional project element rolled out during Q4 namely Palliative Care Paramedics providing eyes on for OPAS/ GPOOH and treatment at site rather than conveyance.

Programme 3: Acute hospital flow and discharge

- SAFER & Red2Green rolled out in 23/ 24

- Patient flow team at MGH working across SBUHB.

- Criteria Led Discharge launched & underway (further work required to fully embed across SBUHB)

- Capital build (SAU) completed, SAU opened and reconfiguration of wards complete.

- Centralised acute admissions has now been embedded and that any service improvements regarding AMU/ SDEC is as part of BAU.

Programme 4: Integrated discharge

- Pilot approved with RBP in June 23 subject to ongoing review, increased EMI capacity (8 beds) in place for 23/24.

- 4 additional beds commissioned for Ty Olwen (14 beds in place)

- Pathway of Care Delays (POCD) Action plan updated and submitted to national team – TBC awaiting feedback. POCD working group set-up with representation from LA’s, Health Board and RPB to drive forward activity with new POCD lead in 24/25

Planned Care

Outpatients & Surgery

- All services have met the target of 0 patients waiting or appointed over 52 weeks.

- All services are expected to achieve 52 weeks by end of March 2024

- Stage 5 – 260 week waits The three outstanding patients that were over 5 years are now cleared at the end of February

- 104 week position – All stages Based on the current trajectory the end of March position is currently forecast to be approximately 98% (against 99% national target)

- Primary care referral pathways projects -

- Effective Referrals project in delivery phase and on track.

- Health Pathways - New go live date confirmed as 23rd April. Launch presentation confirmed at PLTS 11th April.

- Optimising OP processes and delivery projects –

- Job Planning Task and Finish Group established with first meeting in March 2024 for Medical Director, Deputy Medical Director, Chief Operating Officer, Deputy Chief Operating Officer and Service Directors. The group will coordinate tasks and actions to support the development and implementation of the Job Planning Dashboard within each service and will:

- Analyse the demand, capacity and activity within each service to enable the identification of the cause of delays and parts of the system which are causing a backlog;

- Provide an opportunity to enable improvements to be made within existing resource levels by identifying surplus and shortfall within the existing establishment to meet demand.

- Vitals Dashboard is live in T&O and scoped for the rest of the top 5 services.

- Job planning spreadsheet developed and presented to T&O service 4th March 2024. Job planning reports generated from the spreadsheet will be available in all top 5 services within 6 months.

Diagnostics:

- Endoscopy will achieve the revised target with Welsh Government: 3291 patients waiting > 8 weeks by end of March 2024.

- Radiology is on track to deliver against the 8 week ministerial target for: Fluoroscopy, Non-Cardiac CT, Non-Cardiac MR and Non Cardiac Nuclear Medicine.

- DXA - Negotiations have been ongoing much of 2023/2024 regarding an updated SLA  between SBUHB and HDUHB. The SLA was agreed in Q4.  Current breaches of the 8 week target forecast end of March 2024; SBUHB: 340, HDUHB:  Scanning – 2379, Reporting – 2765,

Cancer

- The latest reported SCP position covering February 2024 (50%) demonstrated an improvement on the disappointing January 2024 position (48%).

- Cancer backlog position has recovered since the beginning of 2024 and continues to reduce. The most recently reported backlog position stands at 203 patients, with longest waiting patients backlog down to just 18,  this is a reduction of 31% over the last quarter

- Radiotherapy GMOs progressing well with positive improvements in waiting times and patient care being demonstrated. Implemented recommissioned CTSIM has eliminated pathway breaches related to CT capacity issues.

- SWWCC Bimonthly meetings have been established with Hywel Dda which are assuring timelines are met for regional projects (Radiotherapy and Oncology Outpatients.

- Successful recruitment of 2 JCFs for Haematology. 2 SCFs back out to advert and shortlisting to be completed ASAP.  Reduction in agency spend from Feb 24 will create cost saving within the department.

- 5-day acute oncology service in place at Morriston supported with 5-day Acute Oncology Haematology Assessment Unit (AOHAU) at Singleton.

- Rapid Diagnostic Centre has been funded on a recurring basis with the exclusion of Colorectal pathway.

- Consultant AHP for Cancer commenced in post.

- The first of two OG cancer workshops with CVUHB took place on the 7th of March. Draft pathway was discussed, with next steps to confirm pathway and confirm workforce uplift requirements.

- Continued improvement in SACT wait times.  The SBUHB team are considered an ‘exemplar’ nationally for the significant achievements made in improving efficiency and productivity, e.g. revised internal booking practices and minimise delays to treatment due to avoidable issues as a result of internal processes.

Mental Health & Learning Disabilities

- Improved in 111 Press 2 response times and call rates

- Expanded Adult Sanctuary Service into NPT

- Constructed Seclusion Suite for Taith Newydd, Low Secure Unit

- Successful implementation of SIGNAL, WCP & HEPMA in Adult Inpatient wards

- Development of Dual Diagnosis Strategy

- CMHT Modernisation Board and work streams established.

- CDAT accommodation sourced to allow one base for both Swansea and NPT CDATs

CYP

- Secured funding uplift for SBUHB neonatal service as a result of the phase 1 WHSSC cot capacity reconfiguration across South Wales. The formal outcome and funding have now been received. This has allowed the service to fund the posts which had already been recruited at risk (supported by Health Board), these included nursing, medical and therapy posts. Further focused work continues to deliver robust recruitment and retention strategies for nursing roles. To date, this is proving to be very successful. The service is also working with Head of Child Psychology to recruit to a Psychology post which has been lacking from the service.

- Adult services vacated Morriston Paediatric outpatient department in November 2023 which returned the paediatric outpatient department to sole paediatric use thus increasing outpatient/theatre clinic capacity.

- Launched Welsh Government Neurodivergent Improvement programme prior to Christmas. Childrens services representatives are attending meetings and there is a drive to develop a national model. In the interim, recruiting to key posts to support the service have been positive using Annex 21 following an unsuccessfully recruiting to posts through advertising in 2023. Items of equipment have also been purchased to improve efficiencies within the ADHD pathway, including QB testing software.

Maternity

- Continued implementation of the outcome of the OCPs, with recruitment to key posts in community services and the obstetric unit.   Appointment to Head of Midwifery post successful.

- Clinical Director of Midwifery post advertised.

- Recruitment to HCSW roles underway.

- Maternity Services Improvement and Transformation Board in place.

Population Health

- Supported population health contribution across 24/25 Annual Plan

- Completion of population health components for 24/25 Annual Plan

- Anchor Institution Baselining – scoped external support.

- Developed initial set of strategic population health indicators.

- Initiated development of local population health measures through quarterly SDG reviews.

- Population Health and Partnerships Committee Independent members recommendation to utilise APOG to track progress on cross cutting ministerial priorities.

- Recruitment in key posts to support public/population health delivery.

Workforce

- The digital dashboard tracking the contingent medical workforce is now live.

- The programme of work to record our funded establishment on our ESR system is progressing well, with PCCT Service Group establishments completed in Q4.

- We have continued to embed our new recruitment branding. For example, our digital campaign finished on the 8th of March.

- We have identified additional apprenticeship frameworks which will go live later this year. We also have 13 new apprentices starting in April 2024

- High level data from the 2023 National Staff Survey is being used to refresh our leadership development programme content.

- Cultural conversations continue to take place within the Health Board to support our internationally recruited nurses.

- The new Occupational Health system is now fully embedded. Managers are able to view and track the progress of pre-employment clearances, management referrals and health surveillance status in real time.

- Our Health Surveillance programme has been set up, and, subject to the required information being provided by the relevant managers, the programme will be rolled out over the next planning year and beyond.

Digital

- Signal v3.2 went live, incorporating new fields and reports were included following engagement with clinicians and senior leaders, including significant patient flow and Discharge to Recover and Assess changes.

- The HEPMA implementation in NPT and Singleton hospitals provided invaluable learning prior to the surgical implementation in Morriston hospital which commenced on January 22nd.  The system has been positively received across 10 wards and theatres in Morriston hospital.  The scheduled completion date of this implementation is 12th April.

- The EPMA procurement has concluded and is pending health board approval of preferred option/recommendation.

- Options to use the CAV instance of Open Eyes are being explored in parallel with a Nationally hosted solution. Work is underway to review all outstanding dependencies to assess feasibility of an interim solution.

- Pathology Electronic Test Requesting (ETR) uptake has reached 81% in secondary care and 90% in primary care, towards an aim of 90%. Continued to increase uptake radiology Electronic Test Requesting (ETR) in adult outpatients, MIU NPT and Paediatrics and Neurology in Morriston have gone live.

- A fix to the Phlebotomy Module has been applied, however an additional issue has been identified which is being looked at by DHCW.  The National LIMS team will be testing the additional fix applied, if this has not been resolved it will be passed back to the supplier for resolution.  If the fix is successful, this will be passed to local digital and pathology teams for testing.  Additional functionality has been added which allows the bed location to be displayed on the work list, this prevents users having to log on to signal to locate the patient.

- Self-Service functionality allowing users to create their own charts through choosing different measures and dimensions added to the Mortality Power BI Dashboard and a Mortality App created to replace the existing Qlik Dashboard that has been decommissioned.

- The Patient Safety Huddle Dashboard developed and added to the Urgent and Emergency Care App giving accurate data around key metrics like available beds, EDD, expected admissions etc.

- A forecasting tool for Cancer services looking at future demand for a host of different measures has been developed and is expected to go-live by the end of March 2024.

- A Child Immunisations Dashboard monitoring the uptake of MMR vaccines on a cluster and school basis has gone live during this period.

- Hospital Initiated Referral (formally H2H) training and comms completed in readiness for go live early April.

- Successful WCP go live in Maternity Services on 18.03.24.

- The extra Access Points for the new wireless infrastructure have been deployed. ITU is scheduled for completion 21/03/24. The Wireless Upgrade in Morriston will be completed by the end of Q4.

- The VM/SAN migrations work has been completed for all sites. This means that SBU have no active infrastructure left in the POW Datacentre.