## Sheet1
| KPIs | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
1 | Admitted to Stroke Unit within 4 hours of arrival to hospital | Access to a Stroke Bed within 4 hours to be raised at site meetings with as high profile as other targets and plans to be created for getting ring fenced capacity back | Site Team/ Service Managers | 2022-10-01 | Ongoing / Daily | Raised profile of Ring-fenced stroke capacity in line with specialties such as ITU, A&E, and Cardiac. Service Director has previously instructed that capacity is to be ring-fenced. | Improved compliance against 4 hour target |  | n/a | 53% | 8.6% | 27% | 40% | 95%
|  | Ringfencing of 18 Stroke beds on the ASU To breach a ring fenced stroke bed a proforma should be completed and signed off by gold. | Site Team/ Service Managers | 2023-07-01 | Ongoing / Daily | Maintain 4 ring-fenced beds per 24 hours – do not go into the night without a ring-fenced bed without exec approval. Last bed not to be used for non-stroke admissions unless exec approval. The attached pro-forma is to be populated (by Bed Manager or On-call Manager) each time the ring-fenced bed on the Acute Stroke Unit has been breached (by a non-stroke). This process is being adopted to ensure that the bed management SOP for stroke is applied consistently and that appropriate escalation takes place prior to occupation of the ring fenced bed. Dec 23 Escalated to Site management due to increasing numbers of medical outliers on the ASU (13-14 patients). Under ringfencing agreements there should be a maximum of 6 medical patients. Policy in place but not adhered to due to site pressures | Improved compliance against 4 hour target Reduced LoS from not using the therapies room |  | n/a
|  | Transfer Delays Transfer issues to be raised at 10:30 internal site call and work with other sites to move longest waiters and ensure compliance | Site team(s)/ ECHO manager | 2022-10-01 | Ongoing / Daily | Use the ASU delayed transfer list to highlight transfer delays, monitor them and work to reduce them. Email is sent daily to proactively raise the profile long waiters at Morriston in order for other sites to pull. In place yet other rehab sites – NPTH are reliant on being able to discharge to the community which is no longer straight forward. Highly problematic given lack of social care. Reduced transfer delays at present a benefit of AMSR | Reduced LoS on ASU |  | n/a
2 | CT Scanned within 1 hour | Direct to CT to be explored with radiology | Mark Ramsey/ Toby Wells /Tal Anjum | 2022-10-01 | Implemented July 2023 | July 2023 Direct to CT pilot live from 17/7/23 November 2023 Brainomix Artificial Intelligence now live. December 2023 Pilot in place and due to continue. April 2024 CT Perfusion operating Mon-Fri 9-5pm, with plans to expand to all CT radiographers covering on call to ensure a 24/7 service. | Reduced time to CT Head |  | n/a | 51.2% | 38.6% | 50% | 66% | 95%
3 | Door to needle Thrombolysis - 45 mins | ANP recruitment | Rebecca Bowers | 2023-07-01 | Implemented July 2023 | 6 Stroke ANP (trainees) recruited to date due to be fully qualified in 2026 | Improve door to needle times |  | Funded from agreed recruitment plan | 17.5% | 8% | 25% | 50% | 95%
4 | Stroke consultant review within 24hrs | Recruitment plan for Consultants in place, 1 WTE out to advert in 23/24 and 2 WTE planned for 24/25 | David West/ Claire Thomas | 2023-09-01 | 2024-06-01 | Ongoing recruitment Interviews 10th June 2024 for 1 Stroke Consultant 2 posts be be progressed in 2024 /25 and join hybrid Neuro/Stroke rota to be revived to ensure all future recruits in Neuro go on the Stroke on-call rota. | To sustain stroke consultant review within 24 hours |  | Funded from agreed recruitment plan | 95% | 94.4% | 94% | 95% | 100%
5 | Swallow screen assessment within 4 hrs | Increased education of ED staff | Rebecca Davies/ Karen Ward | 2023-07-01 | 2024-06-01 | Ongoing training and weekly monitoring of preformance | To sustain swallow screen assessment within 4 hours |  | n/a | 79.3% | 75.8% | 82% | 90% | 95%
6 | Formal Swallow screen assessment <=72 hrs | Increased education of ED staff | Rebecca Davies/ Karen Ward | 2023-07-01 | 2024-06-01 | Ongoing training and weekly monitoring of preformance | To sustain formal swallow screen assessment within 72 hours |  | n/a | 95% | 90.3% | 92.5% | 95% | 100%
7 | Discharged Home Directly from ASU <= 72 hours | 2024 GMO (PCT_10): Develop an Integrated Community Stroke Service (ICSS) to enable more stroke survivors to receive their on-going rehabilitation in a community based setting. | Susan Wilson | 2024-04-01 | 2025-03-01 | Develop an Integrated Community Stroke Service (ICSS) to enable more stroke survivors to receive their on-going rehabilitation in a community based setting. To be added to Stroke GMO in MGH Plan as this is part of Phase 2 planning | Stroke evidence base demonstrates significant improvements in outcomes for all stroke patients when they receive community based rehab. |  | £1.2 million. Without investment, GMO won't be delivered | N/A | 20% | 21% | 24% | N/A
8 | Compliance with patients receiving the required minutes for Occupational Therapy | Recruitment underway for additional B6 OT post to support Rehab site. B4 Rehab practitioners x2 appointed and commencing 18th Dec Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | OT interviews Monday 18th Dec Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per the stroke SBAR | 51% | 74.1% | 80% | 95% | 95%
9 | Compliance with patients receiving the required minutes for Physiotherapy | B4 Rehab practitioners x2 appointed and commencing 18th Dec. Out to advert for x1 more B4 post Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per stroke SBAR | 58.8% | 66.9% | 74% | 88% | 95%
10 | Compliance with patients receiving the required minutes for Speech and Language Therapy | B4 Rehab practitioners x2 appointed and commencing 18th Dec Review of data inputting methods | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Data inputting reviewed and adapted | Increase in target compliance as per trajectories in Stroke SBAR |  | As per stroke SBAR | 31.6% | 64.3% | 52% | 83% | 95%
11 | Percentage of applicable patients screened for nutrition and seen by a dietitian by discharge | Recruited to 0.85 WTE B7 dietitian | Sue Wilson | 2023-09-01 | Completed Jan 2024 | Start Date January 2nd 2024 | Improvement of compliance and data analysis |  | As per stroke SBAR | 95.3% | 62.5% | 67% | 90% | 95%
12 | Percentage of patients discharged with ESD | Mutiple posts have been recruited too | Site Team | 2022-10-01 | Completed Jan 2024 | Delayed Transfers of Care discussed every Tuesday via the Clinically optimised meeting. Ward F patients’ profile to be raised as well as other key areas. July 2023 ESD expansion in SBUHB investment plan for 23/24 Dec 2023 Multiple posts recruited to in ESD | Increased patient flow, reduce LOS |  | Part of the Stroke Expediture plan, £280k recurrent ear marked for ESD | 22% | 43% | 44% | 45% | 45%
13 | Six Month patient follow up assessment | Life after stroke clinics | Ceri Eady | 2023-06-01 | Ongoing - weekly | Life after stroke clinics have been running since June 2023. Clinic appointment are being offered at closer three/four months instead of six as patients are requesting input sooner. Face to face / TEAMS/ telephone calls are also still offered at 6 months | Patient experience |  | n/a | 53.5% | 8.6% | 45% | 95% | 95%
14 | SSNAP data | Weekly scrutiny of data in conjunction with consultants, site teams, managers to identify themes | David West | 2022-10-01 | Ongoing -weekly | Completed – Occurs Weekly | Improved Scrutiny of recorded data |  | n/a
15 | TIA Clinics to run 5 days a week where possible. | Clinics to run Mon - Thurs and Friday when required | Dave West | 2021-08-01 | Ongoing - weekly | Implemented. Dedicated Doppler scans. 2 clinics per week back up and running at NPTH | In place – admission avoidance |  | n/a
16 | Ensure SLA with Bristol is maximised for Thrombectomy use | Work with strategy and commissioing team to ensure SLA in place is appropriate | Hannah Roan | 2022-08-01 | 2024-06-01 | Eligible patients transferred to Bristol for Thrombectomy. SLA is between WHSSC and North Bristol NHST which SBUHB benefits from. 50 thrombectomy transfers from Morriston to NBT from June 2020-Dec 2023 | Increased Amount of thrombectomy referrals to Bristol |  | n/a
17 | Mechanical Thrombectomy | CT perfusion introduced in April 2024 Weekly scrutiny meeting over patients sent to Bristol for Thrombectomy as well as those returned that did not received treatment depsite being sent. | David West | 2022-11-01 | 2024-06-01 | Review DU recommendations and findings of their tour of radiology and Stroke services 1/11/22 to aim towards 11% thrombectomy rate. Survey conducted November -December 2022. DU report awaited on findings Direct to CT Pilot –July 2023 envisaged to cut down assessment/referral time for this service. Agreed at Morriston board, start date awaited from WAST as at 17/7/23 SSNAP reporting issue resolved 14/7/23 where SBUHB thrombectomy referrals were not showing due to records not being returned from NBNHST |  |  | SLA in place with NBT
18 | Review of Actions from Thrombolysis Action plan 2019/20 to ensure lessons learnt remain embedded. |  | David West/ Tal Anjum | 2021-09-01 | In Place | 2019/2020 Action Plan: | Lessons learnt and kept on for information |  | n/a
19 | Review of Actions from Therapies Action plan 2020 to ensure lessons learnt remain embedded. |  | David West/ Tal Anjum/ Sue Wilson | 2021-09-01 | In Place | 2020 therapies action plan: Therapies room ring-fenced going forward | Lessons learnt and kept on for information |  | n/a
20 | Porter cover – pool porters & A&E porters to be involved in pathway to ensure we minimise delays. |  | Alan Thorne | 2022-02-01 | In Place | Reduce delays in CT/Ward transfers. | Reduced time to CT |  | n/a
21 | Pre-Alert ED – Site to be alerted ahead of time to pull the patient through to a bed. |  | WAST / SWITCHBOARD |  | In Place | Already in place | Reduced time to first assessment / CT/ Swallow assessment |  | n/a
22 | Hyper Acute Stroke Unit (HASU) / Comprehensive Regional Stroke Unit (CRSC) | Access to beds | ARCH |  | 2026-06-01 | SOP and Ring-fencing policy to be adopted following New HASU Unit. Await approval of HASU business case and implement from April 2023 |  |  | n/a
23 | Hyper Acute Stroke Unit (HASU) / Comprehensive Regional Stroke Unit (CRSC) | Dedicated CT facility to improve scan times. | ARCH |  | 2026-06-01 | £400k in stroke legacy fund to be put towards developing dedicated CT facilities. Additional benefit of working with radiology to bring cardiac scans back to SBUHB also. HDUHB colleagues to be asked about their contribution towards these facilities as requested by the Charitable funds committee December 2023. HDUHB confirmed not contributing towards SBUHB facility. | Improve scan times |  | n/a
24 | Hyper Acute Stroke Unit (HASU) / Comprehensive Regional Stroke Unit (CRSC) | Improved door to needle times from increased ANP workforce | ARCH |  | 2026-06-01 | Increased ANP workforce to improve door to needle times. Reduced time for patients to wait before receiving the medication. 3 candidates recruited and now in post. March 2023. Further 3 ANP posts to go out to advert July 2023 ready to have trained workforce for 2026 to take HDUHB patients. | Improve door to needle times |  | n/a
25 | Hyper Acute Stroke Unit (HASU) / Comprehensive Regional Stroke Unit (CRSC) | Recruitment of 3 x Hybrid Stroke/Neuro consultants | ARCH |  | 2026-06-01 | 3 x Hybrid consultants to be recruited. Ring-fenced funding exists. ARCH to agree financial contribution of the model prior to recruiting which will improve HDUHB Neurology provision. |  |  | £450,000 (funded as part of Business case approved in 2024)
26 | AMSR | Decompression of ED / AMSR redesign - COMPLETE | Morriston Site team | 2022-12-01 | 2023-10-01 | Decompression of ED and Stroke patients going to a dedicated medical area will mean assessments are more focussed and will better tailor for Stroke patients whose symptoms are not immediately obvious of stroke. Anticipated Benefit includes: • Improved CT Head time • Improved door to needle time for Thrombolysis AMSR implementation took place in December 2022. Full audit results and measures awaited at the time of writing but ED and the new AMU remain congested due to a lack of patient flow back into the community. February 2023 Double running phase to complete. No major benefit yet realised from AMSR to date in terms of its impact on Stroke performance. July 2023 ED still 100+ patients most days post AMSR. CT pilot commenced 17/7/23 to avoid delays and release crews. AMSR Closed down October 2023 |  |  | n/a
27 | Third Sector Colloboration |  | David West | 2023-01-01 | 2024-03-01 | Tender being submitted January 2024 | No impact to SSNAP but will allow more support to patients |  | £65k funded and awarded
28 | Speech and Language input | Several vacancies are causing a fall in compliance. National shortage of SLT staff | Jade Farrell | 2024-05-01 | Nov | Explore putting out overtime in the department. Place advert with a locum agency. Overseas recruitment to be explored as an option. Explroe pulling staff from general ward areas to support Stroke. | Increased compliance of therapy time by having more staff to delivery the therapy. |  | Locum costs to be established
| Immediate actions to address 4 hour admission: | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
|  | Decompression of ED with opening of Acute Frailty Unit | Gareth Cottrell | 2024-04-01 | 2024-09-01 | Acute frailty unit coming online in September 2024 is expected to absorb 40% of the medical take alowing quicker assessment times for patients inlcuding those suffering stroke who may not be clinically obvious. | Expected improvement in 4 hours compliance
|  | All site matrons reminded that breach of a Stroke bed needs authorisation from Silver & Gold. | Rebecca Davies | 2024-05-01 | 2024-05-01 | All staff reinformed of this 8/5/2024 Breach proforma reintroduceded | Expected improvement in 4 hours compliance |  | n/a
|  | Medical outliers should be capped at 6 on Ward F. Morriston to link in with NPTH around maximising use of rehabilitation facilities to improve flow | Rebecca Davies / David West | 2023-04-01 | 2024-05-01 | David West & Rebecca Davies to meet with Melanie Collins to speed up Stroke transfers. To be done May 2024. | Expected improvement in patient flow resulting in improvement in 4 hour compliance. |  | n/a
|  | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
| Immediate actions to address Thrombolysis compliance | Thombolysis pathways to be reissued to all medical and ED staff | Tal Anjum /Mark Poulden | 2024-05-01 | 2024-05-01 | Dr Polden and Dr Anjum to send out guidance to capture all eligible patients for thrombolysis. | Expected improvement in thrombolysis compliance by ensuring all eligible patients are given this treatment. |  | n/a
|  | Recruit to develop 7 day a week 8am-10pm cover | Tal Anjum/ David West | 2024-05-01 | 2024-06-01 |  | Expected improvement in thrombolysis compliance by ensuring specialist teams are available all throughout the week. |  | Funded from agreed recruitment plan
2 substantive PA’s to be recruited in place of locum ED team.
These 2 PA’s will join with 2 already in post substantive PA’s as well as 6 ANP’s and 3 CNS’s to form 7 day a week cover
|  | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
| Immediate actions to address CT within 1 hour compliance |  | Hannah Khirwadkah | 2024-05-01 | 2024-07-01 | 17 radiographers to train on CT/MRI perfusion so being trained as and when cases present. | Greater compliance with CT<1hour as well as increased thrombectomy rate from increased ability to identify salvageable brain following Stroke. |  | training costs
Expansion of CT perfusion service from Monday-Friday 9-5pm to 24/7
|  |  | Tal Anjum | 2024-05-01 |  |  |  |  | n/a
Continued education to On-call staff about thrombectomy options
|  | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
|  | Refreshed audit of WAST pilot patients going Straight to CT to update November’s report and to assess if this pilot can be adopted as policy | Tal Anjum | 2024-05-01 | 2024-06-01 | Patient data to be audited and assessment times analysed. | Greater compliance with CT <1 hour. |  | n/a
Meeting to be arranged with WAST following this to see if it can be adopted as policy
|  |  | Hannah Khirwadkah | 2024-05-01 | 2024-07-01 | 17 radiographers to train on CT/MRI perfusion so being trained as and when cases present. | Greater compliance with CT<1hour as well as increased thrombectomy rate from increased ability to identify salvageable brain following Stroke. |  | training costs
Expansion of CT perfusion service from Monday-Friday 9-5pm to 24/7
|  | Decompression of ED with opening of Acute Frailty Unit | Gareth Cottrell | 2024-04-01 | 2024-09-01 | Acute frailty unit coming online in September 2024 is expected to absorb 40% of the medical take from ED decompressing the department and allowing quicker assessment times for patients including those suffering stroke who may not be clinically obvious. | Expected improvement in CT compliance due to quicker identification of patients presenting with Stroke who don’t attend via WAST and maybe not clinically obvious.
Increased WAST conveyance due to reduced community delays resulting in greater numbers benefitting from direct to CT.
|  |  | Tal Anjum | 2024-05-01 | 2024-06-01 | Reception staff being trained in BEFAST tool to identify suspected Stroke patients to expedite triage by nursing staff | Quicker identification of walk in stroked to reduce time to CT, Thrombolysis and thrombectomy. |  | n/a
Training of ED/AMU reception Staff to highlight suspected strokes or expedited triage
|  | Recommendations/ Action | Lead | Start Date | Implementation / End Date | Progress/ Remarks | Expected Benefit/ Impact on SSNAP Score | RAG Status | Budget Implications | 2019 Pre COVID | 2021/22 | 2022/23 | 2023/24 | Staffed to National Standards
| Immediate actions to maximise use of Thrombectomy treatment |  | Hannah Khirwadkah | 2024-05-01 | 2024-07-01 | 17 radiographers to train on CT/MRI perfusion so being trained as and when cases present. | Greater compliance with CT<1hour as well as increased thrombectomy rate from increased ability to identify salvageable brain following Stroke. |  | Training costs
Expansion of CT perfusion service from Monday-Friday 9-5pm to 24/7
|  |  | Tal Anjum | 2024-05-01 | 2024-05-01 | Extended opening hours of this service has been cascaded to senior and junior staff | Increased utilisation of thrombectomy service in North Bristol. |  | n/a
Continued education to On-call staff about thrombectomy options and NBNHST operating policy to be cascaded
|  |  | Tal Anjum | 2024-05-01 | 2025-05-01 | 2 trained as of May 2024, 4 more ANP colleagues to qualify over the next 24 months | Greater use of thrombectomy services due to quicker identification and referral to Bristol in conjunction with reduced CT and Thrombolysis times. |  | n/a
Extended ANP cover due to 2 now been signed off to independently see Stroke patients. Another 4 to come on line over the next 12-24 months