| Meeting Date | 21 May 2024 |  | Agenda Item |  |  | 6.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Performance & Finance Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee (PFC) for scrutiny. |  |  |  |  |  |
| Key Issues | - The Health Board Risk Register was last received by the Board in March 2023. - Since then, Health Board risk register entries have been circulated to lead Executive Directors monthly for review and update. This report presents an extract of risks from the March 2024 HBRR, with additional updates for some risks provided in this covering report, which will be reflected in the next HBRR issued. - Eleven risks are assigned to the Performance & Finance Committee for oversight. One of these is new and one has recently been reduced in score. There are seven risks assessed to meet or exceed the Board risk appetite threshold. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Performance & Finance Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in January 2024. The next meeting is in May 2024.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in January 2024. The next meeting is in May 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to Executive Team for agreement and final version issued. This report presents the risks allocated to this Committee as recorded in the March 2024 HBRR – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent monthly update are highlighted in red font.

3.2 HBRR Performance & Finance Risks

Eleven risks are assigned to this Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 4 | 0 | 0 | 5 | 2 |

Movements since last meeting:

- New risks

  - HBR98 Overall condition/compliance and suitability of Health Board Estate

- Risks increased in score

  - Nil

- Risks reduced in score

  - HBR97 Disruption due to Industrial Action (1612)

- Risks closed/de-escalated

  - Nil

There are seven risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the Performance & Finance Committee

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 25 | Lead: Chief Operating Officer The risk score currently (Urgent & Emergency Care) remains unchanged. The UEC system continues to see high demand, with ambulance attendances in particular being higher than seen previously. This is coupled with reduced flow out of hospital beds due to an imbalance of acute / community / care service provision. These factors are resulting in unacceptable delays in patients accessing UEC services and therefore the risk score remains high. The HBRR entry has been refreshed since the March HBRR was published to reflect current controls and further actions being taken. These are detailed below: Controls: Five main areas of work within the plan: - Frailty strategy – approved via Management Board - Grip & control operational management - Senior decision makers at front door services - Pathway of care delays (PoCD) - Home First - ACT - Interface with local authority - Reconfiguration of Emergency Dept In addition to business as usual, improvement actions: - Continued focussed roll-out of 6-Goals schemes of work - D2RA (Discharge to Recover & Assess)/Trusted assessor model - SAFER - Criteria-led discharge - Continuous Flow Model (CFM) - Robust SDEC (Same Day Emergency Care) model Assurance arrangements: - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the COO - Monthly TI monitoring meetings with Welsh Government - Urgent & Emergency Care Board is meeting monthly, chaired by the COO. - Six Goals programme reviews the plan on a monthly basis Further Actions: - Review of senior decision making capacity within SDEC and AMU (Acute Medical Unit)(Target 30/07/2024) - Implementation of 7-day community services such as Virtual Wards (Target 30/09/2024) - Monitoring of Continuous Flow Model continues to be implemented, despite the challenge of flow. It will be monitored over 12 month period. (Target 30/09/2024) - Criteria led discharge roll out (Target 30/09/2024) Focus on the implementation of the Frailty strategy, to be operational during September 2024. |
| 16 (840) | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Lead: Chief Operating Officer The risk score currently remains unchanged. Whilst the Health Board has eradicated very long waits for surgery, patients are still waiting in excess of 104 weeks for surgical intervention, which is outside of national policy on RTT (Referral To Treatment). The Health Board is currently under escalating performance monitoring from Welsh Government (Targeted Intervention or TI) for delivery of Planned Care services. The improvement plan developed as a response to TI mirrors that already included in the Health Board. The HBRR entry has been refreshed since the March HBRR was published to reflect current controls and further actions being taken. These are detailed below. Controls: - There is a bi-weekly recovery TI meeting specifically for assurance on the recovery of our elective programme. - Specialty level capacity and demand models set out the baseline capacity and identify solutions to bridge the gap this financial year. Non-recurring pump-prime funding is available to support initial recovery measures. Fortnightly performance reviews track progress against delivery. - A focused intervention is in train to support to the 10 specialties with the longest waits. - Long waiting patients are being outsourced to the Independent Sector, where appropriate - Additional internal activity is being delivered on weekends (via insourcing), although this is currently at risk due to changes in policy pertaining to the payment of enhanced rates to A4C staff. - Planned care trajectories are currently being developed and submitted to Welsh Government as part of the annual plan by the end of May. - Governance process put in place to monitor performance against trajectories internally, and with Welsh Government as part of TI. - External & internal validation continues. - A 10-bedded orthopaedic ward was created at Morriston Hospital in December to address the longest waits in the specialty that can only be operated on at Morriston. - All long waiting patients are receiving clinical reviews to ascertain continued need for surgery. Assurances: - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the Chief Operating Officer - Bi-weekly planned care meetings chaired by the Chief Operating Officer - Monthly TI monitoring meetings with Welsh Government Further Action: - Develop comprehensive demand and capacity plans for 2024/25 (Target 31/05/2024) - Work ongoing with Finance colleagues to establish the funding allocation for elective recovery for 2024/25 (Target 31/05/2024) All patients breaching the 104 week target are at treatment stage. Therefore all have a treatment plan in place. |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Lead: Chief Operating Officer The risk score currently remains unchanged. The Health Board remains unable to deliver on the target of 75% of patients being treated within 62 days and is currently under targeted intervention by Welsh Government to improve performance. The Health Board has been given an initial target of 60% to be delivered by the end of Dec-24, increasing to 70% by the end of March 2025. The most recent performance reported for March 2024, where the Health Board attained 56%. The HBRR entry has been refreshed since the March HBRR was published to reflect current controls and further actions being taken. These are detailed below. Controls: - Tight management processes to manage each individual case on the Single Cancer Pathway SCP). Enhanced monitoring & weekly monitoring of action plans for top 6 tumour sites. - Initiatives to protect surgical capacity to support SCPs have been put in place - Tumour sites have been given additional targets to achieve by the end of Qtr1: - Achieve the 10-day 1st Outpatient target - Deliver a decision to treat (DTT) by day 31 - a specific plan is being delivered to support Pathology services and ensure SCP tests are turned around within 5 days. Assurances: - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the COO - Bi-weekly Cancer meetings chaired by the Dep COO - Monthly TI monitoring meetings with Welsh Government Action: - Cancer Performance Group to monitor improvement trajectories for both cancer backlog and SCP performance on a monthly basis (Target 30/06/2024) - Full review of gynaecology / gynae-oncology pathway given service constraints to be done. Additional theatre capacity for gynaecological cancer to be agreed to reduce current backlog (Target 30/09/2024) |
| 92 (3444) | Financial Deficit Achievement Forecast deficit is not met due to insufficient progress on COVID cost reduction, savings identification, run rate reduction and the potential for new in-year pressures. | 20 | Lead: Executive Director of Finance & Performance The risk score currently remains unchanged. Ongoing Actions: - Continuation of weekly escalation meetings and escalation of other areas as necessary - Develop robust cross system service change plans which improve quality of care and reduce system cost |
| 93 (3448) | Capital Plan Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2023/24 | 20 | Lead: Executive Director of Finance & Performance The risk score currently remains unchanged. Ongoing Action: Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk based basis. |
| 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) Failure to have an approvable (Integrated Medium Term Plan) IMTP for 2024/5 then we will lose public confidence and breach legislation. | 20 | Lead: Director of Strategy Action: Development of a robust Annual Plan for 2024/25 and continued work to set out a timeline for financial recovery (31/03/2025). |
| 98 (3692) | Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. The backlog maintenance costs are in excess of £200 million. | 20 New Risk | Lead: Executive Director of Finance & Performance Previous risk HBR13 Environment of Premises overseen at QSC was closed in March 2024 and this risk entry opened and assigned to PFC for oversight. Through the 6 FACET survey a number of key items have been identified covering the Physical condition, Functional suitability, Space utilisation, Quality audit, Statutory compliance and Environmental management. In addition an equality review was undertake on sites. All of which identified significant issues with the current estate, with very few areas achieving condition ‘B’. The overall backlog maintenance is in excess of £200m. Key areas include ventilation and cooling with major infection control and other implications. Theatres/Wards/ED and general acute settings including mental health and learning disabilities being old and not compliant with the latest Welsh health Building Notes (WHBNs) and Welsh Health Technical Memoranda (WHTMs). The heating, power and medical gas systems have also been identified as issues for concern in the 6 FACET surveys and from independent audits. The health board’s latest NWSSP estates audit received a limited assurance due to limited Welsh Government funding available to undertake backlog maintenance and implementation of estates strategy. Current controls in place: - Planned preventative maintenance, prioritising highest risk depending on funding available and linked to creation of decant space through service changes. - Regular reviews of the estate. - Reactive maintenance. - 20% annual review/update of 6 FACET surveys. - Address issues where practicable through EFAB/Discretionary capital. - Estates Strategy and development control plans task and finish group. Further ongoing actions: - Maintain effective engagement with Welsh Government to provide funding to implement estates strategy and development control plans to address all areas outlined. - Work with Welsh Government to source alternative solutions to funding the Health Board estates strategy and development control plans |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 52 (1763) | Strategic Impact Assessments The Health Board does not have sufficient skills & resource in place to undertake impact assessments in line with strategic service change and policy development. | 12 | Lead: Director of Insight Communications & Engagement The risk score currently remains unchanged. |
| 75 (2522) | Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 10 | Lead: Chief Operating Officer Risks in relation to major incidents and business continuity are being reviewed with a view to refreshing/replacing this HBRR entry. |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Lead: Chief Operating Officer The risk score currently remains unchanged. |

Risk HBR 97 Disruption due to Industrial Action is reported within closed session of this Committee.

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 25 | Quality & Safety |
| 16 (840) | Access and Planned Care. There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Quality & Safety |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Quality & Safety |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Quality & Safety |

4. FINANCIAL IMPLICATIONS

There are financial implications to minimising the risks entered on the HBRR in relation to significant revenue implication around strengthening resources in the Health Board, Service Groups and Departments.  Capital monies may also be required in relation to supporting the improvements required to improve and where this is the case further detail is provided in the individual entries on the HBRR.

5. RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PFC which were last reported to the Board in March 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Performance & Finance Committee |  |

This risk is reported in closed session of the Committee.